## AllJobsDetailReport (3)
job_id | state_name | sub_state_name | street | city | state | zip | customer_name | last_approval_date | customer_phone | customer_email | secondary_name | secondary_phone | secondary_email | annual_production | dollars_per_kwh | site_tech | sales_packet_approval_date | system_size | install_manager | partner | account_manager | welcome_call_date | site_survey_date | module_type | module_size | module_number | module_manufacturer | inverter_manufacturer | inverter_model | roof_type | main_panel | fwt_completed_date | sales_stage | product_type | in_hoa | unpermitted_work | internet | home_held_in_trust | re_roof | smoke_carbon_detectors | job_start_date | ICC_completion_date | ICC_work_duration | ICC_target_duration | ICC_owner | ICC_status | Des_completion_date | Des_work_duration | Des_target_duration | Des_owner | Des_status | IP_completion_date | IP_work_duration | IP_target_duration | IP_owner | IP_status | ER_completion_date | ER_work_duration | ER_target_duration | ER_owner | ER_status | PA_completion_date | PA_work_duration | PA_target_duration | PA_owner | PA_status | PR_completion_date | PR_work_duration | PR_target_duration | PR_owner | PR_status | IC_completion_date | IC_work_duration | IC_target_duration | IC_owner | IC_status | PIP_completion_date | PIP_work_duration | PIP_target_duration | PIP_owner | PIP_status | Equipment_Shipped_completion_date | Equipment_Shipped_work_duration | Equipment_Shipped_target_duration | Equipment_Shipped_owner | Equipment_Shipped_status | DA_completion_date | DA_work_duration | DA_target_duration | DA_owner | DA_status | PP_completion_date | PP_work_duration | PP_target_duration | PP_owner | PP_status | F_M1_completion_date | F_M1_work_duration | F_M1_target_duration | F_M1_owner | F_M1_status | IU_completion_date | IU_work_duration | IU_target_duration | IU_owner | IU_status | F_M2_completion_date | F_M2_work_duration | F_M2_target_duration | F_M2_owner | F_M2_status | HOA_PACKET_completion_date | HOA_PACKET_work_duration | HOA_PACKET_target_duration | HOA_PACKET_owner | HOA_PACKET_status | HOA_SUBMITTED_completion_date | HOA_SUBMITTED_work_duration | HOA_SUBMITTED_target_duration | HOA_SUBMITTED_owner | HOA_SUBMITTED_status | HOA_APPROVED_completion_date | HOA_APPROVED_work_duration | HOA_APPROVED_target_duration | HOA_APPROVED_owner | HOA_APPROVED_status | NEM_completion_date | NEM_work_duration | NEM_target_duration | NEM_owner | NEM_status | PTO_completion_date | PTO_work_duration | PTO_target_duration | PTO_owner | PTO_status | PTO_U_completion_date | PTO_U_work_duration | PTO_U_target_duration | PTO_U_owner | PTO_U_status | F_M3_completion_date | F_M3_work_duration | F_M3_target_duration | F_M3_owner | F_M3_status | FINAL_INSPEC_scheduled_date | FINAL_INSPEC_target_date | FINAL_INSPEC_completion_date | FINAL_INSPEC_work_duration | FINAL_INSPEC_target_duration | FINAL_INSPEC_owner | FINAL_INSPEC_status | msp_m_completion_date | msp_m_work_duration | msp_m_target_duration | msp_m_owner | msp_m_status | msp_u_completion_date | msp_u_work_duration | msp_u_target_duration | msp_u_owner | msp_u_status | MANUAL_ENTRY_total_work_time | REROOF_completion_date | REROOF_work_duration | REROOF_target_duration | REROOF_owner | REROOF_status | REROOF_COMPLETE_scheduled_date | REROOF_COMPLETE_completion_date | REROOF_COMPLETE_work_duration | REROOF_COMPLETE_target_duration | REROOF_COMPLETE_owner | REROOF_COMPLETE_status | PERMIT_RECEIVED_expected_date | pip_approved | AHJ_name | AHJ_city | ht_job_link | ht_opf_job_link | sugar_link | solar_expert | sec_solar_expert | contract_date | installer | sugar_customer_id | Days to Final Inspection | Days to PIP | FI Score | PIP Score | FI Accuracy Score | Customer Sat Score | Constant | Total | Category | Weight | Criterion | Range | [5 empty] | Outcome(s)
25159 | SP APPROVED |  | 1501 Norton Street | San Mateo | CA | 94401 | Anne Huynh | 2019-09-23 17:20 | 6505525333 | annehuynh@gmail.com |  |  |  | 5521 |  | Ricardo Virgen | 2019-06-04 | 3.355 | Christina Horton |  | Darlynn Lacap |  | 2019-05-25 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tar and Gravel | NO | 2019-10-21 | Installation Complete | Cash | 0 | 0 |  |  | 1 | 0 | 2019-10-21 07:00 | 2019-09-23 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-24 | 1.84 | 2 | Daniel Speegle | Completed | 2019-10-02 | 6.26 | 1 | Christina Horton | Completed | 2019-10-21 | 2.63 | 5 | Brian Le | Completed | 2019-10-02 | 9.71 | 3 | Ernesto Enriquez | Completed | 2019-10-02 | 0.08 | 10 | Andrew Moralez | Completed | 2019-10-21 | 0.33 | 1 | Christina Horton | Completed |  | 0.17 | 2 | Christina Horton | Current | 2019-10-17 | 21.84 | 2 | Brian Le | Completed | 2019-09-25 | 1.13 | 2 | Darlynn Lacap | Completed | 2019-09-25 | 0.96 | 1 |  | Completed | 2019-10-03 | 13.88 | 1 | Andrew Clemons | Completed |  | 0.54 | 1 | Darlynn Lacap | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-23 13:59 |  |  | 0.17 | 2 | Christina Horton | Current | [10 empty] | 10.5 | 2019-10-02 | 6.79 | 14 | James Fernandez | Completed | 2019-10-15 | 2019-10-15 | 0.54 | 1 | James Fernandez | Completed | 2019-10-16 |  | SAN MATEO | San Mateo | https://heliotrack.completesolar.com/job.php?action=review&jobID=25159 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25159 | https://completesolar.sugarondemand.com/#Opportunities/74007f0c-86f7-11e9-ace2-069e4f790264 | Total HomeSolar |  | 2019-04-30 | OSullivan Green Solar | 74007f0c-86f7-11e9-ace2-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25 | Final Inspection Speed | 100% | Avg. time from min[IC to FI, MSP to FI] | 1 | 2 | 4 | 10 | 20 | 20 | 10 | 7 | 0 | -5 | -15 | -25
25780 | PIP_PENDING | PIP_PENDING | 233 Woodland Drive | Vista | CA | 92083 | Jon Schwank | 2019-08-06 16:45 | 8584136011 | jonschwank@hotmail.com | Lynn Schwank | 7606448529 |  | 14248 | 0.211 | Michael Marlaire | 2019-05-31 | 10.065 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-05-20 | 2019-05-25 09:00 | LR6-60PB-305M | 305 | 33 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | MPU | 2019-10-21 | Installation Complete | SunRun Monthly |  | 0 |  | 0 | 1 |  | 2019-10-21 07:00 | 2019-08-08 | 4.25 | 2 | Marcia Garay | Completed | 2019-08-10 | 1.92 | 2 | Jethro Andal | Completed | 2019-10-02 | 36.38 | 1 | Christina Horton | Completed | 2019-10-21 | 48.08 | 5 | Brian Le | Completed | 2019-08-15 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-15 | 0.08 | 0 | Andrew Moralez | Completed | 2019-10-21 | 0.5 | 3 | Christina Horton | Completed |  | 0.04 | 2 | Christina Horton | Current | 2019-08-13 | 1.04 | 2 | Brian Le | Completed | 2019-08-12 | 0.38 | 2 | Marcia Garay | Completed | 2019-08-14 | 0.08 | 1 |  | Completed | 2019-08-26 | 10.38 | 1 | Andrew Clemons | Completed |  | 0.54 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-22 |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-12 | 0.29 | 2 | Marcia Garay | Completed | 57.63 |  | 51.38 | 14 | James Fernandez | Current | 2019-10-19 |  | 28.67 | 1 | James Fernandez | Current | 2019-08-15 |  | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=25780 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25780 | https://completesolar.sugarondemand.com/#Opportunities/15edbcb2-83f6-11e9-be2f-022c40d974e6 | Matthew McKay |  | 2019-05-20 | Infinity Energy Inc | 15edbcb2-83f6-11e9-be2f-022c40d974e6 |  | 0 | -25 | 5 | 5 | 5 | 5 | -10 | Final Inspection Accuracy | 20% | Final Inspection Pass Attempt | 1st | 2nd | 3rd |  |  |  | 5 | 0 | -5
27930 | PIP_PENDING | PIP_PENDING | 1840 N Carlsbad St | Orange | CA | 92867 | Aaron Bailey | 2019-08-31 15:44 | 7142316130 | atb395@yahoo.com | Heather Bailey | 7143664045 |  | 10874.44 |  | Chris Peaslee | 2019-08-31 | 6.71 | Ara Sotto |  | Darlynn Lacap | 2019-08-30 | 2019-08-31 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE5000H-US RGM | Spanish Tile | NO | 2019-10-21 | Installation Complete | Sunlight Financial Loan | 1 | 0 |  |  | 1 | 1 | 2019-10-03 07:00 | 2019-09-03 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 3.83 | 2 | Daniel Speegle | Completed | 2019-10-04 | 19.21 | 1 | Ara Sotto | Completed | 2019-10-04 | 2.92 | 5 | Brian Le | Completed | 2019-09-16 | 5 | 3 | Ernesto Enriquez | Completed | 2019-09-23 | 5.13 | 1 | Ernesto Enriquez | Completed | 2019-10-21 | 12.21 | 2 | Ara Sotto | Completed |  | 0.29 | 2 | Ara Sotto | Current | 2019-09-26 | 11.88 | 2 | Brian Le | Completed | 2019-09-10 | 1.29 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0.08 | 1 |  | Completed | 2019-09-06 | 0.08 | 1 | Andrew Clemons | Completed | 2019-10-09 | 4.46 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | 2019-09-12 | 6.21 | 4 | Darlynn Lacap | Completed | 2019-09-12 | 0 | 5 | Darlynn Lacap | Completed | 2019-09-25 | 7.04 | 12 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-26 |  | 0.29 | 2 | Ara Sotto | Current | [10 empty] | 4.87 | 2019-10-04 | 6.92 | 14 | James Fernandez | Completed | 2019-10-04 | 2019-10-04 | 0 | 1 | James Fernandez | Completed | 2019-09-17 |  | ORANGE | Orange | https://heliotrack.completesolar.com/job.php?action=review&jobID=27930 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27930 | https://completesolar.sugarondemand.com/#Opportunities/e0f4a6c2-cc40-11e9-9a44-022c40d974e6 | Robert Prado |  | 2019-08-29 | Power Town Solar Electric | e0f4a6c2-cc40-11e9-9a44-022c40d974e6 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25 | Customer Satisfaction | 50% | Customer Satisfaction Rating | 9 | 7 | 5 | 5 |  |  | 5 | 0 | -2 | -10
28215 | PIP_PENDING | PIP_PENDING | 5040 East Avenue T 8 | Palmdale | CA | 93552 | Luis Trancoso | 2019-09-11 13:28 | 8183392279 | trancosoluis@yahoo.com |  |  |  | 8152 | 0.161 | Bill Angevine | 2019-09-11 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-28 | 2019-08-30 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Ground Mount | NO | 2019-10-21 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-15 07:00 | 2019-09-12 | 1 | 2 | Marcia Garay | Completed | 2019-09-16 | 1.88 | 2 | Daniel Speegle | Completed | 2019-10-14 | 19.25 | 1 | Christina Horton | Completed | 2019-10-21 | 5.88 | 5 | Brian Le | Completed | 2019-09-23 | 4.17 | 3 | Andrew Moralez | Completed | 2019-10-01 | 5.75 | 15 | Ernesto Enriquez | Completed | 2019-10-21 | 4.83 | 1 | Ara Sotto | Completed |  | 0.21 | 2 | Ara Sotto | Current | 2019-10-11 | 17.17 | 2 | Brian Le | Completed | 2019-09-18 | 1 | 2 | Marcia Garay | Completed | 2019-09-17 | 0.08 | 1 |  | Completed | 2019-09-24 | 5 | 1 | Andrew Clemons | Completed | 2019-10-17 | 2.88 | 1 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-03 |  | 0.21 | 2 | Ara Sotto | Current | [10 empty] | 1.79 | [11 empty] | 2019-10-14 |  | LOS ANGELES COUNTY | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28215 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28215 | https://completesolar.sugarondemand.com/#Opportunities/b259ceec-d4d2-11e9-8fc3-069e4f790264 | Solar Raze |  | 2019-08-27 | JK Solar | b259ceec-d4d2-11e9-8fc3-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25 | PIP | 30% | Days from IC to PIP Submitted | 1 | 2 | 3 | 4 | 4 |  | 5 | 4 | 2 | 0 | -2
28706 | PIP_PENDING | PIP_PENDING | 4600 Tilyard Court | Bakersfield | CA | 93311 | Derek Nelson | 2019-09-13 15:50 | 6617429717 | dnels002@gmail.com |  |  |  | 5987 | 0.154 | Abraham SiteTech Vazquez | 2019-09-13 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-12 | 2019-09-13 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-21 | 2019-09-16 | 0.88 | 2 | Marcia Garay | Completed | 2019-09-17 | 1.04 | 2 | Daniel Speegle | Completed | 2019-10-15 | 17.71 | 1 | Christina Horton | Completed | 2019-10-21 | 1.96 | 5 | Brian Le | Completed | 2019-09-19 | 2.04 | 3 | Andrew Moralez | Completed | 2019-10-04 | 8.71 | 5 | Andrew Moralez | Completed | 2019-10-21 | 0.21 | 1 | Ara Sotto | Completed |  | 0.29 | 2 | Ara Sotto | Current | 2019-10-17 | 10.75 | 2 | Brian Le | Completed | 2019-10-01 | 9.04 | 2 | Marcia Garay | Completed | 2019-09-17 | 0 | 1 |  | Completed | 2019-09-20 | 2.96 | 1 | Andrew Clemons | Completed |  | 0.54 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-07 |  | 0.29 | 2 | Ara Sotto | Current | [10 empty] | 8 | [11 empty] | 2019-10-02 |  | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=28706 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28706 | https://completesolar.sugarondemand.com/#Opportunities/cad70f6e-d678-11e9-8191-0630baf9dcb8 | Ryan Wilcox |  | 2019-09-12 | Green Road Solar Crew | cad70f6e-d678-11e9-8191-0630baf9dcb8 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25 | Cost | 0% | Base cost per module | [6 empty] | ($162.5-Base)/5 |  | 0.52419 | 0 | *Cost Should be forward Looking
28800 | SP APPROVED |  | 13382 Fawncreek Street | Victorville | CA | 92395 | Yselle Thomas | 2019-09-25 11:23 | 7605717707 | yathomas1@verizon.net |  |  | anisa0813@gmail.com | 7856 | 0.135 | Shaun Labelle | 2019-09-25 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-14 | 2019-09-20 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-21 | 2019-09-25 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 1.5 | 2 | Daniel Speegle | Completed | 2019-10-17 | 14.46 | 1 | Ara Sotto | Completed | 2019-10-21 | 0.58 | 5 | Brian Le | Completed | 2019-10-02 | 0.79 | 3 | Andrew Moralez | Completed | 2019-10-04 | 2.13 | 10 | Andrew Moralez | Completed | 2019-10-21 | 0.42 | 1 | Ara Sotto | Completed |  | 0.08 | 2 | Ara Sotto | Current | 2019-10-20 | 14.33 | 2 | Brian Le | Completed | 2019-09-30 | 1.58 | 2 | Darlynn Lacap | Completed | 2019-10-01 | 2.58 | 1 |  | Completed | 2019-10-04 | 5.54 | 1 | Noe Gomez | Completed | 2019-10-21 | 0.46 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-21 12:58 |  | 2019-10-21 | 0.08 | 2 | Christina Horton | Completed | [10 empty] | 0 | [11 empty] | 2019-10-16 |  | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28800 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28800 | https://completesolar.sugarondemand.com/#Opportunities/8e80cf30-dfc1-11e9-a241-069e4f790264 | CSA Division | Christopher Cellini | 2019-09-14 | Power Town Solar Electric | 8e80cf30-dfc1-11e9-a241-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
28927 | SP APPROVED |  | 16324 Jackson Drive | Fontana | CA | 92336 | Ronald M Lopez | 2019-09-23 17:28 | 3235335546 | morfin_sylvia@yahoo.com | Sylvia Lopez | 3235334674 |  | 9568 | 0.162 | Alex Holdridge | 2019-09-23 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-17 | 2019-09-18 15:00 | LR6-60HPB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-21 | 2019-09-24 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 2.33 | 2 | Daniel Speegle | Completed | 2019-09-30 | 1.58 | 1 | Ara Sotto | Completed |  | 0.71 | 5 | Brian Le | Current | 2019-10-16 | 10.96 | 3 | Ernesto Enriquez | Completed |  | 3.25 | 12 | Andrew Moralez | Current | 2019-10-21 | 0.42 | 2 | Ara Sotto | Completed |  | 0.08 | 2 | Ara Sotto | Current | 2019-10-20 | 12.63 | 2 | Brian Le | Completed | 2019-10-02 | 3.33 | 2 | Marcia Garay | Completed | 2019-10-01 | 2.42 | 1 |  | Completed | 2019-10-03 | 4.5 | 1 | Jeremiah Liend | Completed |  | 0.54 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-25 |  | 0.08 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-11-01 |  | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=28927 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28927 | https://completesolar.sugarondemand.com/#Opportunities/1fbe64fa-de62-11e9-b0dc-02ae981fbade | 300 Stars Inc |  | 2019-09-17 | HDM Electric Inc | 1fbe64fa-de62-11e9-b0dc-02ae981fbade | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
29110 | PIP_PENDING | PIP_PENDING | 37347 52nd Street East | Palmdale | CA | 93552 | Rocky Ramos | 2019-09-25 20:59 | 6612096980 | rrmrimr@att.net | Isabel Ramos | 6619924308 |  | 8257 | 0.149 | Bill Angevine | 2019-09-25 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-23 | 2019-09-25 09:00 | LR6-60HPB-305M | 305 | 14 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-21 07:00 | 2019-09-27 | 1.58 | 2 | Darlynn Lacap | Completed | 2019-10-01 | 2 | 2 | Daniel Speegle | Completed | 2019-10-12 | 8.5 | 1 | Ara Sotto | Completed | 2019-10-21 | 5.96 | 5 | Brian Le | Completed | 2019-10-04 | 2.88 | 3 | Andrew Moralez | Completed | 2019-10-10 | 4.08 | 5 | Andrew Moralez | Completed | 2019-10-21 | 1.84 | 1 | Ara Sotto | Completed |  | 0.08 | 2 | Ara Sotto | Current | 2019-10-11 | 6.13 | 2 | Brian Le | Completed | 2019-10-03 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-10-01 | 0.17 | 1 |  | Completed | 2019-10-04 | 2.83 | 1 | Jill Allen | Completed | 2019-10-15 | 1.5 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-17 |  | 0.08 | 2 | Ara Sotto | Current | [10 empty] | 4.04 | [11 empty] | 2019-10-11 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=29110 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29110 | https://completesolar.sugarondemand.com/#Opportunities/ff9762e2-e011-11e9-8a8e-069e4f790264 | Henry Garcia |  | 2019-09-23 | JK Solar | ff9762e2-e011-11e9-8a8e-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
29134 | PIP_PENDING | PIP_PENDING | 6838 Miramar Lane | Palmdale | CA | 93551 | Omar Chavez | 2019-09-26 06:27 | 6615477619 | oachavez76@gmail.com |  | 6612068752 |  | 11808 | 0.161 | Bill Angevine | 2019-09-25 | 6.1 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-24 | 2019-09-25 15:00 | LR6-60HPB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-21 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-17 07:00 | 2019-09-26 | 0.13 | 2 | Marcia Garay | Completed | 2019-10-01 | 3 | 2 | Daniel Speegle | Completed | 2019-10-09 | 5.96 | 1 | Ara Sotto | Completed | 2019-10-18 | 5 | 5 | Brian Le | Completed | 2019-10-04 | 1.04 | 3 | Andrew Moralez | Completed | 2019-10-10 | 2 | 5 | Andrew Moralez | Completed | 2019-10-21 | 2.79 | 2 | Ara Sotto | Completed |  | 0.21 | 2 | Ara Sotto | Current | 2019-10-11 | 6.96 | 2 | Brian Le | Completed | 2019-10-02 | 1.17 | 2 | Marcia Garay | Completed | 2019-10-01 | 0.17 | 1 |  | Completed | 2019-10-04 | 3.08 | 1 | Andrew Clemons | Completed |  | 3 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-21 | 2019-10-21 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 8.08 | [11 empty] | 2019-10-15 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=29134 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29134 | https://completesolar.sugarondemand.com/#Opportunities/484dc608-e061-11e9-8c9f-022c40d974e6 | SCES Division |  | 2019-09-24 | JK Solar | 484dc608-e061-11e9-8c9f-022c40d974e6 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
29241 | SP APPROVED |  | 14793 Harrison Drive | Adelanto | CA | 92301 | Elizabeth Garcia | 2019-10-02 19:21 | 7606465527 | elizabeth.garcia@hesperiausd.org | Vanessa Vecena | 7605081914 |  | 7237 | 0.147 | Shaun Labelle | 2019-10-02 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-27 | 2019-10-02 15:00 | LR6-60HPB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-21 | 2019-10-03 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-10-07 | 2.08 | 2 | Daniel Speegle | Completed | 2019-10-03 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-21 | 0.58 | 5 | Brian Le | Completed | 2019-10-14 | 4 | 3 | Andrew Moralez | Completed | 2019-10-14 | 0 | 3 | Ernesto Enriquez | Completed | 2019-10-21 | 0.42 | 1 | Ara Sotto | Completed |  | 0.08 | 2 | Ara Sotto | Current | 2019-10-20 | 8.5 | 2 | Brian Le | Completed | 2019-10-08 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-10-08 | 0.92 | 1 |  | Completed | 2019-10-11 | 3.79 | 1 | Jill Allen | Completed |  | 0.54 | 1 | Darlynn Lacap | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-24 |  | 0.08 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-10-17 |  | ADELANTO | Adelanto | https://heliotrack.completesolar.com/job.php?action=review&jobID=29241 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29241 | https://completesolar.sugarondemand.com/#Opportunities/699d41c6-e584-11e9-95a8-02ae981fbade | Christopher Cellini |  | 2019-09-27 | Green Road Solar Crew | 699d41c6-e584-11e9-95a8-02ae981fbade | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
29258 | PIP_PENDING | PIP_PENDING | 3030 Christina Street | Lancaster | CA | 93535 | Daniel Abbatiello | 2019-09-30 17:21 | 6614666487 |  | Patricia Abbatiello | 6619161949 |  | 8552 | 0.128 | Alex Holdridge | 2019-09-30 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-28 | 2019-09-30 15:00 | LR6-60HPB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-21 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-10-18 | 2019-10-03 | 2.71 | 2 | Marcia Garay | Completed | 2019-10-03 | 0 | 2 | Daniel Speegle | Completed | 2019-10-21 | 11.92 | 1 | Ara Sotto | Completed | 2019-10-21 | 5.88 | 5 | Brian Le | Completed | 2019-10-08 | 0.79 | 3 | Andrew Moralez | Completed |  | 9.25 | 6 | Andrew Moralez | Current | 2019-10-21 | 1.33 | 2 | Ara Sotto | Completed |  | 0.21 | 2 | Ara Sotto | Current | 2019-10-11 | 5.04 | 2 | Brian Le | Completed | 2019-10-04 | 1 | 2 | Darlynn Lacap | Completed | 2019-10-07 | 2.08 | 1 |  | Completed | 2019-10-08 | 3.04 | 1 | Andrew Clemons | Completed |  | 1.54 | 1 | Darlynn Lacap | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-24 |  | 0.21 | 2 | Ara Sotto | Current | [10 empty] | 0.04 | [11 empty] | 2019-10-16 |  | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=29258 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29258 | https://completesolar.sugarondemand.com/#Opportunities/60e5efd2-e3e1-11e9-a9cd-069e4f790264 | CUIC Inc | Shane Montana | 2019-09-28 | JK Solar | 60e5efd2-e3e1-11e9-a9cd-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
28202 | PIP_PENDING | PIP_PENDING | 26591 Desert Bloom Ave | Redlands | CA | 92373 | Resa Chase | 2019-09-17 13:03 | 4155968489 | stuff4resa@yahoo.com |  |  |  | 19860 |  | Complete Solar CA Tech 1 | 2019-09-17 | 12.505 | Ara Sotto | HDM Capital | Marcia Garay | 2019-09-03 | 2019-09-10 12:00 | LR6-60PB-305M | 305 | 41 | LONGi Solar | SolarEdge | SE10000A-US RGM | Tile Concrete | NO | 2019-10-18 | Installation Complete | Sunlight Financial Loan | 1 | 0 |  |  | 0 | 1 | 2019-10-17 07:00 | 2019-09-19 | 2 | 2 | Marcia Garay | Completed | 2019-09-23 | 2.08 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-18 | 4.96 | 5 | Brian Le | Completed | 2019-09-26 | 2.04 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 0 | 0 | Ernesto Enriquez | Completed | 2019-10-18 | 1.17 | 3 | Ara Sotto | Completed |  | 1.04 | 2 | Ara Sotto | Current | 2019-10-11 | 13.04 | 2 | Brian Le | Completed | 2019-09-24 | 0.92 | 2 | Marcia Garay | Completed | 2019-09-24 | 0.75 | 1 |  | Completed | 2019-09-25 | 1.88 | 1 | Noe Gomez | Completed |  | 2.25 | 1 | Marcia Garay | Current | 2019-10-21 | 0.08 | 2 | Andrew Clemons | Completed | 2019-09-19 | 0.08 | 4 | Marcia Garay | Completed | 2019-09-27 | 5.75 | 5 | Marcia Garay | Completed |  | 16.29 | 12 | Marcia Garay | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-11 |  | 1.04 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-09-26 |  | LOMA LINDA | Redlands | https://heliotrack.completesolar.com/job.php?action=review&jobID=28202 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28202 | https://completesolar.sugarondemand.com/#Opportunities/1a93b452-d986-11e9-afab-0630baf9dcb8 | Dustin Dunaway | HDM Capital | 2019-09-17 | HDM Electric Inc | 1a93b452-d986-11e9-afab-0630baf9dcb8 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12 |  | *Need to fix IF statement for F1 score if FI is BLANK
28483 | PIP_PENDING | PIP_PENDING | 3725 Cedar Vale Way | Fallbrook | CA | 92028 | Max L Myers | 2019-09-27 10:51 | 4088138399 | maxmyers10@gmail.com |  | 7607235825 |  | 10453 | 0.181 | Michael Marlaire | 2019-09-17 | 6.1 |  | CUIC Inc | Darlynn Lacap | 2019-09-05 | 2019-09-09 09:00 | LR6-60HPB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-18 | Final Permit | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-18 07:00 | 2019-09-27 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 2 | 2 | Daniel Speegle | Completed | 2019-10-08 | 12.79 | 1 | Ara Sotto | Completed | 2019-10-18 | 4.88 | 5 | Brian Le | Completed | 2019-10-01 | 0.79 | 3 | Andrew Moralez | Completed | 2019-10-01 | 0.34 | 1 | Andrew Moralez | Completed | 2019-10-18 | 0.46 | 2 | Ara Sotto | Completed |  | 1.04 | 2 | Ara Sotto | Current | 2019-10-11 | 4 | 2 | Brian Le | Completed | 2019-10-07 | 7.88 | 2 | Darlynn Lacap | Completed | 2019-10-01 | 1.88 | 1 |  | Completed | 2019-10-15 | 16.84 | 1 | Andrew Clemons | Completed | 2019-10-21 | 1.33 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-21 12:19 |  | 2019-10-21 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 5.08 | [11 empty] | 2019-10-02 |  | SAN DIEGO COUNTY | Fallbrook | https://heliotrack.completesolar.com/job.php?action=review&jobID=28483 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28483 | https://completesolar.sugarondemand.com/#Opportunities/e3f8347c-d96c-11e9-bd9d-0630baf9dcb8 | Jimmy Evans |  | 2019-09-05 | iEnergy ElectricSolar | e3f8347c-d96c-11e9-bd9d-0630baf9dcb8 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
28510 | PIP_PENDING | PIP_PENDING | 15107 South Frailey Avenue | Compton | CA | 90221 | Agustina Alvarez | 2019-09-16 13:20 | 5627559056 | tinaalvarez1965@gmail.com |  |  |  | 7043 | 0.153 |  | 2019-09-09 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-06 | 2019-09-13 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-18 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-18 07:00 | 2019-09-16 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.96 | 2 | Daniel Speegle | Completed | 2019-10-12 | 17.41 | 1 | Ara Sotto | Completed |  | 6.04 | 5 | Brian Le | Current | 2019-09-27 | 4.96 | 3 | Andrew Moralez | Completed | 2019-10-04 | 5 | 15 | Andrew Moralez | Completed | 2019-10-18 | 0.46 | 1 | Ara Sotto | Completed |  | 1.04 | 2 | Ara Sotto | Current | 2019-10-11 | 16.04 | 2 | Brian Le | Completed | 2019-09-19 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 2 | 1 |  | Completed | 2019-10-18 | 21.91 | 1 | Noe Gomez | Completed |  | 1.54 | 1 | Darlynn Lacap | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-31 15:28 |  |  | 1.04 | 2 | Ara Sotto | Current | [10 empty] | 8.28 | [11 empty] | 2019-10-18 |  | LOS ANGELES COUNTY | Compton | https://heliotrack.completesolar.com/job.php?action=review&jobID=28510 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28510 | https://completesolar.sugarondemand.com/#Opportunities/d795e060-d32e-11e9-8cf1-02ae981fbade | Cesar Valdizan | Cesar Valdizan | 2019-09-06 | Green Road Solar Crew | d795e060-d32e-11e9-8cf1-02ae981fbade | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
28864 | PIP_APPROVED | PIP_APPROVED | 7514 Dunkirk Avenue | Highland | CA | 92346 | Kelly Robbins | 2019-10-12 10:18 | 9512368401 | kmonville918@gmail.com | Kevin Robbins | 9512039209 |  | 9353 | 0.16 | Shaun Labelle | 2019-09-23 | 5.795 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-18 | 2019-09-21 12:00 | LR6-60HPB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-10-18 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-17 | 2019-10-14 | 5.59 | 2 | Marcia Garay | Completed | 2019-10-14 | 0.12 | 2 | Daniel Speegle | Completed |  | 10.88 | 1 | Ara Sotto | Current |  | 1.04 | 5 | Brian Le | Current | 2019-10-14 | 3.26 | 3 | Andrew Moralez | Completed | 2019-10-14 | 0.08 | 4 | Andrew Moralez | Completed | 2019-10-18 | 1.46 | 2 | Ara Sotto | Completed | 2019-10-21 | 0.71 | 2 | Ara Sotto | Completed | 2019-10-18 | 6.67 | 2 | Brian Le | Completed | 2019-10-15 | 3 | 2 | Marcia Garay | Completed | 2019-10-14 | 0.08 | 1 |  | Completed | 2019-10-18 | 6.21 | 1 | Andrew Clemons | Completed |  | 2.54 | 1 | Marcia Garay | Current |  | 0.33 | 2 | Noe Gomez | Current | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-23 |  | 0 | 2 |  | Inactive |  | 2.54 | 1 | Ara Sotto | Current | 2019-10-15 | 1.63 | 2 | Marcia Garay | Completed | 6.25 | [11 empty] | 2019-10-18 | 2019-10-21 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28864 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28864 | https://completesolar.sugarondemand.com/#Opportunities/95544b90-de25-11e9-9dd2-069e4f790264 | Summit Marketing Inc | Martha Reyes | 2019-09-16 | HDM Electric Inc | 95544b90-de25-11e9-9dd2-069e4f790264 |  | 3 | -25 | 2 | 5 | 5 | 5 | -13
29021 | SP APPROVED |  | 9490 Santa Cruz Road | Desert Hot Springs | CA | 92240 | Sandra Cornejo | 2019-09-23 11:13 | 7606607945 | sscornejo58@gmail.com |  |  |  | 5539 | 0.122 | Shaun Labelle | 2019-09-23 | 3.05 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-19 | 2019-09-20 09:00 | LR6-60PE-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-18 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-18 07:00 | 2019-09-23 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-25 | 2.17 | 2 | Daniel Speegle | Completed | 2019-10-03 | 5.71 | 1 | Ara Sotto | Completed | 2019-10-10 | 4.21 | 5 | Brian Le | Completed | 2019-10-02 | 3.5 | 3 | Andrew Moralez | Completed | 2019-10-08 | 4.08 | 2 | Andrew Moralez | Completed | 2019-10-18 | 2.25 | 1 | Ara Sotto | Completed |  | 1.04 | 2 | Ara Sotto | Current | 2019-10-04 | 5.17 | 2 | Brian Le | Completed | 2019-09-27 | 1.67 | 2 | Marcia Garay | Completed | 2019-09-26 | 0.92 | 1 |  | Completed | 2019-09-30 | 2.79 | 1 | Jeremiah Liend | Completed |  | 3.33 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 15:27 |  |  | 1.04 | 2 | Ara Sotto | Current | [10 empty] | 2.29 | [11 empty] | 2019-10-04 |  | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=29021 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29021 | https://completesolar.sugarondemand.com/#Opportunities/cb23cf72-de2d-11e9-b96a-0630baf9dcb8 | PJB Division |  | 2019-09-19 | Green Road Solar Crew | cb23cf72-de2d-11e9-b96a-0630baf9dcb8 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26919 | PIP_APPROVED | PIP_APPROVED | 1122 Sagebrush Avenue | San Jacinto | CA | 92582 | Carolina Valencia | 2019-09-21 19:18 | 9092516855 | morathis909@gmail.com | Yesenia Valencia |  | yesvalencia21@yahoo.com | 8466 | 0.17 | Michael Marlaire | 2019-09-21 | 5.49 | Ara Sotto | Branden Williams | Darlynn Lacap | 2019-09-20 | 2019-09-21 15:00 | LR6-60HPB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-17 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-16 07:00 | 2019-09-24 | 1.54 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 2.08 | 2 | Daniel Speegle | Completed | 2019-10-10 | 10.13 | 1 | Ara Sotto | Completed | 2019-10-17 | 3.75 | 5 | Brian Le | Completed | 2019-10-02 | 3.04 | 3 | Andrew Moralez | Completed | 2019-10-08 | 4.08 | 10 | Andrew Moralez | Completed | 2019-10-17 | 1.25 | 2 | Ara Sotto | Completed | 2019-10-17 | 0.08 | 2 | Ara Sotto | Completed | 2019-10-11 | 10.08 | 2 | Brian Le | Completed | 2019-09-27 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 0.75 | 1 |  | Completed | 2019-10-04 | 5.88 | 1 | Noe Gomez | Completed | 2019-10-17 | 1.5 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 1.79 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-23 |  | 2.29 | 2 | Ara Sotto | Current | [10 empty] | 1.84 | [11 empty] | 2019-10-16 | 2019-10-17 | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26919 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26919 | https://completesolar.sugarondemand.com/#Opportunities/3eaa321a-dcdf-11e9-8be6-069e4f790264 | Branden Williams |  | 2019-07-05 | HDM Electric Inc | 3eaa321a-dcdf-11e9-8be6-069e4f790264 | 4 | 0 | 0 | 5 | 5 | 5 | 5 | 15
27502 | PIP_APPROVED | PIP_APPROVED | 1480 Kilt Avenue | Placentia | CA | 92870 | Donald Lohoff | 2019-08-01 13:39 | 7143099597 | tslohoff@gmail.com | Tammy Lohoff | 7143093735 |  | 17796 | 0.171 | Chris Peaslee | 2019-08-01 | 12.81 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-27 | 2019-08-01 12:00 | LR6-60PB-305M | 305 | 42 | LONGi Solar | SolarEdge | SE11400A-US RGM | Composite | Line-side Tap | 2019-10-17 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-21 07:00 | 2019-08-05 | 1.88 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 4.13 | 2 | Jethro Andal | Completed | 2019-08-02 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-17 | 23.75 | 5 | Brian Le | Completed | 2019-08-21 | 3 | 3 | Andrew Moralez | Completed | 2019-09-13 | 15.88 | 14 | Andrew Moralez | Completed | 2019-10-17 | 18.42 | 3 | Ara Sotto | Completed | 2019-09-25 | 0.08 | 2 | Ara Sotto | Completed | 2019-09-13 | 23.04 | 2 | Brian Le | Completed | 2019-08-12 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 4.92 | 1 |  | Completed | 2019-08-21 | 7.92 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 4.5 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 1.92 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-10 |  | 0 | 2 |  | Inactive |  | 20.71 | 1 | Ara Sotto | Current | 2019-08-12 | 0.79 | 2 | Darlynn Lacap | Completed | 1.12 | [11 empty] | 2019-09-11 | 2019-09-25 | PLACENTIA | Placentia | https://heliotrack.completesolar.com/job.php?action=review&jobID=27502 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27502 | https://completesolar.sugarondemand.com/#Opportunities/71efaa76-b49c-11e9-a5bf-02ae981fbade | Marco Valdizan |  | 2019-07-27 | HDM Electric Inc | 71efaa76-b49c-11e9-a5bf-02ae981fbade |  | 0 | -25 | 5 | 5 | 5 | 5 | -10
27999 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1737 Date Palm Drive | Palmdale | CA | 93551 | Thomas Lackey | 2019-08-24 07:24 | 6613179837 | tomlackeyhq@gmail.com | Justin Lackey | 6612085087 |  | 15884 | 0.138 | Bill Angevine | 2019-08-23 | 10.065 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-16 | 2019-08-23 15:00 | LR6-60PE-305M | 305 | 33 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Tile Concrete | Line-side Tap | 2019-10-17 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-27 07:00 | 2019-08-26 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-08-28 | 1.71 | 2 | Daniel Speegle | Completed | 2019-09-10 | 5.96 | 1 | Ara Sotto | Completed | 2019-10-12 | 12.54 | 5 | Brian Le | Completed | 2019-09-04 | 1.92 | 3 | Andrew Moralez | Completed | 2019-09-18 | 10.13 | 5 | Andrew Moralez | Completed | 2019-10-17 | 14.25 | 3 | Ara Sotto | Completed |  | 2.29 | 2 | Ara Sotto | Current | 2019-09-13 | 9.04 | 2 | Brian Le | Completed | 2019-08-30 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-28 | 0.08 | 1 |  | Completed | 2019-09-10 | 5.79 | 1 | Andrew Clemons | Completed | 2019-09-27 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-20 |  | 2.29 | 2 | Ara Sotto | Current | 2019-10-17 | 14.25 | 1 | Ara Sotto | Completed | 2019-08-29 | 0.96 | 2 | Darlynn Lacap | Completed | 10.75 | [11 empty] | 2019-09-11 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27999 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27999 | https://completesolar.sugarondemand.com/#Opportunities/c9cbe436-c67a-11e9-b63d-0630baf9dcb8 | George Sarkis |  | 2019-08-16 | JK Solar | c9cbe436-c67a-11e9-b63d-0630baf9dcb8 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28364 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 4741 Opal Avenue | Palmdale | CA | 93552 | Dennis Mcgrail | 2019-09-09 09:29 | 6619655334 | grail1950@gmail.com | Donna McGrail | 6619655325 |  | 7605 | 0.155 | Shaun Labelle | 2019-09-09 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-31 | 2019-09-04 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-10-17 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-17 07:00 | 2019-09-09 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.96 | 2 | Daniel Speegle | Completed | 2019-09-18 | 5.71 | 1 | Ara Sotto | Completed | 2019-10-17 | 10.83 | 5 | Brian Le | Completed | 2019-09-17 | 3.88 | 3 | Ernesto Enriquez | Completed | 2019-10-04 | 12.96 | 5 | Ernesto Enriquez | Completed | 2019-10-17 | 15.25 | 1 | Ara Sotto | Completed |  | 2.29 | 2 | Ara Sotto | Current | 2019-09-19 | 6.75 | 2 | Brian Le | Completed | 2019-09-10 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 0.88 | 1 |  | Completed | 2019-09-17 | 4.88 | 1 | Jeremiah Liend | Completed | 2019-10-17 | 1.58 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-01 |  | 2.29 | 2 | Ara Sotto | Current | [10 empty] | 10.21 | [11 empty] | 2019-09-24 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28364 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28364 | https://completesolar.sugarondemand.com/#Opportunities/f2cd7a2e-d31e-11e9-b1d6-02ae981fbade | Solar Raze | Kevin Adams | 2019-08-31 | JK Solar | f2cd7a2e-d31e-11e9-b1d6-02ae981fbade | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28615 | SP APPROVED |  | 3544 North Amberwood Avenue | Rialto | CA | 92377 | Veronica Hernandez | 2019-09-11 17:22 | 9095438000 | preshus1221@yahoo.com | Tyron Potter | 3109959815 |  | 14.5 |  | Shaun Labelle | 2019-09-11 | 4.88 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-09-10 | 2019-09-11 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-17 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-17 07:00 | 2019-09-12 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-09-13 | 1.04 | 2 | Daniel Speegle | Completed | 2019-09-26 | 8.96 | 1 | Ara Sotto | Completed | 2019-10-17 | 3.96 | 5 | Brian Le | Completed | 2019-09-17 | 0 | 3 | Andrew Moralez | Completed | 2019-10-09 | 16.08 | 7 | Andrew Moralez | Completed | 2019-10-17 | 0.46 | 1 | Ara Sotto | Completed |  | 2.08 | 2 | Ara Sotto | Current | 2019-10-11 | 18.96 | 2 | Brian Le | Completed | 2019-09-16 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.83 | 1 |  | Completed | 2019-09-19 | 4.04 | 1 | Jill Allen | Completed | 2019-10-17 | 0.5 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-21 15:13 |  |  | 2.08 | 2 | Ara Sotto | Current | [10 empty] | 13.13 | [11 empty] | 2019-09-26 |  | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28615 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28615 | https://completesolar.sugarondemand.com/#Opportunities/4abca1bc-d4f3-11e9-9b97-02ae981fbade | Dominic Labadie |  | 2019-09-10 | Blalock Electric&Solar | 4abca1bc-d4f3-11e9-9b97-02ae981fbade | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28811 | SP APPROVED |  | 26456 Ridge Vale Drive | Santa Clarita | CA | 91321 | Patricia Lopez Medina | 2019-09-17 07:47 | 6616005765 | pgmp11@gmail.com |  |  |  | 5535 | 0.16 | Alex Holdridge | 2019-09-17 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-14 | 2019-09-16 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-10-12 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-12 | 2019-09-19 | 2.13 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.92 | 1 | Ara Sotto | Completed | 2019-10-12 | 5.38 | 5 | Brian Le | Completed | 2019-10-02 | 7.88 | 3 | Ernesto Enriquez | Completed | 2019-10-04 | 2.08 | 0 | Andrew Moralez | Completed | 2019-10-17 | 4.29 | 1 | Ara Sotto | Completed |  | 2.37 | 2 | Ara Sotto | Current | 2019-10-04 | 10.96 | 2 | Brian Le | Completed | 2019-09-19 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 1.04 | 1 |  | Completed | 2019-09-24 | 2.88 | 1 | Andrew Clemons | Completed | 2019-10-17 | 4.46 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-09 |  | 0 | 2 |  | Inactive |  | 6.5 | 1 | Ara Sotto | Current | 2019-10-01 | 1.42 | 2 | Darlynn Lacap | Completed | 3.62 | [11 empty] | 2019-10-02 |  | SANTA CLARITA | Newhall | https://heliotrack.completesolar.com/job.php?action=review&jobID=28811 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28811 | https://completesolar.sugarondemand.com/#Opportunities/f37dffe8-d959-11e9-bad4-022c40d974e6 | Emily Bowden |  | 2019-09-14 | Green Road Solar Crew | f37dffe8-d959-11e9-bad4-022c40d974e6 |  | 4 | -25 | 0 | 5 | 5 | 5 | -15
28930 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 10278 Antrim Way | San Diego | CA | 92126 | Keyvan Mahdavifar | 2019-09-23 20:51 | 8582439460 | keyvanmahdavi@gmail.com | Edelita Mahdavifar | 8586881358 |  | 5104 | 0.187 | Chad Malloy | 2019-09-23 | 3.05 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-21 | 2019-09-23 15:00 | LR6-60HPB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-17 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-10-17 07:00 | 2019-09-24 | 0.63 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.04 | 2 | Daniel Speegle | Completed | 2019-10-10 | 2 | 1 | Christina Horton | Completed | 2019-10-17 | 0 | 5 | Brian Le | Completed |  | 9.08 | 3 | Andrew Moralez | Current |  | 0 | 4 |  | Inactive | 2019-10-17 | 0.42 | 1 | Christina Horton | Completed |  | 2.13 | 2 | Christina Horton | Current | 2019-10-17 | 5.88 | 2 | Brian Le | Completed | 2019-10-09 | 0.88 | 2 | Marcia Garay | Completed | 2019-10-07 | 0.08 | 1 |  | Completed | 2019-10-09 | 1 | 1 | Noe Gomez | Completed |  | 2.54 | 1 | Marcia Garay | Current | 2019-10-21 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-28 |  | 2.13 | 2 | Christina Horton | Current | [10 empty] | 8.83 | 2019-10-11 | 7.25 | 14 | James Fernandez | Completed | 2019-10-11 | 2019-10-11 | 0.46 | 1 | James Fernandez | Completed |  |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=28930 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28930 | https://completesolar.sugarondemand.com/#Opportunities/76d22d5a-de7e-11e9-9821-02ae981fbade | Thomas Noble |  | 2019-09-18 | Infinity Energy Inc | 76d22d5a-de7e-11e9-9821-02ae981fbade | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
27867 | PIP_PENDING | PIP_PENDING | 5366 Country View Drive | Richmond | CA | 94803 | John Laset | 2019-08-15 06:51 | 4084696625 | john.laset@gmail.com | Ning Laset | 4084490140 |  | 5643.15 |  | Ricardo Virgen | 2019-08-15 | 4.07 | Christina Horton | SolarIT Inc | Marcia Garay | 2019-08-12 | 2019-08-13 15:00 | LG370Q1C-V5 | 370 | 11 | LG Electronics | Enphase | IQ7-60-2-US | Tile Concrete | NO | 2019-10-16 | Final Permit | Sunlight Financial Loan | 1 | 0 |  |  | 0 | 1 | 2019-10-15 07:00 | 2019-08-15 | 0.33 | 2 | Marcia Garay | Completed | 2019-08-19 | 1.88 | 2 | Jethro Andal | Completed | 2019-08-20 | 0.92 | 1 | Christina Horton | Completed | 2019-10-15 | 1.88 | 5 | Brian Le | Completed | 2019-08-20 | 1 | 3 | Andrew Moralez | Completed | 2019-08-30 | 7.88 | 5 | Andrew Moralez | Completed | 2019-10-16 | 1.75 | 1 | Christina Horton | Completed |  | 2.96 | 2 | Christina Horton | Current | 2019-10-11 | 37.04 | 2 | Brian Le | Completed | 2019-08-20 | 1.04 | 2 | Marcia Garay | Completed | 2019-08-19 | 0 | 1 |  | Completed | 2019-09-03 | 7.55 | 1 | Andrew Clemons | Completed |  | 4.75 | 1 | Marcia Garay | Current | 2019-10-18 | 0.08 | 2 | Andrew Clemons | Completed | 2019-08-29 | 9.75 | 4 | Marcia Garay | Completed | 2019-09-06 | 4.96 | 5 | Marcia Garay | Completed | 2019-09-12 | 3.96 | 12 | Marcia Garay | Completed |  | 2.33 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-16 15:00 |  | 2019-10-17 | 0.63 | 2 | Christina Horton | Completed | [10 empty] | 2.42 | [11 empty] | 2019-08-27 |  | CONTRA COSTA COUNTY | El Sobrante | https://heliotrack.completesolar.com/job.php?action=review&jobID=27867 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27867 | https://completesolar.sugarondemand.com/#Opportunities/954d2aa8-bf63-11e9-85fd-02ae981fbade | SolarIT Inc |  | 2019-08-12 | OSullivan Green Solar | 954d2aa8-bf63-11e9-85fd-02ae981fbade | 1 | 5 | 10 | -2 | 5 | 5 | 5 | 18
28858 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 6186 Paseo Monona | Carlsbad | CA | 92009 | Laura Wolf | 2019-09-20 12:10 | 8587759029 | lauraewolf@icloud.com | Scott Wolf | 8587759028 |  | 5650.85 |  | Ryan Malloy | 2019-09-20 | 6.03 |  | CUIC Inc | Darlynn Lacap | 2019-09-19 | 2019-09-20 09:00 | LG335N1C-A5 | 335 | 18 | LG Electronics | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-16 | Final Permit | SunRun PPA Prepaid | 0 | 0 |  | 0 | 0 | 1 | 2019-10-16 07:00 | 2019-09-20 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 2 | 2 | Daniel Speegle | Completed | 2019-10-08 | 9.92 | 1 | Ara Sotto | Completed | 2019-10-16 | 0.08 | 5 | Christina Horton | Completed | 2019-09-27 | 0.04 | 3 | Andrew Moralez | Completed | 2019-09-27 | 0.08 | 1 | Andrew Moralez | Completed | 2019-10-16 | 0.54 | 2 | Ara Sotto | Completed |  | 3 | 2 | Ara Sotto | Current | 2019-10-16 | 15.75 | 2 | Brian Le | Completed | 2019-09-24 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.08 | 1 |  | Completed | 2019-10-08 | 10.04 | 1 | Jill Allen | Completed | 2019-10-17 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-18 17:27 |  | 2019-10-18 | 1.75 | 2 | Ara Sotto | Completed | [10 empty] | 20.12 | [11 empty] | 2019-09-30 |  | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=28858 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28858 | https://completesolar.sugarondemand.com/#Opportunities/290be684-dbda-11e9-b8b6-02ae981fbade | Straight Talk Solar Co | Eddie Alberton | 2019-09-16 | iEnergy ElectricSolar | 290be684-dbda-11e9-b8b6-02ae981fbade | 2 | 5 | 7 | -2 | 5 | 5 | 5 | 15
28936 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1422 Santa Rosa Street | Oceanside | CA | 92058 | Joe Anderson | 2019-09-27 09:01 | 9493501501 | joeguntheranderson@hotmail.com | Shelli Anderson | 9493501414 |  | 4830 | 0.002 | Chad Malloy | 2019-09-27 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-09-24 | 2019-09-25 15:00 | LR6-60HPB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-16 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-16 07:00 | 2019-10-03 | 2.17 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 0 | 2 | Daniel Speegle | Completed | 2019-10-10 | 4.92 | 1 | Christina Horton | Completed | 2019-10-16 | 4.79 | 5 | Brian Le | Completed | 2019-10-04 | 0.67 | 3 | Ernesto Enriquez | Completed |  | 11.21 | 2 | Ernesto Enriquez | Current | 2019-10-16 | 0.42 | 1 | Christina Horton | Completed |  | 3.08 | 2 | Christina Horton | Current | 2019-10-08 | 0.08 | 2 | Brian Le | Completed | 2019-10-09 | 2.87 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 0.04 | 1 |  | Completed | 2019-10-08 | 2.88 | 1 | Jeremiah Liend | Completed | 2019-10-17 | 1.5 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-21 |  | 3.08 | 2 | Christina Horton | Current | [10 empty] | 3.17 | [11 empty] | 2019-10-08 |  | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28936 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28936 | https://completesolar.sugarondemand.com/#Opportunities/f0eaf964-e13f-11e9-8861-022c40d974e6 | Alan Moberg | Chris Moberg | 2019-09-18 | Infinity Energy Inc | f0eaf964-e13f-11e9-8861-022c40d974e6 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
28982 | SP APPROVED |  | 1443 Capri Lane | San Jacinto | CA | 92583 | Ismael Balcazar | 2019-09-23 18:16 | 9515524092 | yzzy47@yahoo.com | Gracelia Balcazar | 9514875923 |  | 7529 | 0.126 | Chris Peaslee | 2019-09-23 | 4.575 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-18 | 2019-09-23 15:00 | LR6-60HPB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-16 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-16 07:00 | 2019-09-24 | 0.63 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.21 | 2 | Daniel Speegle | Completed | 2019-10-03 | 4.75 | 1 | Ara Sotto | Completed | 2019-10-16 | 2.92 | 5 | Brian Le | Completed | 2019-10-02 | 3.04 | 3 | Andrew Moralez | Completed | 2019-10-07 | 3.17 | 10 | Andrew Moralez | Completed | 2019-10-16 | 0.38 | 1 | Ara Sotto | Completed |  | 3.13 | 2 | Ara Sotto | Current | 2019-10-11 | 10.21 | 2 | Brian Le | Completed | 2019-09-27 | 0.75 | 2 | Marcia Garay | Completed | 2019-09-27 | 0.79 | 1 |  | Completed | 2019-10-03 | 4.92 | 1 | Andrew Clemons | Completed |  | 3.54 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-22 |  | 3.13 | 2 | Ara Sotto | Current | [10 empty] | 6.17 | [11 empty] | 2019-10-16 |  | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28982 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28982 | https://completesolar.sugarondemand.com/#Opportunities/d993d7ba-de68-11e9-9ad9-069e4f790264 | PJB Division |  | 2019-09-18 | Power Town Solar Electric | d993d7ba-de68-11e9-9ad9-069e4f790264 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
26914 | PIP_APPROVED | PIP_APPROVED | 9064 Rosecrest Lane | Fontana | CA | 92335 | Martin Munoz | 2019-09-12 13:55 | 6263945431 | martinmunoz61589@gmail.com |  |  |  | 9315 | 0.139 | Shaun Labelle | 2019-08-28 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-04-16 | 2019-07-20 15:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-15 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-15 07:00 | 2019-09-12 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 5.75 | 2 | Daniel Speegle | Completed | 2019-09-26 | 13.13 | 1 | Ara Sotto | Completed | 2019-10-15 | 0.67 | 5 | Brian Le | Completed | 2019-09-27 | 10.09 | 3 | Andrew Moralez | Completed | 2019-10-11 | 12.17 | 12 | Andrew Moralez | Completed | 2019-10-15 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-21 | 3.75 | 2 | Ara Sotto | Completed | 2019-10-11 | 21.12 | 2 | Brian Le | Completed | 2019-09-17 | 3.01 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.79 | 1 |  | Completed | 2019-09-26 | 13.17 | 1 | Noe Gomez | Completed | 2019-10-17 | 2.5 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-17 15:03 |  |  | 4.08 | 2 | Ara Sotto | Current | [10 empty] | 11.6 | [11 empty] | 2019-10-11 | 2019-10-20 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=26914 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26914 | https://completesolar.sugarondemand.com/#Opportunities/90167eae-c9e5-11e9-a7db-022c40d974e6 | 300 Stars Inc | Administrator 300 Stars | 2019-07-05 | Power Town Solar Electric | 90167eae-c9e5-11e9-a7db-022c40d974e6 | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27690 | PIP_PENDING | PIP_PENDING | 2040 Bear Valley Parkway | Escondido | CA | 92027 | Haydee Hill | 2019-09-03 12:12 | 7605057512 | haydee_92025@yahoo.com | Preston Hill | 7605057113 |  | 13092 |  | Michael Marlaire | 2019-09-03 | 9.15 |  | Kyle Wilson | Darlynn Lacap | 2019-08-14 | 2019-08-19 09:00 | LR6-60PB-305M | 305 | 30 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-10-15 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-10-15 07:00 | 2019-09-03 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 3.04 | 2 | Daniel Speegle | Completed | 2019-10-08 | 14.66 | 1 | Ara Sotto | Completed |  | 1.25 | 5 | Brian Le | Current | 2019-09-09 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-09 | 0.08 | 15 | Andrew Moralez | Completed | 2019-10-15 | 0.42 | 2 | Ara Sotto | Completed |  | 4.08 | 2 | Ara Sotto | Current | 2019-10-11 | 16.79 | 2 | Brian Le | Completed | 2019-09-09 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-23 | 3.71 | 1 | Andrew Clemons | Completed | 2019-10-16 | 1.42 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-17 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 0.96 | 2 | Ashley Rockwood | Completed |  | 1.08 | 2 | Darlynn Lacap | Current | 2019-10-21 | 0.92 | 1 | Noe Gomez | Completed | 2019-10-16 14:59 |  | 2019-10-16 | 0.96 | 2 | Ara Sotto | Completed | [10 empty] | 16.02 | [11 empty] | 2019-09-30 |  | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=27690 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27690 | https://completesolar.sugarondemand.com/#Opportunities/acb4bc5e-ce7e-11e9-aaae-022c40d974e6 | Kyle Wilson |  | 2019-08-06 | iEnergy ElectricSolar | acb4bc5e-ce7e-11e9-aaae-022c40d974e6 | 1 | 6 | 10 | -2 | 5 | 5 | 5 | 18
28085 | SP APPROVED |  | 36555 Silverado Drive | Palmdale | CA | 93550 | Hector Torres | 2019-09-03 14:47 | 8183264985 | hectorres88@gmail.com | Sonia Alvares | 8189294706 |  | 6785 | 0.13 | Bill Angevine | 2019-09-03 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-28 | 2019-08-29 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-15 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-15 07:00 | 2019-09-04 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 5.54 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-15 | 10.13 | 5 | Brian Le | Completed | 2019-09-26 | 7.08 | 3 | Andrew Moralez | Completed | 2019-09-26 | 0 | 5 | Ernesto Enriquez | Completed | 2019-10-15 | 0.42 | 1 | Ara Sotto | Completed |  | 4.08 | 2 | Ara Sotto | Current | 2019-10-01 | 7.08 | 2 | Brian Le | Completed | 2019-09-20 | 3.79 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.96 | 1 |  | Completed | 2019-09-26 | 7.92 | 1 | Andrew Clemons | Completed | 2019-10-17 | 2.5 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-17 15:00 |  |  | 4.08 | 2 | Ara Sotto | Current | [10 empty] | 11.3 | [11 empty] | 2019-10-03 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28085 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28085 | https://completesolar.sugarondemand.com/#Opportunities/512c2cbc-ce94-11e9-82df-022c40d974e6 | Solar Raze | Emily Bowden | 2019-08-20 | JK Solar | 512c2cbc-ce94-11e9-82df-022c40d974e6 | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28400 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3400 Dovewood Street | Bakersfield | CA | 93309 | Mahlon Keel | 2019-09-20 15:42 | 6618351729 | mkeel@att.net |  | 6618894313 |  | 8038 | 0.162 | Bill Angevine | 2019-09-04 | 6.1 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-09-03 | 2019-09-04 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-15 | Install | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-14 07:00 | 2019-09-20 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 2.71 | 2 | Daniel Speegle | Completed | 2019-10-01 | 15.09 | 1 | Christina Horton | Completed | 2019-10-14 | 0.71 | 5 | Brian Le | Completed | 2019-10-14 | 15.83 | 3 | Andrew Moralez | Completed | 2019-10-15 | 9.05 | 5 | Andrew Moralez | Completed | 2019-10-15 | 1.71 | 2 | Christina Horton | Completed |  | 4.17 | 2 | Christina Horton | Current | 2019-10-04 | 7 | 2 | Brian Le | Completed | 2019-09-25 | 3.96 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.21 | 1 |  | Completed | 2019-10-11 | 18.12 | 1 | Andrew Clemons | Completed | 2019-10-17 | 3.88 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-23 |  | 4.17 | 2 | Christina Horton | Current | [10 empty] | 14.83 | [11 empty] | 2019-10-14 |  | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=28400 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28400 | https://completesolar.sugarondemand.com/#Opportunities/b44fb7c0-cf6e-11e9-b3c4-02ae981fbade | Ryan Wilcox |  | 2019-09-03 | Anley Electric | b44fb7c0-cf6e-11e9-b3c4-02ae981fbade | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28574 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 14954 Pebblebrook Place | Victorville | CA | 92394 | Jeffrey Bahra | 2019-09-13 07:19 | 7143053500 | nimpue@gmail.com | Eric Bahra | 7145016615 |  | 13878 | 0.166 | Shaun Labelle | 2019-09-12 | 7.625 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-09 | 2019-09-10 12:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-15 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-15 07:00 | 2019-09-16 | 1.33 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.92 | 2 | Daniel Speegle | Completed | 2019-10-12 | 10.63 | 1 | Ara Sotto | Completed | 2019-10-15 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-25 | 0.08 | 10 | Andrew Moralez | Completed | 2019-10-15 | 0.42 | 2 | Ara Sotto | Completed |  | 4.08 | 2 | Ara Sotto | Current | 2019-10-17 | 8.88 | 2 | Brian Le | Completed | 2019-10-03 | 3.21 | 2 | Darlynn Lacap | Completed | 2019-09-18 | 0.83 | 1 |  | Completed | 2019-09-25 | 5.29 | 1 | Andrew Clemons | Completed | 2019-10-16 | 1.5 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-16 14:56 |  |  | 4.08 | 2 | Ara Sotto | Current | [10 empty] | 12.12 | [11 empty] | 2019-10-09 |  | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28574 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28574 | https://completesolar.sugarondemand.com/#Opportunities/59db910a-d631-11e9-a1e4-022c40d974e6 | CUIC Inc | Christopher Cellini | 2019-09-09 | HDM Electric Inc | 59db910a-d631-11e9-a1e4-022c40d974e6 | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28590 | PIP_APPROVED | PIP_APPROVED | 76820 Florida Avenue | Palm Desert | CA | 92211 | Driaanne Tuicotombo | 2019-09-20 10:34 | 7609843123 | driatuico@gmail.com | Kenneth Tombo | 7608958266 |  | 15137 | 0.139 | Michael Marlaire | 2019-09-20 | 8.235 | Ara Sotto | Solar Power Marketing | Marcia Garay | 2019-09-09 | 2019-09-17 12:00 | LR6-60PB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-10-15 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-10-15 | 2019-10-02 | 4.17 | 2 | Marcia Garay | Completed | 2019-09-25 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-15 | 1.96 | 5 | Brian Le | Completed | 2019-10-02 | 0.08 | 3 | Andrew Moralez | Completed | 2019-10-15 | 9 | 5 | Andrew Moralez | Completed | 2019-10-15 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-18 | 3.04 | 2 | Ara Sotto | Completed | 2019-10-11 | 7 | 2 | Brian Le | Completed | 2019-10-02 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-26 | 0.08 | 1 |  | Completed | 2019-10-03 | 1 | 1 | Andrew Clemons | Completed | 2019-10-16 | 1.46 | 1 | Marcia Garay | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-18 | 1.04 | 2 | Ashley Rockwood | Completed |  | 1.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-16 15:00 |  | 2019-10-17 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 3.88 | 2019-10-11 | 7.08 | 14 | James Fernandez | Completed | 2019-10-11 | 2019-10-11 | 0.46 | 1 | James Fernandez | Completed | 2019-10-09 | 2019-10-18 | PALM DESERT | Palm Desert | https://heliotrack.completesolar.com/job.php?action=review&jobID=28590 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28590 | https://completesolar.sugarondemand.com/#Opportunities/d20e01f8-dbcc-11e9-b21b-02ae981fbade | Solar Power Marketing |  | 2019-09-09 | Green Road Solar Crew | d20e01f8-dbcc-11e9-b21b-02ae981fbade | 2 | 3 | 7 | 2 | 5 | 5 | 5 | 19
28961 | PIP_APPROVED | PIP_APPROVED | 11477 Palisades Court | Adelanto | CA | 92301 | Regina Parker | 2019-09-24 10:33 | 7603017357 | geegee86@live.com | Novella | 7606235535 |  | 8341 | 0.15 | Bill Angevine | 2019-09-20 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-18 | 2019-09-20 09:00 | LR6-60HPB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-15 | Install | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-14 07:00 | 2019-09-24 | 2 | 2 | Darlynn Lacap | Completed | 2019-09-25 | 0.88 | 2 | Daniel Speegle | Completed | 2019-10-02 | 4.92 | 1 | Ara Sotto | Completed | 2019-10-15 | 7 | 5 | Brian Le | Completed | 2019-10-02 | 3.79 | 3 | Ernesto Enriquez | Completed | 2019-10-17 | 11.13 | 3 | Andrew Moralez | Completed | 2019-10-15 | 2.88 | 2 | Ara Sotto | Completed | 2019-10-15 | 0.17 | 2 | Ara Sotto | Completed | 2019-10-04 | 6.92 | 2 | Brian Le | Completed | 2019-09-25 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1.13 | 1 |  | Completed | 2019-09-27 | 2.08 | 1 | Andrew Clemons | Completed | 2019-10-17 | 4.96 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.79 | 2 | Jill Allen | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-14 |  | 4.08 | 2 | Ara Sotto | Current | [10 empty] | 6 | [11 empty] | 2019-10-07 | 2019-10-15 | ADELANTO | Adelanto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28961 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28961 | https://completesolar.sugarondemand.com/#Opportunities/0610614a-dbea-11e9-9e0d-02ae981fbade | CUIC Inc | Christopher Cellini | 2019-09-18 | HDM Electric Inc | 0610614a-dbea-11e9-9e0d-02ae981fbade | 6 | 0 | -5 | 5 | 5 | 5 | 5 | 10
26517 | PIP_PENDING | PIP_PENDING | 4252 Gordon Way | La Mesa | CA | 91942 | Sabrina Gill | 2019-07-05 12:30 | 6199489263 | sabrinalg@att.net |  |  |  | 8505.76 |  | Ryan Malloy | 2019-07-05 | 4.69 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-29 | 2019-07-01 15:00 | LG335N1C-A5 | 335 | 14 | LG Electronics | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-10-14 | Installation Complete | Sunlight Financial Loan | 0 | 0 |  |  | 0 | 1 | 2019-10-14 | 2019-07-05 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-09 | 2 | 2 | Daniel Speegle | Completed | 2019-08-28 | 32.88 | 1 | Christina Horton | Completed | 2019-10-14 | 58.29 | 5 | Brian Le | Completed | 2019-07-17 | 1.21 | 3 | Andrew Moralez | Completed | 2019-07-29 | 7.96 | 0 | Andrew Moralez | Completed | 2019-10-14 | 0.5 | 1 | Christina Horton | Completed |  | 5 | 2 | Christina Horton | Current | 2019-07-15 | 0.04 | 2 | Brian Le | Completed | 2019-07-15 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-16 | 1.79 | 1 |  | Completed | 2019-07-20 | 5.33 | 1 | Andrew Clemons | Completed |  | 5.54 | 1 | Marcia Garay | Current | 2019-10-15 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-07-09 | 0.04 | 2 | Marcia Garay | Completed | 9.42 | [11 empty] | 2019-07-17 |  | LA MESA | La Mesa | https://heliotrack.completesolar.com/job.php?action=review&jobID=26517 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26517 | https://completesolar.sugarondemand.com/#Opportunities/2f8c8650-9f5b-11e9-a565-022c40d974e6 | Blake Sanders |  | 2019-06-18 | Infinity Energy Inc | 2f8c8650-9f5b-11e9-a565-022c40d974e6 |  | 7 | -25 | -2 | 5 | 5 | 5 | -17
27059 | PIP_PENDING | PIP_PENDING | 11 Maitland Avenue | Hawthorne | NJ | 7506 | Eric Kanowitz | 2019-07-15 16:22 | 6319024800 | kanoweric@yahoo.com | Jessica Elliot |  | 9734491133 | 6538.56 |  | Andrew Weber | 2019-07-15 | 4.88 | Christina Horton | Sunlogic Power | Marcia Garay | 2019-07-11 | 2019-07-13 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-14 | Installation Complete | Sunlight Financial Loan | 0 | 0 |  |  |  |  | 2019-10-14 07:00 | 2019-07-16 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-18 | 2.25 | 2 | Jethro Andal | Completed | 2019-08-19 | 21.63 | 1 | Christina Horton | Completed | 2019-10-14 | 0.08 | 5 | Christina Horton | Completed | 2019-07-29 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-19 | 29.83 | 10 | Ernesto Enriquez | Completed | 2019-10-14 | 0.5 | 1 | Christina Horton | Completed |  | 5 | 2 | Christina Horton | Current | 2019-10-14 | 59.79 | 2 | Brian Le | Completed | 2019-07-19 | 0.63 | 2 | Marcia Garay | Completed | 2019-07-22 | 1.58 | 1 |  | Completed | 2019-07-20 | 1.13 | 1 | Noe Gomez | Completed |  | 5.17 | 1 | Marcia Garay | Current | 2019-10-15 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-29 08:50 |  |  | 1.71 | 2 | Christina Horton | Current | [10 empty] | 20.87 | [11 empty] | 2019-08-21 |  | Default | Hawthorne | https://heliotrack.completesolar.com/job.php?action=review&jobID=27059 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27059 | https://completesolar.sugarondemand.com/#Opportunities/60ebcf18-a757-11e9-acb6-0630baf9dcb8 | Anthony Fowler |  | 2019-07-11 | Skyline Solar | 60ebcf18-a757-11e9-acb6-0630baf9dcb8 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
27973 | PIP_PENDING | PIP_PENDING | 1289 Hamilton Avenue Unit A | Seaside | CA | 93955 | Moises Hernandez | 2019-08-19 15:58 | 8313834961 | moises2303@att.net |  |  |  | 533 |  | Ricardo Virgen | 2019-08-19 | 3.355 | Christina Horton | Total HomeSolar | Marcia Garay | 2019-08-15 | 2019-08-19 12:00 | LR6-60PE-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-10-14 | Installation Complete | SVN Loan |  |  |  |  | 1 |  | 2019-10-07 07:00 | 2019-08-19 | 0.08 | 2 | Marcia Garay | Completed | 2019-08-22 | 2.79 | 2 | Jethro Andal | Completed | 2019-09-26 | 23.96 | 1 | Christina Horton | Completed | 2019-10-14 | 0.71 | 5 | Brian Le | Completed | 2019-08-27 | 3 | 3 | Andrew Moralez | Completed | 2019-09-06 | 6.92 | 0 | Andrew Moralez | Completed | 2019-10-14 | 5.5 | 2 | Christina Horton | Completed |  | 5 | 2 | Christina Horton | Current | 2019-10-04 | 29.21 | 2 | Brian Le | Completed | 2019-08-23 | 0.59 | 2 | Marcia Garay | Completed | 2019-08-22 | 0.04 | 1 |  | Completed | 2019-08-28 | 3.79 | 1 | Andrew Clemons | Completed | 2019-10-07 | 0.46 | 1 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 4.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-11 | 2019-10-15 | 0.92 | 2 | Christina Horton | Completed | 2019-10-08 | 0.5 | 1 | Christina Horton | Completed | 2019-08-27 | 2.67 | 2 | Marcia Garay | Completed | 5.17 | 2019-09-10 | 14.67 | 14 | James Fernandez | Completed | 2019-09-10 | 2019-09-10 | 0 | 1 | James Fernandez | Completed | 2019-08-27 |  | SEASIDE | Seaside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27973 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27973 | https://completesolar.sugarondemand.com/#Opportunities/a3c056aa-c2ce-11e9-a0d6-02ae981fbade | Total HomeSolar |  | 2019-08-18 | OSullivan Green Solar | a3c056aa-c2ce-11e9-a0d6-02ae981fbade | 1 | 7 | 10 | -2 | 5 | 5 | 5 | 18
27974 | PIP_PENDING | PIP_PENDING | 1289 Hamilton Avenue Unit B | Seaside | CA | 93955 | Moises Hernandez | 2019-08-19 15:58 | 8313834961 | moises2303@att.net |  |  |  | 5533 |  | Ricardo Virgen | 2019-08-19 | 3.355 | Christina Horton |  | Marcia Garay |  | 2019-08-19 13:00 | LR6-60PE-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-10-14 | NEM Submitted | SVN Loan |  |  |  |  | 1 |  | 2019-10-07 07:00 | 2019-08-19 | 0.08 | 2 | Marcia Garay | Completed | 2019-08-22 | 2.83 | 2 | Jethro Andal | Completed | 2019-09-26 | 23.96 | 1 | Christina Horton | Completed | 2019-10-14 | 0.71 | 5 | Brian Le | Completed | 2019-08-27 | 3 | 3 | Andrew Moralez | Completed | 2019-09-06 | 6.92 | 0 | Andrew Moralez | Completed | 2019-10-14 | 5.5 | 2 | Christina Horton | Completed |  | 5 | 2 | Christina Horton | Current | 2019-10-04 | 29.21 | 2 | Brian Le | Completed | 2019-08-23 | 0.79 | 2 | Marcia Garay | Completed | 2019-08-22 | 0.04 | 1 |  | Completed | 2019-08-28 | 3.75 | 1 | Andrew Clemons | Completed | 2019-10-07 | 0.46 | 1 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive | [15 empty] | 2019-10-21 | 3.88 | 2 | Ashley Rockwood | Completed |  | 0.17 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-11 | 2019-10-15 | 0.92 | 2 | Christina Horton | Completed | 2019-10-08 | 0.92 | 1 | Christina Horton | Completed | 2019-08-27 | 2.67 | 2 | Marcia Garay | Completed | 5 | 2019-09-09 | 14.08 | 14 | James Fernandez | Completed | 2019-09-09 | 2019-09-09 | 0.08 | 1 | James Fernandez | Completed | 2019-08-27 |  | SEASIDE | Seaside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27974 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27974 | https://completesolar.sugarondemand.com/#Opportunities/bcc1ff9a-c2cf-11e9-9a89-022c40d974e6 | Total HomeSolar |  | 2019-08-15 | OSullivan Green Solar | bcc1ff9a-c2cf-11e9-9a89-022c40d974e6 | 1 | 7 | 10 | -2 | 5 | 5 | 5 | 18
28801 | PIP_APPROVED | PIP_APPROVED | 1096 North Lancewood Avenue | Rialto | CA | 92376 | Jose F Garcia | 2019-09-17 10:17 | 9099008678 | lucilag11@yahoo.com | Lucila Garcia |  |  | 4924 | 0.18 | Shaun Labelle | 2019-09-17 | 3.355 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-14 | 2019-09-16 12:00 | LR6-60HPB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-14 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-14 | 2019-09-18 | 1.21 | 2 | Marcia Garay | Completed | 2019-09-20 | 1.71 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.04 | 1 | Ara Sotto | Completed | 2019-10-14 | 1 | 5 | Brian Le | Completed | 2019-09-25 | 1.88 | 3 | Andrew Moralez | Completed | 2019-10-09 | 10.13 | 7 | Andrew Moralez | Completed | 2019-10-14 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-15 | 1.17 | 2 | Ara Sotto | Completed | 2019-10-11 | 13.08 | 2 | Brian Le | Completed | 2019-09-24 | 2.08 | 2 | Marcia Garay | Completed | 2019-09-23 | 1.13 | 1 |  | Completed | 2019-09-24 | 2.04 | 1 | Andrew Clemons | Completed |  | 5.54 | 1 | Marcia Garay | Current | 2019-10-16 | 0.75 | 2 | Jill Allen | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-15 16:40 |  |  | 5.04 | 2 | Ara Sotto | Current | [10 empty] | 1.54 | [11 empty] | 2019-10-04 | 2019-10-15 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28801 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28801 | https://completesolar.sugarondemand.com/#Opportunities/e24f2f3e-d96e-11e9-95f0-02ae981fbade | 300 Stars Inc | Oscar Hernandez | 2019-09-14 | HDM Electric Inc | e24f2f3e-d96e-11e9-95f0-02ae981fbade | 7 | 1 | -5 | 5 | 5 | 5 | 5 | 10
28870 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 71600 Painted Canyon Road | Palm Desert | CA | 92260 | Barbara Hubbard | 2019-09-17 12:35 | 7602726672 | hubbard.barbara@gmail.com |  |  |  | 8617 | 0.132 | Michael Marlaire | 2019-09-17 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-16 | 2019-09-17 09:00 | LR6-60HPB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-14 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-14 07:00 | 2019-09-18 | 0.83 | 2 | Marcia Garay | Completed | 2019-09-20 | 2.17 | 2 | Daniel Speegle | Completed | 2019-09-24 | 1.92 | 1 | Ara Sotto | Completed | 2019-10-14 | 12.04 | 5 | Brian Le | Completed | 2019-09-25 | 2.08 | 3 | Ernesto Enriquez | Completed | 2019-10-10 | 10.71 | 0 | Andrew Moralez | Completed | 2019-10-14 | 0.5 | 1 | Ara Sotto | Completed |  | 5.04 | 2 | Ara Sotto | Current | 2019-09-26 | 3.96 | 2 | Brian Le | Completed | 2019-09-20 | 0 | 2 | Marcia Garay | Completed | 2019-09-23 | 0.96 | 1 |  | Completed | 2019-09-26 | 3.83 | 1 | Andrew Clemons | Completed | 2019-10-16 | 2.42 | 1 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-15 16:18 |  |  | 5.04 | 2 | Ara Sotto | Current | [10 empty] | 1.33 | [11 empty] | 2019-09-25 |  | RIVERSIDE COUNTY | Palm Desert | https://heliotrack.completesolar.com/job.php?action=review&jobID=28870 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28870 | https://completesolar.sugarondemand.com/#Opportunities/3388c64a-d982-11e9-a96c-022c40d974e6 | PJB Division |  | 2019-09-16 | Green Road Solar Crew | 3388c64a-d982-11e9-a96c-022c40d974e6 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
25437 | PIP_APPROVED | PIP_APPROVED | 487 East 18th Street | San Bernardino | CA | 92404 | Pamela Weaver | 2019-10-02 09:49 | 9098557855 | weavpj2010@gmail.com | Adam Pilbeam | 9098867314 |  | 15805 | 0.19 | Alex Holdridge | 2019-05-15 | 11.285 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-05-08 | 2019-05-15 13:00 | LR6-60PB-305M | 305 | 37 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | MPU | 2019-10-12 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 1 | 1 | 2019-10-11 07:00 | 2019-10-02 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-10-02 | 4.41 | 2 | Daniel Speegle | Completed | 2019-10-08 | 37.88 | 1 | Ara Sotto | Completed | 2019-10-12 | 13.67 | 5 | Brian Le | Completed | 2019-10-02 | 9.79 | 3 | Andrew Moralez | Completed | 2019-10-02 | 15.25 | 1 | Andrew Moralez | Completed | 2019-10-12 | 1.04 | 3 | Ara Sotto | Completed | 2019-10-15 | 1.5 | 2 | Ara Sotto | Completed | 2019-10-04 | 22.76 | 2 | Brian Le | Completed | 2019-10-02 | 6.5 | 2 | Darlynn Lacap | Completed | 2019-10-02 | 1.79 | 1 |  | Completed | 2019-10-03 | 30.34 | 1 | Jeremiah Liend | Completed | 2019-10-17 | 4.75 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 1.13 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-16 |  | 0 | 2 |  | Inactive |  | 6.79 | 1 | Ara Sotto | Current | 2019-10-03 | 2.76 | 2 | Darlynn Lacap | Completed | 25.83 | 2019-10-11 | 22 | 14 | James Fernandez | Completed | 2019-10-03 | 2019-10-11 | 15.5 | 1 | James Fernandez | Completed | 2019-10-02 | 2019-10-15 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=25437 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25437 | https://completesolar.sugarondemand.com/#Opportunities/71d63c9a-775b-11e9-88c9-0630baf9dcb8 | Summit Marketing Inc | Martha Reyes | 2019-05-08 | Power Town Solar Electric | 71d63c9a-775b-11e9-88c9-0630baf9dcb8 |  | 3 | -25 | 2 | 5 | 5 | 5 | -13
28554 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1786 Sunshine Parkway | Palmdale | CA | 93551 | George Shahla | 2019-09-11 16:46 | 6612661030 | gshahla@avc.edu |  |  |  | 11198 | 0.14 | Bill Angevine | 2019-09-11 | 7.015 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-07 | 2019-09-11 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-12 | Final Permit | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-10 07:00 | 2019-09-13 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-09-13 | 0.13 | 2 | Daniel Speegle | Completed | 2019-09-27 | 4.21 | 1 | Ara Sotto | Completed | 2019-10-10 | 7.33 | 5 | Brian Le | Completed | 2019-09-26 | 2.38 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 0 | 5 | Ernesto Enriquez | Completed | 2019-10-12 | 2.04 | 2 | Ara Sotto | Completed |  | 5.71 | 2 | Ara Sotto | Current | 2019-10-01 | 4.29 | 2 | Brian Le | Completed | 2019-09-17 | 1.83 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.92 | 1 |  | Completed | 2019-10-01 | 6.26 | 1 | Andrew Clemons | Completed | 2019-10-16 | 4.75 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-21 21:25 |  | 2019-10-21 | 5.5 | 2 | Ara Sotto | Completed | [10 empty] | 8.08 | [11 empty] | 2019-10-03 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28554 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28554 | https://completesolar.sugarondemand.com/#Opportunities/49d62e8a-d4ee-11e9-b16f-022c40d974e6 | SCES Division | George Sarkis | 2019-09-07 | JK Solar | 49d62e8a-d4ee-11e9-b16f-022c40d974e6 | 9 | 9 | -5 | -2 | 5 | 5 | 5 | 3
27374 | PIP_PENDING | PIP_PENDING | 474 Steele Rd | New Hartford | CT | 6057 | Amanda Marsted | 2019-07-27 11:51 | 3476107017 | agmarsted@yahoo.com |  |  |  | 4787.4 |  | Hiram Velez | 2019-07-27 | 3.66 | Christina Horton | Sunlogic Power | Marcia Garay | 2019-07-23 | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-10-11 | Installation Complete | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-10-10 07:00 | 2019-07-30 | 1.63 | 2 | Darlynn Lacap | Completed | 2019-08-05 | 3.71 | 2 | Jethro Andal | Completed | 2019-08-19 | 7.92 | 1 | Christina Horton | Completed | 2019-10-10 | 0.08 | 5 | Christina Horton | Completed | 2019-08-14 | 3 | 3 | Andrew Moralez | Completed | 2019-08-23 | 7.08 | 10 | Ernesto Enriquez | Completed | 2019-10-11 | 1.5 | 1 | Christina Horton | Completed |  | 6 | 2 | Christina Horton | Current | 2019-10-04 | 26.21 | 2 | Brian Le | Completed | 2019-08-15 | 5.04 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 1.79 | 1 |  | Completed | 2019-08-19 | 7.79 | 1 | Andrew Clemons | Completed |  | 5.5 | 1 | Marcia Garay | Current | 2019-10-16 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-24 11:37 |  |  | 6 | 2 | Christina Horton | Current | [10 empty] | 26.56 | [11 empty] | 2019-08-28 |  | Default |  | https://heliotrack.completesolar.com/job.php?action=review&jobID=27374 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27374 | https://completesolar.sugarondemand.com/#Opportunities/6f2e1c24-b09f-11e9-92d8-0630baf9dcb8 | Anthony Fowler |  | 2019-07-23 | Skyline Solar | 6f2e1c24-b09f-11e9-92d8-0630baf9dcb8 | 10 | 10 | -5 | -2 | 5 | 5 | 5 | 3
28340 | PIP_PENDING | PIP_PENDING | 832 Tafolla St | Placentia | CA | 92870 | Judy Monteverde | 2019-09-17 10:39 | 7143185987 | andrewmonteverde@yahoo.com |  |  |  | 10504.15 |  | Chris Peaslee | 2019-09-17 | 6.71 | Ara Sotto | CS Direct | Darlynn Lacap | 2019-09-11 | 2019-09-14 15:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-11 | Installation Complete | SVN Loan | 0 | 0 |  |  |  | 0 | 2019-10-11 | 2019-09-18 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 1.42 | 2 | Daniel Speegle | Completed | 2019-10-03 | 9.58 | 1 | Ara Sotto | Completed | 2019-10-11 | 4.96 | 5 | Brian Le | Completed | 2019-09-23 | 0.08 | 3 | Andrew Moralez | Completed | 2019-10-01 | 2.25 | 14 | Andrew Moralez | Completed | 2019-10-11 | 0 | 2 | Ara Sotto | Completed |  | 6.13 | 2 | Ara Sotto | Current | 2019-10-04 | 9.21 | 2 | Brian Le | Completed | 2019-09-23 | 1.54 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 0.08 | 1 |  | Completed | 2019-10-11 | 15.75 | 1 | Andrew Clemons | Completed | 2019-10-17 | 4.08 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-23 |  | 6.13 | 2 | Ara Sotto | Current | [10 empty] | 10.67 | [11 empty] | 2019-10-17 |  | PLACENTIA | Placentia | https://heliotrack.completesolar.com/job.php?action=review&jobID=28340 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28340 | https://completesolar.sugarondemand.com/#Opportunities/f8002fce-d971-11e9-9a7b-022c40d974e6 | Robert Prado |  | 2019-09-17 | HDM Electric Inc | f8002fce-d971-11e9-9a7b-022c40d974e6 | 10 | 10 | -5 | -2 | 5 | 5 | 5 | 3
28561 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3101 Wellington Drive | Palmdale | CA | 93551 | David Chaffey | 2019-09-16 07:03 | 6616180221 | dcgold@dcgold.com | Laurie Chaffey | 6616182050 |  | 13376 | 0.124 | Bill Angevine | 2019-09-16 | 7.32 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-08 | 2019-09-10 15:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | Line-side Tap | 2019-10-11 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-11 | 2019-09-16 | 0.25 | 2 | Marcia Garay | Completed | 2019-09-19 | 2.88 | 2 | Daniel Speegle | Completed | 2019-10-09 | 13.96 | 1 | Ara Sotto | Completed | 2019-10-11 | 4.92 | 5 | Brian Le | Completed | 2019-10-01 | 7.04 | 3 | Andrew Moralez | Completed | 2019-10-01 | 0 | 5 | Andrew Moralez | Completed | 2019-10-11 | 0 | 2 | Ara Sotto | Completed |  | 6.13 | 2 | Ara Sotto | Current | 2019-10-04 | 11.04 | 2 | Brian Le | Completed | 2019-09-19 | 0.08 | 2 | Marcia Garay | Completed | 2019-09-20 | 1.08 | 1 |  | Completed | 2019-09-23 | 2.21 | 1 | Andrew Clemons | Completed |  | 6.13 | 1 | Marcia Garay | Current | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-09 |  | 0 | 2 |  | Inactive |  | 6.13 | 1 | Ara Sotto | Current | 2019-09-20 | 0.88 | 2 | Marcia Garay | Completed | 0.71 | [11 empty] | 2019-10-08 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28561 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28561 | https://completesolar.sugarondemand.com/#Opportunities/a26d49a8-d88a-11e9-9f43-0630baf9dcb8 | SCES Division |  | 2019-09-08 | JK Solar | a26d49a8-d88a-11e9-9f43-0630baf9dcb8 |  | 10 | -25 | -2 | 5 | 5 | 5 | -17
28582 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 216 Umber Court | San Diego | CA | 92114 | Oscar Medina | 2019-09-10 17:47 | 6198691308 | mylo_star@yahoo.com | Mylee Medina | 6196756254 |  | 7369 | 0.145 | Ryan Malloy | 2019-09-10 | 4.88 |  | Solar Power Marketing | Marcia Garay | 2019-09-09 | 2019-09-10 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-11 | Install | SunRun Monthly |  | 0 |  |  |  |  | 2019-10-11 07:00 | 2019-09-11 | 0.79 | 2 | Marcia Garay | Completed | 2019-09-16 | 2.88 | 2 | Daniel Speegle | Completed | 2019-10-01 | 10.92 | 1 | Christina Horton | Completed | 2019-10-11 | 4.92 | 5 | Brian Le | Completed | 2019-09-23 | 1.04 | 3 | Andrew Moralez | Completed | 2019-10-12 | 14.33 | 15 | Andrew Moralez | Completed | 2019-10-11 | 0.42 | 1 | Christina Horton | Completed |  | 6.13 | 2 | Christina Horton | Current | 2019-10-04 | 10.96 | 2 | Brian Le | Completed | 2019-09-19 | 2.92 | 2 | Marcia Garay | Completed | 2019-09-20 | 2 | 1 |  | Completed | 2019-09-24 | 5.96 | 1 | Jill Allen | Completed | 2019-10-16 | 3.5 | 1 | Marcia Garay | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-17 15:12 |  |  | 5.92 | 2 | Christina Horton | Inactive | [10 empty] | 7.09 | [11 empty] | 2019-10-14 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=28582 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28582 | https://completesolar.sugarondemand.com/#Opportunities/9c573ea4-d42d-11e9-96b2-022c40d974e6 | Solar Power Marketing |  | 2019-09-09 | iEnergy ElectricSolar | 9c573ea4-d42d-11e9-96b2-022c40d974e6 | 10 | 10 | -5 | -2 | 5 | 5 | 5 | 3
28904 | PIP_APPROVED | PIP_APPROVED | 2813 Brandeis Drive | Oceanside | CA | 92056 | Adam Warner (WinBack) | 2019-09-21 13:37 | 9495790452 | courtniebeers@gmail.com | Courtnie Beers | 7608916604 | adam.warner83@gmail.com | 11659 | 0.145 |  | 2019-09-21 | 8.235 |  |  | Darlynn Lacap |  |  | LR6-60HPB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE7600H-US RGM |  | NO | 2019-10-11 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-10-09 07:00 | 2019-09-23 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.96 | 2 | Daniel Speegle | Completed | 2019-10-04 | 8.08 | 1 | Ara Sotto | Completed | 2019-10-10 | 4.08 | 5 | Brian Le | Completed | 2019-09-25 | 0.08 | 3 | Andrew Moralez | Completed | 2019-10-09 | 0.08 | 2 | Andrew Moralez | Completed | 2019-10-11 | 2.54 | 2 | Ara Sotto | Completed | 2019-10-17 | 3.67 | 2 | Ara Sotto | Completed | 2019-10-04 | 7.92 | 2 | Brian Le | Completed | 2019-09-24 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-25 | 0.92 | 1 |  | Completed | 2019-09-27 | 2.96 | 1 | Jill Allen | Completed | 2019-10-09 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-10-16 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-17 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 2.04 | 2 | Ashley Rockwood | Completed |  | 0.25 | 2 | Darlynn Lacap | Current |  | 0.25 | 1 | Noe Gomez | Current | 2019-10-15 12:29 |  | 2019-10-15 | 1.88 | 2 | Ara Sotto | Completed | [10 empty] | 0 | 2019-10-10 | 11.75 | 14 | James Fernandez | Completed | 2019-10-08 | 2019-10-10 | 1.96 | 1 | James Fernandez | Completed | 2019-10-11 | 2019-10-17 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28904 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28904 | https://completesolar.sugarondemand.com/#Opportunities/90828e96-dcaf-11e9-ba6c-022c40d974e6 | Cory Borbon |  | 2019-09-17 | iEnergy ElectricSolar | 90828e96-dcaf-11e9-ba6c-022c40d974e6 | 4 | 6 | 0 | -2 | 5 | 5 | 5 | 8
27703 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3646 Lake Shore Road | Fallbrook | CA | 92028 | George Cimino | 2019-09-03 17:04 | 7609787845 | george.cimino@yahoo.com |  |  |  | 9358 | 0.18 | Michael Marlaire | 2019-08-13 | 6.1 |  | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-10 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-10 | Installation Complete | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-10-10 07:00 | 2019-09-03 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 2.92 | 2 | Daniel Speegle | Completed | 2019-09-25 | 25.96 | 1 | Christina Horton | Completed | 2019-10-10 | 2.88 | 5 | Brian Le | Completed | 2019-09-06 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-06 | 1.13 | 1 | Andrew Moralez | Completed | 2019-10-10 | 0.46 | 1 | Christina Horton | Completed |  | 7.08 | 2 | Christina Horton | Current | 2019-10-07 | 32.13 | 2 | Brian Le | Completed | 2019-09-06 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.96 | 1 |  | Completed | 2019-09-16 | 19.17 | 1 | Andrew Clemons | Completed | 2019-09-27 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | 2019-09-05 | 14.21 | 4 | Darlynn Lacap | Completed | 2019-09-23 | 11.88 | 5 | Darlynn Lacap | Completed | 2019-09-24 | 1.13 | 12 | Darlynn Lacap | Completed |  | 0.96 | 2 | Ashley Rockwood | Inactive |  | 0.71 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-25 |  | 5.04 | 2 | Christina Horton | Current | [10 empty] | 6.33 | [11 empty] | 2019-09-06 |  | SAN DIEGO COUNTY | Fallbrook | https://heliotrack.completesolar.com/job.php?action=review&jobID=27703 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27703 | https://completesolar.sugarondemand.com/#Opportunities/a2ffd8a8-be32-11e9-91cd-0630baf9dcb8 | Jimmy Evans |  | 2019-08-06 | iEnergy ElectricSolar | a2ffd8a8-be32-11e9-91cd-0630baf9dcb8 | 11 | 11 | -15 | -2 | 5 | 5 | 5 | -7
28145 | PIP_PENDING | PIP_PENDING | 23458 Mount Lassen Way | Murrieta | CA | 92562 | Diane Reed | 2019-09-19 11:46 | 6197884071 | dreed2962@gmail.com |  |  |  | 9897 | 0.141 | Alex Holdridge | 2019-09-11 | 5.795 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-23 | 2019-08-27 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Tile Concrete | NO | 2019-10-10 | Final Permit | SunRun Monthly | [6 empty] | 2019-10-10 07:00 | 2019-09-19 | 6.08 | 2 | Marcia Garay | Completed | 2019-09-24 | 3 | 2 | Daniel Speegle | Completed | 2019-10-03 | 6.96 | 1 | Christina Horton | Completed | 2019-10-10 | 5.08 | 5 | Brian Le | Completed | 2019-09-26 | 1.79 | 3 | Andrew Moralez | Completed | 2019-10-09 | 9.13 | 1 | Andrew Moralez | Completed | 2019-10-10 | 0.33 | 2 | Christina Horton | Completed |  | 7.17 | 2 | Christina Horton | Current | 2019-09-30 | 0.32 | 2 | Brian Le | Completed | 2019-10-02 | 6.21 | 2 | Marcia Garay | Completed | 2019-09-24 | 0.16 | 1 |  | Completed | 2019-09-19 | 0.08 | 1 | Noe Gomez | Completed | 2019-10-16 | 4.25 | 1 | Marcia Garay | Completed | 2019-10-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.04 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-15 15:07 |  | 2019-10-16 | 3.79 | 2 | Christina Horton | Completed | [10 empty] | 17.92 | [11 empty] | 2019-09-27 |  | MURRIETA | Murrieta | https://heliotrack.completesolar.com/job.php?action=review&jobID=28145 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28145 | https://completesolar.sugarondemand.com/#Opportunities/9c11bd90-d4b7-11e9-80f1-02ae981fbade | Lindsey Lange | Michael Foster | 2019-08-23 | Infinity Energy Inc | 9c11bd90-d4b7-11e9-80f1-02ae981fbade | 6 | 11 | -5 | -2 | 5 | 5 | 5 | 3
28177 | PIP_APPROVED | PIP_APPROVED | 3812 Frost Way | Bakersfield | CA | 93311 | Carol Sanchez | 2019-08-31 08:22 | 6612054056 | carolsnchz56@gmail.com |  |  |  | 5482 | 0.133 | Bill Angevine | 2019-08-27 | 3.965 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-08-24 | 2019-08-27 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-10 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-08 07:00 | 2019-09-03 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 2 | 2 | Daniel Speegle | Completed | 2019-09-25 | 13.75 | 1 | Christina Horton | Completed | 2019-10-10 | 0.08 | 5 | Brian Le | Completed | 2019-09-06 | 0.83 | 3 | Andrew Moralez | Completed | 2019-10-04 | 20.04 | 5 | Ernesto Enriquez | Completed | 2019-10-10 | 2.54 | 1 | Christina Horton | Completed | 2019-10-15 | 2.96 | 2 | Christina Horton | Completed | 2019-10-04 | 20.04 | 2 | Brian Le | Completed | 2019-09-06 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 0 | 1 |  | Completed | 2019-09-10 | 3.04 | 1 | Noe Gomez | Completed | 2019-10-09 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-15 | 0.96 | 2 | Ashley Rockwood | Completed |  | 4.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-14 16:05 |  | 2019-10-14 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 6.92 | [11 empty] | 2019-09-13 | 2019-10-15 | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=28177 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28177 | https://completesolar.sugarondemand.com/#Opportunities/075b183e-cc03-11e9-98ef-02ae981fbade | Ryan Wilcox |  | 2019-08-24 | Anley Electric | 075b183e-cc03-11e9-98ef-02ae981fbade | 4 | 5 | 0 | -2 | 5 | 5 | 5 | 8
28220 | PIP_APPROVED | PIP_APPROVED | 15590 El Centro Road | Hesperia | CA | 92345 | Derilyn Johnson | 2019-09-16 11:25 | 3105923486 | deparie@hotmail.com |  |  |  | 5915 | 0.145 | Shaun Labelle | 2019-09-16 | 3.05 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-27 | 2019-09-10 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-10 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-10-10 | 2019-09-17 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-18 | 1.25 | 2 | Daniel Speegle | Completed | 2019-09-20 | 1.79 | 1 | Ara Sotto | Completed | 2019-10-10 | 4.17 | 5 | Brian Le | Completed | 2019-09-27 | 3.96 | 3 | Ernesto Enriquez | Completed | 2019-09-27 | 0.08 | 14 | Andrew Moralez | Completed | 2019-10-10 | 0 | 1 | Ara Sotto | Completed | 2019-10-11 | 0.58 | 2 | Ara Sotto | Completed | 2019-10-04 | 11.88 | 2 | Brian Le | Completed | 2019-09-18 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.88 | 1 |  | Completed | 2019-09-24 | 3.96 | 1 | Andrew Clemons | Completed | 2019-10-09 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.88 | 2 | Andrew Clemons | Completed | [16 empty] | 0.17 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-21 | 2019-10-21 | 6.71 | 2 | Ara Sotto | Completed | [10 empty] | 0 | 2019-10-02 | 6.88 | 14 | James Fernandez | Completed | 2019-10-02 | 2019-10-02 | 0.08 | 1 | James Fernandez | Completed | 2019-10-17 | 2019-10-10 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=28220 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28220 | https://completesolar.sugarondemand.com/#Opportunities/4b20542c-d8af-11e9-89a0-069e4f790264 | Cory Hartman | Cory Hartman | 2019-08-27 | Power Town Solar Electric | 4b20542c-d8af-11e9-89a0-069e4f790264 | 11 | 1 | -15 | 5 | 5 | 5 | 5 | 0
28494 | PIP_APPROVED | PIP_APPROVED | 2565 Bonita Drive | Highland | CA | 92346 | Elaine Nicole Garcia | 2019-09-12 12:31 | 9099632130 | elaine4garcia15@gmail.com |  |  |  | 7119 | 0.165 | Chris Peaslee | 2019-09-12 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-06 | 2019-09-12 09:00 | Q.PEAK-G4.1 305 | 305 | 13 | Hanwha Q CELLS | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-10 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-10-10 | 2019-09-16 | 2 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-16 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-10 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-20 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-20 | 0.08 | 14 | Andrew Moralez | Completed | 2019-10-10 | 0 | 1 | Ara Sotto | Completed | 2019-10-11 | 0.75 | 2 | Ara Sotto | Completed | 2019-10-04 | 8.13 | 2 | Brian Le | Completed | 2019-09-17 | 1 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.08 | 1 |  | Completed | 2019-10-14 | 9.88 | 1 | Andrew Clemons | Completed | 2019-10-17 | 4.75 | 1 | Darlynn Lacap | Completed | 2019-10-21 | 0.16 | 2 | Noe Gomez | Completed | [16 empty] | 2.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-15 19:19 |  | 2019-10-17 | 4.75 | 2 | Ara Sotto | Completed | [10 empty] | 24.34 | 2019-10-02 | 6 | 14 | James Fernandez | Completed | 2019-10-02 | 2019-10-02 | 0 | 1 | James Fernandez | Completed | 2019-10-10 | 2019-10-11 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28494 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28494 | https://completesolar.sugarondemand.com/#Opportunities/d2bbf7ac-d593-11e9-88f2-02ae981fbade | Oscar Hernandez |  | 2019-09-06 | HDM Electric Inc | d2bbf7ac-d593-11e9-88f2-02ae981fbade | 7 | 1 | -5 | 5 | 5 | 5 | 5 | 10
28612 | PIP_APPROVED | PIP_APPROVED | 10732 El Nopal | Santee | CA | 92071 | Wendi Bender | 2019-09-18 17:41 | 6198716486 | wendisilver@hotmail.com | Charles Bender | 6198519736 |  | 8939 | 0.175 | Ryan Malloy | 2019-09-18 | 5.795 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-17 | 2019-09-18 15:00 | LR6-60HPB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-10 07:00 | 2019-09-19 | 0.92 | 2 | Marcia Garay | Completed | 2019-09-23 | 1.96 | 2 | Daniel Speegle | Completed | 2019-10-04 | 8.79 | 1 | Christina Horton | Completed | 2019-10-10 | 7.88 | 5 | Brian Le | Completed | 2019-09-26 | 2.75 | 3 | Andrew Moralez | Completed | 2019-10-03 | 5.33 | 10 | Andrew Moralez | Completed | 2019-10-10 | 0.38 | 2 | Christina Horton | Completed | 2019-10-14 | 2.04 | 2 | Christina Horton | Completed | 2019-09-30 | 2.25 | 2 | Brian Le | Completed | 2019-09-26 | 2.71 | 2 | Marcia Garay | Completed | 2019-09-23 | 0 | 1 |  | Completed | 2019-09-27 | 3.96 | 1 | Andrew Clemons | Completed |  | 7.54 | 1 | Marcia Garay | Current | 2019-10-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-15 | 1 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 2.92 | 2 | Ashley Rockwood | Completed |  | 1.13 | 2 | Marcia Garay | Current | 2019-10-21 | 0.79 | 1 | Noe Gomez | Completed | 2019-10-14 16:23 |  | 2019-10-14 | 2.04 | 2 | Christina Horton | Completed | [10 empty] | 0.54 | [11 empty] | 2019-10-10 | 2019-10-14 | SANTEE | Santee | https://heliotrack.completesolar.com/job.php?action=review&jobID=28612 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28612 | https://completesolar.sugarondemand.com/#Opportunities/2c2a25e8-da76-11e9-9a6a-02ae981fbade | Lee Allison |  | 2019-09-10 | Infinity Energy Inc | 2c2a25e8-da76-11e9-9a6a-02ae981fbade | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28710 | PIP_APPROVED | PIP_APPROVED | 6937 Mountain Avenue | Highland | CA | 92346 | Rodey Dyke | 2019-09-17 08:36 | 9095575969 | rodnco@gmail.com |  |  |  | 6063 | 0.155 | Shaun Labelle | 2019-09-16 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-12 | 2019-09-13 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-10 | 2019-09-20 | 2.96 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-10 | 4.17 | 5 | Brian Le | Completed | 2019-09-23 | 1.17 | 3 | Andrew Moralez | Completed | 2019-09-26 | 2.92 | 14 | Andrew Moralez | Completed | 2019-10-10 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-11 | 0.71 | 2 | Ara Sotto | Completed | 2019-10-04 | 10.21 | 2 | Brian Le | Completed | 2019-09-20 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 0.08 | 1 |  | Completed | 2019-10-04 | 10.17 | 1 | Jeremiah Liend | Completed | 2019-10-17 | 4.75 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.79 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-18 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 1.04 | 2 | Ashley Rockwood | Completed |  | 0.29 | 2 | Darlynn Lacap | Current |  | 0.29 | 1 | Noe Gomez | Current | 2019-10-15 19:16 |  | 2019-10-17 | 4.75 | 2 | Ara Sotto | Completed | [10 empty] | 1.75 | [11 empty] | 2019-10-11 | 2019-10-11 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28710 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28710 | https://completesolar.sugarondemand.com/#Opportunities/d516635e-d960-11e9-8f81-02ae981fbade | 300 Stars Inc | Oscar Hernandez | 2019-09-12 | HDM Electric Inc | d516635e-d960-11e9-8f81-02ae981fbade | 7 | 1 | -5 | 5 | 5 | 5 | 5 | 10
28926 | PIP_APPROVED | PIP_APPROVED | 25901 Deerberry Drive | Moreno Valley | CA | 92553 | Amador Galeana Perez | 2019-09-19 17:52 | 9515707752 | rosendolopez881@gmail.com | Maria Elena Galeana | (951)601-0086 |  | 5871 | 0.17 | Chris Peaslee | 2019-09-19 | 3.355 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-18 | 2019-09-19 15:00 | LR6-60HPB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-10 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-10 07:00 | 2019-09-20 | 0.63 | 2 | Marcia Garay | Completed | 2019-09-25 | 3.21 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-09 | 2.83 | 5 | Brian Le | Completed | 2019-09-30 | 1.13 | 3 | Andrew Moralez | Completed | 2019-09-30 | 0 | 3 | Andrew Moralez | Completed | 2019-10-10 | 1.88 | 1 | Ara Sotto | Completed | 2019-10-15 | 2.79 | 2 | Ara Sotto | Completed | 2019-10-04 | 1.13 | 2 | Brian Le | Completed | 2019-10-03 | 5.04 | 2 | Marcia Garay | Completed | 2019-09-27 | 1.79 | 1 |  | Completed | 2019-10-03 | 5.88 | 1 | Andrew Clemons | Completed |  | 8.79 | 1 | Marcia Garay | Current | 2019-10-21 | 3.71 | 2 | Jill Allen | Completed | [16 empty] | 2.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-11 15:17 |  | 2019-10-17 | 4.75 | 2 | Ara Sotto | Completed | [10 empty] | 0.79 | [11 empty] | 2019-10-03 | 2019-10-15 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28926 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28926 | https://completesolar.sugarondemand.com/#Opportunities/cd5e9dca-db40-11e9-803a-069e4f790264 | Oscar Hernandez |  | 2019-09-17 | Power Town Solar Electric | cd5e9dca-db40-11e9-803a-069e4f790264 | 7 | 5 | -5 | -2 | 5 | 5 | 5 | 3
28978 | PIP_APPROVED | PIP_APPROVED | 2131 East San Marcus Street | Compton | CA | 90221 | Irene Zepeda | 2019-09-23 15:14 | 4242369187 | irenezpd@yahoo.com | Jose Diaz | 3107224380 |  | 4575 | 0.146 | Chris Peaslee | 2019-09-23 | 3.05 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-18 | 2019-09-21 09:00 | LR6-60HPB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-10 | Installation Complete | SunRun Monthly | 0 | 0 | 1 | 0 |  | 1 | 2019-10-10 | 2019-09-24 | 0.83 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-26 | 0.04 | 1 | Ara Sotto | Completed | 2019-10-10 | 3.08 | 5 | Brian Le | Completed | 2019-10-04 | 2.92 | 3 | Andrew Moralez | Completed |  | 11.13 | 1 | Andrew Moralez | Current | 2019-10-10 | 0.63 | 1 | Ara Sotto | Completed | 2019-10-14 | 1.75 | 2 | Ara Sotto | Completed |  | 14.08 | 2 | Brian Le | Current | 2019-09-26 | 0 | 2 | Marcia Garay | Completed | 2019-10-01 | 3.04 | 1 |  | Completed | 2019-10-11 | 10.88 | 1 | Andrew Clemons | Completed |  | 7.54 | 1 | Marcia Garay | Current | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-15 |  | 6.88 | 2 | Ara Sotto | Current | [10 empty] | 5 | [11 empty] | 2019-10-07 | 2019-10-11 | COMPTON | Compton | https://heliotrack.completesolar.com/job.php?action=review&jobID=28978 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28978 | https://completesolar.sugarondemand.com/#Opportunities/79ff86c8-de4f-11e9-b1cd-069e4f790264 | Solar Raze | Cesar Valdizan | 2019-09-18 | Green Road Solar Crew | 79ff86c8-de4f-11e9-b1cd-069e4f790264 | 11 | 4 | -15 | 0 | 5 | 5 | 5 | -5
29068 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1644 Manor Drive | Vista | CA | 92084 | Sergio Martinez | 2019-09-23 19:07 | 7604969652 | fidelmartinezm13@gmail.com |  |  |  | 5727 | 0.142 | Michael Marlaire | 2019-09-23 | 3.355 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-21 | 2019-09-23 09:00 | LR6-60HPB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-10-10 | Install | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-10-10 | 2019-09-24 | 0.71 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.08 | 2 | Daniel Speegle | Completed | 2019-10-02 | 3.79 | 1 | Ara Sotto | Completed | 2019-10-10 | 2.96 | 5 | Brian Le | Completed | 2019-10-21 | 16.17 | 3 | Andrew Moralez | Completed | 2019-10-21 | 0.08 | 2 | Andrew Moralez | Completed | 2019-10-10 | 0.46 | 1 | Christina Horton | Completed |  | 7.04 | 2 | Christina Horton | Current | 2019-10-07 | 0.29 | 2 | Brian Le | Completed | 2019-10-02 | 4.16 | 2 | Marcia Garay | Completed | 2019-09-27 | 0.79 | 1 |  | Completed | 2019-09-30 | 1.83 | 1 | Jeremiah Liend | Completed |  | 7.54 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-15 |  | 0 | 2 |  | Inactive |  | 3.17 | 1 | Christina Horton | Inactive | 2019-09-27 | 0.75 | 2 | Marcia Garay | Completed | 7.96 | [11 empty] | 2019-10-23 |  | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=29068 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=29068 | https://completesolar.sugarondemand.com/#Opportunities/aad9dc46-de34-11e9-991c-02ae981fbade | Brett Martinez |  | 2019-09-21 | Infinity Energy Inc | aad9dc46-de34-11e9-991c-02ae981fbade |  | 11 | -25 | -2 | 5 | 5 | 5 | -17
23917 | PIP_PENDING | PIP_PENDING | 41146 Circle D Court | Temecula | CA | 92592 | Zorina Bennett | 2019-09-23 10:17 | 9516930895 | coppergirls@verizon.net | Deanna Williams | 9515512824 |  | 25107 |  | Chris Peaslee | 2019-05-06 | 16.165 | Ara Sotto | America's Choice | Darlynn Lacap | 2019-04-17 | 2019-04-22 11:00 | Q.PEAK-G4.1 305 | 305 | 53 | Hanwha Q CELLS | SolarEdge | SE11400A-US RGM | Composite | NO | 2019-10-09 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-02 07:00 | 2019-09-23 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 2.04 | 2 | Daniel Speegle | Completed | 2019-10-03 | 17.08 | 1 | Ara Sotto | Completed | 2019-10-09 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-24 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-24 | 0.08 | 0 | Andrew Moralez | Completed | 2019-10-09 | 5.46 | 4 | Ara Sotto | Completed |  | 8.04 | 2 | Ara Sotto | Current | 2019-09-30 | 12.79 | 2 | Brian Le | Completed | 2019-09-24 | 1.12 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.08 | 1 |  | Completed | 2019-09-26 | 12.04 | 1 | Andrew Clemons | Completed | 2019-10-17 | 11.5 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-14 15:56 |  |  | 8.04 | 2 | Ara Sotto | Current | [10 empty] | 48.94 | [11 empty] | 2019-09-24 |  | TEMECULA | Temecula | https://heliotrack.completesolar.com/job.php?action=review&jobID=23917 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=23917 | https://completesolar.sugarondemand.com/#Opportunities/a988c5e6-7011-11e9-868d-0630baf9dcb8 | America's Choice |  | 2019-03-20 | T&M Solar | a988c5e6-7011-11e9-868d-0630baf9dcb8 | 12 | 12 | -15 | -2 | 5 | 5 | 5 | -7
26654 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 17 Stonecastle Road | New Milford | CT | 6776 | Robert Reda | 2019-09-16 09:01 | 8603545354 | rreda2000@hotmail.com |  |  |  | 14460 | 0.18 | Hiram Velez | 2019-07-12 | 14.335 | Christina Horton | Solara Solar | Darlynn Lacap | 2019-07-10 | 2019-07-12 09:00 | LR6-60PB-305M | 305 | 47 | LONGi Solar | SolarEdge | SE11400A-US RGM | Composite | NO | 2019-10-09 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-08 07:00 | 2019-09-16 | 2.88 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 5.09 | 2 | Daniel Speegle | Completed | 2019-09-19 | 15.84 | 1 | Christina Horton | Completed | 2019-10-08 | 0.08 | 5 | Brian Le | Completed | 2019-09-16 | 0.96 | 3 | Andrew Moralez | Completed | 2019-09-16 | 4.83 | 10 | Andrew Moralez | Completed | 2019-10-09 | 1.42 | 3 | Christina Horton | Completed |  | 8.13 | 2 | Christina Horton | Current | 2019-10-04 | 14.25 | 2 | Brian Le | Completed | 2019-09-17 | 4.63 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 3.08 | 1 |  | Completed | 2019-09-17 | 18.93 | 1 | Andrew Clemons | Completed | 2019-10-09 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 09:01 |  |  | 6.79 | 2 | Christina Horton | Current | [10 empty] | 53.03 | [11 empty] | 2019-09-23 |  | Default |  | https://heliotrack.completesolar.com/job.php?action=review&jobID=26654 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26654 | https://completesolar.sugarondemand.com/#Opportunities/06ffddaa-a51d-11e9-9d7f-069e4f790264 | Solara Solar |  | 2019-06-24 | Skyline Solar | 06ffddaa-a51d-11e9-9d7f-069e4f790264 | 12 | 12 | -15 | -2 | 5 | 5 | 5 | -7
26944 | PIP_APPROVED | PIP_APPROVED | 361 West Cornell Drive | Rialto | CA | 92376 | Maria Ruiz | 2019-09-24 18:41 | 9098963724 | jovita_ruiz@yahoo.com | Salvador Delacruz | 6268482429 |  | 4761 | 0.164 | Alex Holdridge | 2019-07-17 | 3.05 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-09 | 2019-07-10 16:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-09 | NEM Submitted | SunRun Monthly | 0 | 1 |  |  | 0 | 1 | 2019-10-09 | 2019-09-25 | 1.63 | 2 | Marcia Garay | Completed | 2019-09-25 | 1.79 | 2 | Daniel Speegle | Completed | 2019-09-30 | 6.42 | 1 | Ara Sotto | Completed | 2019-10-09 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-25 | 0.17 | 3 | Andrew Moralez | Completed | 2019-09-27 | 9.25 | 7 | Andrew Moralez | Completed | 2019-10-09 | 0 | 1 | Ara Sotto | Completed | 2019-10-14 | 2.96 | 2 | Ara Sotto | Completed | 2019-10-04 | 16.04 | 2 | Brian Le | Completed | 2019-09-25 | 0.17 | 2 | Marcia Garay | Completed | 2019-09-25 | 1.88 | 1 |  | Completed | 2019-10-01 | 13.26 | 1 | Jill Allen | Completed |  | 8.04 | 1 | Marcia Garay | Current | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 6.04 | 2 | Ashley Rockwood | Completed |  | 0.25 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 15:48 |  | 2019-10-11 | 1.71 | 2 | Ara Sotto | Completed | [10 empty] | 18.62 | [11 empty] | 2019-09-25 | 2019-10-14 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26944 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26944 | https://completesolar.sugarondemand.com/#Opportunities/18beaa3c-a8e5-11e9-8e71-069e4f790264 | 300 Stars Inc |  | 2019-07-06 | Green Road Solar Crew | 18beaa3c-a8e5-11e9-8e71-069e4f790264 | 2 | 5 | 7 | -2 | 5 | 5 | 5 | 15
27387 | PIP_APPROVED | PIP_APPROVED | 1484 Leslie Drive | Hemet | CA | 92544 | Clara Perez | 2019-07-27 17:17 | 9512596983 | perezc69@gmail.com |  |  |  | 10190 | 0.132 | Chris Peaslee | 2019-07-27 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-23 | 2019-07-27 15:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-09 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-05 07:00 | 2019-07-29 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 1.79 | 2 | Jethro Andal | Completed | 2019-07-30 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-04 | 5.17 | 5 | Brian Le | Completed | 2019-08-13 | 8.04 | 3 | Andrew Moralez | Completed | 2019-09-27 | 30.79 | 1 | Andrew Moralez | Completed | 2019-10-09 | 4.46 | 2 | Ara Sotto | Completed | 2019-10-09 | 0.08 | 2 | Ara Sotto | Completed | 2019-09-26 | 39 | 2 | Brian Le | Completed | 2019-08-01 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 0.96 | 1 |  | Completed | 2019-08-07 | 4.75 | 1 | Andrew Clemons | Completed | 2019-10-09 | 4.42 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.92 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 7.79 | 2 | Ashley Rockwood | Completed |  | 0.25 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-21 | 2019-10-09 | 0.08 | 2 | Ara Sotto | Completed | [10 empty] | 6.6 | [11 empty] | 2019-08-20 | 2019-10-09 | HEMET | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=27387 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27387 | https://completesolar.sugarondemand.com/#Opportunities/eeef2bd8-b0cc-11e9-b9ea-069e4f790264 | SCES Division | PJB Division | 2019-07-23 | Power Town Solar Electric | eeef2bd8-b0cc-11e9-b9ea-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
27392 | SP APPROVED |  | 3437 Merrimac Avenue | San Diego | CA | 92117 | Daniel Stokes | 2019-08-21 15:11 | 8587524633 | dan.is.stoked@gmail.com | Judy Stokes | 8588693365 |  | 3685.25 | 0.18 | Chad Malloy | 2019-08-14 | 2.135 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-23 | 2019-07-26 09:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-10-09 | Installation Complete | Cash | 0 | 0 |  | 1 | 1 | 1 | 2019-10-09 07:00 | 2019-08-22 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2.46 | 2 | Daniel Speegle | Completed | 2019-10-02 | 29.83 | 1 | Christina Horton | Completed | 2019-10-09 | 24 | 5 | Brian Le | Completed | 2019-09-06 | 4.25 | 3 | Ernesto Enriquez | Completed | 2019-09-19 | 9 | 15 | Ernesto Enriquez | Completed | 2019-10-09 | 0.21 | 1 | Christina Horton | Completed |  | 8.33 | 2 | Christina Horton | Current | 2019-08-27 | 0.08 | 2 | Brian Le | Completed | 2019-08-29 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 7.54 | 1 |  | Completed | 2019-08-29 | 6.54 | 1 | Noe Gomez | Completed | 2019-10-09 | 0.46 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-23 |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-23 | 1.76 | 2 | Darlynn Lacap | Completed | 16.59 | 2019-10-02 | 32.13 | 14 | James Fernandez | Completed | 2019-10-02 | 2019-10-02 | 0.08 | 1 | James Fernandez | Completed | 2019-09-27 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27392 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27392 | https://completesolar.sugarondemand.com/#Opportunities/29e38c7e-bf60-11e9-8c88-069e4f790264 | Robert Blessing |  | 2019-07-23 | Infinity Energy Inc | 29e38c7e-bf60-11e9-8c88-069e4f790264 |  | 12 | -25 | -2 | 5 | 5 | 5 | -17
28141 | SP APPROVED |  | 1216 Van Pelt Avenue | Los Angeles | CA | 90063 | Daniel Garcia | 2019-08-26 11:45 | 3239152435 | fhukingslurms6@gmail.com | Pablo Garcia | 3235364741 |  | 6870 | 0.175 | Alex Holdridge | 2019-08-26 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-24 | 2019-08-26 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | MPU | 2019-10-09 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-08 | 2019-08-26 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 4 | 2 | Daniel Speegle | Completed | 2019-09-10 | 3.92 | 1 | Ara Sotto | Completed | 2019-10-09 | 0.08 | 5 | Brian Le | Completed | 2019-09-06 | 2 | 3 | Andrew Moralez | Completed |  | 31.08 | 15 | Andrew Moralez | Current | 2019-10-09 | 1.25 | 2 | Ara Sotto | Completed |  | 8.29 | 2 | Ara Sotto | Current | 2019-10-04 | 21.96 | 2 | Brian Le | Completed | 2019-08-30 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 1 |  | Completed | 2019-09-19 | 11 | 1 | Jeremiah Liend | Completed | 2019-10-09 | 1.46 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-19 |  | 0 | 2 |  | Inactive |  | 9.54 | 1 | Ara Sotto | Current | 2019-09-03 | 0.75 | 2 | Darlynn Lacap | Completed | 17.34 | [11 empty] | 2019-09-27 |  | LOS ANGELES COUNTY | Los Angeles | https://heliotrack.completesolar.com/job.php?action=review&jobID=28141 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28141 | https://completesolar.sugarondemand.com/#Opportunities/88d7a60a-c831-11e9-87bb-02ae981fbade | Oscar Hernandez |  | 2019-08-23 | Green Road Solar Crew | 88d7a60a-c831-11e9-87bb-02ae981fbade |  | 12 | -25 | -2 | 5 | 5 | 5 | -17
28354 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 716 Sonora Street East | San Bernardino | CA | 92404 | Claudio Ornelas | 2019-08-31 13:41 | 9097146899 | claudioornelas67@yahoo.com | Rosie Ornelas | 9095797226 |  | 17267 | 0.168 | Alex Holdridge | 2019-08-31 | 10.675 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-30 | 2019-08-31 12:00 | LR6-60PB-305M | 305 | 35 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | Line-side Tap | 2019-10-09 | Final Permit | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-07 07:00 | 2019-09-03 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 4.04 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed |  | 6.04 | 5 | Brian Le | Current | 2019-09-11 | 1 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 11.04 | 1 | Ernesto Enriquez | Completed | 2019-10-09 | 2.46 | 3 | Ara Sotto | Completed |  | 8.04 | 2 | Ara Sotto | Current | 2019-10-04 | 18.83 | 2 | Brian Le | Completed | 2019-09-09 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.88 | 1 |  | Completed | 2019-09-12 | 2.67 | 1 | Jill Allen | Completed | 2019-10-09 | 2.21 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.04 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 15:36 |  | 2019-10-11 | 0 | 2 | Ara Sotto | Completed | 2019-10-11 | 3.63 | 1 | Ara Sotto | Completed | 2019-09-09 | 0.04 | 2 | Darlynn Lacap | Completed | 12.24 | [11 empty] | 2019-09-12 |  | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=28354 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28354 | https://completesolar.sugarondemand.com/#Opportunities/9f2653d2-cc2f-11e9-86ab-022c40d974e6 | 300 Stars Inc | Oscar Hernandez | 2019-08-30 | Power Town Solar Electric | 9f2653d2-cc2f-11e9-86ab-022c40d974e6 | 0 | 12 | 10 | -2 | 5 | 5 | 5 | 18
28362 | PIP_APPROVED | PIP_APPROVED | 27809 Pebble Court | Highland | CA | 92346 | Cecilia Cherny | 2019-09-14 11:33 | 9515058880 | ccherny1224@gmail.com |  |  |  | 10117 | 0.18 | Shaun Labelle | 2019-09-14 | 6.71 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-10 | 2019-09-14 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-10-09 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-09 | 2019-09-17 | 1.38 | 2 | Marcia Garay | Completed | 2019-09-18 | 1 | 2 | Daniel Speegle | Completed | 2019-10-09 | 15 | 1 | Ara Sotto | Completed | 2019-10-09 | 2.83 | 5 | Brian Le | Completed | 2019-09-20 | 1.75 | 3 | Andrew Moralez | Completed | 2019-09-26 | 4.13 | 14 | Andrew Moralez | Completed | 2019-10-09 | 0 | 2 | Ara Sotto | Completed | 2019-10-15 | 4.38 | 2 | Ara Sotto | Completed | 2019-10-04 | 9.04 | 2 | Brian Le | Completed | 2019-09-23 | 3.08 | 2 | Marcia Garay | Completed | 2019-09-18 | 0.21 | 1 |  | Completed | 2019-09-26 | 6.17 | 1 | Jill Allen | Completed |  | 8.25 | 1 | Marcia Garay | Current | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 2.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 22:55 |  | 2019-10-17 | 6.08 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-10-10 | 2019-10-15 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28362 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28362 | https://completesolar.sugarondemand.com/#Opportunities/13863a78-d71e-11e9-ad09-0630baf9dcb8 | Oscar Hernandez |  | 2019-08-31 | Power Town Solar Electric | 13863a78-d71e-11e9-ad09-0630baf9dcb8 | 8 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28431 | PIP_APPROVED | PIP_APPROVED | 9244 Alder Avenue | Fontana | CA | 92335 | Monica C Gonzales | 2019-09-12 14:52 | 9092220707 | mgfamily54@gmail.com | Robert Gonzales | 9092228350 |  | 11525 | 0.151 | Michael Marlaire | 2019-09-06 | 7.625 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-04 | 2019-09-06 09:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tar and Gravel | NO | 2019-10-09 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-08 | 2019-09-12 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 2.87 | 2 | Daniel Speegle | Completed | 2019-10-02 | 12.71 | 1 | Ara Sotto | Completed |  | 6.04 | 5 | Brian Le | Current | 2019-09-19 | 1 | 3 | Andrew Moralez | Completed | 2019-09-27 | 6.09 | 12 | Andrew Moralez | Completed | 2019-10-09 | 1.25 | 2 | Ara Sotto | Completed | 2019-10-09 | 0.13 | 2 | Ara Sotto | Completed | 2019-10-04 | 14.13 | 2 | Brian Le | Completed | 2019-09-17 | 1.87 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 3.79 | 1 |  | Completed | 2019-09-26 | 9.96 | 1 | Jill Allen | Completed | 2019-10-09 | 1.46 | 1 | Darlynn Lacap | Completed |  | 8.13 | 2 | Andrew Clemons | Current | [16 empty] | 2.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 10:11 |  | 2019-10-17 | 6.13 | 2 | Ara Sotto | Completed | [10 empty] | 6.17 | [11 empty] | 2019-10-05 | 2019-10-09 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=28431 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28431 | https://completesolar.sugarondemand.com/#Opportunities/b0570e34-d171-11e9-ada4-022c40d974e6 | Oscar Hernandez |  | 2019-09-04 | HDM Electric Inc | b0570e34-d171-11e9-ada4-022c40d974e6 | 8 | 0 | -5 | 5 | 5 | 5 | 5 | 10
28460 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3533 North Amberwood Avenue | Rialto | CA | 92377 | Darnel McDermott | 2019-09-23 18:12 | 9099364447 | darnel.mcdermott@gmail.com |  |  |  | 12115 | 0.139 | Chris Peaslee | 2019-09-07 | 7.32 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-09-04 | 2019-09-07 09:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | MPU | 2019-10-09 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-03 07:00 | 2019-09-24 | 1.05 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.26 | 2 | Daniel Speegle | Completed | 2019-09-26 | 3.83 | 1 | Ara Sotto | Completed | 2019-10-09 | 5.96 | 5 | Brian Le | Completed | 2019-09-25 | 2.75 | 3 | Andrew Moralez | Completed | 2019-09-27 | 9.25 | 7 | Andrew Moralez | Completed | 2019-10-09 | 4.46 | 2 | Ara Sotto | Completed |  | 8.04 | 2 | Ara Sotto | Current | 2019-09-30 | 4.13 | 2 | Brian Le | Completed | 2019-09-24 | 5.2 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 0.87 | 1 |  | Completed | 2019-10-11 | 23.13 | 1 | Andrew Clemons | Completed | 2019-10-09 | 4.46 | 1 | Darlynn Lacap | Completed | 2019-10-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-17 |  | 8.04 | 2 | Ara Sotto | Current | 2019-10-09 | 4.46 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.83 | 2 | Darlynn Lacap | Completed | 7.12 | [11 empty] | 2019-09-25 |  | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28460 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28460 | https://completesolar.sugarondemand.com/#Opportunities/d5d6ce3a-d19c-11e9-8850-069e4f790264 | Dominic Labadie |  | 2019-09-04 | Blalock Electric&Solar | d5d6ce3a-d19c-11e9-8850-069e4f790264 | 12 | 12 | -15 | -2 | 5 | 5 | 5 | -7
28819 | PIP_APPROVED | PIP_APPROVED | 13888 Clydesdale Run Lane | Victorville | CA | 92394 | Nicholas Whitehall | 2019-09-27 11:27 | 7602212593 | ghostrg8@yahoo.com |  | (760)298-1472 |  | 11879 | 0.165 | Alex Holdridge | 2019-09-19 | 6.71 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-14 | 2019-09-19 15:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM |  | NO | 2019-10-09 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-09 | 2019-09-27 | 1.79 | 2 | Marcia Garay | Completed | 2019-09-27 | 1.25 | 2 | Daniel Speegle | Completed | 2019-10-08 | 7 | 1 | Ara Sotto | Completed | 2019-10-09 | 2.83 | 5 | Brian Le | Completed | 2019-10-01 | 0 | 3 | Ernesto Enriquez | Completed | 2019-10-02 | 1.91 | 10 | Ernesto Enriquez | Completed | 2019-10-09 | 0 | 2 | Ara Sotto | Completed | 2019-10-08 | 0.08 | 2 | Ara Sotto | Completed | 2019-10-04 | 5.04 | 2 | Brian Le | Completed | 2019-09-30 | 2.67 | 2 | Marcia Garay | Completed | 2019-10-01 | 3.71 | 1 |  | Completed | 2019-10-01 | 4.84 | 1 | Noe Gomez | Completed |  | 8.25 | 1 | Marcia Garay | Current | 2019-10-10 | 1.13 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-18 |  | 8.25 | 2 | Ara Sotto | Current | [10 empty] | 0.21 | [11 empty] | 2019-10-14 | 2019-10-07 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28819 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28819 | https://completesolar.sugarondemand.com/#Opportunities/4c1747d8-db38-11e9-ac1a-0630baf9dcb8 | Christopher Cellini |  | 2019-09-14 | Power Town Solar Electric | 4c1747d8-db38-11e9-ac1a-0630baf9dcb8 | 12 | 0 | -15 | 5 | 5 | 5 | 5 | 0
28828 | PIP_APPROVED | PIP_APPROVED | 2224 Cottage Way | Vista | CA | 92081 | Timothy Macias | 2019-09-23 10:09 | 7605252065 | timtommacias@gmail.com | Tamis Macias | (760) 419-4054 | tamislobo@gmail.com | 7216 | 0.143 | Ryan Malloy | 2019-09-23 | 4.575 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-19 | 2019-09-20 15:00 | LR6-60HPB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-09 | NEM Submitted | SunRun Monthly | 1 | 0 |  | 0 | 0 | 0 | 2019-10-09 07:00 | 2019-09-23 | 0.08 | 2 | Marcia Garay | Completed | 2019-09-25 | 2.08 | 2 | Daniel Speegle | Completed | 2019-10-03 | 6.08 | 1 | Ara Sotto | Completed | 2019-10-09 | 5.04 | 5 | Brian Le | Completed | 2019-09-27 | 1.04 | 3 | Ernesto Enriquez | Completed | 2019-09-27 | 0 | 2 | Andrew Moralez | Completed | 2019-10-09 | 0.42 | 1 | Christina Horton | Completed | 2019-10-14 | 2.96 | 2 | Christina Horton | Completed | 2019-09-30 | 2.67 | 2 | Brian Le | Completed | 2019-09-25 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-26 | 0.92 | 1 |  | Completed | 2019-09-27 | 2.04 | 1 | Jeremiah Liend | Completed |  | 8.54 | 1 | Marcia Garay | Current | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | 2019-10-01 | 6.04 | 4 | Marcia Garay | Completed | 2019-10-03 | 2.13 | 5 | Marcia Garay | Completed |  | 7 | 12 | Marcia Garay | Current | 2019-10-15 | 1 | 2 | Ashley Rockwood | Completed |  | 4.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-14 14:01 |  | 2019-10-14 | 2.96 | 2 | Christina Horton | Completed | [10 empty] | 7.09 | [11 empty] | 2019-10-01 | 2019-10-14 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=28828 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28828 | https://completesolar.sugarondemand.com/#Opportunities/c590a084-de24-11e9-91e9-0630baf9dcb8 | Alexis Cain |  | 2019-09-14 | Infinity Energy Inc | c590a084-de24-11e9-91e9-0630baf9dcb8 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
28923 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 5624 Malaga Court | Palmdale | CA | 93552 | Takeira Hicks | 2019-09-19 08:19 | 5622936076 | takeirah@gmail.com | Johanna Valdez | 5625002161 |  | 12529 | 0.147 | Bill Angevine | 2019-09-19 | 7.015 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-17 | 2019-09-18 12:00 | LR6-60PE-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-09 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-08 07:00 | 2019-09-20 | 1.08 | 2 | Marcia Garay | Completed | 2019-09-25 | 3.13 | 2 | Daniel Speegle | Completed | 2019-10-02 | 4.83 | 1 | Ara Sotto | Completed | 2019-10-09 | 2.83 | 5 | Brian Le | Completed | 2019-10-01 | 2.75 | 3 | Ernesto Enriquez | Completed | 2019-10-04 | 3.08 | 5 | Ernesto Enriquez | Completed | 2019-10-09 | 1.25 | 2 | Ara Sotto | Completed |  | 8.29 | 2 | Ara Sotto | Current | 2019-10-04 | 7 | 2 | Brian Le | Completed | 2019-09-25 | 0 | 2 | Marcia Garay | Completed | 2019-09-26 | 1.08 | 1 |  | Completed | 2019-09-30 | 2.75 | 1 | Jill Allen | Completed | 2019-10-07 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 22:14 |  |  | 8.29 | 2 | Ara Sotto | Current | [10 empty] | 4.08 | [11 empty] | 2019-10-08 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28923 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28923 | https://completesolar.sugarondemand.com/#Opportunities/d5663686-daf0-11e9-a210-02ae981fbade | George Sarkis |  | 2019-09-17 | JK Solar | d5663686-daf0-11e9-a210-02ae981fbade | 12 | 12 | -15 | -2 | 5 | 5 | 5 | -7
28938 | PIP_APPROVED | PIP_APPROVED | 13103 Bender Drive | Moreno Valley | CA | 92553 | Vicente Miranda | 2019-09-20 11:50 | 9515676455 | mirandamirn@aol.com | Mirna Miranda | 7142130658 |  | 7686 | 0.145 | Chris Peaslee | 2019-09-20 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-19 | 2019-09-20 09:00 | LR6-60HPB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-09 | Install | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-09 | 2019-09-26 | 3 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 0 | 2 | Daniel Speegle | Completed | 2019-10-02 | 3.79 | 1 | Ara Sotto | Completed | 2019-10-09 | 3.04 | 5 | Brian Le | Completed | 2019-10-11 | 10.17 | 3 | Andrew Moralez | Completed | 2019-10-11 | 0 | 3 | Andrew Moralez | Completed | 2019-10-09 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-11 | 1.88 | 2 | Ara Sotto | Completed | 2019-10-04 | 4.17 | 2 | Brian Le | Completed | 2019-09-30 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 0.83 | 1 |  | Completed | 2019-09-30 | 1.88 | 1 | Andrew Clemons | Completed | 2019-10-17 | 6.5 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-11 15:45 |  |  | 8.04 | 2 | Ara Sotto | Current | [10 empty] | 1.17 | [11 empty] | 2019-10-16 | 2019-10-10 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28938 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28938 | https://completesolar.sugarondemand.com/#Opportunities/742eda8e-dbd7-11e9-9f50-022c40d974e6 | Oscar Hernandez |  | 2019-09-18 | HDM Electric Inc | 742eda8e-dbd7-11e9-9f50-022c40d974e6 | 12 | 2 | -15 | 4 | 5 | 5 | 5 | -1
28434 | PIP_APPROVED | PIP_APPROVED | 23840 Barberry Place | Murrieta | CA | 92562 | Jacob Van Waardenburg | 2019-09-11 09:51 | 3103391548 | Jacobvanw@hotmail.com | Sunni Waardenburg | 3102924477 |  | 11570.9 |  | Michael Marlaire | 2019-09-11 | 7.015 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-04 | 2019-09-07 15:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-07 | NEM Submitted | Sunlight Financial Loan |  | 0 |  |  |  |  | 2019-10-07 07:00 | 2019-09-11 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-12 | 1 | 2 | Daniel Speegle | Completed | 2019-09-24 | 8 | 1 | Ara Sotto | Completed | 2019-10-07 | 6.46 | 5 | Brian Le | Completed | 2019-09-17 | 2.79 | 3 | Andrew Moralez | Completed | 2019-09-20 | 3.17 | 1 | Andrew Moralez | Completed | 2019-10-07 | 0.38 | 2 | Christina Horton | Completed | 2019-10-10 | 3 | 2 | Christina Horton | Completed | 2019-09-24 | 7 | 2 | Brian Le | Completed | 2019-09-13 | 1.04 | 2 | Marcia Garay | Completed | 2019-09-12 | 0.13 | 1 |  | Completed | 2019-10-03 | 12.67 | 1 | Andrew Clemons | Completed |  | 10.54 | 1 | Marcia Garay | Current | 2019-10-10 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-15 | 3.21 | 2 | Ashley Rockwood | Completed |  | 4.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 15:16 |  | 2019-10-10 | 2.83 | 2 | Christina Horton | Completed | [10 empty] | 5.21 | [11 empty] | 2019-09-18 | 2019-10-10 | MURRIETA | Murrieta | https://heliotrack.completesolar.com/job.php?action=review&jobID=28434 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28434 | https://completesolar.sugarondemand.com/#Opportunities/5bada3de-d4b4-11e9-8e8c-02ae981fbade | Michael Foster |  | 2019-09-04 | Infinity Energy Inc | 5bada3de-d4b4-11e9-8e8c-02ae981fbade | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
28537 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 120 Mankato Street | Chula Vista | CA | 91910 | Mike Roberts | 2019-09-12 14:38 | 6195073205 | croberts81@cox.net |  |  |  | 8867 | 0.168 | Ryan Malloy | 2019-09-11 | 5.795 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-07 | 2019-09-09 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-07 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-07 07:00 | 2019-09-13 | 1 | 2 | Marcia Garay | Completed | 2019-09-13 | 1 | 2 | Daniel Speegle | Completed | 2019-10-03 | 14.26 | 1 | Christina Horton | Completed | 2019-10-07 | 11.04 | 5 | Brian Le | Completed | 2019-09-18 | 0 | 3 | Andrew Moralez | Completed | 2019-10-04 | 12.04 | 7 | Ernesto Enriquez | Completed | 2019-10-07 | 0.38 | 2 | Christina Horton | Completed |  | 10.17 | 2 | Christina Horton | Current | 2019-09-16 | 0.16 | 2 | Brian Le | Completed | 2019-09-20 | 4.84 | 2 | Marcia Garay | Completed | 2019-09-18 | 2.87 | 1 |  | Completed | 2019-09-19 | 4.17 | 1 | Andrew Clemons | Completed | 2019-10-15 | 6.25 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-28 12:34 |  |  | 10.17 | 2 | Christina Horton | Current | [10 empty] | 1.17 | [11 empty] | 2019-09-27 |  | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=28537 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28537 | https://completesolar.sugarondemand.com/#Opportunities/37694b6e-d350-11e9-8ee1-069e4f790264 | Blake Sanders | Jonathan Weaver | 2019-09-07 | Infinity Energy Inc | 37694b6e-d350-11e9-8ee1-069e4f790264 | 14 | 14 | -15 | -2 | 5 | 5 | 5 | -7
27971 | PIP_APPROVED | PIP_APPROVED | 303 Durian Street | Vista | CA | 92083 | Joseph Porter | 2019-09-16 09:28 | 7608551810 | nubieporter@gmail.com | Lauren Porter |  |  | 6886 | 0.13 | Chad Malloy | 2019-08-24 | 4.575 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-17 | 2019-08-24 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-10-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-05 07:00 | 2019-09-16 | 0.67 | 2 | Marcia Garay | Completed | 2019-09-17 | 1 | 2 | Daniel Speegle | Completed | 2019-09-18 | 7.08 | 1 | Christina Horton | Completed | 2019-10-05 | 13.42 | 5 | Brian Le | Completed | 2019-09-17 | 1 | 3 | Andrew Moralez | Completed | 2019-09-17 | 0 | 5 | Andrew Moralez | Completed | 2019-10-05 | 0.08 | 1 | Christina Horton | Completed | 2019-10-10 | 3.71 | 2 | Christina Horton | Completed | 2019-09-17 | 3.12 | 2 | Brian Le | Completed | 2019-09-19 | 2.91 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.83 | 1 |  | Completed | 2019-09-19 | 5.71 | 1 | Andrew Clemons | Completed | 2019-10-04 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-16 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 2.08 | 2 | Ashley Rockwood | Completed |  | 1.04 | 2 | Darlynn Lacap | Current |  | 1.04 | 1 | Noe Gomez | Current | 2019-10-10 07:47 |  | 2019-10-10 | 3.59 | 2 | Christina Horton | Completed | [10 empty] | 12.44 | [11 empty] | 2019-09-24 | 2019-10-10 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27971 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27971 | https://completesolar.sugarondemand.com/#Opportunities/d5ed969c-c6c5-11e9-830f-0630baf9dcb8 | Alexis Cain |  | 2019-08-15 | Infinity Energy Inc | d5ed969c-c6c5-11e9-830f-0630baf9dcb8 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
28084 | PIP_APPROVED | PIP_APPROVED | 5622 Jasper Street | Rancho Cucamonga | CA | 91701 | Kimberly Errington | 2019-08-30 13:28 | 7143458393 | jerrington714@gmail.com | JASON W ERRINGTON | 9095187796 |  | 15151 | 0.151 | Shaun Labelle | 2019-08-30 | 8.845 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-27 | 2019-08-28 15:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | MPU | 2019-10-04 | Installation Complete | SunRun Monthly | [6 empty] | 2019-10-04 07:00 | 2019-09-06 | 2.96 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.17 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-04 | 3.17 | 5 | Brian Le | Completed | 2019-09-09 | 0.92 | 3 | Andrew Moralez | Completed | 2019-09-10 | 0.92 | 15 | Andrew Moralez | Completed | 2019-10-04 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-09 | 2.63 | 2 | Ara Sotto | Completed | 2019-10-01 | 13.54 | 2 | Brian Le | Completed | 2019-09-06 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.13 | 1 |  | Completed | 2019-09-13 | 2.91 | 1 | Andrew Clemons | Completed | 2019-10-09 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 1.25 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-09 |  | 0 | 2 |  | Inactive |  | 11.54 | 1 | Ara Sotto | Current | 2019-09-09 | 0.75 | 2 | Darlynn Lacap | Completed | 4.08 | [11 empty] | 2019-09-30 | 2019-10-09 | RANCHO CUCAMONGA | Rancho Cucamonga | https://heliotrack.completesolar.com/job.php?action=review&jobID=28084 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28084 | https://completesolar.sugarondemand.com/#Opportunities/a29de46a-cb64-11e9-af19-02ae981fbade | Summit Marketing Inc | Matt Cox | 2019-08-20 | HDM Electric Inc | a29de46a-cb64-11e9-af19-02ae981fbade |  | 5 | -25 | -2 | 5 | 5 | 5 | -17
28208 | PIP_APPROVED | PIP_APPROVED | 13874 Hidden Pines Court | Victorville | CA | 92392 | Deward Iii Childs | 2019-09-13 14:55 | 3232757448 | dchilds65@yahoo.com | LAMEKA SHANNET CHILDS | 6194717937 |  | 13422 | 0 | Alex Holdridge | 2019-09-13 | 7.93 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-26 | 2019-08-29 09:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-04 | PTO Received | CalFirst SunRun Prepaid | 0 | 0 |  |  |  | 1 | 2019-10-04 | 2019-09-16 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 4.13 | 2 | Daniel Speegle | Completed | 2019-09-26 | 3.96 | 1 | Ara Sotto | Completed | 2019-10-04 | 3.17 | 5 | Brian Le | Completed | 2019-09-24 | 1.04 | 3 | Andrew Moralez | Completed | 2019-09-26 | 1.96 | 10 | Andrew Moralez | Completed | 2019-10-04 | 0 | 2 | Ara Sotto | Completed | 2019-10-14 | 5.92 | 2 | Ara Sotto | Completed | 2019-10-01 | 5.88 | 2 | Brian Le | Completed | 2019-09-23 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 0.92 | 1 |  | Completed | 2019-09-25 | 2.79 | 1 | Jeremiah Liend | Completed | 2019-10-07 | 0.88 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-10 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 0.71 | 2 | Ashley Rockwood | Completed |  | 4.08 | 2 | Darlynn Lacap | Inactive | 2019-10-14 | 0.92 | 1 | Andrew Clemons | Completed | 2019-10-07 15:41 |  | 2019-10-07 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 4.13 | [11 empty] | 2019-10-08 | 2019-10-11 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28208 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28208 | https://completesolar.sugarondemand.com/#Opportunities/29ad5190-d671-11e9-b1c5-069e4f790264 | Cory Hartman | JW Pitchford | 2019-08-26 | Power Town Solar Electric | 29ad5190-d671-11e9-b1c5-069e4f790264 | 3 | 10 | 0 | -2 | 5 | 5 | 5 | 8
28414 | PIP_APPROVED | PIP_APPROVED | 12946 Shearwater Road | Victorville | CA | 92392 | Sara Torres | 2019-09-16 11:34 | 7602655808 | saracachanilla760@gmail.com | Samuel Torres | 7605087713 | samueltorressr@hotmail.com | 8353 | 0.15 | Shaun Labelle | 2019-09-05 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-03 | 2019-09-05 12:30 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-04 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-04 07:00 | 2019-09-16 | 3.8 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.04 | 2 | Daniel Speegle | Completed | 2019-09-24 | 8.04 | 1 | Ara Sotto | Completed | 2019-10-04 | 0.08 | 5 | Brian Le | Completed | 2019-09-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-10-06 | 15.5 | 10 | Andrew Moralez | Completed | 2019-10-04 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-09 | 2.83 | 2 | Ara Sotto | Completed | 2019-10-01 | 2.83 | 2 | Brian Le | Completed | 2019-09-25 | 6.24 | 2 | Darlynn Lacap | Completed | 2019-09-18 | 1.04 | 1 |  | Completed | 2019-09-20 | 6.04 | 1 | Noe Gomez | Completed | 2019-10-07 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 1.04 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-10-10 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 1.71 | 2 | Ashley Rockwood | Completed |  | 5.33 | 2 | Darlynn Lacap | Current | 2019-10-18 | 3.92 | 1 | Andrew Clemons | Completed | 2019-10-07 15:47 |  | 2019-10-07 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 15.12 | [11 empty] | 2019-09-27 | 2019-10-09 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28414 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28414 | https://completesolar.sugarondemand.com/#Opportunities/5bae50f2-d033-11e9-9521-0630baf9dcb8 | Christopher Cellini |  | 2019-09-03 | Green Road Solar Crew | 5bae50f2-d033-11e9-9521-0630baf9dcb8 | 3 | 5 | 0 | -2 | 5 | 5 | 5 | 8
28499 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 45117 Loma Vista Drive | Lancaster | CA | 93535 | Lonnie Surratt | 2019-09-10 18:42 | 6612028645 | ls7rats@msn.com |  | (661)946-0392 |  | 13766 | 0.147 | Bill Angevine | 2019-09-10 | 7.93 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-06 | 2019-09-10 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-10-04 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-10-03 07:00 | 2019-09-12 | 1.67 | 2 | Marcia Garay | Completed | 2019-09-17 | 3.04 | 2 | Daniel Speegle | Completed | 2019-09-18 | 0.79 | 1 | Ara Sotto | Completed | 2019-10-04 | 6.04 | 5 | Brian Le | Completed | 2019-09-18 | 0.08 | 3 | Andrew Moralez | Completed |  | 0 | 1 |  | Inactive | 2019-10-04 | 1.46 | 2 | Ara Sotto | Completed |  | 11.04 | 2 | Ara Sotto | Current | 2019-09-26 | 6.96 | 2 | Brian Le | Completed | 2019-09-17 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-18 | 1.04 | 1 |  | Completed | 2019-09-26 | 6.88 | 1 | Andrew Clemons | Completed | 2019-10-07 | 2.46 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-14 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 0.88 | 2 | Ashley Rockwood | Completed |  | 4.25 | 2 | Marcia Garay | Current | 2019-10-16 | 1.17 | 1 | Noe Gomez | Completed | 2019-10-08 15:44 |  | 2019-10-09 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 2.42 | [13 empty] | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28499 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28499 | https://completesolar.sugarondemand.com/#Opportunities/61ccb158-d435-11e9-a9bc-069e4f790264 | George Sarkis |  | 2019-09-06 | JK Solar | 61ccb158-d435-11e9-a9bc-069e4f790264 | 5 | 17 | -5 | -2 | 5 | 5 | 5 | 3
28553 | PIP_APPROVED | PIP_APPROVED | 4652 Marblehead Bay Drive | Oceanside | CA | 92057 | Justin Wagner | 2019-09-17 10:27 | 7604731210 | merlinwagner2@gmail.com |  |  |  | 6228 | 0.186 | Michael Marlaire | 2019-09-17 | 3.66 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-09-07 | 2019-09-10 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-04 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-04 07:00 | 2019-09-18 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 1.29 | 2 | Daniel Speegle | Completed | 2019-09-27 | 5.67 | 1 | Christina Horton | Completed | 2019-10-04 | 8.79 | 5 | Brian Le | Completed | 2019-09-20 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-27 | 0.08 | 10 | Andrew Moralez | Completed | 2019-10-04 | 0.21 | 1 | Ara Sotto | Completed | 2019-10-11 | 5.42 | 2 | Ara Sotto | Completed | 2019-09-23 | 0.21 | 2 | Brian Le | Completed | 2019-09-23 | 1.5 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 0.71 | 1 |  | Completed | 2019-09-26 | 4.79 | 1 | Noe Gomez | Completed | 2019-10-08 | 2.29 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-09 | 1.21 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 0 | 2 | Ashley Rockwood | Completed |  | 5.04 | 2 | Darlynn Lacap | Current | 2019-10-16 | 1.96 | 1 | Andrew Clemons | Completed | 2019-10-07 14:44 |  | 2019-10-08 | 2.04 | 2 | Ara Sotto | Completed | [10 empty] | 8.04 | [11 empty] | 2019-10-11 | 2019-10-11 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28553 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28553 | https://completesolar.sugarondemand.com/#Opportunities/47ccf1ce-d970-11e9-8df5-069e4f790264 | Alan Moberg |  | 2019-09-07 | Zachary Noah Gamez | 47ccf1ce-d970-11e9-8df5-069e4f790264 | 4 | 7 | 0 | -2 | 5 | 5 | 5 | 8
28743 | SP APPROVED |  | 76739 Florida Avenue | Palm Desert | CA | 92211 | Adriana Pangilinan | 2019-09-18 13:37 | 9518184024 | didipangilinan@gmail.com |  |  |  | 6610 | 0.175 | Shaun Labelle | 2019-09-18 | 5.49 | Ara Sotto | Solar Power Marketing | Marcia Garay | 2019-09-13 | 2019-09-18 09:00 | LR6-60HPB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-10-04 | NEM Submitted | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-10-04 | 2019-09-19 | 1 | 2 | Marcia Garay | Completed | 2019-09-23 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-30 | 2.71 | 1 | Ara Sotto | Completed | 2019-10-04 | 4.04 | 5 | Brian Le | Completed | 2019-09-30 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-10-09 | 6.79 | 5 | Andrew Moralez | Completed | 2019-10-04 | 0.46 | 2 | Ara Sotto | Completed |  | 11.04 | 2 | Ara Sotto | Current | 2019-09-30 | 0.96 | 2 | Brian Le | Completed | 2019-09-27 | 1.84 | 2 | Marcia Garay | Completed | 2019-09-30 | 0.08 | 1 |  | Completed | 2019-10-03 | 5.67 | 1 | Jeremiah Liend | Completed | 2019-10-11 | 5.25 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-15 | 2.21 | 2 | Ashley Rockwood | Completed |  | 4.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 16:27 |  | 2019-10-11 | 1.63 | 2 | Ara Sotto | Completed | 2019-10-09 | 3.5 | 1 | Ara Sotto | Completed | 2019-09-24 | 0.67 | 2 | Marcia Garay | Completed | 7.21 | [11 empty] | 2019-10-07 |  | PALM DESERT | Palm Desert | https://heliotrack.completesolar.com/job.php?action=review&jobID=28743 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28743 | https://completesolar.sugarondemand.com/#Opportunities/1bf26f40-da54-11e9-9660-022c40d974e6 | Solar Power Marketing |  | 2019-09-13 | Zachary Noah Gamez | 1bf26f40-da54-11e9-9660-022c40d974e6 | 2 | 17 | 7 | -2 | 5 | 5 | 5 | 15
28857 | PIP_APPROVED | PIP_APPROVED | 4479 Inverness Drive | Oceanside | CA | 92057 | Norma Sicat | 2019-09-19 10:33 | 7603313062 | nsicat@gmail.com | Leo Sicat | 6199339267 |  | 4179 | 0.14 | Ryan Malloy | 2019-09-19 | 2.44 |  | Kyle Wilson | Darlynn Lacap | 2019-09-16 | 2019-09-17 12:00 | LR6-60HPB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-04 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-04 07:00 | 2019-09-19 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.13 | 2 | Daniel Speegle | Completed | 2019-09-26 | 2.96 | 1 | Ara Sotto | Completed | 2019-10-04 | 4.96 | 5 | Brian Le | Completed | 2019-09-24 | 0.92 | 3 | Ernesto Enriquez | Completed | 2019-10-04 | 8 | 2 | Ernesto Enriquez | Completed | 2019-10-04 | 0.33 | 1 | Ara Sotto | Completed | 2019-10-15 | 7.29 | 2 | Ara Sotto | Completed | 2019-09-27 | 2.88 | 2 | Brian Le | Completed | 2019-09-24 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 0 | 1 |  | Completed | 2019-09-26 | 2.96 | 1 | Noe Gomez | Completed | 2019-10-09 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 5.88 | 2 | Ashley Rockwood | Completed |  | 0.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-10 14:02 |  | 2019-10-11 | 5.13 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-26 | 2019-10-15 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28857 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28857 | https://completesolar.sugarondemand.com/#Opportunities/86e6641e-db03-11e9-9bd9-022c40d974e6 | Kyle Wilson |  | 2019-09-16 | iEnergy ElectricSolar | 86e6641e-db03-11e9-9bd9-022c40d974e6 | 7 | 11 | -5 | -2 | 5 | 5 | 5 | 3
28862 | PIP_APPROVED | PIP_APPROVED | 15264 Stone Street | Adelanto | CA | 92301 | Arthur Gonzales | 2019-09-18 07:08 | 4422491403 | gonzalesjean@att.net | Jean Gonzales |  |  | 7413 | 0.157 | Bill Angevine | 2019-09-17 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-16 | 2019-09-17 15:00 | LR6-60PE-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-04 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-04 07:00 | 2019-09-18 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 2.25 | 2 | Daniel Speegle | Completed | 2019-09-20 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-04 | 3.17 | 5 | Brian Le | Completed | 2019-09-27 | 3.96 | 3 | Andrew Moralez | Completed | 2019-09-27 | 0 | 3 | Andrew Moralez | Completed | 2019-10-04 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-08 | 1.79 | 2 | Ara Sotto | Completed | 2019-10-01 | 6 | 2 | Brian Le | Completed | 2019-09-23 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 0.92 | 1 |  | Completed | 2019-09-26 | 3.79 | 1 | Jeremiah Liend | Completed | 2019-10-07 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.88 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-09 | 2 | 2 | Ashley Rockwood | Completed | 2019-10-16 | 4.88 | 2 | Ashley Rockwood | Completed |  | 3.29 | 2 | Darlynn Lacap | Current | 2019-10-18 | 1.92 | 1 | Andrew Clemons | Completed | 2019-10-07 15:32 |  | 2019-10-07 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-10-02 | 2019-10-08 | ADELANTO | Adelanto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28862 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28862 | https://completesolar.sugarondemand.com/#Opportunities/a3de1ee0-da1d-11e9-b2f1-02ae981fbade | Christopher Cellini |  | 2019-09-16 | Green Road Solar Crew | a3de1ee0-da1d-11e9-b2f1-02ae981fbade | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
26926 | PIP_APPROVED | PIP_APPROVED | 409 South 20th Street | Richmond | CA | 94804 | Salvador De Jesus Lopez | 2019-07-09 13:30 | 5103750284 | salvadorwow@gmail.com |  |  |  | 5595 | 0.15 | Ricardo Virgen | 2019-07-09 | 3.66 | Christina Horton | Total HomeSolar | Marcia Garay |  | 2019-07-09 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | MPU | 2019-10-03 | NEM Submitted | SunRun Monthly | [6 empty] | 2019-10-02 07:00 | 2019-07-10 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-15 | 3 | 2 | Jethro Andal | Completed | 2019-07-25 | 7.08 | 1 | Christina Horton | Completed | 2019-10-02 | 12.29 | 5 | Brian Le | Completed | 2019-07-23 | 5.21 | 3 | Andrew Moralez | Completed | 2019-07-23 | 0 | 10 | Ernesto Enriquez | Completed | 2019-10-03 | 1.55 | 1 | Christina Horton | Completed | 2019-10-17 | 10.08 | 2 | Christina Horton | Completed | 2019-07-25 | 7.13 | 2 | Brian Le | Completed | 2019-07-16 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-16 | 0.04 | 1 |  | Completed | 2019-07-25 | 6.79 | 1 | Andrew Clemons | Completed | 2019-10-08 | 4.84 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-18 | 1.25 | 2 | Ashley Rockwood | Completed |  | 1.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-17 11:09 |  | 2019-10-17 | 6.08 | 2 | Christina Horton | Completed | 2019-10-09 | 1.51 | 1 | Christina Horton | Completed | 2019-07-16 | 1.08 | 2 | Marcia Garay | Completed | 39.46 | [11 empty] | 2019-08-06 | 2019-10-17 | RICHMOND | Richmond | https://heliotrack.completesolar.com/job.php?action=review&jobID=26926 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26926 | https://completesolar.sugarondemand.com/#Opportunities/4d2423e6-a288-11e9-bd6b-0630baf9dcb8 | Total HomeSolar |  | 2019-07-05 | Golden Gate Electric Service | 4d2423e6-a288-11e9-bd6b-0630baf9dcb8 | 8 | 14 | -5 | -2 | 5 | 5 | 5 | 3
26994 | PIP_APPROVED | PIP_APPROVED | 2843 Fremontia Drive | San Bernardino | CA | 92404 | Jordan Gomez | 2019-09-18 17:40 | 9099363226 | jtgws7@icloud.com | Danna Flores | 909-453-8155 |  | 6535 | 0.18 | Alex Holdridge | 2019-07-10 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-09 | 2019-07-10 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-03 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-03 | 2019-09-19 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 4.88 | 2 | Daniel Speegle | Completed | 2019-09-27 | 4 | 1 | Ara Sotto | Completed | 2019-10-03 | 0.08 | 5 | Brian Le | Completed | 2019-09-26 | 2.21 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 0 | 1 | Ernesto Enriquez | Completed | 2019-10-03 | 0 | 1 | Ara Sotto | Completed | 2019-10-08 | 3.25 | 2 | Ara Sotto | Completed | 2019-09-30 | 13.09 | 2 | Brian Le | Completed | 2019-09-19 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-24 | 2.71 | 1 |  | Completed | 2019-09-30 | 12.84 | 1 | Andrew Clemons | Completed | 2019-10-07 | 2.04 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.54 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-14 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 4.75 | 2 | Ashley Rockwood | Completed |  | 0.29 | 2 | Darlynn Lacap | Current |  | 0.29 | 1 | Noe Gomez | Current | 2019-10-04 13:23 |  | 2019-10-09 | 4.08 | 2 | Ara Sotto | Completed | [10 empty] | 33.62 | [11 empty] | 2019-09-27 | 2019-10-08 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=26994 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26994 | https://completesolar.sugarondemand.com/#Opportunities/6564db1c-a382-11e9-a4a0-069e4f790264 | 300 Stars Inc | Oscar Hernandez | 2019-07-09 | HDM Electric Inc | 6564db1c-a382-11e9-a4a0-069e4f790264 | 6 | 5 | -5 | -2 | 5 | 5 | 5 | 3
27831 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 38885 Yucca Tree Street | Palmdale | CA | 93551 | Cynthia Piontkowski | 2019-09-05 16:40 | 6613503638 | cindysec@sbcglobal.net | Gary Piontkowski | 6612020077 | garynechancis@sbcglobal.com | 20500 | 0.122 | Shaun Labelle | 2019-08-12 | 11.59 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-10 | 2019-08-12 12:00 | LR6-60PB-305M | 305 | 38 | LONGi Solar | SolarEdge | SE11400H-US | Composite | NO | 2019-10-03 | Install | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-02 07:00 | 2019-09-05 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 5.67 | 2 | Daniel Speegle | Completed | 2019-10-03 | 17.04 | 1 | Ara Sotto | Completed | 2019-10-03 | 4.83 | 5 | Brian Le | Completed | 2019-09-16 | 2 | 3 | Andrew Moralez | Completed | 2019-10-10 | 18 | 15 | Ernesto Enriquez | Completed | 2019-10-03 | 1.25 | 3 | Ara Sotto | Completed |  | 12.29 | 2 | Ara Sotto | Current | 2019-09-26 | 12.04 | 2 | Brian Le | Completed | 2019-09-12 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 1.21 | 1 |  | Completed | 2019-09-20 | 8.21 | 1 | Andrew Clemons | Completed | 2019-10-09 | 5.46 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-20 |  | 12.29 | 2 | Ara Sotto | Current | [10 empty] | 18.97 | [11 empty] | 2019-10-07 |  | LOS ANGELES COUNTY | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27831 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27831 | https://completesolar.sugarondemand.com/#Opportunities/ab909fce-bd6b-11e9-8368-069e4f790264 | SCES ADMIN |  | 2019-08-10 | JK Solar | ab909fce-bd6b-11e9-8368-069e4f790264 | 18 | 18 | -15 | -2 | 5 | 5 | 5 | -7
27861 | PIP_APPROVED | PIP_APPROVED | 4853 Katrina Place | Palmdale | CA | 93552 | Samuel Brisco | 2019-08-30 15:10 | 6613059721 | mockerfan@icloud.com | Kathy Brisco | 6613058394 |  | 14807 | 0.136 | Bill Angevine | 2019-08-13 | 9.76 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-12 | 2019-08-13 09:00 | LR6-60PB-305M | 305 | 32 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-10-03 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-02 07:00 | 2019-09-05 | 3.58 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 5.05 | 2 | Daniel Speegle | Completed | 2019-09-25 | 12 | 1 | Ara Sotto | Completed | 2019-10-03 | 3.96 | 5 | Brian Le | Completed | 2019-09-17 | 2.96 | 3 | Andrew Moralez | Completed | 2019-09-30 | 8.92 | 0 | Andrew Moralez | Completed | 2019-10-03 | 2.5 | 3 | Ara Sotto | Completed | 2019-10-15 | 8.25 | 2 | Ara Sotto | Completed | 2019-09-26 | 8.17 | 2 | Brian Le | Completed | 2019-09-16 | 4.92 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 3 | 1 |  | Completed | 2019-09-12 | 2.92 | 1 | Noe Gomez | Completed | 2019-10-10 | 7.58 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-14 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 3.08 | 2 | Darlynn Lacap | Completed | 2019-10-16 | 1.17 | 1 | Andrew Clemons | Completed |  | 2019-09-18 | 2019-10-09 | 4.25 | 2 | Ara Sotto | Completed | [10 empty] | 12.21 | [11 empty] | 2019-09-17 | 2019-10-15 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27861 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27861 | https://completesolar.sugarondemand.com/#Opportunities/18de0b38-be1c-11e9-8b2c-022c40d974e6 | SCES Division | George Sarkis | 2019-08-12 | JK Solar | 18de0b38-be1c-11e9-8b2c-022c40d974e6 | 6 | 12 | -5 | -2 | 5 | 5 | 5 | 3
28105 | PIP_APPROVED | PIP_APPROVED | 41373 Collegian Way | Hemet | CA | 92544 | Angela Tice | 2019-09-18 17:23 | 9517759893 | ticegirl@verizon.net | Anthony Labado | 9517838555 |  | 14161 | 0.147 | Michael Marlaire | 2019-09-09 | 8.845 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-21 | 2019-08-26 09:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-10-03 | Installation Complete | SunRun Monthly | 0 |  |  |  | 1 | 1 | 2019-10-02 07:00 | 2019-09-19 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 0.29 | 2 | Daniel Speegle | Completed | 2019-10-03 | 10.55 | 1 | Ara Sotto | Completed | 2019-10-03 | 3.96 | 5 | Brian Le | Completed | 2019-09-23 | 1.25 | 3 | Andrew Moralez | Completed | 2019-09-23 | 1.37 | 0 | Ernesto Enriquez | Completed | 2019-10-03 | 1.25 | 2 | Ara Sotto | Completed | 2019-10-09 | 4.5 | 2 | Ara Sotto | Completed | 2019-09-26 | 5.13 | 2 | Brian Le | Completed | 2019-09-19 | 1 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 0.71 | 1 |  | Completed | 2019-10-09 | 13.71 | 1 | Noe Gomez | Completed | 2019-10-09 | 5.46 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-07 15:15 | 2019-10-07 |  | 12.29 | 2 | Ara Sotto | Current | [10 empty] | 7.33 | 2019-09-30 | 7.37 | 14 | James Fernandez | Completed | 2019-09-30 | 2019-09-30 | 0 | 1 | James Fernandez | Completed | 2019-09-23 | 2019-10-09 | RIVERSIDE COUNTY | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=28105 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28105 | https://completesolar.sugarondemand.com/#Opportunities/0d371ae0-d320-11e9-874c-02ae981fbade | PJB Division | PJB Division | 2019-08-21 | Power Town Solar Electric | 0d371ae0-d320-11e9-874c-02ae981fbade | 18 | 6 | -15 | -2 | 5 | 5 | 5 | -7
28183 | PIP_APPROVED | PIP_APPROVED | 1529 Temple Heights Drive | Oceanside | CA | 92056 | Donald Skelton | 2019-09-17 11:59 | 2066127732 | Dskelton913@gmail.com | Denise Skelton | 2066128062 |  | 6306 | 0.165 | Chad Malloy | 2019-09-13 | 4.27 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-28 | 2019-08-29 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-10-03 | NEM Submitted | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-10-03 07:00 | 2019-09-17 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 4.05 | 2 | Daniel Speegle | Completed | 2019-09-30 | 5.88 | 1 | Christina Horton | Completed | 2019-10-03 | 6.05 | 5 | Brian Le | Completed | 2019-09-20 | 0 | 3 | Andrew Moralez | Completed | 2019-09-24 | 2 | 10 | Andrew Moralez | Completed | 2019-10-03 | 0.33 | 1 | Christina Horton | Completed | 2019-10-04 | 0.88 | 2 | Christina Horton | Completed | 2019-09-23 | 0 | 2 | Brian Le | Completed | 2019-09-23 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-20 | 0 | 1 |  | Completed | 2019-09-26 | 4 | 1 | Noe Gomez | Completed | 2019-10-04 | 1.25 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 2.96 | 2 | Andrew Clemons | Completed | 2019-09-23 | 4.96 | 4 | Darlynn Lacap | Completed | 2019-09-23 | 0 | 5 | Darlynn Lacap | Completed | 2019-09-27 | 3.83 | 12 | Darlynn Lacap | Completed | 2019-10-09 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 2.83 | 2 | Ashley Rockwood | Completed |  | 5.29 | 2 | Darlynn Lacap | Current |  | 5.29 | 1 | Andrew Clemons | Current | 2019-10-04 12:21 |  | 2019-10-04 | 0.88 | 2 | Christina Horton | Completed | [10 empty] | 2.79 | [11 empty] | 2019-10-04 | 2019-10-04 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28183 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28183 | https://completesolar.sugarondemand.com/#Opportunities/da827492-d64d-11e9-a421-022c40d974e6 | Lee Allison |  | 2019-08-26 | Infinity Energy Inc | da827492-d64d-11e9-a421-022c40d974e6 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
28238 | PIP_APPROVED | PIP_APPROVED | 7255 Mimosa Drive | Carlsbad | CA | 92011 | Gerard Spahn | 2019-09-11 14:35 | 7609318707 | jspahn@roadrunner.com |  | 8585189411 |  | 6551 | 0.166 | Chad Malloy | 2019-08-29 | 4.575 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-27 | 2019-08-28 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-03 | Final Permit | SunRun Monthly |  | 0 |  |  |  |  | 2019-10-03 | 2019-09-12 | 1 | 2 | Darlynn Lacap | Completed | 2019-09-13 | 2.09 | 2 | Daniel Speegle | Completed | 2019-09-18 | 5.29 | 1 | Christina Horton | Completed | 2019-10-03 | 11.17 | 5 | Brian Le | Completed | 2019-09-17 | 3.92 | 3 | Andrew Moralez | Completed | 2019-09-17 | 0 | 15 | Andrew Moralez | Completed | 2019-10-03 | 0.42 | 1 | Christina Horton | Completed | 2019-10-09 | 3.83 | 2 | Christina Horton | Completed | 2019-09-16 | 0.16 | 2 | Brian Le | Completed | 2019-09-18 | 4.83 | 2 | Darlynn Lacap | Completed | 2019-09-13 | 0.08 | 1 |  | Completed | 2019-10-03 | 16.08 | 1 | Andrew Clemons | Completed | 2019-10-04 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 11.17 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-04 12:49 |  | 2019-10-04 | 0.92 | 2 | Christina Horton | Completed | [10 empty] | 8.17 | [11 empty] | 2019-10-08 | 2019-10-09 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=28238 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28238 | https://completesolar.sugarondemand.com/#Opportunities/7874e326-ca71-11e9-bb37-02ae981fbade | Perry Ustick |  | 2019-08-27 | Infinity Energy Inc | 7874e326-ca71-11e9-bb37-02ae981fbade | 1 | 6 | 10 | -2 | 5 | 5 | 5 | 18
28321 | PIP_APPROVED | PIP_APPROVED | 5952 Carlson Road | Yuba City | CA | 95993 | Gurcharan Dhokal | 2019-09-04 12:16 | 5303303430 | gurcharandhokal@gmail.com |  |  |  | 9805 | 0.18 | Ricardo Virgen | 2019-09-04 | 7.015 | Christina Horton | Blue Bright | Darlynn Lacap | 2019-08-31 | 2019-09-04 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-03 | PTO Received | SunRun Monthly | [6 empty] | 2019-10-03 07:00 | 2019-09-10 | 3.96 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-10 | 0.21 | 1 | Christina Horton | Completed | 2019-10-03 | 3.88 | 5 | Brian Le | Completed | 2019-09-10 | 0.13 | 3 | Ernesto Enriquez | Completed | 2019-09-25 | 10.83 | 0 | Andrew Moralez | Completed | 2019-10-03 | 0.58 | 2 | Christina Horton | Completed | 2019-10-18 | 10.5 | 2 | Christina Horton | Completed | 2019-09-26 | 11.92 | 2 | Brian Le | Completed | 2019-09-10 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-11 | 1.13 | 1 | Andrew Clemons | Completed | 2019-10-07 | 2.42 | 1 | Darlynn Lacap | Completed | 2019-10-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-14 | 5.04 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 4.67 | 2 | Ashley Rockwood | Completed |  | 0.33 | 2 | Darlynn Lacap | Current |  | 0.33 | 1 | Noe Gomez | Current | 2019-10-07 12:37 |  | 2019-10-07 | 1.79 | 2 | Christina Horton | Completed | [10 empty] | 2.92 | [11 empty] | 2019-09-10 | 2019-10-18 | SUTTER | Yuba City | https://heliotrack.completesolar.com/job.php?action=review&jobID=28321 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28321 | https://completesolar.sugarondemand.com/#Opportunities/749dca98-cf48-11e9-b184-0630baf9dcb8 | Blue Bright |  | 2019-08-29 | Golden Gate Electric Service | 749dca98-cf48-11e9-b184-0630baf9dcb8 | 4 | 15 | 0 | -2 | 5 | 5 | 5 | 8
28356 | PIP_APPROVED | PIP_APPROVED | 15641 Coventry Lane | Fontana | CA | 92337 | Travis Taylor | 2019-09-03 12:26 | 9098516567 | trizavisam@msn.com |  |  |  | 10725 | 0.143 |  | 2019-08-30 | 7.32 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-08-30 | 2019-08-31 15:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-03 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-03 | 2019-09-03 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 4.83 | 2 | Daniel Speegle | Completed | 2019-09-05 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-03 | 1.83 | 5 | Brian Le | Completed | 2019-09-12 | 1.79 | 3 | Andrew Moralez | Completed |  | 27.25 | 12 | Andrew Moralez | Current | 2019-10-03 | 0.08 | 2 | Ara Sotto | Completed | 2019-10-08 | 2.79 | 2 | Ara Sotto | Completed | 2019-09-26 | 11.88 | 2 | Brian Le | Completed | 2019-09-10 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.21 | 1 |  | Completed | 2019-09-13 | 2.88 | 1 | Andrew Clemons | Completed | 2019-10-17 | 10.13 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 1 | 2 | Jeremiah Liend | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-07 |  | 12.13 | 2 | Ara Sotto | Current | [10 empty] | 5.26 | [11 empty] | 2019-09-30 | 2019-10-08 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=28356 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28356 | https://completesolar.sugarondemand.com/#Opportunities/a7a5262a-ce80-11e9-8901-069e4f790264 | Dominic Labadie |  | 2019-08-30 | Blalock Electric&Solar | a7a5262a-ce80-11e9-8901-069e4f790264 | 18 | 5 | -15 | -2 | 5 | 5 | 5 | -7
28455 | PIP_APPROVED | PIP_APPROVED | 4412 Foxboro Avenue | Bakersfield | CA | 93309 | Donald Hall | 2019-09-06 06:47 | 6618340501 | dhall8@bak.rr.com | Gloria Hall |  |  | 9134 | 0.182 | Bill Angevine | 2019-09-06 | 6.1 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-09-04 | 2019-09-05 10:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-03 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-10-03 07:00 | 2019-09-09 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0.13 | 2 | Daniel Speegle | Completed | 2019-09-25 | 11.79 | 1 | Christina Horton | Completed | 2019-10-03 | 1.63 | 5 | Brian Le | Completed | 2019-09-10 | 1 | 3 | Andrew Moralez | Completed | 2019-10-04 | 17.88 | 5 | Andrew Moralez | Completed | 2019-10-03 | 0.42 | 2 | Christina Horton | Completed | 2019-10-11 | 6.21 | 2 | Christina Horton | Completed | 2019-09-27 | 11.92 | 2 | Brian Le | Completed | 2019-09-11 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0 | 1 |  | Completed | 2019-09-12 | 3 | 1 | Andrew Clemons | Completed | 2019-10-02 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-14 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 4.71 | 2 | Ashley Rockwood | Completed |  | 0.33 | 2 | Darlynn Lacap | Current |  | 0.33 | 1 | Noe Gomez | Current | 2019-10-09 10:43 |  | 2019-10-09 | 4 | 2 | Christina Horton | Completed | [10 empty] | 4.08 | [11 empty] | 2019-09-17 | 2019-10-11 | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=28455 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28455 | https://completesolar.sugarondemand.com/#Opportunities/c2d725b4-d0ac-11e9-b3a0-0630baf9dcb8 | Ryan Wilcox |  | 2019-09-04 | Anley Electric | c2d725b4-d0ac-11e9-b3a0-0630baf9dcb8 | 6 | 8 | -5 | -2 | 5 | 5 | 5 | 3
28522 | PIP_APPROVED | PIP_APPROVED | 12460 Madera Street | Victorville | CA | 92392 | Arleen Pollard | 2019-09-13 12:47 | 3108712354 | apolfran@gmail.com |  |  |  | 14022 | 0.157 | Shaun Labelle | 2019-09-13 | 8.235 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-06 | 2019-09-13 09:00 | LR6-60PB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-10-03 | Final Permit | SunRun Monthly | [6 empty] | 2019-10-02 07:00 | 2019-09-17 | 2.04 | 2 | Marcia Garay | Completed | 2019-09-17 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-25 | 5.83 | 1 | Ara Sotto | Completed | 2019-10-03 | 4.96 | 5 | Brian Le | Completed | 2019-09-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-25 | 4.75 | 10 | Andrew Moralez | Completed | 2019-10-03 | 1.38 | 2 | Ara Sotto | Completed | 2019-10-09 | 3.96 | 2 | Ara Sotto | Completed | 2019-09-26 | 5.17 | 2 | Brian Le | Completed | 2019-09-17 | 0 | 2 | Marcia Garay | Completed | 2019-09-18 | 1.04 | 1 |  | Completed | 2019-09-24 | 4.79 | 1 | Jill Allen | Completed | 2019-10-07 | 3.38 | 1 | Marcia Garay | Completed | 2019-10-10 | 1.04 | 2 | Jeremiah Liend | Completed | [16 empty] | 3.13 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-04 13:03 |  | 2019-10-07 | 1.96 | 2 | Ara Sotto | Completed | [10 empty] | 8.83 | [11 empty] | 2019-10-02 | 2019-10-09 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28522 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28522 | https://completesolar.sugarondemand.com/#Opportunities/3bfdc40e-d65f-11e9-b7fc-0630baf9dcb8 | CSA Division | Christopher Cellini | 2019-09-06 | HDM Electric Inc | 3bfdc40e-d65f-11e9-b7fc-0630baf9dcb8 | 4 | 6 | 0 | -2 | 5 | 5 | 5 | 8
28577 | PIP_APPROVED | PIP_APPROVED | 639 North Spruce Avenue | Rialto | CA | 92376 | Alfonso Cazares | 2019-09-12 12:00 | 9092588165 | alfonsocazares62@gmail.com | Patricia Cazares | 9092650973 |  | 6711 | 0.17 | Shaun Labelle | 2019-09-12 | 3.965 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-10 | 2019-09-11 09:00 | Q.PEAK-G4.1 305 | 305 | 13 | Hanwha Q CELLS | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-03 | Final Permit | SunRun Monthly | [6 empty] | 2019-10-03 07:00 | 2019-09-13 | 1.04 | 2 | Marcia Garay | Completed | 2019-09-16 | 0.88 | 2 | Daniel Speegle | Completed | 2019-09-25 | 6.92 | 1 | Ara Sotto | Completed | 2019-10-03 | 2.08 | 5 | Brian Le | Completed | 2019-09-18 | 0.96 | 3 | Ernesto Enriquez | Completed | 2019-09-27 | 6.79 | 7 | Andrew Moralez | Completed | 2019-10-03 | 0.38 | 1 | Ara Sotto | Completed | 2019-10-08 | 2.88 | 2 | Ara Sotto | Completed | 2019-10-01 | 8.83 | 2 | Brian Le | Completed | 2019-09-18 | 1.96 | 2 | Marcia Garay | Completed | 2019-09-17 | 1.17 | 1 |  | Completed | 2019-09-30 | 9.88 | 1 | Andrew Clemons | Completed | 2019-10-07 | 2.38 | 1 | Marcia Garay | Completed | 2019-10-14 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 10.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-07 13:31 |  | 2019-10-07 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 25.76 | [11 empty] | 2019-09-27 | 2019-10-08 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28577 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28577 | https://completesolar.sugarondemand.com/#Opportunities/75d34418-d58f-11e9-b760-0630baf9dcb8 | 300 Stars Inc | Oscar Hernandez | 2019-09-09 | Green Road Solar Crew | 75d34418-d58f-11e9-b760-0630baf9dcb8 | 4 | 5 | 0 | -2 | 5 | 5 | 5 | 8
27752 | PIP_APPROVED | PIP_APPROVED | 216 Lovell Street | Worcester | MA | 1603 | Gerald Kehoe | 2019-08-09 15:10 | 5082088757 | jjk4210@yahoo.com |  |  |  | 3272 | 0.193 | Hiram Velez | 2019-08-09 | 3.965 | Christina Horton | Solara Solar | Darlynn Lacap | 2019-08-08 | 2019-08-09 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-02 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  |  | 2019-10-01 07:00 | 2019-08-12 | 0.79 | 2 | Marcia Garay | Completed | 2019-08-14 | 2.08 | 2 | Daniel Speegle | Completed | 2019-08-19 | 2.92 | 1 | Christina Horton | Completed | 2019-10-01 | 4.04 | 5 | Brian Le | Completed | 2019-08-19 | 0 | 3 | Andrew Moralez | Completed | 2019-08-21 | 2 | 10 | Andrew Moralez | Completed | 2019-10-02 | 1.17 | 1 | Christina Horton | Completed | 2019-10-21 | 13 | 2 | Christina Horton | Completed | 2019-09-24 | 16.04 | 2 | Brian Le | Completed | 2019-08-16 | 1.79 | 2 | Marcia Garay | Completed | 2019-08-19 | 2.96 | 1 |  | Completed | 2019-09-12 | 20.04 | 1 | Noe Gomez | Completed | 2019-10-03 | 1.25 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-09 | 1.21 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 3.71 | 2 | Ashley Rockwood | Completed |  | 4.34 | 2 | Darlynn Lacap | Current | 2019-10-16 | 1.25 | 1 | Andrew Clemons | Completed | 2019-10-08 08:13 |  | 2019-10-08 | 4 | 2 | Christina Horton | Completed | [10 empty] | 22.29 | [11 empty] | 2019-09-03 | 2019-10-21 | Default | Worcester | https://heliotrack.completesolar.com/job.php?action=review&jobID=27752 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27752 | https://completesolar.sugarondemand.com/#Opportunities/6056ca9a-baf2-11e9-b9df-02ae981fbade | Solara Solar | Von Ayers | 2019-08-08 | Skyline Solar | 6056ca9a-baf2-11e9-b9df-02ae981fbade | 6 | 19 | -5 | -2 | 5 | 5 | 5 | 3
28469 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 717 El Monte Road | El Cajon | CA | 92020 | Salvador H Buelna | 2019-09-07 14:28 | 6196475568 | salbuelna@yahoo.com | ELVIA C BUELNA |  |  | 8533 | 0.192 | Ryan Malloy | 2019-09-07 | 5.49 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-04 | 2019-09-07 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-02 | PTO Received | SunRun Monthly | [6 empty] | 2019-10-02 07:00 | 2019-09-11 | 2.46 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-18 | 4.83 | 1 | Ara Sotto | Completed | 2019-10-02 | 14.38 | 5 | Brian Le | Completed | 2019-09-11 | 0 | 3 | Andrew Moralez | Completed | 2019-09-30 | 13.08 | 5 | Andrew Moralez | Completed | 2019-10-02 | 0.58 | 2 | Christina Horton | Completed |  | 12.92 | 2 | Christina Horton | Current | 2019-09-12 | 0.88 | 2 | Brian Le | Completed | 2019-09-11 | 0.08 | 2 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 1 |  | Completed | 2019-09-16 | 3.13 | 1 | Noe Gomez | Completed | 2019-10-07 | 3.42 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-18 | 8.96 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 0.88 | 2 | Ashley Rockwood | Completed |  | 0.25 | 2 | Marcia Garay | Current |  | 0.25 | 1 | Noe Gomez | Current | 2019-10-07 10:16 |  | 2019-10-07 | 2.79 | 2 | Christina Horton | Completed | [10 empty] | 3.29 | [11 empty] | 2019-09-18 |  | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=28469 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28469 | https://completesolar.sugarondemand.com/#Opportunities/507680a4-d1b6-11e9-8f78-02ae981fbade | Daniel Boyce | Valerie Jetter | 2019-09-04 | Infinity Energy Inc | 507680a4-d1b6-11e9-8f78-02ae981fbade | 5 | 19 | -5 | -2 | 5 | 5 | 5 | 3
28481 | PIP_APPROVED | PIP_APPROVED | 42546 32nd Street West | Quartz Hill | CA | 93536 | Heather Callaway | 2019-09-09 15:14 | 6619920302 | pooka716@gmail.com |  |  |  | 10662 | 0.144 | Bill Angevine | 2019-09-09 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-06 | 2019-09-07 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-02 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-26 | 2019-09-12 | 2.96 | 2 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-30 | 11.92 | 1 | Ara Sotto | Completed | 2019-09-30 | 3.04 | 5 | Brian Le | Completed | 2019-09-12 | 0 | 3 | Andrew Moralez | Completed | 2019-09-18 | 4 | 1 | Andrew Moralez | Completed | 2019-10-02 | 4.46 | 2 | Ara Sotto | Completed | 2019-10-09 | 5.04 | 2 | Ara Sotto | Completed | 2019-09-19 | 2.08 | 2 | Brian Le | Completed | 2019-09-17 | 2.75 | 2 | Marcia Garay | Completed | 2019-09-12 | 0.08 | 1 |  | Completed | 2019-09-16 | 2 | 1 | Andrew Clemons | Completed | 2019-10-04 | 6.5 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-04 15:01 |  |  | 13.08 | 2 | Ara Sotto | Current | [10 empty] | 3.96 | [11 empty] | 2019-09-13 | 2019-10-09 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28481 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28481 | https://completesolar.sugarondemand.com/#Opportunities/2dfcd9de-d34f-11e9-a5de-0630baf9dcb8 | Kevin Adams | Emily Bowden | 2019-09-05 | JK Solar | 2dfcd9de-d34f-11e9-a5de-0630baf9dcb8 | 19 | 7 | -15 | -2 | 5 | 5 | 5 | -7
27080 | PIP_APPROVED | PIP_APPROVED | 1973 Ainsley Road | San Diego | CA | 92123 | Christine Kowalski | 2019-09-23 10:27 | 8582430729 | christine@univmgmt.com |  |  |  | 5044.96 |  | Ryan Malloy | 2019-07-17 | 3.05 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-12 | 2019-07-13 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-10-01 | PTO Received | Cash |  | 0 |  |  |  |  | 2019-10-01 07:00 | 2019-09-23 | 1 | 2 | Marcia Garay | Completed | 2019-09-23 | 1.21 | 2 | Daniel Speegle | Completed | 2019-09-24 | 6.46 | 1 | Christina Horton | Completed | 2019-10-01 | 9.88 | 5 | Brian Le | Completed | 2019-09-23 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-23 | 0.08 | 15 | Andrew Moralez | Completed | 2019-10-01 | 0.79 | 1 | Christina Horton | Completed | 2019-10-21 | 14.04 | 2 | Christina Horton | Completed | 2019-09-23 | 4.92 | 2 | Brian Le | Completed | 2019-09-23 | 0.71 | 2 | Marcia Garay | Completed | 2019-09-23 | 0.12 | 1 |  | Completed | 2019-09-24 | 3.46 | 1 | Andrew Clemons | Completed | 2019-10-03 | 1.04 | 1 | Marcia Garay | Completed |  | 0.13 | 2 | Noe Gomez | Current | [15 empty] | 2019-10-03 | 0.25 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 1.67 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 8.04 | 2 | Marcia Garay | Completed |  | 10.38 | 1 | Andrew Clemons | Current | 2019-10-03 12:24 |  | 2019-10-03 | 1.83 | 2 | Christina Horton | Completed | [10 empty] | 31.59 | [11 empty] | 2019-10-12 | 2019-10-03 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27080 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27080 | https://completesolar.sugarondemand.com/#Opportunities/36ab76d6-a8e7-11e9-bb8b-0630baf9dcb8 | Robert Blessing |  | 2019-07-12 | Infinity Energy Inc | 36ab76d6-a8e7-11e9-bb8b-0630baf9dcb8 | 2 | 20 | 7 | -2 | 5 | 5 | 5 | 15
27779 | PIP_APPROVED | PIP_APPROVED | 8242 Flanders Drive | San Diego | CA | 92126 | Spencer Hall | 2019-09-11 18:28 | 8583619353 | shall@proautocon.com |  |  |  | 8459 | 0.195 | Ryan Malloy | 2019-08-21 | 5.795 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-12 | 2019-08-16 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-10-01 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 1 | 1 | 2019-10-01 07:00 | 2019-09-12 | 1.2 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 6.92 | 2 | Daniel Speegle | Completed | 2019-09-26 | 15.51 | 1 | Christina Horton | Completed | 2019-10-01 | 10.04 | 5 | Brian Le | Completed | 2019-09-17 | 1.95 | 3 | Andrew Moralez | Completed | 2019-09-27 | 8.41 | 15 | Andrew Moralez | Completed | 2019-10-01 | 0.33 | 2 | Christina Horton | Completed | 2019-10-03 | 2.08 | 2 | Christina Horton | Completed | 2019-09-16 | 3.12 | 2 | Brian Le | Completed | 2019-09-16 | 4.76 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 5.55 | 1 |  | Completed | 2019-09-23 | 12.56 | 1 | Jill Allen | Completed | 2019-10-03 | 2.46 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-10 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 5.21 | 2 | Darlynn Lacap | Completed | 2019-10-16 | 2.25 | 1 | Andrew Clemons | Completed | 2019-10-03 08:41 |  | 2019-10-03 | 2.08 | 2 | Christina Horton | Completed | [10 empty] | 11.85 | 2019-09-18 | 10.12 | 14 | James Fernandez | Completed | 2019-09-18 | 2019-09-18 | 0 | 1 | James Fernandez | Completed | 2019-10-08 | 2019-10-03 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27779 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27779 | https://completesolar.sugarondemand.com/#Opportunities/64715984-c433-11e9-98ee-0630baf9dcb8 | Thomas Noble |  | 2019-08-09 | Infinity Energy Inc | 64715984-c433-11e9-98ee-0630baf9dcb8 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
27786 | PIP_APPROVED | PIP_APPROVED | 26943 Messina Street | Highland | CA | 92346 | Donna McAnelly | 2019-08-31 11:09 | 3107554957 | bigmc51@yahoo.com | SHAWANA KING | 5628220903 |  | 9657 | 0.16 | Alex Holdridge | 2019-08-31 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-09 | 2019-08-10 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-10-01 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-01 07:00 | 2019-09-03 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 1.08 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-01 | 0.13 | 5 | Brian Le | Completed | 2019-09-23 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 2.92 | 14 | Ernesto Enriquez | Completed | 2019-10-01 | 0.42 | 2 | Ara Sotto | Completed | 2019-10-02 | 1 | 2 | Ara Sotto | Completed | 2019-10-01 | 13.79 | 2 | Brian Le | Completed | 2019-09-11 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.17 | 1 |  | Completed | 2019-09-23 | 8.83 | 1 | Noe Gomez | Completed | 2019-10-09 | 6.46 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.75 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-09 |  | 0 | 2 |  | Inactive |  | 14.54 | 1 | Ara Sotto | Current | 2019-09-11 | 0.46 | 2 | Darlynn Lacap | Completed | 11.04 | [11 empty] | 2019-10-11 | 2019-10-02 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=27786 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27786 | https://completesolar.sugarondemand.com/#Opportunities/5f7e3b2e-cc1a-11e9-9624-0630baf9dcb8 | Hugo Vicuna |  | 2019-08-09 | HDM Electric Inc | 5f7e3b2e-cc1a-11e9-9624-0630baf9dcb8 |  | 1 | -25 | 5 | 5 | 5 | 5 | -10
27823 | PIP_APPROVED | PIP_APPROVED | 31319 Whispering Palms Trail | Cathedral City | CA | 92234 | Rene Agluba | 2019-08-13 12:18 | 7608806699 | hapinhopin@gmail.com | Rosalyn Agluba | 7608087293 |  | 10081 | 0.174 | Michael Marlaire | 2019-08-13 | 6.405 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-10 | 2019-08-12 09:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-01 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-01 07:00 | 2019-08-13 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 2.08 | 2 | Jethro Andal | Completed | 2019-08-15 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-01 | 2.13 | 5 | Brian Le | Completed | 2019-08-23 | 3.75 | 3 | Ernesto Enriquez | Completed | 2019-09-24 | 21.21 | 7 | Ernesto Enriquez | Completed | 2019-10-01 | 0.92 | 2 | Ara Sotto | Completed | 2019-10-02 | 1.04 | 2 | Ara Sotto | Completed | 2019-09-26 | 27.08 | 2 | Brian Le | Completed | 2019-08-16 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.17 | 1 |  | Completed | 2019-08-26 | 4.92 | 1 | Andrew Clemons | Completed | 2019-10-09 | 6.84 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.67 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-10-17 | 5.92 | 2 | Ashley Rockwood | Completed |  | 2.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-09 14:39 |  | 2019-10-09 | 6.04 | 2 | Ara Sotto | Completed | [10 empty] | 4.84 | [11 empty] | 2019-09-04 | 2019-10-02 | CATHEDRAL CITY | Cathedral City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27823 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27823 | https://completesolar.sugarondemand.com/#Opportunities/1f4b2824-bdff-11e9-a086-02ae981fbade | Oscar Hernandez |  | 2019-08-10 | HDM Electric Inc | 1f4b2824-bdff-11e9-a086-02ae981fbade | 8 | 1 | -5 | 5 | 5 | 5 | 5 | 10
28103 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3749 East Avenue S-12 | Palmdale | CA | 93550 | Isaura Espino | 2019-08-27 09:15 | 6612364508 | miacastia87@gmail.com |  |  |  | 8619 | 0.138 | Shaun Labelle | 2019-08-27 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-22 | 2019-08-23 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-09-30 07:00 | 2019-08-28 | 1.08 | 2 | Marcia Garay | Completed | 2019-08-28 | 0.17 | 2 | Daniel Speegle | Completed | 2019-09-24 | 17.88 | 1 | Ara Sotto | Completed | 2019-10-01 | 3 | 5 | Brian Le | Completed | 2019-09-11 | 7.92 | 3 | Andrew Moralez | Completed | 2019-09-20 | 7.21 | 5 | Andrew Moralez | Completed | 2019-10-01 | 1.42 | 1 | Ara Sotto | Completed |  | 14.08 | 2 | Ara Sotto | Current | 2019-09-26 | 19.04 | 2 | Brian Le | Completed | 2019-08-29 | 0.83 | 2 | Marcia Garay | Completed | 2019-08-29 | 0.83 | 1 |  | Completed | 2019-09-06 | 5.88 | 1 | Andrew Clemons | Completed | 2019-10-07 | 5.42 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-08 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 3.88 | 2 | Ashley Rockwood | Completed |  | 5.21 | 2 | Darlynn Lacap | Current | 2019-10-16 | 2.13 | 1 | Jeremiah Liend | Completed |  | 2019-09-19 | 2019-10-07 | 3.96 | 2 | Ara Sotto | Completed | [10 empty] | 1.88 | [11 empty] | 2019-09-18 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28103 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28103 | https://completesolar.sugarondemand.com/#Opportunities/c991f240-c8e5-11e9-b322-069e4f790264 | Solar Raze | Emily Bowden | 2019-08-21 | JK Solar | c991f240-c8e5-11e9-b322-069e4f790264 | 6 | 20 | -5 | -2 | 5 | 5 | 5 | 3
28126 | PIP_APPROVED | PIP_APPROVED | 1914 Ivory Avenue | Palmdale | CA | 93550 | Timothy Lowther | 2019-08-29 14:49 | 5054170752 | tslowther2@gmail.com |  |  |  | 7807 | 0.16 | Shaun Labelle | 2019-08-29 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-22 | 2019-08-23 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-10-01 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-30 07:00 | 2019-09-09 | 4.04 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.16 | 2 | Daniel Speegle | Completed | 2019-09-18 | 6.92 | 1 | Ara Sotto | Completed | 2019-10-01 | 4.13 | 5 | Brian Le | Completed | 2019-09-11 | 1.79 | 3 | Andrew Moralez | Completed | 2019-09-20 | 7.17 | 5 | Andrew Moralez | Completed | 2019-10-01 | 1.92 | 1 | Ara Sotto | Completed | 2019-10-11 | 7.75 | 2 | Ara Sotto | Completed | 2019-09-19 | 5.79 | 2 | Brian Le | Completed | 2019-09-11 | 2 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-19 | 7.79 | 1 | Andrew Clemons | Completed | 2019-10-07 | 5.8 | 1 | Darlynn Lacap | Completed | 2019-10-11 | 0 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-16 | 6.96 | 2 | Ashley Rockwood | Completed |  | 3.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-23 | 2019-10-07 | 3.96 | 2 | Ara Sotto | Completed | [10 empty] | 5.88 | [11 empty] | 2019-09-18 | 2019-10-10 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28126 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28126 | https://completesolar.sugarondemand.com/#Opportunities/d20a92a2-caa6-11e9-9046-022c40d974e6 | Solar Raze | Emily Bowden | 2019-08-22 | JK Solar | d20a92a2-caa6-11e9-9046-022c40d974e6 | 6 | 10 | -5 | -2 | 5 | 5 | 5 | 3
28384 | PIP_APPROVED | PIP_APPROVED | 20083 Sahale Road | Apple Valley | CA | 92307 | Nicholas Wright | 2019-09-10 14:05 | 7608872233 | nicholas.wright.20083@gmail.com |  |  |  | 10187 | 0.112 | Shaun Labelle | 2019-09-10 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-02 | 2019-09-09 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-10-01 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-30 07:00 | 2019-09-11 | 1.04 | 2 | Marcia Garay | Completed | 2019-09-12 | 0.83 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-10-01 | 0.08 | 5 | Brian Le | Completed | 2019-09-20 | 5.96 | 3 | Ernesto Enriquez | Completed | 2019-09-23 | 0.92 | 14 | Ernesto Enriquez | Completed | 2019-10-01 | 1.42 | 2 | Ara Sotto | Completed | 2019-10-09 | 5.88 | 2 | Ara Sotto | Completed | 2019-09-26 | 9.08 | 2 | Brian Le | Completed | 2019-09-13 | 0.96 | 2 | Marcia Garay | Completed | 2019-09-12 | 0.17 | 1 |  | Completed | 2019-09-26 | 9.96 | 1 | Andrew Clemons | Completed | 2019-10-16 | 12.42 | 1 | Marcia Garay | Completed | 2019-10-09 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-16 |  | 14.08 | 2 | Ara Sotto | Current | [10 empty] | 3.13 | [11 empty] | 2019-10-10 | 2019-10-09 | APPLE VALLEY | Apple Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28384 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28384 | https://completesolar.sugarondemand.com/#Opportunities/99503b58-d40e-11e9-8879-069e4f790264 | SCES Division |  | 2019-09-02 | HDM Electric Inc | 99503b58-d40e-11e9-8879-069e4f790264 | 20 | 8 | -15 | -2 | 5 | 5 | 5 | -7
28583 | PIP_APPROVED | PIP_APPROVED | 7886 Arcadia Avenue | Hesperia | CA | 92345 | Richard Granfield | 2019-09-12 12:16 | 7604752969 | rickg19@verizon.net |  |  |  | 18058 | 0.105 | Alex Holdridge | 2019-09-12 | 10.675 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-09-09 | 2019-09-12 09:00 | LR6-60PB-305M | 305 | 35 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Tile Concrete | NO | 2019-10-01 | Final Permit | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-10-01 07:00 | 2019-09-20 | 4 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 1.16 | 2 | Daniel Speegle | Completed | 2019-09-27 | 3.08 | 1 | Ara Sotto | Completed | 2019-10-01 | 0.92 | 5 | Brian Le | Completed | 2019-09-27 | 2.96 | 3 | Ernesto Enriquez | Completed | 2019-09-27 | 0 | 14 | Andrew Moralez | Completed | 2019-10-01 | 0.42 | 3 | Ara Sotto | Completed | 2019-10-04 | 2.83 | 2 | Ara Sotto | Completed | 2019-09-30 | 4.04 | 2 | Brian Le | Completed | 2019-09-24 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 0.16 | 1 |  | Completed | 2019-09-30 | 3.75 | 1 | Andrew Clemons | Completed | 2019-10-07 | 4.38 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0.83 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-02 14:35 |  | 2019-10-07 | 3.88 | 2 | Ara Sotto | Completed | [10 empty] | 25.83 | [11 empty] | 2019-10-17 | 2019-10-04 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=28583 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28583 | https://completesolar.sugarondemand.com/#Opportunities/c8ba915c-d591-11e9-9afe-022c40d974e6 | Dominic Labadie |  | 2019-09-09 | Blalock Electric&Solar | c8ba915c-d591-11e9-9afe-022c40d974e6 | 6 | 3 | -5 | 2 | 5 | 5 | 5 | 7
28614 | PIP_APPROVED | PIP_APPROVED | 14722 Clydesdale Circle | Victorville | CA | 92394 | Michael Rizo | 2019-09-14 17:10 | 7606055075 | mikerizojr@yahoo.com | Heather Rizo | 7605084149 |  | 12719 | 0 | Alex Holdridge | 2019-09-14 | 7.015 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-10 | 2019-09-14 15:00 | LR6-60PE-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-10-01 | PTO Received | SunRun PPA Prepaid | 0 | 0 |  |  | 0 | 1 | 2019-10-01 07:00 | 2019-09-16 | 0.67 | 2 | Marcia Garay | Completed | 2019-09-17 | 0.88 | 2 | Daniel Speegle | Completed | 2019-10-01 | 10 | 1 | Ara Sotto | Completed |  | 14.08 | 5 | Brian Le | Current | 2019-09-18 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-09-25 | 4.83 | 10 | Ernesto Enriquez | Completed | 2019-10-01 | 0.42 | 2 | Ara Sotto | Completed | 2019-10-02 | 1.21 | 2 | Ara Sotto | Completed | 2019-10-01 | 9.92 | 2 | Brian Le | Completed | 2019-09-17 | 0.04 | 2 | Marcia Garay | Completed | 2019-09-18 | 0.96 | 1 |  | Completed | 2019-09-26 | 7.04 | 1 | Jill Allen | Completed | 2019-10-04 | 3.25 | 1 | Marcia Garay | Completed | 2019-10-10 | 5.71 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-08 | 2.17 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 5.92 | 2 | Marcia Garay | Completed | 2019-10-10 | 1.08 | 1 | Andrew Clemons | Completed | 2019-10-02 14:40 |  | 2019-10-04 | 2.75 | 2 | Ara Sotto | Completed | [10 empty] | 3 | [11 empty] | 2019-10-02 | 2019-10-02 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28614 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28614 | https://completesolar.sugarondemand.com/#Opportunities/2ad4efd8-d74d-11e9-b47b-02ae981fbade | CSA Division | Christopher Cellini | 2019-09-10 | Power Town Solar Electric | 2ad4efd8-d74d-11e9-b47b-02ae981fbade | 3 | 1 | 0 | 5 | 5 | 5 | 5 | 15
28658 | SP APPROVED |  | 13213 Vista Del Sol Court | Victorville | CA | 92394 | Randy Williams | 2019-09-23 11:08 | 7602676662 | randy.l.williams2@gmail.com |  |  |  | 6913 | 0.155 | Alex Holdridge | 2019-09-12 | 3.965 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-11 | 2019-09-12 12:00 | LR6-60PE-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-10-01 | PTO Received | SunRun Monthly |  | 0 |  |  |  |  | 2019-10-01 | 2019-09-23 | 2.75 | 2 | Marcia Garay | Completed | 2019-09-25 | 2.17 | 2 | Daniel Speegle | Completed | 2019-10-01 | 7.84 | 1 | Ara Sotto | Completed | 2019-10-01 | 2.96 | 5 | Brian Le | Completed | 2019-09-24 | 0.08 | 3 | Andrew Moralez | Completed | 2019-10-16 | 17.84 | 10 | Andrew Moralez | Completed | 2019-10-01 | 1.21 | 1 | Ara Sotto | Completed |  | 14.13 | 2 | Ara Sotto | Current | 2019-09-26 | 3.08 | 2 | Brian Le | Completed | 2019-09-26 | 1.88 | 2 | Marcia Garay | Completed | 2019-09-25 | 1.17 | 1 |  | Completed | 2019-09-27 | 6.05 | 1 | Jill Allen | Completed | 2019-10-15 | 11.17 | 1 | Marcia Garay | Completed | 2019-10-03 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-18 | 1 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 0.92 | 2 | Ashley Rockwood | Completed |  | 0.17 | 2 | Marcia Garay | Current |  | 0.17 | 1 | Noe Gomez | Current | 2019-10-10 16:16 |  | 2019-10-17 | 12 | 2 | Ara Sotto | Completed | [10 empty] | 1.04 | [11 empty] | 2019-10-04 |  | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28658 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28658 | https://completesolar.sugarondemand.com/#Opportunities/c7b5b4c6-d5a0-11e9-a3bc-0630baf9dcb8 | Christopher Cellini | Cory Hartman | 2019-09-11 | Zachary Noah Gamez | c7b5b4c6-d5a0-11e9-a3bc-0630baf9dcb8 | 16 | 20 | -15 | -2 | 5 | 5 | 5 | -7
24754 | PIP_APPROVED | PIP_APPROVED | 158 Saint Vincent Court | Danville | CA | 94526 | Brad Edgren | 2019-08-23 13:56 | 9257431640 | bradeca@gmail.com |  |  |  | 24920.21 |  | Ricardo Virgen | 2019-07-08 | 18.09 | Christina Horton | CS Direct | Darlynn Lacap |  | 2019-05-24 08:30 | LG335N1C-A5 | 335 | 54 | LG Electronics | SolarEdge Technologies | SE10000H-US | Composite | NO | 2019-09-30 | PTO Received | Cash | 1 | 0 |  |  |  | 1 | 2019-09-30 07:00 | 2019-08-26 | 2.88 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 5.88 | 2 | Daniel Speegle | Completed | 2019-09-03 | 4.59 | 1 | Christina Horton | Completed | 2019-09-30 | 1.83 | 5 | Brian Le | Completed | 2019-08-30 | 4.04 | 3 | Andrew Moralez | Completed | 2019-08-30 | 0.08 | 1 | Andrew Moralez | Completed | 2019-09-30 | 0.29 | 4 | Christina Horton | Completed | 2019-10-17 | 13.17 | 2 | Christina Horton | Completed | 2019-09-26 | 4.83 | 2 | Brian Le | Completed | 2019-08-30 | 12.35 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.29 | 1 |  | Completed | 2019-08-29 | 9.84 | 1 | Andrew Clemons | Completed | 2019-10-02 | 2.54 | 1 | Darlynn Lacap | Completed |  | 2.04 | 2 | Jill Allen | Current | 2019-08-27 | 15.6 | 4 | Darlynn Lacap | Completed | 2019-08-27 | 0.08 | 5 | Darlynn Lacap | Completed | 2019-08-27 | 3.13 | 12 | Darlynn Lacap | Completed | 2019-10-03 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 0.83 | 2 | Ashley Rockwood | Completed |  | 11.21 | 2 | Darlynn Lacap | Current |  | 11.21 | 1 | Jeremiah Liend | Current | 2019-10-02 11:30 |  | 2019-10-02 | 2.08 | 2 | Christina Horton | Completed | [10 empty] | 47.91 | [11 empty] | 2019-08-31 | 2019-10-02 | DANVILLE | Danville | https://heliotrack.completesolar.com/job.php?action=review&jobID=24754 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24754 | https://completesolar.sugarondemand.com/#Opportunities/4c7b2f0e-a1b9-11e9-8f7a-0630baf9dcb8 | CS Direct |  | 2019-04-18 | Golden Gate Electric Service | 4c7b2f0e-a1b9-11e9-8f7a-0630baf9dcb8 | 2 | 17 | 7 | -2 | 5 | 5 | 5 | 15
26386 | PIP_APPROVED | PIP_APPROVED | 365 Los Altos Avenue | Long Beach | CA | 90814 | Olivera Sakic | 2019-08-15 12:51 | 3107676856 | olivera@dienter.com |  |  |  | 24679 |  | Chris Peaslee | 2019-07-30 | 12.58 | Ara Sotto | CS Direct | Darlynn Lacap | 2019-07-25 | 2019-08-12 09:00 | LR6-60HPB-305M | 305 | 34 | LONGi Solar | Enphase Energy | String Inverter |  | NO | 2019-09-30 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-09-25 07:00 | 2019-08-15 | 1.12 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 8.04 | 2 | Jethro Andal | Completed | 2019-09-10 | 15.99 | 1 | Ara Sotto | Completed | 2019-09-30 | 7.17 | 5 | Brian Le | Completed | 2019-08-21 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-18 | 17.13 | 20 | Andrew Moralez | Completed | 2019-09-30 | 3.46 | 3 | Ara Sotto | Completed | 2019-10-03 | 3 | 2 | Ara Sotto | Completed | 2019-09-19 | 20.71 | 2 | Brian Le | Completed | 2019-08-19 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.75 | 1 |  | Completed | 2019-08-21 | 3 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 2.38 | 1 | Darlynn Lacap | Completed | 2019-10-02 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-07 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5 | 2 | Ashley Rockwood | Completed |  | 5.13 | 2 | Darlynn Lacap | Current | 2019-10-15 | 0.92 | 1 | Jeremiah Liend | Completed | 2019-09-30 15:08 |  | 2019-09-30 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 16.13 | [11 empty] | 2019-09-23 | 2019-09-30 | LONG BEACH | Long Beach | https://heliotrack.completesolar.com/job.php?action=review&jobID=26386 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26386 | https://completesolar.sugarondemand.com/#Opportunities/c81471aa-b309-11e9-8deb-069e4f790264 | Robert Prado |  | 2019-06-14 | Power Town Solar Electric | c81471aa-b309-11e9-8deb-069e4f790264 | 0 | 3 | 10 | 2 | 5 | 5 | 5 | 22
27610 | PIP_APPROVED | PIP_APPROVED | 1124 1st Avenue House B | Dinuba | CA | 93618 | Ignacio Madriz #2 | 2019-08-19 10:56 | 5598028651 | 56mignacio@gmail.com | Cinthia Madriz |  |  | 10194.37 |  | Abraham SiteTech Vazquez | 2019-08-15 | 2.44 | Christina Horton | Sunmatter Inc | Marcia Garay | 2019-08-12 | 2019-08-15 15:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Metal Corrugated | NO | 2019-09-30 | Final Permit | Sunlight Financial Loan |  |  |  |  | 1 |  | 2019-09-30 | 2019-08-19 | 1.83 | 2 | Marcia Garay | Completed | 2019-08-20 | 1.04 | 2 | Jethro Andal | Completed | 2019-09-17 | 17.92 | 1 | Christina Horton | Completed | 2019-09-30 | 3.25 | 5 | Brian Le | Completed | 2019-08-22 | 0.92 | 3 | Andrew Moralez | Completed | 2019-09-04 | 7.96 | 0 | Andrew Moralez | Completed | 2019-09-30 | 0.08 | 2 | Christina Horton | Completed | 2019-10-21 | 14.75 | 2 | Christina Horton | Completed | 2019-09-17 | 17.04 | 2 | Brian Le | Completed | 2019-08-22 | 0.88 | 2 | Marcia Garay | Completed | 2019-08-20 | 0.08 | 1 |  | Completed | 2019-08-28 | 4.71 | 1 | Jeremiah Liend | Completed | 2019-10-02 | 2.08 | 1 | Marcia Garay | Completed | 2019-10-02 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 3.79 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-02 13:22 |  | 2019-10-02 | 1.92 | 2 | Christina Horton | Completed | [10 empty] | 21.58 | 2019-09-13 | 16.79 | 14 | James Fernandez | Completed | 2019-09-10 | 2019-09-30 | 4 | 1 | James Fernandez | Completed | 2019-08-22 | 2019-10-02 | DINUBA | Dinuba | https://heliotrack.completesolar.com/job.php?action=review&jobID=27610 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27610 | https://completesolar.sugarondemand.com/#Opportunities/f1bb54fa-bf8f-11e9-bae0-022c40d974e6 | People Builders |  | 2019-08-18 | Peak Energy Electric | f1bb54fa-bf8f-11e9-bae0-022c40d974e6 | 2 | 21 | 7 | -2 | 5 | 5 | 5 | 15
28052 | SP APPROVED |  | 13035 Julian Drive | Desert Hot Springs | CA | 92240 | Margarita Silva | 2019-09-09 09:44 | 7609058277 | cilerhead@gmail.com |  |  |  | 10732 | 0.13 | Shaun Labelle | 2019-09-09 | 6.1 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-19 | 2019-08-20 15:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-30 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-30 07:00 | 2019-09-10 | 1.25 | 2 | Marcia Garay | Completed | 2019-09-11 | 0.88 | 2 | Daniel Speegle | Completed | 2019-09-16 | 2.83 | 1 | Ara Sotto | Completed | 2019-09-30 | 0.08 | 5 | Brian Le | Completed | 2019-09-17 | 2.83 | 3 | Andrew Moralez | Completed | 2019-09-24 | 5.13 | 14 | Andrew Moralez | Completed | 2019-09-30 | 0.29 | 2 | Ara Sotto | Completed |  | 15.21 | 2 | Ara Sotto | Current | 2019-09-26 | 7.92 | 2 | Brian Le | Completed | 2019-09-16 | 3.04 | 2 | Marcia Garay | Completed | 2019-09-12 | 1 | 1 |  | Completed | 2019-09-17 | 3.88 | 1 | Andrew Clemons | Completed |  | 15.54 | 1 | Marcia Garay | Current | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 15.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-30 23:56 |  | 2019-09-30 | 0.17 | 2 | Ara Sotto | Completed | [10 empty] | 3.08 | [11 empty] | 2019-10-07 |  | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=28052 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28052 | https://completesolar.sugarondemand.com/#Opportunities/0c76e878-d321-11e9-8981-022c40d974e6 | PJB Division |  | 2019-08-19 | Zachary Noah Gamez | 0c76e878-d321-11e9-8981-022c40d974e6 | 0 | 21 | 10 | -2 | 5 | 5 | 5 | 18
28226 | PIP_APPROVED | PIP_APPROVED | 1635 Goldfield Place | Pomona | CA | 91766 | John Meyer | 2019-08-30 10:58 | 9096309560 | jessiecmeyer67@gmail.com | Jessie Meyer | 9096233801 |  | 7528 | 0.195 | Alex Holdridge | 2019-08-30 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-27 | 2019-08-30 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-30 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-30 07:00 | 2019-09-04 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-30 | 1.13 | 5 | Brian Le | Completed | 2019-09-04 | 0.13 | 3 | Andrew Moralez | Completed | 2019-09-27 | 16.79 | 5 | Andrew Moralez | Completed | 2019-09-30 | 0.42 | 1 | Ara Sotto | Completed | 2019-10-01 | 1.29 | 2 | Ara Sotto | Completed | 2019-09-26 | 14.96 | 2 | Brian Le | Completed | 2019-09-05 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.04 | 1 |  | Completed | 2019-09-10 | 4.25 | 1 | Andrew Clemons | Completed | 2019-10-09 | 7.46 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 7.75 | 2 | Ashley Rockwood | Completed |  | 0.25 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-30 14:23 |  | 2019-10-09 | 7.08 | 2 | Ara Sotto | Completed | [10 empty] | 2.09 | [11 empty] | 2019-09-11 | 2019-10-01 | POMONA | Pomona | https://heliotrack.completesolar.com/job.php?action=review&jobID=28226 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28226 | https://completesolar.sugarondemand.com/#Opportunities/a52eed60-cb4f-11e9-a621-022c40d974e6 | Summit Marketing Inc |  | 2019-08-27 | HDM Electric Inc | a52eed60-cb4f-11e9-a621-022c40d974e6 | 9 | 1 | -5 | 5 | 5 | 5 | 5 | 10
28247 | PIP_APPROVED | PIP_APPROVED | 14850 Riverside Street | Hesperia | CA | 92345 | Lora Wade | 2019-08-31 07:46 | 7608877452 | lorawho@hotmail.com | Ryan Wade | 7606465123 |  | 9487 | 0.132 | Shaun Labelle | 2019-08-31 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-29 | 2019-08-30 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-09-30 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 0 | 2019-09-30 | 2019-09-04 | 1.38 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.17 | 2 | Daniel Speegle | Completed | 2019-09-24 | 13.92 | 1 | Ara Sotto | Completed |  | 16.25 | 5 | Brian Le | Current | 2019-09-23 | 12.13 | 3 | Andrew Moralez | Completed | 2019-09-23 | 0 | 14 | Ernesto Enriquez | Completed | 2019-09-30 | 0 | 1 | Ara Sotto | Completed | 2019-10-01 | 1.21 | 2 | Ara Sotto | Completed | 2019-09-26 | 15.83 | 2 | Brian Le | Completed | 2019-09-04 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 0.88 | 1 |  | Completed | 2019-09-12 | 6.04 | 1 | Jill Allen | Completed | 2019-09-30 | 0 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 4.71 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-08 | 2019-09-30 | 0.08 | 2 | Ara Sotto | Completed | [10 empty] | 11.16 | [11 empty] | 2019-10-11 | 2019-09-30 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=28247 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28247 | https://completesolar.sugarondemand.com/#Opportunities/1a40974e-cbfe-11e9-a60d-0630baf9dcb8 | Cory Hartman |  | 2019-08-28 | Power Town Solar Electric | 1a40974e-cbfe-11e9-a60d-0630baf9dcb8 | 0 | 1 | 10 | 5 | 5 | 5 | 5 | 25
28261 | PIP_APPROVED | PIP_APPROVED | 14013 Rogers Lane | Victorville | CA | 92392 | Sonia Zepeda | 2019-08-31 19:21 | 7605051298 | sonzep63@yahoo.com | Angel Zepeda |  |  | 9216 | 0.135 | Bill Angevine | 2019-08-31 | 4.575 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-28 | 2019-08-31 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-30 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-20 07:00 | 2019-09-03 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.92 | 2 | Daniel Speegle | Completed | 2019-09-11 | 4.67 | 1 | Christina Horton | Completed |  | 18.25 | 5 | Brian Le | Current | 2019-09-05 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-30 | 8.79 | 1 | Ara Sotto | Completed | 2019-10-09 | 7.38 | 2 | Ara Sotto | Completed | 2019-09-16 | 6.92 | 2 | Brian Le | Completed | 2019-09-05 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 0.08 | 1 |  | Completed | 2019-09-16 | 7.92 | 1 | Jeremiah Liend | Completed | 2019-09-30 | 8.84 | 1 | Marcia Garay | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 4.83 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-23 16:54 | 2019-10-02 | 2019-09-30 | 0.08 | 2 | Ara Sotto | Completed | [10 empty] | 27.17 | [11 empty] | 2019-09-24 | 2019-10-09 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28261 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28261 | https://completesolar.sugarondemand.com/#Opportunities/10b31bf0-cc5f-11e9-8118-0630baf9dcb8 | SCES Division |  | 2019-08-28 | JK Solar | 10b31bf0-cc5f-11e9-8118-0630baf9dcb8 | 0 | 9 | 10 | -2 | 5 | 5 | 5 | 18
28386 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 25546 Sierra Leone Court | Moreno Valley | CA | 92551 | Sheri(John) Pendleton | 2019-09-12 14:57 | 9514882778 | sherilynn79@gmail.com | John Salazar | 9512012941 |  | 4330 | 0.17 | Michael Marlaire | 2019-09-12 | 2.745 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-06 | 2019-09-12 12:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-30 | Installation Complete | SunRun Monthly | 1 | 0 |  |  | 0 | 1 | 2019-09-30 07:00 | 2019-09-16 | 1.96 | 2 | Marcia Garay | Completed | 2019-09-16 | 0 | 2 | Daniel Speegle | Completed | 2019-09-24 | 5.92 | 1 | Ara Sotto | Completed | 2019-09-30 | 2.04 | 5 | Brian Le | Completed | 2019-09-20 | 1 | 3 | Andrew Moralez | Completed | 2019-09-20 | 0 | 25 | Andrew Moralez | Completed | 2019-09-30 | 0.42 | 1 | Ara Sotto | Completed |  | 15.13 | 2 | Ara Sotto | Current | 2019-09-26 | 7.13 | 2 | Brian Le | Completed | 2019-09-17 | 0.71 | 2 | Marcia Garay | Completed | 2019-09-19 | 2.75 | 1 |  | Completed | 2019-09-26 | 7.75 | 1 | Andrew Clemons | Completed |  | 15.54 | 1 | Marcia Garay | Current | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | 2019-09-18 | 2 | 4 | Marcia Garay | Completed | 2019-09-24 | 3.71 | 5 | Marcia Garay | Completed | 2019-09-24 | 0 | 12 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-11-01 |  | 15.13 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-10-25 |  | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28386 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28386 | https://completesolar.sugarondemand.com/#Opportunities/30ddfaa6-d5a8-11e9-8df7-069e4f790264 | Oscar Hernandez |  | 2019-09-02 | Green Road Solar Crew | 30ddfaa6-d5a8-11e9-8df7-069e4f790264 | 21 | 21 | -25 | -2 | 5 | 5 | 5 | -17
28397 | PIP_APPROVED | PIP_APPROVED | 6560 La Praix Street | Highland | CA | 92346 | Jacob Stacy | 2019-09-11 13:56 | 9094964997 | jacobstcy1@yahoo.com | Leslie Gamboa | 9093581456 |  | 9041 | 0.18 | Shaun Labelle | 2019-09-11 | 5.795 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-04 | 2019-09-11 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-30 | NEM Submitted | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-09-30 07:00 | 2019-09-16 | 3.08 | 2 | Marcia Garay | Completed | 2019-09-16 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-26 | 7.92 | 1 | Ara Sotto | Completed | 2019-09-30 | 0.58 | 5 | Brian Le | Completed | 2019-09-20 | 2 | 3 | Ernesto Enriquez | Completed | 2019-09-26 | 4.13 | 14 | Andrew Moralez | Completed | 2019-09-30 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-02 | 2.29 | 2 | Ara Sotto | Completed | 2019-09-29 | 9.29 | 2 | Brian Le | Completed | 2019-09-16 | 0 | 2 | Marcia Garay | Completed | 2019-09-18 | 1.71 | 1 |  | Completed | 2019-09-23 | 5 | 1 | Jill Allen | Completed |  | 15.54 | 1 | Marcia Garay | Current | 2019-10-09 | 4.42 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-17 | 0.08 | 2 | Ashley Rockwood | Completed |  | 2.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-17 14:26 |  | 2019-10-17 | 12.92 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-10-10 | 2019-10-02 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28397 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28397 | https://completesolar.sugarondemand.com/#Opportunities/92095424-d4d6-11e9-a319-02ae981fbade | Summit Marketing Inc | Tiburon Mike Weber | 2019-09-03 | Power Town Solar Electric | 92095424-d4d6-11e9-a319-02ae981fbade | 17 | 2 | -15 | 4 | 5 | 5 | 5 | -1
27216 | PIP_APPROVED | PIP_APPROVED | 1448 Pluto Road | Vista | CA | 92083 | Dionicio Montes | 2019-08-01 14:56 | 4422739158 | doniciopluto1448@gmail.com |  |  |  | 10018 | 0.185 | Michael Marlaire | 2019-08-01 | 7.015 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-22 | 2019-08-01 12:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | MPU | 2019-09-28 | Final Permit | SunRun Monthly |  |  |  |  | 1 |  | 2019-09-27 07:00 | 2019-08-05 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 4 | 2 | Jethro Andal | Completed | 2019-09-19 | 23.13 | 1 | Christina Horton | Completed | 2019-09-27 | 29.67 | 5 | Brian Le | Completed | 2019-08-16 | 0.13 | 3 | Andrew Moralez | Completed | 2019-08-16 | 0 | 0 | Andrew Moralez | Completed | 2019-09-28 | 0.79 | 2 | Christina Horton | Completed | 2019-10-18 | 14.67 | 2 | Christina Horton | Completed | 2019-08-13 | 0.08 | 2 | Brian Le | Completed | 2019-08-15 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 0.88 | 1 |  | Completed | 2019-08-26 | 6.63 | 1 | Jill Allen | Completed | 2019-09-27 | 0.33 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.29 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-16 12:58 |  | 2019-10-18 | 2.83 | 2 | Christina Horton | Completed | 2019-10-15 | 1.33 | 1 | Christina Horton | Completed | 2019-08-12 | 0.83 | 2 | Darlynn Lacap | Completed | 30.18 | 2019-08-15 | 0 | 14 | James Fernandez | Completed | 2019-08-15 | 2019-08-15 | 0 | 1 | James Fernandez | Completed | 2019-08-16 | 2019-10-18 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27216 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27216 | https://completesolar.sugarondemand.com/#Opportunities/316f33b2-b4a7-11e9-8a19-02ae981fbade | Alexis Cain |  | 2019-07-17 | Infinity Energy Inc | 316f33b2-b4a7-11e9-8a19-02ae981fbade | 3 | 20 | 0 | -2 | 5 | 5 | 5 | 8
28325 | PIP_APPROVED | PIP_APPROVED | 4571 Westridge Drive | Oceanside | CA | 92056 | Catherine Huerta | 2019-09-05 06:44 | 7759343553 | sweet530i@gmail.com | Edward Huerta | 7759343552 | huerta.catherine@gmail.com | 4725 | 0.185 | Michael Marlaire | 2019-09-05 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-29 | 2019-09-03 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-28 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-27 12:00 | 2019-09-05 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 1.88 | 2 | Daniel Speegle | Completed | 2019-09-26 | 13.04 | 1 | Ara Sotto | Completed | 2019-09-27 | 11.13 | 5 | Brian Le | Completed | 2019-09-09 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-28 | 0.79 | 1 | Christina Horton | Completed | 2019-10-02 | 2.58 | 2 | Christina Horton | Completed | 2019-09-12 | 0.96 | 2 | Brian Le | Completed | 2019-09-11 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0 | 1 |  | Completed | 2019-09-13 | 3.88 | 1 | Andrew Clemons | Completed | 2019-09-27 | 0.33 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | 2019-09-20 | 11.04 | 4 | Darlynn Lacap | Completed | 2019-09-20 | 0 | 5 | Darlynn Lacap | Completed | 2019-09-26 | 3.79 | 12 | Darlynn Lacap | Completed | 2019-10-07 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 4.96 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 4.96 | 2 | Darlynn Lacap | Completed | 2019-10-16 | 1.96 | 1 | Andrew Clemons | Completed | 2019-10-02 11:58 |  | 2019-10-02 | 2.58 | 2 | Christina Horton | Completed | [10 empty] | 0 | [11 empty] | 2019-09-24 | 2019-10-02 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28325 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28325 | https://completesolar.sugarondemand.com/#Opportunities/264917ee-cfe3-11e9-a67c-02ae981fbade | Lee Allison |  | 2019-08-29 | Infinity Energy Inc | 264917ee-cfe3-11e9-a67c-02ae981fbade | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28773 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3242 Roberta Lane | Oceanside | CA | 92054 | Karen Albarado | 2019-09-18 10:30 | 7608032318 | Songsbrat51@cox.net |  |  |  | 6014 | 0.175 | Ryan Malloy | 2019-09-18 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-09-16 | 2019-09-17 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-09-28 | Install | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-28 07:00 | 2019-09-18 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 3.04 | 2 | Daniel Speegle | Completed | 2019-09-26 | 3.04 | 1 | Christina Horton | Completed | 2019-09-28 | 3.46 | 5 | Brian Le | Completed | 2019-09-24 | 0.92 | 3 | Ernesto Enriquez | Completed | 2019-10-02 | 5.92 | 2 | Ernesto Enriquez | Completed | 2019-09-28 | 0.08 | 1 | Christina Horton | Completed |  | 15.71 | 2 | Christina Horton | Current | 2019-09-24 | 0.08 | 2 | Brian Le | Completed | 2019-09-24 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 1 |  | Completed | 2019-09-26 | 3.04 | 1 | Andrew Clemons | Completed | 2019-10-09 | 7.63 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-10 |  | 0 | 2 |  | Inactive |  | 11.33 | 1 | Christina Horton | Inactive | 2019-09-23 | 0 | 2 | Darlynn Lacap | Completed | 0 | [11 empty] | 2019-09-26 |  | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28773 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28773 | https://completesolar.sugarondemand.com/#Opportunities/ee8320aa-da39-11e9-b6c1-022c40d974e6 | Trey Greenhill |  | 2019-09-13 | Infinity Energy Inc | ee8320aa-da39-11e9-b6c1-022c40d974e6 |  | 23 | -25 | -2 | 5 | 5 | 5 | -17
27164 | PIP_APPROVED | PIP_APPROVED | 35286 Sunnyside Drive | Yucaipa | CA | 92399 | Emily Lanyon | 2019-07-19 12:54 | 9092534085 | javsakama@hotmail.com | Javin Sakama |  |  | 9346 | 0.152 | Michael Marlaire | 2019-07-19 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-16 | 2019-07-19 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-26 07:00 | 2019-07-22 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 1.04 | 2 | Jethro Andal | Completed | 2019-07-22 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-30 | 3.04 | 5 | Brian Le | Completed | 2019-07-24 | 0 | 3 | Andrew Moralez | Completed | 2019-09-17 | 37.96 | 3 | Darlynn Lacap | Completed | 2019-09-27 | 9.92 | 1 | Ara Sotto | Completed | 2019-10-01 | 1.92 | 2 | Ara Sotto | Completed | 2019-09-19 | 39.92 | 2 | Brian Le | Completed | 2019-07-24 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 0.92 | 1 |  | Completed | 2019-07-29 | 4.08 | 1 | Noe Gomez | Completed | 2019-09-27 | 5.96 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 1 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 5.88 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 3.79 | 1 | Andrew Clemons | Completed |  |  | 2019-09-30 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 11.38 | [11 empty] | 2019-07-29 | 2019-10-01 | YUCAIPA | Yucaipa | https://heliotrack.completesolar.com/job.php?action=review&jobID=27164 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27164 | https://completesolar.sugarondemand.com/#Opportunities/e0b57cf8-aa5e-11e9-be15-022c40d974e6 | Summit Marketing Inc | Tiburon Mike Weber | 2019-07-16 | Green Road Solar Crew | e0b57cf8-aa5e-11e9-be15-022c40d974e6 | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
27372 | PIP_APPROVED | PIP_APPROVED | 1701 Elizabeth Avenue | Modesto | CA | 95355 | Ismael Hernandez Acencio | 2019-08-08 16:28 | 4086609976 | hernandezblanca03231994@gmail.com |  |  |  | 9734.65 |  | Ricardo Virgen | 2019-08-08 | 6.1 | Christina Horton |  | Marcia Garay | 2019-07-24 | 2019-08-03 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-09-27 | PTO Received | Sunlight Financial Loan | [6 empty] | 2019-09-26 07:00 | 2019-08-09 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 1.71 | 2 | Jethro Andal | Completed | 2019-09-19 | 22.96 | 1 | Christina Horton | Completed | 2019-09-26 | 0.96 | 5 | Brian Le | Completed | 2019-08-16 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-23 | 4.67 | 0 | Andrew Moralez | Completed | 2019-09-27 | 1.38 | 2 | Christina Horton | Completed | 2019-10-09 | 8.08 | 2 | Christina Horton | Completed | 2019-09-20 | 22.04 | 2 | Brian Le | Completed | 2019-08-20 | 1.71 | 2 | Marcia Garay | Completed | 2019-08-14 | 0.08 | 1 |  | Completed | 2019-08-14 | 0.08 | 1 | Andrew Clemons | Completed | 2019-10-03 | 5.33 | 1 | Marcia Garay | Completed | 2019-10-02 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-11 | 5.83 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 4 | 2 | Ashley Rockwood | Completed |  | 2.33 | 2 | Marcia Garay | Current |  | 2.33 | 1 | Andrew Clemons | Current | 2019-10-02 13:05 |  | 2019-10-03 | 3.92 | 2 | Christina Horton | Completed | 2019-09-27 | 1.38 | 1 | Christina Horton | Completed | 2019-09-23 | 7.75 | 2 | Marcia Garay | Completed | 26.34 | [11 empty] | 2019-08-16 | 2019-09-30 | MODESTO | Modesto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27372 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27372 | https://completesolar.sugarondemand.com/#Opportunities/7ad67fb8-ae78-11e9-9fbf-069e4f790264 | Total HomeSolar |  | 2019-07-23 | Sepac EnergySystems | 7ad67fb8-ae78-11e9-9fbf-069e4f790264 | 6 | 12 | -5 | -2 | 5 | 5 | 5 | 3
27471 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 4312 East Avenue Q-14 | Palmdale | CA | 93552 | Abraham Cayeros | 2019-09-23 13:29 | 6618601850 | acayeros@yahoo.com | Veronica | 6618601078 |  | 6582 | 0.12 | Bill Angevine | 2019-08-05 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-26 | 2019-07-29 12:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-09-27 | 2019-09-24 | 0.87 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 3 | 2 | Daniel Speegle | Completed | 2019-10-04 | 24.75 | 1 | Ara Sotto | Completed |  | 23.13 | 5 | Brian Le | Current | 2019-09-23 | 4.12 | 3 | Andrew Moralez | Completed | 2019-09-23 | 6.96 | 0 | Ernesto Enriquez | Completed | 2019-09-27 | 4 | 1 | Ara Sotto | Completed |  | 16 | 2 | Ara Sotto | Current | 2019-09-24 | 15.83 | 2 | Brian Le | Completed | 2019-09-24 | 1.21 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 4.96 | 1 |  | Completed | 2019-09-30 | 22.25 | 1 | Andrew Clemons | Completed | 2019-10-04 | 6.8 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-17 | 9.21 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 0.96 | 2 | Ashley Rockwood | Completed |  | 1.17 | 2 | Darlynn Lacap | Current | 2019-10-21 | 0.79 | 1 | Noe Gomez | Completed |  | 2019-09-26 | 2019-10-04 | 4.67 | 2 | Ara Sotto | Completed | [10 empty] | 7.33 | [11 empty] | 2019-09-23 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27471 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27471 | https://completesolar.sugarondemand.com/#Opportunities/7e406f5e-b7c6-11e9-ad09-069e4f790264 | Kevin Adams | Emily Bowden | 2019-07-26 | JK Solar | 7e406f5e-b7c6-11e9-ad09-069e4f790264 | 7 | 24 | -5 | -2 | 5 | 5 | 5 | 3
27940 | PIP_APPROVED | PIP_APPROVED | 1741 Dale Street | San Diego | CA | 92102 | Tara Gasparian | 2019-08-22 06:37 | 6198087872 | taragasparian@cox.net |  |  |  | 4335 | 0.17 | Chad Malloy | 2019-08-22 | 2.745 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-14 | 2019-08-17 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-27 07:00 | 2019-08-22 | 0.25 | 2 | Marcia Garay | Completed | 2019-08-26 | 2 | 2 | Daniel Speegle | Completed | 2019-09-20 | 14.8 | 1 | Christina Horton | Completed | 2019-09-27 | 15.88 | 5 | Brian Le | Completed | 2019-09-06 | 4.04 | 3 | Ernesto Enriquez | Completed | 2019-09-19 | 5.87 | 15 | Ernesto Enriquez | Completed | 2019-09-27 | 0.38 | 1 | Christina Horton | Completed | 2019-10-01 | 2 | 2 | Christina Horton | Completed | 2019-08-28 | 0.08 | 2 | Brian Le | Completed | 2019-08-30 | 2.84 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 4 | 1 |  | Completed | 2019-08-30 | 3.92 | 1 | Andrew Clemons | Completed | 2019-09-27 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-08 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 7.88 | 2 | Darlynn Lacap | Completed | 2019-10-11 | 1.88 | 1 | Jill Allen | Completed | 2019-09-30 13:26 |  | 2019-09-30 | 1 | 2 | Christina Horton | Completed | [10 empty] | 8.99 | [11 empty] | 2019-10-02 | 2019-10-01 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27940 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27940 | https://completesolar.sugarondemand.com/#Opportunities/e4112080-c4e1-11e9-a6bf-02ae981fbade | Blake Sanders | Lisa Mcdermott | 2019-08-14 | Infinity Energy Inc | e4112080-c4e1-11e9-a6bf-02ae981fbade | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28143 | PIP_APPROVED | PIP_APPROVED | 109 Davis Street | Lake Elsinore | CA | 92530 | Manuel Asuncion | 2019-08-30 15:49 | 5622533020 | manuelasuncion6@aol.com |  |  |  | 7373 | 0 | Chris Peaslee | 2019-08-24 | 4.27 | Ara Sotto | Solar Power Marketing | Darlynn Lacap | 2019-08-23 | 2019-08-24 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-27 | Final Permit | CalFirst SunRun Prepaid | 0 | 0 |  | 0 | 0 | 1 | 2019-09-27 07:00 | 2019-08-30 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 0.96 | 2 | Daniel Speegle | Completed | 2019-09-18 | 9.84 | 1 | Ara Sotto | Completed |  | 22.21 | 5 | Brian Le | Current | 2019-09-06 | 2.13 | 3 | Andrew Moralez | Completed | 2019-09-10 | 2 | 1 | Andrew Moralez | Completed | 2019-09-27 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-01 | 1.63 | 2 | Ara Sotto | Completed | 2019-09-19 | 4.17 | 2 | Brian Le | Completed | 2019-09-11 | 5.75 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.96 | 1 |  | Completed | 2019-09-23 | 13.13 | 1 | Andrew Clemons | Completed | 2019-09-27 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.25 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-19 | 2019-09-27 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 26.33 | [11 empty] | 2019-09-09 | 2019-09-27 | LAKE ELSINORE | Lake Elsinore | https://heliotrack.completesolar.com/job.php?action=review&jobID=28143 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28143 | https://completesolar.sugarondemand.com/#Opportunities/d3fe472c-c6da-11e9-bc6b-022c40d974e6 | Solar Power Marketing |  | 2019-08-23 | Power Town Solar Electric | d3fe472c-c6da-11e9-bc6b-022c40d974e6 | 0 | 4 | 10 | 0 | 5 | 5 | 5 | 20
28156 | PIP_APPROVED | PIP_APPROVED | 18107 Montgomery Avenue | Fontana | CA | 92336 | Maynor Lopez | 2019-08-28 15:44 | 9096441484 | mplopezc@msn.com | Bertha Lopez | 9096440751 |  | 5841 | 0.168 | Michael Marlaire | 2019-08-28 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-24 | 2019-08-26 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-27 07:00 | 2019-08-29 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 2.96 | 2 | Daniel Speegle | Completed | 2019-09-05 | 0.92 | 1 | Ara Sotto | Completed | 2019-09-30 | 3.04 | 5 | Brian Le | Completed | 2019-09-10 | 3.08 | 3 | Andrew Moralez | Completed | 2019-09-27 | 12.83 | 12 | Andrew Moralez | Completed | 2019-09-27 | 0.5 | 1 | Ara Sotto | Completed | 2019-10-01 | 2.17 | 2 | Ara Sotto | Completed | 2019-09-19 | 10.88 | 2 | Brian Le | Completed | 2019-09-04 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 1 | 1 |  | Completed | 2019-09-11 | 5.17 | 1 | Noe Gomez | Completed | 2019-09-27 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 3.96 | 1 | Andrew Clemons | Completed |  | 2019-10-01 | 2019-09-30 | 0.83 | 2 | Ara Sotto | Completed | [10 empty] | 5 | [11 empty] | 2019-09-26 | 2019-10-01 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=28156 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28156 | https://completesolar.sugarondemand.com/#Opportunities/5b993388-c9e5-11e9-81b5-0630baf9dcb8 | Oscar Hernandez |  | 2019-08-23 | Green Road Solar Crew | 5b993388-c9e5-11e9-81b5-0630baf9dcb8 | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
28181 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 28 Date Avenue | Chula Vista | CA | 91910 | Shaun Eisenthal | 2019-09-03 06:46 | 6192272540 | luv2stunt7@yahoo.com | Vanessa Eisenthal | 6196064034 |  | 4884 | 0.18 | Ryan Malloy | 2019-09-03 | 3.05 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-29 | 2019-08-31 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-27 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-27 07:00 | 2019-09-03 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 2 | 2 | Daniel Speegle | Completed | 2019-09-19 | 8.29 | 1 | Christina Horton | Completed | 2019-09-27 | 12.92 | 5 | Brian Le | Completed | 2019-09-06 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-18 | 5.88 | 7 | Andrew Moralez | Completed | 2019-09-27 | 0.38 | 1 | Christina Horton | Completed |  | 16.17 | 2 | Christina Horton | Current | 2019-09-10 | 0.08 | 2 | Brian Le | Completed | 2019-09-10 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-16 | 5.21 | 1 | Jill Allen | Completed |  | 16.54 | 1 | Marcia Garay | Current | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 13:13 |  |  | 16.17 | 2 | Christina Horton | Current | [10 empty] | 6.13 | [11 empty] | 2019-09-19 |  | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=28181 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28181 | https://completesolar.sugarondemand.com/#Opportunities/16e5f0ee-ce51-11e9-a5d8-022c40d974e6 | Thomas Noble | Shavonte Davis | 2019-08-26 | Infinity Energy Inc | 16e5f0ee-ce51-11e9-a5d8-022c40d974e6 | 24 | 24 | -25 | -2 | 5 | 5 | 5 | -17
28192 | PIP_APPROVED | PIP_APPROVED | 25569 Fruit Tree Street | Moreno Valley | CA | 92553 | Frances Bayot | 2019-08-27 18:01 | 9519418866 | bingfrance2@gmail.com | Liza Tam | 9516409740 |  | 553633 |  | Shaun Labelle | 2019-08-27 | 3.66 | Ara Sotto | Solar Power Marketing | Darlynn Lacap | 2019-08-26 | 2019-08-27 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-27 | PTO Received | Sunlight Financial Loan | [6 empty] | 2019-09-27 07:00 | 2019-08-30 | 2.58 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 3.17 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed |  | 15.17 | 5 | Brian Le | Current | 2019-09-12 | 1 | 3 | Ernesto Enriquez | Completed | 2019-09-23 | 6.92 | 25 | Andrew Moralez | Completed | 2019-09-27 | 0.04 | 1 | Ara Sotto | Completed | 2019-10-09 | 7.92 | 2 | Ara Sotto | Completed | 2019-09-30 | 16.79 | 2 | Brian Le | Completed | 2019-09-05 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 3.88 | 1 |  | Completed | 2019-09-06 | 1.08 | 1 | Noe Gomez | Completed | 2019-09-30 | 0.92 | 1 | Darlynn Lacap | Completed | 2019-10-02 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-04 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 7.83 | 2 | Darlynn Lacap | Completed | 2019-10-10 | 2.96 | 1 | Andrew Clemons | Completed |  | 2019-10-17 | 2019-09-30 | 0.79 | 2 | Ara Sotto | Completed | [10 empty] | 0.96 | [11 empty] | 2019-10-17 | 2019-09-30 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28192 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28192 | https://completesolar.sugarondemand.com/#Opportunities/475b86e8-c92f-11e9-8114-069e4f790264 | Solar Power Marketing |  | 2019-08-26 | Green Road Solar Crew | 475b86e8-c92f-11e9-8114-069e4f790264 | 3 | 12 | 0 | -2 | 5 | 5 | 5 | 8
28267 | PIP_APPROVED | PIP_APPROVED | 41340 Merriwood Drive | Hemet | CA | 92544 | Ronald W Bursma | 2019-09-09 09:23 | 9512164292 | rbursco@earthlink.net | Beverly Bursma | (951) 929-2704 |  | 5108 | 0.14 | Chad Malloy | 2019-09-09 | 3.05 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-28 | 2019-08-30 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-27 07:00 | 2019-09-09 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 1.88 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-30 | 6.04 | 5 | Brian Le | Completed | 2019-09-12 | 1 | 3 | Ernesto Enriquez | Completed | 2019-09-20 | 5.79 | 0 | Andrew Moralez | Completed | 2019-09-27 | 0.54 | 1 | Ara Sotto | Completed | 2019-10-14 | 10.88 | 2 | Ara Sotto | Completed | 2019-09-20 | 5.96 | 2 | Brian Le | Completed | 2019-09-12 | 1.13 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 0.13 | 1 |  | Completed | 2019-09-16 | 3.13 | 1 | Noe Gomez | Completed | 2019-09-27 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-07 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 0.92 | 2 | Ashley Rockwood | Completed |  | 9.21 | 2 | Darlynn Lacap | Current |  | 9.21 | 1 | Jill Allen | Current |  | 2019-10-01 | 2019-09-30 | 0.92 | 2 | Ara Sotto | Completed | [10 empty] | 1.04 | [11 empty] | 2019-09-12 | 2019-10-11 | RIVERSIDE COUNTY | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=28267 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28267 | https://completesolar.sugarondemand.com/#Opportunities/20f5ce5c-d31e-11e9-a7d0-02ae981fbade | PJB Division |  | 2019-08-28 | Green Road Solar Crew | 20f5ce5c-d31e-11e9-a7d0-02ae981fbade | 3 | 17 | 0 | -2 | 5 | 5 | 5 | 8
28660 | PIP_APPROVED | PIP_APPROVED | 24164 Finley Drive | Moreno Valley | CA | 92553 | Donald Lee | 2019-09-13 12:35 | 9092403906 | dlee241645@gmail.com | Candy Lee | 9515326411 |  | 9125 | 0.166 | Michael Marlaire | 2019-09-13 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-12 | 2019-09-13 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-27 07:00 | 2019-09-16 | 1.04 | 2 | Marcia Garay | Completed | 2019-09-16 | 0 | 2 | Daniel Speegle | Completed | 2019-09-20 | 3.88 | 1 | Ara Sotto | Completed |  | 21.13 | 5 | Brian Le | Current | 2019-09-20 | 1 | 3 | Andrew Moralez | Completed | 2019-09-20 | 0 | 25 | Andrew Moralez | Completed | 2019-09-27 | 0.5 | 2 | Ara Sotto | Completed | 2019-09-30 | 0.92 | 2 | Ara Sotto | Completed | 2019-09-20 | 3.13 | 2 | Brian Le | Completed | 2019-09-17 | 0.79 | 2 | Marcia Garay | Completed | 2019-09-19 | 2.79 | 1 |  | Completed | 2019-09-20 | 4.04 | 1 | Andrew Clemons | Completed | 2019-10-04 | 5.25 | 1 | Marcia Garay | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-08 | 2.13 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 3.96 | 2 | Marcia Garay | Completed | 2019-10-10 | 1.13 | 1 | Andrew Clemons | Completed |  | 2019-11-05 | 2019-10-04 | 4.67 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-10-25 | 2019-09-30 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28660 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28660 | https://completesolar.sugarondemand.com/#Opportunities/a1025c36-d65d-11e9-abc2-022c40d974e6 | Oscar Hernandez |  | 2019-09-11 | HDM Electric Inc | a1025c36-d65d-11e9-abc2-022c40d974e6 | 7 | 3 | -5 | 2 | 5 | 5 | 5 | 7
27847 | PIP_APPROVED | PIP_APPROVED | 1381 Claremont Drive | San Bruno | CA | 94066 | David Ocampo | 2019-08-20 13:28 | 6502552317 | davelaw5@aol.com |  |  |  | 8535.44 |  |  | 2019-08-20 | 5.31 | Christina Horton | Solar Gain | Darlynn Lacap | 2019-08-13 | 2019-08-16 12:00 | Plus SW 295 MONO BLACK | 295 | 18 | SolarWorld | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-09-26 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-09-26 07:00 | 2019-08-21 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 1.13 | 2 | Jethro Andal | Completed | 2019-09-03 | 6.75 | 1 | Christina Horton | Completed | 2019-09-26 | 3.96 | 5 | Brian Le | Completed | 2019-08-30 | 5.79 | 3 | Ernesto Enriquez | Completed | 2019-09-09 | 5.17 | 10 | Ernesto Enriquez | Completed | 2019-09-26 | 0.38 | 2 | Christina Horton | Completed | 2019-10-15 | 13.08 | 2 | Christina Horton | Completed | 2019-09-20 | 19.08 | 2 | Brian Le | Completed | 2019-08-23 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 0 | 1 |  | Completed | 2019-08-29 | 4.75 | 1 | Noe Gomez | Completed | 2019-09-27 | 1.33 | 1 | Darlynn Lacap | Completed |  | 4.04 | 2 | Noe Gomez | Current | [15 empty] | 2019-10-04 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 3.21 | 2 | Darlynn Lacap | Completed |  | 5.33 | 1 | Andrew Clemons | Current | 2019-10-02 11:58 |  | 2019-10-02 | 4 | 2 | Christina Horton | Completed | [10 empty] | 0.83 | [11 empty] | 2019-09-16 | 2019-10-02 | SAN BRUNO | San Bruno | https://heliotrack.completesolar.com/job.php?action=review&jobID=27847 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27847 | https://completesolar.sugarondemand.com/#Opportunities/f0968cdc-c388-11e9-a616-02ae981fbade | Solar Gain | Tom Cotter | 2019-08-12 | OSullivan Green Solar | f0968cdc-c388-11e9-a616-02ae981fbade | 6 | 19 | -5 | -2 | 5 | 5 | 5 | 3
27860 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 757 Arthur Avenue | Oceanside | CA | 92057 | Leticia Fernandez | 2019-08-27 08:30 | 7608053229 | robertocarlos1705@yahoo.com | Felipe Garcia | 7606851684 |  | 4802 | 0.17 | Chad Malloy | 2019-08-27 | 2.745 | Ara Sotto | Revo Home Solutions | Marcia Garay | 2019-08-23 | 2019-08-26 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-09-26 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-26 07:00 | 2019-08-28 | 1.08 | 2 | Marcia Garay | Completed | 2019-08-28 | 0.13 | 2 | Daniel Speegle | Completed | 2019-09-20 | 11 | 1 | Christina Horton | Completed | 2019-09-26 | 4.96 | 5 | Brian Le | Completed | 2019-08-29 | 0.83 | 3 | Andrew Moralez | Completed | 2019-08-30 | 1.08 | 10 | Andrew Moralez | Completed | 2019-09-26 | 0.42 | 1 | Ara Sotto | Completed |  | 17.13 | 2 | Ara Sotto | Current | 2019-09-19 | 8.29 | 2 | Brian Le | Completed | 2019-08-30 | 1.79 | 2 | Marcia Garay | Completed | 2019-08-28 | 0 | 1 |  | Completed | 2019-09-20 | 11.16 | 1 | Andrew Clemons | Completed | 2019-09-27 | 1.38 | 1 | Marcia Garay | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-03 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 2.71 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 7.25 | 2 | Marcia Garay | Completed | 2019-10-09 | 1 | 1 | Noe Gomez | Completed | 2019-09-27 14:22 |  | 2019-09-27 | 0.92 | 2 | Ara Sotto | Completed | [10 empty] | 12.91 | [11 empty] | 2019-09-13 |  | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27860 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27860 | https://completesolar.sugarondemand.com/#Opportunities/967a0d94-c8df-11e9-ac1a-02ae981fbade | Brett Martinez |  | 2019-08-12 | Zachary Noah Gamez | 967a0d94-c8df-11e9-ac1a-02ae981fbade | 1 | 25 | 10 | -2 | 5 | 5 | 5 | 18
28559 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1378 Lindenwood Drive | El Cajon | CA | 92021 | Robert Corriere | 2019-09-12 13:06 | 6193963245 | lesliecorriere@yahoo.com | Leslie Corriere |  | robert.corriere@yahoo.com | 8281 | 0.171 | Chad Malloy | 2019-09-12 | 5.49 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-09-10 | 2019-09-12 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-26 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-26 07:00 | 2019-09-16 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0 | 2 | Daniel Speegle | Completed | 2019-09-18 | 2.04 | 1 | Christina Horton | Completed | 2019-09-26 | 4.83 | 5 | Brian Le | Completed | 2019-09-18 | 0 | 3 | Ernesto Enriquez | Completed | 2019-09-18 | 0.17 | 1 | Ernesto Enriquez | Completed | 2019-09-26 | 0.29 | 2 | Christina Horton | Completed |  | 17.25 | 2 | Christina Horton | Current | 2019-09-19 | 0.96 | 2 | Brian Le | Completed | 2019-09-18 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-09-18 | 1.75 | 1 |  | Completed | 2019-09-20 | 3.92 | 1 | Andrew Clemons | Completed | 2019-09-27 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-11-11 |  | 2.13 | 2 | Christina Horton | Inactive | [10 empty] | 15.08 | [11 empty] | 2019-09-19 |  | SAN DIEGO COUNTY | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=28559 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28559 | https://completesolar.sugarondemand.com/#Opportunities/bc87b7fa-d598-11e9-af7e-069e4f790264 | Blake Sanders | Jonathan Weaver | 2019-09-07 | Infinity Energy Inc | bc87b7fa-d598-11e9-af7e-069e4f790264 | 25 | 25 | -25 | -2 | 5 | 5 | 5 | -17
27625 | PIP_APPROVED | PIP_APPROVED | 1501 Meadow Road | El Cajon | CA | 92021 | Jose Diaz | 2019-09-06 17:56 | 6195224579 | magicmaidsplus@gmail.com |  |  |  | 7900 | 0.21 | Ryan Malloy | 2019-08-07 | 5.49 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-08-02 | 2019-08-05 16:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-09-25 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-09-20 07:00 | 2019-09-09 | 5.75 | 2 | Marcia Garay | Completed | 2019-09-10 | 1.29 | 2 | Daniel Speegle | Completed | 2019-09-18 | 6.04 | 1 | Ara Sotto | Completed | 2019-09-25 | 3.96 | 5 | Brian Le | Completed | 2019-09-10 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 0 | 0 | Andrew Moralez | Completed | 2019-09-25 | 5.71 | 2 | Ara Sotto | Completed | 2019-09-27 | 1.96 | 2 | Ara Sotto | Completed | 2019-09-13 | 1.96 | 2 | Brian Le | Completed | 2019-09-11 | 0.92 | 2 | Marcia Garay | Completed | 2019-09-10 | 0.08 | 1 |  | Completed | 2019-09-12 | 1.96 | 1 | Jill Allen | Completed |  | 24 | 1 | Marcia Garay | Current | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-03 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-10-08 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-10-17 | 0.08 | 2 | Zedel Morgan | Completed | 2019-10-09 | 0.08 | 1 | Noe Gomez | Completed | 2019-09-17 16:52 | 2019-09-24 | 2019-09-26 | 0.08 | 2 | Ara Sotto | Completed |  | 19.25 | 1 | Ara Sotto | Current | 2019-09-25 | 0.79 | 2 | Marcia Garay | Completed | 13.33 | [11 empty] | 2019-09-10 | 2019-09-26 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=27625 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27625 | https://completesolar.sugarondemand.com/#Opportunities/e5b2fbd4-b924-11e9-8259-069e4f790264 | Jordan Litrownik | Jimmy Evans | 2019-08-02 | Blalock Electric&Solar | e5b2fbd4-b924-11e9-8259-069e4f790264 | 1 | 2 | 10 | 4 | 5 | 5 | 5 | 24
27924 | PIP_APPROVED | PIP_APPROVED | 42491 66th Street West | Lancaster | CA | 93536 | Gary Rosales | 2019-09-09 10:51 | 6618164900 | carmenrose5@yahoo.com |  |  | garyrose5@yahoo.com | 11686 | 0.185 | Bill Angevine | 2019-08-22 | 7.93 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-14 | 2019-08-15 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-25 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-25 07:00 | 2019-09-09 | 3.92 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-20 | 6.17 | 1 | Ara Sotto | Completed | 2019-09-25 | 3.04 | 5 | Brian Le | Completed | 2019-09-11 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-18 | 5 | 1 | Ernesto Enriquez | Completed | 2019-09-25 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-08 | 9.29 | 2 | Ara Sotto | Completed | 2019-09-20 | 0.17 | 2 | Brian Le | Completed | 2019-09-19 | 3.29 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 0.25 | 1 |  | Completed | 2019-10-18 | 26.25 | 1 | Noe Gomez | Completed | 2019-09-27 | 2.33 | 1 | Darlynn Lacap | Completed | 2019-10-18 | 7.54 | 2 | Jill Allen | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-27 15:07 |  |  | 18.08 | 2 | Ara Sotto | Current | [10 empty] | 10.83 | [11 empty] | 2019-09-12 | 2019-10-08 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27924 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27924 | https://completesolar.sugarondemand.com/#Opportunities/ef4e1630-c507-11e9-98f1-02ae981fbade | Solar Raze | Emily Bowden | 2019-08-14 | Green Road Solar Crew | ef4e1630-c507-11e9-98f1-02ae981fbade | 26 | 13 | -25 | -2 | 5 | 5 | 5 | -17
27992 | PIP_APPROVED | PIP_APPROVED | 931 Begonia Court | Carlsbad | CA | 92011 | Patricia Gibbons | 2019-09-10 12:03 | 7605199501 | undrconstruction@roadrunner.com | Danny Watts | 7604389501 |  | 10277 | 0.19 | Chad Malloy | 2019-08-19 | 6.405 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-16 | 2019-08-19 09:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-25 07:00 | 2019-09-10 | 4.54 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 1.91 | 2 | Daniel Speegle | Completed | 2019-09-24 | 8.08 | 1 | Christina Horton | Completed | 2019-09-25 | 5.67 | 5 | Brian Le | Completed | 2019-09-16 | 2.08 | 3 | Andrew Moralez | Completed | 2019-09-16 | 0.16 | 15 | Andrew Moralez | Completed | 2019-09-25 | 0.38 | 2 | Christina Horton | Completed | 2019-10-04 | 6.96 | 2 | Christina Horton | Completed | 2019-09-16 | 0.24 | 2 | Brian Le | Completed | 2019-09-17 | 3.29 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 1 |  | Completed | 2019-09-19 | 4.92 | 1 | Andrew Clemons | Completed | 2019-09-27 | 2.38 | 1 | Darlynn Lacap | Completed | 2019-09-27 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-17 | 9 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 1.04 | 2 | Ashley Rockwood | Completed |  | 1.08 | 2 | Darlynn Lacap | Current |  | 1.08 | 1 | Noe Gomez | Current | 2019-10-04 12:52 |  | 2019-10-04 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 22.8 | [11 empty] | 2019-10-05 | 2019-10-04 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=27992 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27992 | https://completesolar.sugarondemand.com/#Opportunities/0d91439e-c2b3-11e9-aa5f-069e4f790264 | Allen Rivers |  | 2019-08-16 | Infinity Energy Inc | 0d91439e-c2b3-11e9-aa5f-069e4f790264 | 9 | 9 | -5 | -2 | 5 | 5 | 5 | 3
28031 | PIP_APPROVED | PIP_APPROVED | 37558 Penara Street | Palmdale | CA | 93552 | Jorge Zecena | 2019-08-19 18:17 | 8183595481 | ramos77jr@gmail.com |  |  |  | 7166 | 0.158 | Bill Angevine | 2019-08-19 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-17 | 2019-08-19 09:00 | LR6-60PE-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-24 07:00 | 2019-08-20 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 1.83 | 2 | Daniel Speegle | Completed | 2019-09-06 | 10.08 | 1 | Ara Sotto | Completed | 2019-09-25 | 7.71 | 5 | Brian Le | Completed | 2019-09-04 | 7 | 3 | Andrew Moralez | Completed | 2019-09-18 | 10.13 | 0 | Andrew Moralez | Completed | 2019-09-25 | 1.46 | 1 | Ara Sotto | Completed | 2019-10-02 | 5.08 | 2 | Ara Sotto | Completed | 2019-09-13 | 15.04 | 2 | Brian Le | Completed | 2019-08-22 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 1.04 | 1 |  | Completed | 2019-08-27 | 2.96 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 3.62 | 1 | Darlynn Lacap | Completed | 2019-09-27 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-07 | 7.21 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 5.83 | 2 | Ashley Rockwood | Completed |  | 4.25 | 2 | Darlynn Lacap | Current | 2019-10-16 | 1.17 | 1 | Noe Gomez | Completed | 2019-09-25 15:04 |  | 2019-09-26 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 6.09 | [11 empty] | 2019-09-04 | 2019-10-01 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28031 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28031 | https://completesolar.sugarondemand.com/#Opportunities/3d3270de-c2e8-11e9-a468-022c40d974e6 | SCES Division |  | 2019-08-17 | JK Solar | 3d3270de-c2e8-11e9-a468-022c40d974e6 | 1 | 7 | 10 | -2 | 5 | 5 | 5 | 18
28064 | SP APPROVED |  | 69150 San Susanna Avenue | Cathedral City | CA | 92234 | Juana Gonzalez | 2019-08-21 10:10 | 7604086003 | gonzalez5158@aol.com | Trinidad Gonzalez | 7607022292 |  | 11926 | 0.18 | Shaun Labelle | 2019-08-21 | 7.625 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-19 | 2019-08-20 12:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-24 07:00 | 2019-08-21 | 0 | 2 | Marcia Garay | Completed | 2019-08-22 | 1.21 | 2 | Daniel Speegle | Completed | 2019-09-05 | 8.67 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.17 | 5 | Brian Le | Completed | 2019-08-29 | 2.88 | 3 | Andrew Moralez | Completed | 2019-09-24 | 17.21 | 7 | Andrew Moralez | Completed | 2019-09-25 | 1.42 | 2 | Ara Sotto | Completed |  | 18.08 | 2 | Ara Sotto | Current | 2019-09-19 | 16.96 | 2 | Brian Le | Completed | 2019-08-26 | 1.79 | 2 | Marcia Garay | Completed | 2019-08-26 | 1.83 | 1 |  | Completed | 2019-08-28 | 3.88 | 1 | Andrew Clemons | Completed |  | 19.54 | 1 | Marcia Garay | Current | 2019-09-27 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-04 | 6.17 | 2 | Ashley Rockwood | Completed | 2019-10-10 | 3.79 | 2 | Ashley Rockwood | Completed |  | 7.29 | 2 | Marcia Garay | Current |  | 7.29 | 1 | Jeremiah Liend | Current | 2019-09-25 14:56 |  | 2019-09-26 | 0.79 | 2 | Ara Sotto | Completed | [10 empty] | 4.92 | [11 empty] | 2019-09-10 |  | CATHEDRAL CITY | Cathedral City | https://heliotrack.completesolar.com/job.php?action=review&jobID=28064 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28064 | https://completesolar.sugarondemand.com/#Opportunities/7e177ffa-c436-11e9-8113-0630baf9dcb8 | Oscar Hernandez |  | 2019-08-19 | Zachary Noah Gamez | 7e177ffa-c436-11e9-8113-0630baf9dcb8 | 1 | 26 | 10 | -2 | 5 | 5 | 5 | 18
28158 | PIP_APPROVED | PIP_APPROVED | 37902 26th Street East | Palmdale | CA | 93550 | Fidel Hernandez | 2019-08-27 19:55 | 8189430807 | michoacanitalinda90@gmail.com | Maribel Jacinto | 8189156430 |  | 8211 | 0.125 | Bill Angevine | 2019-08-27 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-24 | 2019-08-27 09:00 | LR6-60PE-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-25 07:00 | 2019-08-28 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 3 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.88 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.17 | 5 | Brian Le | Completed | 2019-09-10 | 2.96 | 3 | Ernesto Enriquez | Completed | 2019-09-20 | 8.17 | 5 | Ernesto Enriquez | Completed | 2019-09-25 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-08 | 8.67 | 2 | Ara Sotto | Completed | 2019-09-19 | 5.75 | 2 | Brian Le | Completed | 2019-09-11 | 6.21 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 2 | 1 |  | Completed | 2019-09-06 | 3.13 | 1 | Andrew Clemons | Completed | 2019-09-27 | 2.33 | 1 | Darlynn Lacap | Completed | 2019-09-27 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-08 | 2.25 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 5.83 | 2 | Darlynn Lacap | Completed | 2019-10-10 | 1 | 1 | Jeremiah Liend | Completed | 2019-09-30 15:03 |  | 2019-10-04 | 6.71 | 2 | Ara Sotto | Completed | [10 empty] | 4 | [11 empty] | 2019-09-17 | 2019-10-08 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28158 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28158 | https://completesolar.sugarondemand.com/#Opportunities/37fc9f74-c93f-11e9-92a3-0630baf9dcb8 | SCES Division |  | 2019-08-24 | JK Solar | 37fc9f74-c93f-11e9-92a3-0630baf9dcb8 | 9 | 13 | -5 | -2 | 5 | 5 | 5 | 3
28173 | PIP_APPROVED | PIP_APPROVED | 672 Irene Road | Oceanside | CA | 92057 | Kimberly Martinez | 2019-09-11 07:52 | 7603176203 | jammincustoms@yahoo.com | Benjamin Martinez | 7603177210 |  | 6759 | 0.19 | Chad Malloy | 2019-09-10 | 4.27 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-24 | 2019-09-07 15:00 | LR6-60PE-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-25 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-25 07:00 | 2019-09-11 | 0.13 | 2 | Marcia Garay | Completed | 2019-09-12 | 1.17 | 2 | Daniel Speegle | Completed | 2019-09-19 | 4.75 | 1 | Ara Sotto | Completed | 2019-09-25 | 4.75 | 5 | Brian Le | Completed | 2019-09-12 | 0 | 3 | Andrew Moralez | Completed | 2019-09-13 | 0.96 | 10 | Andrew Moralez | Completed | 2019-09-25 | 0.38 | 1 | Christina Horton | Completed | 2019-10-16 | 14.71 | 2 | Christina Horton | Completed | 2019-09-16 | 0.08 | 2 | Brian Le | Completed | 2019-09-18 | 3.67 | 2 | Marcia Garay | Completed | 2019-09-12 | 0 | 1 |  | Completed | 2019-09-19 | 4.96 | 1 | Jill Allen | Completed | 2019-09-24 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-03 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 2.71 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 7.21 | 2 | Marcia Garay | Completed | 2019-10-09 | 1 | 1 | Jeremiah Liend | Completed |  | 2019-10-10 | 2019-09-26 | 0.96 | 2 | Christina Horton | Completed | [10 empty] | 0.33 | [11 empty] | 2019-09-26 | 2019-10-15 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28173 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28173 | https://completesolar.sugarondemand.com/#Opportunities/867794c2-d413-11e9-855b-0630baf9dcb8 | Brett Martinez | Omar Jackson | 2019-08-24 | Infinity Energy Inc | 867794c2-d413-11e9-855b-0630baf9dcb8 | 1 | 21 | 10 | -2 | 5 | 5 | 5 | 18
28369 | PIP_APPROVED | PIP_APPROVED | 45326 Bison Circle | Lancaster | CA | 93535 | Cruz Sanchez | 2019-09-07 16:38 | 6619920227 | crnlchez1234@gmail.com |  |  |  | 8681 | 0.14 | Bill Angevine | 2019-09-07 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-31 | 2019-09-07 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-13 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-25 07:00 | 2019-09-10 | 1.54 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-13 | 3.13 | 1 | Ara Sotto | Completed | 2019-09-13 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-10 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-18 | 6.04 | 1 | Ernesto Enriquez | Completed | 2019-09-25 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-09 | 13.17 | 2 | Ara Sotto | Completed | 2019-09-19 | 6.83 | 2 | Brian Le | Completed | 2019-09-10 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 1 |  | Completed | 2019-09-17 | 4.92 | 1 | Jill Allen | Completed | 2019-09-27 | 5.29 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-07 | 5.96 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 7.04 | 2 | Darlynn Lacap | Completed | 2019-10-11 | 2.96 | 1 | Jeremiah Liend | Completed | 2019-09-27 15:06 |  | 2019-09-27 | 4.84 | 2 | Ara Sotto | Completed | [10 empty] | 3.96 | [11 empty] | 2019-09-11 | 2019-10-09 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28369 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28369 | https://completesolar.sugarondemand.com/#Opportunities/8df5bdac-d1c8-11e9-b804-069e4f790264 | SCES Division | Henry Garcia | 2019-08-31 | JK Solar | 8df5bdac-d1c8-11e9-b804-069e4f790264 | 2 | 14 | 7 | -2 | 5 | 5 | 5 | 15
28430 | PIP_APPROVED | PIP_APPROVED | 3890 28th Street East | Highland | CA | 92346 | Rosario Ortiz | 2019-09-07 14:44 | 9097759059 | rose_j909@yahoo.com | Victor Lewis | 9094422975 |  | 10414 | 0.16 | Shaun Labelle | 2019-09-07 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-05 | 2019-09-07 15:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-09-25 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-25 07:00 | 2019-09-10 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.71 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.17 | 5 | Brian Le | Completed | 2019-09-17 | 3.21 | 3 | Andrew Moralez | Completed | 2019-09-17 | 0 | 1 | Andrew Moralez | Completed | 2019-09-25 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-02 | 4.67 | 2 | Ara Sotto | Completed | 2019-09-19 | 6.79 | 2 | Brian Le | Completed | 2019-09-10 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 1.71 | 1 |  | Completed | 2019-09-13 | 2.63 | 1 | Jill Allen | Completed | 2019-09-27 | 2.38 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-15 |  | 0 | 2 |  | Inactive |  | 18.54 | 1 | Ara Sotto | Current | 2019-09-11 | 0.58 | 2 | Darlynn Lacap | Completed | 3.92 | [11 empty] | 2019-09-18 | 2019-10-02 | SAN BERNARDINO | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=28430 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28430 | https://completesolar.sugarondemand.com/#Opportunities/a36ea24e-d1b8-11e9-9d25-022c40d974e6 | Oscar Hernandez |  | 2019-09-04 | HDM Electric Inc | a36ea24e-d1b8-11e9-9d25-022c40d974e6 |  | 7 | -25 | -2 | 5 | 5 | 5 | -17
28515 | PIP_APPROVED | PIP_APPROVED | 12621 Sunglow Lane | Victorville | CA | 92392 | Jose Suarez | 2019-09-09 14:32 | 9092020677 | joselsuarez01@yahoo.com | Andrea Lopez | 9095570775 |  | 7229 | 0.151 | Shaun Labelle | 2019-09-09 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-06 | 2019-09-09 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-25 | Installation Complete | SunRun Monthly |  | 0 |  |  |  |  | 2019-09-25 07:00 | 2019-09-10 | 0.96 | 2 | Marcia Garay | Completed | 2019-09-11 | 0.88 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.17 | 5 | Brian Le | Completed | 2019-09-11 | 0 | 3 | Andrew Moralez | Completed | 2019-09-18 | 4.96 | 10 | Andrew Moralez | Completed | 2019-09-25 | 0 | 1 | Ara Sotto | Completed | 2019-09-26 | 0.83 | 2 | Ara Sotto | Completed | 2019-09-19 | 5.83 | 2 | Brian Le | Completed | 2019-09-11 | 0.13 | 2 | Marcia Garay | Completed | 2019-09-11 | 0.13 | 1 |  | Completed | 2019-09-16 | 3.13 | 1 | Jill Allen | Completed |  | 18.08 | 1 | Marcia Garay | Current | 2019-09-27 | 0.79 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-26 15:14 |  |  | 18.08 | 2 | Ara Sotto | Current | [10 empty] | 3.96 | [11 empty] | 2019-09-25 | 2019-09-26 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28515 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28515 | https://completesolar.sugarondemand.com/#Opportunities/38da08b4-d349-11e9-949b-0630baf9dcb8 | CSA Division | Christopher Cellini | 2019-09-06 | HDM Electric Inc | 38da08b4-d349-11e9-949b-0630baf9dcb8 | 26 | 1 | -25 | 5 | 5 | 5 | 5 | -10
27705 | PIP_APPROVED | PIP_APPROVED | 43933 Maria Circle | Lancaster | CA | 93535 | Jacob Underwood | 2019-08-09 18:46 | 7607770535 | bundy078@gmail.com | Elizabeth Underwood | 5623430238 |  | 7401 | 0.132 | Shaun Labelle | 2019-08-09 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-09 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-24 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-24 07:00 | 2019-08-12 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 2.08 | 2 | Daniel Speegle | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-24 | 3.13 | 5 | Brian Le | Completed | 2019-08-15 | 0.25 | 3 | Andrew Moralez | Completed | 2019-09-17 | 21.83 | 1 | Andrew Moralez | Completed | 2019-09-24 | 0.71 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.67 | 2 | Ara Sotto | Completed | 2019-09-19 | 22.88 | 2 | Brian Le | Completed | 2019-08-16 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.63 | 1 |  | Completed | 2019-08-19 | 2.83 | 1 | Noe Gomez | Completed | 2019-09-27 | 3.62 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 1.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-07 | 4.96 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5 | 2 | Ashley Rockwood | Completed |  | 5.17 | 2 | Darlynn Lacap | Current | 2019-10-16 | 2.08 | 1 | Jeremiah Liend | Completed | 2019-09-26 14:58 |  | 2019-09-30 | 3.88 | 2 | Ara Sotto | Completed | [10 empty] | 8.8 | [11 empty] | 2019-08-16 | 2019-09-25 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27705 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27705 | https://completesolar.sugarondemand.com/#Opportunities/9ed6b46a-bb10-11e9-8af7-02ae981fbade | Henry Garcia |  | 2019-08-06 | HDM Electric Inc | 9ed6b46a-bb10-11e9-8af7-02ae981fbade | 6 | 1 | -5 | 5 | 5 | 5 | 5 | 10
27798 | PIP_APPROVED | PIP_APPROVED | 4951 Claire Drive | Oceanside | CA | 92057 | Linojun Ramos | 2019-08-14 16:52 | 8587622531 | mosranuj@yahoo.com | Jane Ramos | 8587622571 |  | 5587 | 0.193 | Michael Marlaire | 2019-08-14 | 3.355 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-10 | 2019-08-13 16:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-24 | PTO Received | SunRun Monthly | 0 | 1 |  |  |  | 1 | 2019-09-24 07:00 | 2019-08-16 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 1 | 2 | Daniel Speegle | Completed | 2019-09-09 | 3.25 | 1 | Christina Horton | Completed | 2019-09-24 | 9.75 | 5 | Brian Le | Completed | 2019-08-19 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-12 | 5.88 | 10 | Andrew Moralez | Completed | 2019-09-24 | 0.38 | 1 | Christina Horton | Completed | 2019-09-26 | 1.88 | 2 | Christina Horton | Completed | 2019-09-10 | 4.04 | 2 | Brian Le | Completed | 2019-08-20 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 1 |  | Completed | 2019-09-19 | 10.75 | 1 | Andrew Clemons | Completed | 2019-09-26 | 2.29 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 0.25 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-07 | 6.96 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 2 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 5.92 | 2 | Darlynn Lacap | Completed | 2019-10-10 | 1.08 | 1 | Andrew Clemons | Completed | 2019-09-26 12:14 |  | 2019-09-26 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 11.22 | [11 empty] | 2019-09-18 | 2019-09-26 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27798 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27798 | https://completesolar.sugarondemand.com/#Opportunities/6ef1878e-beee-11e9-b428-022c40d974e6 | Brett Martinez |  | 2019-08-09 | Infinity Energy Inc | 6ef1878e-beee-11e9-b428-022c40d974e6 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
27951 | PIP_APPROVED | PIP_APPROVED | 14026 Twin Peaks Road | Poway | CA | 92064 | Anne Cahua | 2019-09-04 14:42 | 3148140866 | anniecahua@gmail.com |  |  |  | 7468 | 0.188 | Ryan Malloy | 2019-08-20 | 4.27 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-08-14 | 2019-08-17 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-24 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-24 07:00 | 2019-09-04 | 1.12 | 2 | Marcia Garay | Completed | 2019-09-05 | 1.04 | 2 | Daniel Speegle | Completed | 2019-09-11 | 3.87 | 1 | Ara Sotto | Completed | 2019-09-24 | 2.04 | 5 | Brian Le | Completed | 2019-09-05 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-09 | 2 | 14 | Andrew Moralez | Completed | 2019-09-24 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-14 | 14.04 | 2 | Ara Sotto | Completed | 2019-09-13 | 3.17 | 2 | Brian Le | Completed | 2019-09-10 | 2.75 | 2 | Marcia Garay | Completed | 2019-09-05 | 0.08 | 1 |  | Completed | 2019-09-20 | 9.09 | 1 | Andrew Clemons | Completed |  | 19.54 | 1 | Marcia Garay | Current | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-04 | 5.29 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 0.08 | 2 | Jeremiah Liend | Completed |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-25 16:56 |  | 2019-09-26 | 1.79 | 2 | Ara Sotto | Completed | [10 empty] | 30.97 | [11 empty] | 2019-09-25 | 2019-10-14 | POWAY | Poway | https://heliotrack.completesolar.com/job.php?action=review&jobID=27951 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27951 | https://completesolar.sugarondemand.com/#Opportunities/61be2044-c363-11e9-816b-0630baf9dcb8 | Jordan Litrownik |  | 2019-08-14 | Blalock Electric&Solar | 61be2044-c363-11e9-816b-0630baf9dcb8 | 2 | 20 | 7 | -2 | 5 | 5 | 5 | 15
28206 | PIP_APPROVED | PIP_APPROVED | 495 West Grove Street | Rialto | CA | 92376 | Anna Carra | 2019-08-27 20:13 | 9513340173 | anacarra73@gmail.com | Jose Carra | 9512501506 |  | 7299 | 0.161 | Michael Marlaire | 2019-08-27 | 4.575 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-26 | 2019-08-27 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-24 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-24 07:00 | 2019-09-09 | 3.91 | 2 | Marcia Garay | Completed | 2019-09-05 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-18 | 6.67 | 1 | Ara Sotto | Completed | 2019-09-24 | 0.08 | 5 | Brian Le | Completed | 2019-09-07 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-17 | 5.96 | 7 | Ernesto Enriquez | Completed | 2019-09-24 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-25 | 0.75 | 2 | Ara Sotto | Completed | 2019-09-19 | 5.88 | 2 | Brian Le | Completed | 2019-09-11 | 1.92 | 2 | Marcia Garay | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-10 | 1.04 | 1 | Jill Allen | Completed | 2019-10-15 | 15.17 | 1 | Marcia Garay | Completed | 2019-09-26 | 1 | 2 | Jill Allen | Completed | [15 empty] | 2019-10-02 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 1 | 2 | Ashley Rockwood | Completed |  | 12.25 | 2 | Marcia Garay | Current | 2019-10-11 | 6.04 | 1 | Andrew Clemons | Completed | 2019-09-24 15:06 |  | 2019-09-26 | 1.75 | 2 | Ara Sotto | Completed | [10 empty] | 7.92 | [11 empty] | 2019-09-18 | 2019-09-25 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28206 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28206 | https://completesolar.sugarondemand.com/#Opportunities/bee01e42-c941-11e9-8174-02ae981fbade | 300 Stars Inc | Oscar Hernandez | 2019-08-26 | Power Town Solar Electric | bee01e42-c941-11e9-8174-02ae981fbade | 2 | 1 | 7 | 5 | 5 | 5 | 5 | 22
28550 | PIP_APPROVED | PIP_APPROVED | 826 West Grove Street | Rialto | CA | 92376 | Ivan Alejo | 2019-09-09 15:19 | 9095611984 | ivanalejo92@gmail.com | Stephanie Diaz | 9099975541 |  | 5336 | 0.161 | Alex Holdridge | 2019-09-09 | 3.05 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-07 | 2019-09-09 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-24 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-23 07:00 | 2019-09-11 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.08 | 1 | Ara Sotto | Completed |  | 18.25 | 5 | Brian Le | Current | 2019-09-11 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-17 | 4.04 | 7 | Andrew Moralez | Completed | 2019-09-24 | 1.42 | 1 | Ara Sotto | Completed | 2019-10-01 | 5 | 2 | Ara Sotto | Completed | 2019-09-19 | 5.88 | 2 | Brian Le | Completed | 2019-09-11 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 1 |  | Completed | 2019-09-17 | 3.92 | 1 | Jeremiah Liend | Completed | 2019-09-26 | 3.29 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 3.92 | 1 | Andrew Clemons | Completed | 2019-09-25 15:12 |  | 2019-09-26 | 1.79 | 2 | Ara Sotto | Completed | [10 empty] | 3.92 | [11 empty] | 2019-09-20 | 2019-09-30 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=28550 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28550 | https://completesolar.sugarondemand.com/#Opportunities/c6baa700-d34f-11e9-be0f-069e4f790264 | 300 Stars Inc | Oscar Hernandez | 2019-09-07 | Green Road Solar Crew | c6baa700-d34f-11e9-be0f-069e4f790264 | 2 | 7 | 7 | -2 | 5 | 5 | 5 | 15
27310 | PIP_APPROVED | PIP_APPROVED | 3627 Apollo Avenue | Palmdale | CA | 93550 | Jose Coria | 2019-08-22 15:09 | 6615760487 | josecoria1960@gmail.com | Hilda Arrevelo | 6615760487 |  | 11249 | 0.14 | Bill Angevine | 2019-08-10 | 6.71 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-23 | 2019-07-24 15:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-23 07:00 | 2019-08-28 | 8.42 | 2 | Marcia Garay | Completed | 2019-08-28 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-23 | 17.25 | 1 | Ara Sotto | Completed |  | 18.25 | 5 | Brian Le | Current | 2019-09-04 | 2.79 | 3 | Ernesto Enriquez | Completed | 2019-09-18 | 10.13 | 0 | Andrew Moralez | Completed | 2019-09-23 | 0.46 | 2 | Ara Sotto | Completed | 2019-10-03 | 7.96 | 2 | Ara Sotto | Completed | 2019-09-19 | 13.92 | 2 | Brian Le | Completed | 2019-08-29 | 1.08 | 2 | Marcia Garay | Completed | 2019-08-28 | 0.17 | 1 |  | Completed | 2019-09-03 | 2.79 | 1 | Jeremiah Liend | Completed |  | 20.54 | 1 | Marcia Garay | Current | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 5.88 | 2 | Marcia Garay | Completed | 2019-10-09 | 3.83 | 1 | Andrew Clemons | Completed | 2019-09-26 15:16 |  | 2019-09-26 | 2.79 | 2 | Ara Sotto | Completed | [10 empty] | 10.86 | [11 empty] | 2019-09-04 | 2019-10-03 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27310 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27310 | https://completesolar.sugarondemand.com/#Opportunities/0aeb929c-bba7-11e9-832e-0630baf9dcb8 | SCES Division | Henry Garcia | 2019-07-22 | JK Solar | 0aeb929c-bba7-11e9-832e-0630baf9dcb8 | 3 | 10 | 0 | -2 | 5 | 5 | 5 | 8
28129 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 43100 Sunny Lane | Lancaster | CA | 93536 | Nancy Cardenas | 2019-08-24 06:54 | 6617540829 | cardenasnancy08@gmail.com |  |  |  | 13401 | 0.13 | Bill Angevine | 2019-08-23 | 7.015 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-22 | 2019-08-23 15:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-23 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-09-13 | 2019-08-26 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 1.13 | 2 | Daniel Speegle | Completed | 2019-09-06 | 7.08 | 1 | Ara Sotto | Completed | 2019-09-23 | 8.96 | 5 | Brian Le | Completed | 2019-08-28 | 0 | 3 | Andrew Moralez | Completed | 2019-09-06 | 6 | 1 | Andrew Moralez | Completed | 2019-09-23 | 6.42 | 2 | Ara Sotto | Completed |  | 20.08 | 2 | Ara Sotto | Current | 2019-09-10 | 8.13 | 2 | Brian Le | Completed | 2019-08-28 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-28 | 0.96 | 1 |  | Completed | 2019-09-03 | 3.63 | 1 | Jill Allen | Completed | 2019-09-27 | 9.34 | 1 | Darlynn Lacap | Completed | 2019-10-01 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-19 |  | 20.08 | 2 | Ara Sotto | Current | [10 empty] | 0.96 | [11 empty] | 2019-08-29 |  | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28129 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28129 | https://completesolar.sugarondemand.com/#Opportunities/9c2ebef8-c676-11e9-ab41-022c40d974e6 | George Sarkis |  | 2019-08-22 | JK Solar | 9c2ebef8-c676-11e9-ab41-022c40d974e6 | 28 | 28 | -25 | -2 | 5 | 5 | 5 | -17
28417 | PIP_APPROVED | PIP_APPROVED | 12724 Via Posada Court | Victorville | CA | 92392 | Tressie Scott | 2019-09-07 19:46 | 7602856527 | djwigg27@gmail.com | Daroyl Scott | (760) 285-6529 |  | 15383 | 0.15 | Bill Angevine | 2019-09-06 | 7.93 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-09-03 | 2019-09-06 15:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-23 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-09-23 | 2019-09-13 | 4.42 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-23 | 0.08 | 5 | Brian Le | Completed | 2019-09-11 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-18 | 3.17 | 10 | Ernesto Enriquez | Completed | 2019-09-23 | 0.08 | 2 | Ara Sotto | Completed | 2019-09-26 | 3.29 | 2 | Ara Sotto | Completed | 2019-09-19 | 0.75 | 2 | Brian Le | Completed | 2019-09-18 | 3.21 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 1 |  | Completed | 2019-09-13 | 0.08 | 1 | Noe Gomez | Completed | 2019-09-26 | 2.88 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 3.88 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 4.21 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 6.79 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 0.75 | 1 | Andrew Clemons | Completed | 2019-09-26 14:59 |  | 2019-09-26 | 2.88 | 2 | Ara Sotto | Completed | [10 empty] | 6.71 | [11 empty] | 2019-09-27 | 2019-09-26 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28417 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28417 | https://completesolar.sugarondemand.com/#Opportunities/b98a0ba2-d1e2-11e9-b5e3-069e4f790264 | CSA Division | Christopher Cellini | 2019-09-03 | Power Town Solar Electric | b98a0ba2-d1e2-11e9-b5e3-069e4f790264 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
28546 | PIP_APPROVED | PIP_APPROVED | 4545 Royal Oak Drive | Oceanside | CA | 92056 | Sharan L Roebuck | 2019-09-09 16:39 | 7605057819 | sharan.roebuck@ryan.com | Tom Brummer | 7607122889 |  | 4787 | 0.19 | Michael Marlaire | 2019-09-09 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-09-07 | 2019-09-09 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-23 | NEM Submitted | SunRun Monthly | [6 empty] | 2019-09-23 07:00 | 2019-09-11 | 1.88 | 2 | Marcia Garay | Completed | 2019-09-11 | 0 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.13 | 1 | Christina Horton | Completed | 2019-09-23 | 7.21 | 5 | Brian Le | Completed | 2019-09-11 | 0 | 3 | Andrew Moralez | Completed | 2019-09-13 | 1.92 | 10 | Ernesto Enriquez | Completed | 2019-09-23 | 0.42 | 1 | Christina Horton | Completed | 2019-10-04 | 8.75 | 2 | Christina Horton | Completed | 2019-09-12 | 0.71 | 2 | Brian Le | Completed | 2019-09-11 | 0 | 2 | Marcia Garay | Completed | 2019-09-11 | 0 | 1 |  | Completed | 2019-09-16 | 3 | 1 | Andrew Clemons | Completed |  | 20.54 | 1 | Marcia Garay | Current | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 19 | 2 | Ashley Rockwood | Completed |  | 0.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-24 14:36 |  | 2019-09-24 | 0.83 | 2 | Christina Horton | Completed | [10 empty] | 1.29 | [11 empty] | 2019-09-25 | 2019-10-04 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28546 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28546 | https://completesolar.sugarondemand.com/#Opportunities/09341c96-d35b-11e9-b587-069e4f790264 | Lee Allison |  | 2019-09-07 | Infinity Energy Inc | 09341c96-d35b-11e9-b587-069e4f790264 | 1 | 11 | 10 | -2 | 5 | 5 | 5 | 18
26002 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 17883 California 94 | Dulzura | CA | 91917 | Cecilia Catlin | 2019-07-02 10:18 | 6198557276 | ccatlin7@gmail.com | Bobby Chettom | 6192089970 |  | 340222.27 |  | Ryan Malloy | 2019-07-02 | 20.435 |  | UpGrid Inc | Darlynn Lacap | 2019-06-28 | 2019-07-01 12:00 | LR6-60PB-305M | 305 | 67 | LONGi Solar | Enphase Energy | IQ7PLUS-72-2-US | Tile Concrete | MPU | 2019-09-20 | Installation Complete | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-09-18 07:00 | 2019-07-02 | 0 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 3.42 | 2 | Daniel Speegle | Completed | 2019-09-13 | 14.34 | 1 | Christina Horton | Completed | 2019-09-18 | 2.54 | 5 | Brian Le | Completed | 2019-07-09 | 0.25 | 3 | Ernesto Enriquez | Completed | 2019-07-10 | 0.5 | 0 | Ernesto Enriquez | Completed | 2019-09-20 | 2.25 | 5 | Christina Horton | Completed |  | 21.29 | 2 | Christina Horton | Current | 2019-09-16 | 47.33 | 2 | Brian Le | Completed | 2019-07-09 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 0.71 | 1 |  | Completed | 2019-07-02 | 0.08 | 1 | Andrew Clemons | Completed | 2019-09-27 | 7.33 | 1 | Darlynn Lacap | Completed | 2019-09-24 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 14.34 | 1 | Christina Horton | Inactive | 2019-07-09 | 0.71 | 2 | Darlynn Lacap | Completed | 40.38 | [11 empty] | 2019-07-09 |  | DULZURA | Dulzura | https://heliotrack.completesolar.com/job.php?action=review&jobID=26002 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26002 | https://completesolar.sugarondemand.com/#Opportunities/496fccc8-9ced-11e9-8575-02ae981fbade | Josh Garcia |  | 2019-05-29 | iEnergy ElectricSolar | 496fccc8-9ced-11e9-8575-02ae981fbade |  | 31 | -25 | -2 | 5 | 5 | 5 | -17
27619 | PIP_APPROVED | PIP_APPROVED | 2137 Aviator Avenue | Dos Palos | CA | 93620 | Carmen Zavala | 2019-08-14 09:48 | 2095097143 | ccallejas135@gmail.com | Carolina Zavala | 2098299974 |  | 7799.67 |  | Ricardo Virgen | 2019-08-03 | 5.185 | Christina Horton | Sunmatter Inc | Marcia Garay | 2019-08-02 | 2019-08-03 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-20 | Final Permit | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-09-20 07:00 | 2019-08-15 | 1.63 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 5.13 | 2 | Jethro Andal | Completed | 2019-09-04 | 14.5 | 1 | Christina Horton | Completed | 2019-09-20 | 4.92 | 5 | Brian Le | Completed | 2019-08-27 | 1.17 | 3 | Andrew Moralez | Completed | 2019-09-11 | 9.75 | 0 | Andrew Moralez | Completed | 2019-09-20 | 0.67 | 2 | Christina Horton | Completed | 2019-10-07 | 10.88 | 2 | Christina Horton | Completed | 2019-09-13 | 16.92 | 2 | Brian Le | Completed | 2019-08-20 | 3.92 | 2 | Marcia Garay | Completed | 2019-08-26 | 4.75 | 1 |  | Completed | 2019-08-26 | 8.42 | 1 | Andrew Clemons | Completed | 2019-10-07 | 11.51 | 1 | Marcia Garay | Completed |  | 10.13 | 2 | Jeremiah Liend | Current | [15 empty] | 2019-10-15 | 6.08 | 2 | Ashley Rockwood | Completed |  | 4.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-07 17:06 |  | 2019-10-07 | 10.83 | 2 | Christina Horton | Completed | [10 empty] | 4.99 | [11 empty] | 2019-08-27 | 2019-10-07 | DOS PALOS | Dos Palos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27619 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27619 | https://completesolar.sugarondemand.com/#Opportunities/f8c59056-b65e-11e9-96ac-069e4f790264 | People Builders |  | 2019-08-02 | Peak Energy Electric | f8c59056-b65e-11e9-96ac-069e4f790264 | 17 | 17 | -15 | -2 | 5 | 5 | 5 | -7
27910 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 8640 56th Street | Riverside | CA | 92509 | Raydel Gomez | 2019-08-21 13:32 | 9519411770 | rmrgmf@icloud.com | Maria Gomez | 9513124680 |  | 9169 | 0.15 | Shaun Labelle | 2019-08-21 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-20 | 2019-08-21 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-20 | NEM Submitted | SunRun Monthly |  | 0 |  |  |  |  | 2019-09-20 07:00 | 2019-08-22 | 1.08 | 2 | Marcia Garay | Completed | 2019-08-26 | 1.88 | 2 | Daniel Speegle | Completed | 2019-09-09 | 9.21 | 1 | Christina Horton | Completed | 2019-09-20 | 2.58 | 5 | Brian Le | Completed | 2019-08-28 | 1.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 8.04 | 10 | Andrew Moralez | Completed | 2019-09-20 | 0.54 | 2 | Christina Horton | Completed |  | 21 | 2 | Christina Horton | Current | 2019-09-10 | 7.92 | 2 | Brian Le | Completed | 2019-08-27 | 0.96 | 2 | Marcia Garay | Completed | 2019-08-27 | 0.88 | 1 |  | Completed | 2019-08-29 | 3.08 | 1 | Andrew Clemons | Completed | 2019-09-24 | 2.38 | 1 | Marcia Garay | Completed | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-21 | 11.79 | 2 | Ashley Rockwood | Completed |  | 0.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-03 12:53 |  | 2019-10-03 | 7.97 | 2 | Christina Horton | Completed | [10 empty] | 8.25 | [11 empty] | 2019-09-12 |  | RIVERSIDE | Riverside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27910 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27910 | https://completesolar.sugarondemand.com/#Opportunities/c7eb4f3c-c452-11e9-bd11-069e4f790264 | Lindsey Lange | Robert Garcia | 2019-08-13 | Infinity Energy Inc | c7eb4f3c-c452-11e9-bd11-069e4f790264 | 13 | 31 | -15 | -2 | 5 | 5 | 5 | -7
27955 | PIP_APPROVED | PIP_APPROVED | 44033 D Street | Hemet | CA | 92544 | Gabriela Pelazini | 2019-08-17 15:01 | 9513558202 | gpelazini@gmail.com |  |  |  | 6613 | 0.135 | Shaun Labelle | 2019-08-17 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-14 | 2019-08-17 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | MPU | 2019-09-20 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-20 07:00 | 2019-08-20 | 1.42 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2.25 | 2 | Daniel Speegle | Completed | 2019-08-19 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-20 | 5 | 5 | Brian Le | Completed | 2019-09-10 | 8.04 | 3 | Andrew Moralez | Completed | 2019-09-10 | 0.25 | 0 | Andrew Moralez | Completed | 2019-09-20 | 0.75 | 1 | Ara Sotto | Completed | 2019-09-25 | 2.67 | 2 | Ara Sotto | Completed | 2019-09-13 | 10.63 | 2 | Brian Le | Completed | 2019-08-26 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 1.58 | 1 |  | Completed | 2019-09-17 | 14.17 | 1 | Andrew Clemons | Completed | 2019-09-27 | 5.62 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 1.04 | 2 | Jeremiah Liend | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-11 |  | 0 | 2 |  | Inactive |  | 21.83 | 1 | Ara Sotto | Current | 2019-09-05 | 0.13 | 2 | Darlynn Lacap | Completed | 12.12 | [11 empty] | 2019-09-10 | 2019-09-24 | RIVERSIDE COUNTY | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=27955 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27955 | https://completesolar.sugarondemand.com/#Opportunities/781755ac-c13a-11e9-903c-0630baf9dcb8 | Cory Hartman |  | 2019-08-14 | HDM Electric Inc | 781755ac-c13a-11e9-903c-0630baf9dcb8 |  | 5 | -25 | -2 | 5 | 5 | 5 | -17
26500 | PIP_APPROVED | PIP_APPROVED | 2814 East Avenue R12 | Palmdale | CA | 93550 | Fortunato Mendoza | 2019-07-24 17:38 | 6613175428 | natomendoza21@yahoo.com |  | 6619475939 |  | 10549 | 0.13 | Bill Angevine | 2019-06-25 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-18 | 2019-06-24 10:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-19 | PTO Received | SunRun Monthly | 0 | 0 |  | 1 | 1 | 1 | 2019-09-17 07:00 | 2019-07-24 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 3.75 | 2 | Jethro Andal | Completed | 2019-07-29 | 2 | 1 | Ara Sotto | Completed | 2019-09-19 | 19.79 | 5 | Brian Le | Completed | 2019-07-25 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-25 | 0 | 0 | Andrew Moralez | Completed | 2019-09-19 | 2.21 | 2 | Ara Sotto | Completed | 2019-09-26 | 5 | 2 | Ara Sotto | Completed | 2019-08-21 | 13.13 | 2 | Brian Le | Completed | 2019-08-02 | 2.92 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.08 | 1 |  | Completed | 2019-07-29 | 2 | 1 | Andrew Clemons | Completed | 2019-09-27 | 8.33 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-10-03 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 5.92 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 3.88 | 1 | Jeremiah Liend | Completed | 2019-09-24 16:40 |  | 2019-09-26 | 5 | 2 | Ara Sotto | Completed | [10 empty] | 11.37 | 2019-09-09 | 12.62 | 14 | James Fernandez | Completed | 2019-09-09 | 2019-09-09 | 2.79 | 1 | James Fernandez | Completed | 2019-07-25 | 2019-09-26 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26500 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26500 | https://completesolar.sugarondemand.com/#Opportunities/6f2db530-97a0-11e9-9f02-022c40d974e6 | Henry Garcia |  | 2019-06-18 | JK Solar | 6f2db530-97a0-11e9-9f02-022c40d974e6 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26829 | PIP_APPROVED | PIP_APPROVED | 17398 Holly Drive | Fontana | CA | 92335 | Saul Lopez | 2019-08-16 15:10 | 9098220291 | saulteresa.lopez@gmail.com | Elvira Lopez | 9095619999 |  | 8259 | 0.155 | Chris Peaslee | 2019-07-24 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-01 | 2019-07-02 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | Line-side Tap | 2019-09-19 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-19 07:00 | 2019-08-16 | 2.71 | 2 | Marcia Garay | Completed | 2019-08-23 | 1.83 | 2 | Daniel Speegle | Completed | 2019-09-06 | 8.16 | 1 | Ara Sotto | Completed | 2019-09-19 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-06 | 8.33 | 3 | Andrew Moralez | Completed | 2019-09-19 | 11.88 | 12 | Ernesto Enriquez | Completed | 2019-09-19 | 0.67 | 1 | Ara Sotto | Completed | 2019-10-01 | 8 | 2 | Ara Sotto | Completed | 2019-09-16 | 9.34 | 2 | Brian Le | Completed | 2019-09-03 | 6.96 | 2 | Marcia Garay | Completed | 2019-08-26 | 0.16 | 1 |  | Completed | 2019-09-16 | 14.25 | 1 | Noe Gomez | Completed | 2019-10-15 | 18.71 | 1 | Marcia Garay | Completed | 2019-09-26 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-04 |  | 0 | 2 |  | Inactive |  | 22.83 | 1 | Ara Sotto | Current | 2019-08-23 | 0.17 | 2 | Marcia Garay | Completed | 39.24 | [11 empty] | 2019-09-19 | 2019-09-30 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=26829 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26829 | https://completesolar.sugarondemand.com/#Opportunities/8c5eee02-ae67-11e9-b7cf-069e4f790264 | CUIC Inc | 300 Stars Inc | 2019-07-01 | Green Road Solar Crew | 8c5eee02-ae67-11e9-b7cf-069e4f790264 |  | 12 | -25 | -2 | 5 | 5 | 5 | -17
27461 | PIP_APPROVED | PIP_APPROVED | 38121 41st Street East | Palmdale | CA | 93552 | Nelly Valencia | 2019-08-21 07:18 | 6615745723 | nellyvalencia1027@gmail.com |  |  |  | 9192 | 0.138 | Bill Angevine | 2019-07-31 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-29 | 2019-07-31 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-19 | Final Permit | SunRun Monthly | [6 empty] | 2019-09-19 07:00 | 2019-08-21 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2.13 | 2 | Jethro Andal | Completed | 2019-09-09 | 10.92 | 1 | Ara Sotto | Completed |  | 30.13 | 5 | Brian Le | Current | 2019-08-22 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-22 | 0.08 | 0 | Andrew Moralez | Completed | 2019-09-19 | 3.54 | 2 | Ara Sotto | Completed | 2019-10-02 | 9.25 | 2 | Ara Sotto | Completed | 2019-09-09 | 7.75 | 2 | Brian Le | Completed | 2019-08-27 | 3.17 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 1 |  | Completed | 2019-09-17 | 16.88 | 1 | Noe Gomez | Completed | 2019-09-27 | 9.71 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 11.71 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-19 15:23 |  | 2019-09-19 | 0.21 | 2 | Ara Sotto | Completed | [10 empty] | 27.7 | [11 empty] | 2019-08-22 | 2019-10-02 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27461 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27461 | https://completesolar.sugarondemand.com/#Opportunities/e16f584a-b403-11e9-afdd-0630baf9dcb8 | Kevin Adams | Emily Bowden | 2019-07-26 | JK Solar | e16f584a-b403-11e9-afdd-0630baf9dcb8 | 0 | 13 | 10 | -2 | 5 | 5 | 5 | 18
27486 | PIP_APPROVED | PIP_APPROVED | 856 Fremont Place | Hemet | CA | 92543 | Linda R Yerky | 2019-08-01 10:47 | 9512030059 | lryerkey@hotmail.com |  |  |  | 4925 | 0.145 | Alex Holdridge | 2019-08-01 | 2.745 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-27 | 2019-08-01 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-19 07:00 | 2019-08-01 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 1.42 | 2 | Daniel Speegle | Completed | 2019-08-11 | 5 | 1 | Ara Sotto | Completed | 2019-09-19 | 3.79 | 5 | Brian Le | Completed | 2019-08-08 | 3.67 | 3 | Ernesto Enriquez | Completed | 2019-09-11 | 22.71 | 1 | Ernesto Enriquez | Completed | 2019-09-19 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-23 | 2.13 | 2 | Ara Sotto | Completed | 2019-09-13 | 26.37 | 2 | Brian Le | Completed | 2019-08-05 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-08-03 | 0 | 1 |  | Completed | 2019-08-07 | 2.33 | 1 | Andrew Clemons | Completed | 2019-09-26 | 5.54 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-09 | 9.21 | 2 | Ashley Rockwood | Completed | 2019-10-10 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 4.75 | 2 | Darlynn Lacap | Completed | 2019-10-11 | 0.88 | 1 | Andrew Clemons | Completed | 2019-09-20 16:57 |  | 2019-09-26 | 5 | 2 | Ara Sotto | Completed | [10 empty] | 8.12 | [11 empty] | 2019-08-09 | 2019-09-23 | HEMET | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=27486 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27486 | https://completesolar.sugarondemand.com/#Opportunities/686f884e-b484-11e9-a94d-022c40d974e6 | PJB Division |  | 2019-07-27 | Green Road Solar Crew | 686f884e-b484-11e9-a94d-022c40d974e6 | 7 | 4 | -5 | 0 | 5 | 5 | 5 | 5
27994 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 565 2nd Avenue | Chula Vista | CA | 91910 | Gricelda Garcia | 2019-08-26 11:43 | 6196513597 | grace07@cox.net | Steve Garcia | 6199419737 |  | 5445 | 0.179 | Ryan Malloy | 2019-08-21 | 3.66 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-16 | 2019-08-19 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-19 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-19 07:00 | 2019-08-26 | 0.04 | 2 | Marcia Garay | Completed | 2019-08-27 | 4.04 | 2 | Daniel Speegle | Completed | 2019-09-10 | 9.13 | 1 | Christina Horton | Completed | 2019-09-19 | 2.75 | 5 | Brian Le | Completed | 2019-08-27 | 0 | 3 | Andrew Moralez | Completed | 2019-09-10 | 9 | 7 | Andrew Moralez | Completed | 2019-09-19 | 0.46 | 1 | Christina Horton | Completed |  | 22.04 | 2 | Christina Horton | Current | 2019-09-10 | 0.88 | 2 | Brian Le | Completed | 2019-09-09 | 8.04 | 2 | Marcia Garay | Completed | 2019-08-27 | 0 | 1 |  | Completed | 2019-09-03 | 3.67 | 1 | Andrew Clemons | Completed | 2019-10-09 | 14.25 | 1 | Marcia Garay | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 15:42 |  |  | 22.04 | 2 | Christina Horton | Current | [10 empty] | 24.59 | [11 empty] | 2019-09-06 |  | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27994 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27994 | https://completesolar.sugarondemand.com/#Opportunities/850bfb06-c431-11e9-9421-0630baf9dcb8 | Daniel Boyce | Henry Rendon | 2019-08-16 | Infinity Energy Inc | 850bfb06-c431-11e9-9421-0630baf9dcb8 | 32 | 32 | -25 | -2 | 5 | 5 | 5 | -17
28089 | PIP_APPROVED | PIP_APPROVED | 37441 Cambridge Lane | Palmdale | CA | 93550 | Erik Swanson | 2019-08-24 12:59 | 8182357664 | civswan@gmail.com | Victoria Swanson | 8182357669 |  | 9829 | 0.13 | Bill Angevine | 2019-08-21 | 7.32 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-20 | 2019-08-21 09:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-19 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-18 07:00 | 2019-08-26 | 1.09 | 2 | Marcia Garay | Completed | 2019-08-27 | 2.38 | 2 | Daniel Speegle | Completed | 2019-09-04 | 4.92 | 1 | Ara Sotto | Completed | 2019-09-19 | 3.83 | 5 | Brian Le | Completed | 2019-08-30 | 1.92 | 3 | Andrew Moralez | Completed | 2019-09-11 | 6.83 | 5 | Andrew Moralez | Completed | 2019-09-19 | 1.21 | 2 | Ara Sotto | Completed | 2019-09-25 | 4.17 | 2 | Ara Sotto | Completed | 2019-09-13 | 10.96 | 2 | Brian Le | Completed | 2019-08-28 | 1.17 | 2 | Marcia Garay | Completed | 2019-08-27 | 0.17 | 1 |  | Completed | 2019-09-10 | 9.25 | 1 | Noe Gomez | Completed | 2019-10-11 | 17.29 | 1 | Marcia Garay | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-07 | 6.96 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5.17 | 2 | Ashley Rockwood | Completed |  | 5.13 | 2 | Marcia Garay | Current | 2019-10-16 | 2.04 | 1 | Noe Gomez | Completed | 2019-09-24 16:57 |  | 2019-09-26 | 5 | 2 | Ara Sotto | Completed | [10 empty] | 1.66 | [11 empty] | 2019-09-09 | 2019-09-25 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28089 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28089 | https://completesolar.sugarondemand.com/#Opportunities/3af3d892-c48e-11e9-9b20-069e4f790264 | SCES Division |  | 2019-08-20 | JK Solar | 3af3d892-c48e-11e9-9b20-069e4f790264 | 7 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28132 | PIP_APPROVED | PIP_APPROVED | 6401 Manchester Lane | Bakersfield | CA | 93309 | Sukhdev Brar | 2019-08-23 20:58 | 6614409960 | bebrar@kern.org | Berverly Brar | 6614379993 |  | 10950 | 0.18 | Bill Angevine | 2019-08-23 | 7.93 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-08-22 | 2019-08-23 09:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-19 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-18 07:00 | 2019-08-26 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 0.21 | 2 | Daniel Speegle | Completed | 2019-09-11 | 10.83 | 1 | Christina Horton | Completed | 2019-09-18 | 0.63 | 5 | Brian Le | Completed | 2019-08-29 | 2 | 3 | Andrew Moralez | Completed | 2019-09-10 | 7.13 | 5 | Andrew Moralez | Completed | 2019-09-19 | 1.25 | 2 | Christina Horton | Completed | 2019-09-26 | 5.5 | 2 | Christina Horton | Completed | 2019-09-13 | 11.13 | 2 | Brian Le | Completed | 2019-08-28 | 1.75 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.71 | 1 |  | Completed | 2019-08-30 | 3.79 | 1 | Andrew Clemons | Completed | 2019-09-25 | 5.5 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-17 | 15.88 | 2 | Ashley Rockwood | Completed |  | 2.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-25 13:33 |  | 2019-09-25 | 3.05 | 2 | Christina Horton | Completed | [10 empty] | 5.38 | [11 empty] | 2019-09-06 | 2019-09-26 | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=28132 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28132 | https://completesolar.sugarondemand.com/#Opportunities/5e18e876-c623-11e9-be35-069e4f790264 | Ryan Wilcox |  | 2019-08-22 | Peak Energy Electric | 5e18e876-c623-11e9-be35-069e4f790264 | 6 | 7 | -5 | -2 | 5 | 5 | 5 | 3
28174 | PIP_APPROVED | PIP_APPROVED | 13280 High Desert Road | Victorville | CA | 92392 | Adrian Manibusan | 2019-09-09 11:28 | 7604038526 | r_mrtnz68@yahoo.com | Rosalie Martinez | 7605086189 |  | 19490 | 0.15 |  | 2019-08-27 | 11.59 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-24 | 2019-08-31 15:00 | LR6-60PB-305M | 305 | 38 | LONGi Solar | SolarEdge | SE10000A-US RGM | Tile Concrete | Line-side Tap | 2019-09-19 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-09-17 07:00 | 2019-09-09 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 6.96 | 2 | Daniel Speegle | Completed | 2019-09-11 | 0.16 | 1 | Ara Sotto | Completed | 2019-09-19 | 2.96 | 5 | Brian Le | Completed | 2019-09-17 | 0.91 | 3 | Andrew Moralez | Completed | 2019-09-17 | 2.08 | 10 | Andrew Moralez | Completed | 2019-09-19 | 2.42 | 3 | Ara Sotto | Completed | 2019-09-25 | 4 | 2 | Ara Sotto | Completed | 2019-09-13 | 0.08 | 2 | Brian Le | Completed | 2019-09-16 | 3.29 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.37 | 1 |  | Completed | 2019-09-19 | 6 | 1 | Andrew Clemons | Completed | 2019-09-27 | 8.33 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-03 |  | 0 | 2 |  | Inactive |  | 24.54 | 1 | Ara Sotto | Current | 2019-09-12 | 1 | 2 | Darlynn Lacap | Completed | 13.05 | [11 empty] | 2019-09-27 | 2019-09-20 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28174 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28174 | https://completesolar.sugarondemand.com/#Opportunities/3fed3a6a-c997-11e9-b4be-0630baf9dcb8 | Christopher Cellini |  | 2019-08-24 | HDM Electric Inc | 3fed3a6a-c997-11e9-b4be-0630baf9dcb8 |  | 6 | -25 | -2 | 5 | 5 | 5 | -17
28179 | SP APPROVED |  | 63 Millan Court | Chula Vista | CA | 91910 | Maria Gomez | 2019-08-29 11:36 | 6192895753 | Malenitagomezm@gmail.com | Javier Huerta |  |  | 6190 | 0.185 | Chad Malloy | 2019-08-29 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-27 | 2019-08-29 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-19 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-19 12:00 | 2019-08-29 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 0.96 | 2 | Daniel Speegle | Completed | 2019-09-11 | 6.96 | 1 | Ara Sotto | Completed | 2019-09-19 | 0.13 | 5 | Brian Le | Completed | 2019-08-30 | 0 | 3 | Andrew Moralez | Completed | 2019-09-10 | 5.88 | 7 | Andrew Moralez | Completed | 2019-09-19 | 0.46 | 1 | Christina Horton | Completed |  | 22.04 | 2 | Christina Horton | Current | 2019-09-10 | 0.08 | 2 | Brian Le | Completed | 2019-09-11 | 3.08 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 0 | 1 |  | Completed | 2019-09-06 | 3.71 | 1 | Andrew Clemons | Completed | 2019-09-27 | 6.33 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 15:32 |  |  | 22.04 | 2 | Christina Horton | Current | [10 empty] | 11.58 | [11 empty] | 2019-09-11 |  | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=28179 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28179 | https://completesolar.sugarondemand.com/#Opportunities/cb33ab78-ca8b-11e9-85e2-0630baf9dcb8 | Daniel Boyce | Henry Rendon | 2019-08-24 | Infinity Energy Inc | cb33ab78-ca8b-11e9-85e2-0630baf9dcb8 | 32 | 32 | -25 | -2 | 5 | 5 | 5 | -17
28296 | SP APPROVED |  | 13955 Valley View Court | Desert Hot Springs | CA | 92240 | Edward Wilson | 2019-09-10 15:45 | 3232731280 | eeddwilson@aol.com |  |  |  | 10324 | 0.159 | Shaun Labelle | 2019-08-31 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-29 | 2019-08-31 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM |  | NO | 2019-09-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-18 07:00 | 2019-09-11 | 1.33 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 0.16 | 2 | Daniel Speegle | Completed | 2019-09-13 | 6.92 | 1 | Ara Sotto | Completed | 2019-09-19 | 4.04 | 5 | Brian Le | Completed | 2019-09-17 | 5.21 | 3 | Andrew Moralez | Completed | 2019-09-24 | 6.96 | 14 | Andrew Moralez | Completed | 2019-09-19 | 0.96 | 2 | Ara Sotto | Completed |  | 22.08 | 2 | Ara Sotto | Current | 2019-09-13 | 5.13 | 2 | Brian Le | Completed | 2019-09-12 | 1.87 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 1.75 | 1 |  | Completed | 2019-09-16 | 7.13 | 1 | Andrew Clemons | Completed | 2019-09-27 | 6.88 | 1 | Darlynn Lacap | Completed | 2019-09-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-01 | 8 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 4.88 | 2 | Ashley Rockwood | Completed |  | 9.17 | 2 | Darlynn Lacap | Current | 2019-10-09 | 0.83 | 1 | Jeremiah Liend | Completed | 2019-09-19 15:38 |  | 2019-09-19 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 4.25 | [11 empty] | 2019-10-03 |  | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=28296 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28296 | https://completesolar.sugarondemand.com/#Opportunities/e1c30742-cc3b-11e9-8492-0630baf9dcb8 | PJB Division |  | 2019-08-29 | Zachary Noah Gamez | e1c30742-cc3b-11e9-8492-0630baf9dcb8 | 0 | 32 | 10 | -2 | 5 | 5 | 5 | 18
28375 | PIP_APPROVED | PIP_APPROVED | 12521 Lucero Street | Victorville | CA | 92392 | Jose Castillo | 2019-09-03 18:06 | 3109187456 | jfernando1580@yahoo.com | Martha Castillo | 3109187457 |  | 9832 | 0.15 | Bill Angevine | 2019-09-03 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-31 | 2019-09-03 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-19 | 2019-09-04 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 3 | 2 | Daniel Speegle | Completed | 2019-09-05 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-19 | 4.04 | 5 | Brian Le | Completed | 2019-09-11 | 0 | 3 | Andrew Moralez | Completed | 2019-09-11 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-19 | 0 | 2 | Ara Sotto | Completed | 2019-09-24 | 3.08 | 2 | Ara Sotto | Completed | 2019-09-13 | 2.88 | 2 | Brian Le | Completed | 2019-09-10 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.04 | 1 |  | Completed | 2019-09-13 | 3.88 | 1 | Noe Gomez | Completed | 2019-09-27 | 5.96 | 1 | Darlynn Lacap | Completed | 2019-09-26 | 1.75 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-04 | 9.83 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 4.21 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 2 | 1 | Andrew Clemons | Completed | 2019-09-20 13:26 |  | 2019-09-20 | 1.08 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-25 | 2019-09-24 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28375 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28375 | https://completesolar.sugarondemand.com/#Opportunities/22333f10-ceb0-11e9-8683-0630baf9dcb8 | CSA Division | Christopher Cellini | 2019-08-31 | Green Road Solar Crew | 22333f10-ceb0-11e9-8683-0630baf9dcb8 | 1 | 5 | 10 | -2 | 5 | 5 | 5 | 18
25590 | PIP_APPROVED | PIP_APPROVED | 1732 Mallow Court | Carlsbad | CA | 92011 | Hellene Brodsky | 2019-08-20 08:32 | 7608460969 | hellene@journeyschool.net |  |  |  | 3315 | 0.171 | Chad Malloy | 2019-08-20 | 2.44 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-17 | 2019-08-19 12:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-18 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-18 07:00 | 2019-08-20 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 1.71 | 2 | Daniel Speegle | Completed | 2019-08-30 | 2.96 | 1 | Ara Sotto | Completed | 2019-09-18 | 8.68 | 5 | Brian Le | Completed | 2019-08-28 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-28 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-18 | 0.54 | 1 | Christina Horton | Completed | 2019-10-03 | 10.83 | 2 | Christina Horton | Completed | 2019-08-27 | 0.08 | 2 | Brian Le | Completed | 2019-08-28 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.08 | 1 |  | Completed | 2019-09-17 | 9.88 | 1 | Andrew Clemons | Completed | 2019-09-27 | 7.33 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-26 | 3.79 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-10-10 | 7.88 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Jill Allen | Completed |  | 2019-09-26 | 2019-09-20 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 11.34 | [11 empty] | 2019-09-19 | 2019-10-03 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=25590 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25590 | https://completesolar.sugarondemand.com/#Opportunities/9cefb956-c35f-11e9-b068-02ae981fbade | Gavin Seeberger |  | 2019-05-14 | Infinity Energy Inc | 9cefb956-c35f-11e9-b068-02ae981fbade | 2 | 15 | 7 | -2 | 5 | 5 | 5 | 15
25703 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 7889 New Salem Street | San Diego | CA | 92126 | Edward Webb | 2019-05-31 18:12 | 6199256204 | EWebb46@earthlink.net | Gina Webb | 8583227482 |  | 10162 | 0.19 | Ryan Malloy | 2019-05-31 | 7.32 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-05-28 | 2019-05-31 16:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | MPU | 2019-09-18 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-17 07:00 | 2019-06-03 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 3.13 | 2 | Daniel Speegle | Completed | 2019-07-30 | 23.83 | 1 | Christina Horton | Completed | 2019-09-18 | 43.8 | 5 | Brian Le | Completed | 2019-06-26 | 0 | 3 | Andrew Moralez | Completed | 2019-07-12 | 10.88 | 15 | Andrew Moralez | Completed | 2019-09-18 | 1.13 | 1 | Christina Horton | Completed |  | 23.38 | 2 | Christina Horton | Current | 2019-06-25 | 0.08 | 2 | Brian Le | Completed | 2019-06-26 | 1 | 2 | Marcia Garay | Completed | 2019-06-26 | 1.08 | 1 |  | Completed | 2019-06-30 | 3.38 | 1 | Andrew Clemons | Completed | 2019-09-26 | 7.46 | 1 | Marcia Garay | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 24.54 | 1 | Christina Horton | Current | 2019-06-26 | 0.83 | 2 | Marcia Garay | Completed | 35.64 | [11 empty] | 2019-07-18 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=25703 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25703 | https://completesolar.sugarondemand.com/#Opportunities/454a6302-840a-11e9-99ae-069e4f790264 | Kellee Benjamin | Andrew Goff | 2019-05-17 | Infinity Energy Inc | 454a6302-840a-11e9-99ae-069e4f790264 |  | 33 | -25 | -2 | 5 | 5 | 5 | -17
27028 | PIP_APPROVED | PIP_APPROVED | 2836 Cebu Court | Carlsbad | CA | 92009 | Dennis Kushner | 2019-08-26 14:39 | 4086210930 | dennytk@aol.com | Laurie Kushner | 7608142773 |  | 4574 | 0.175 | Bill Angevine | 2019-08-07 | 3.05 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-23 | 2019-08-07 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-18 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-18 07:00 | 2019-08-26 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 0.12 | 2 | Daniel Speegle | Completed | 2019-08-30 | 4.21 | 1 | Christina Horton | Completed | 2019-09-18 | 14.92 | 5 | Brian Le | Completed | 2019-08-26 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-26 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-18 | 0.63 | 1 | Ara Sotto | Completed | 2019-10-08 | 14.33 | 2 | Ara Sotto | Completed | 2019-09-06 | 0 | 2 | Brian Le | Completed | 2019-08-27 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 0.08 | 1 |  | Completed | 2019-09-13 | 13.17 | 1 | Andrew Clemons | Completed | 2019-09-27 | 7.58 | 1 | Darlynn Lacap | Completed |  | 8.79 | 2 | Jeremiah Liend | Current | [15 empty] | 2019-09-25 | 0.17 | 2 | Ashley Rockwood | Completed |  | 5.79 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-23 17:37 |  | 2019-09-25 | 4.83 | 2 | Ara Sotto | Completed | [10 empty] | 32.29 | [11 empty] | 2019-09-16 | 2019-10-08 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=27028 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27028 | https://completesolar.sugarondemand.com/#Opportunities/7754cbf4-b97e-11e9-a0ae-022c40d974e6 | Perry Ustick |  | 2019-07-10 | Zachary Noah Gamez | 7754cbf4-b97e-11e9-a0ae-022c40d974e6 | 7 | 20 | -5 | -2 | 5 | 5 | 5 | 3
27672 | PIP_APPROVED | PIP_APPROVED | 656 Nantucket Street | San Jacinto | CA | 92583 | Edna Saucedo | 2019-08-10 15:57 | 9516922043 | saucedo.edna@yahoo.com | David Leyva | 9513929493 |  | 6032 | 0.135 | Michael Marlaire | 2019-08-10 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-05 | 2019-08-10 12:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-18 | PTO Received | SunRun Monthly | 0 | 1 |  |  |  | 1 | 2019-09-18 | 2019-08-15 | 2.46 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 0.88 | 2 | Jethro Andal | Completed | 2019-09-13 | 18.79 | 1 | Ara Sotto | Completed | 2019-09-19 | 4.04 | 5 | Brian Le | Completed | 2019-08-30 | 9 | 3 | Andrew Moralez | Completed | 2019-09-10 | 3.88 | 10 | Andrew Moralez | Completed | 2019-09-18 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-19 | 1.17 | 2 | Ara Sotto | Completed | 2019-09-13 | 17.96 | 2 | Brian Le | Completed | 2019-08-19 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.83 | 1 |  | Completed | 2019-08-26 | 5.75 | 1 | Andrew Clemons | Completed | 2019-09-27 | 7.33 | 1 | Darlynn Lacap | Completed |  | 21.88 | 2 | Jeremiah Liend | Current | [15 empty] | 2019-09-20 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 2.13 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1.79 | 1 | Noe Gomez | Completed | 2019-09-19 16:56 |  | 2019-09-19 | 0.96 | 2 | Ara Sotto | Completed | [10 empty] | 7.13 | [11 empty] | 2019-09-18 | 2019-09-19 | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27672 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27672 | https://completesolar.sugarondemand.com/#Opportunities/15573572-bbc2-11e9-a13a-022c40d974e6 | PJB Division |  | 2019-08-05 | HDM Electric Inc | 15573572-bbc2-11e9-a13a-022c40d974e6 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
28037 | PIP_APPROVED | PIP_APPROVED | 11745 Fern Pine Street | Victorville | CA | 92392 | Ruben Olguin | 2019-09-03 16:47 | 9515459949 | ruben@californiaskateparks.com |  |  |  | 6555 | 0.156 | Shaun Labelle | 2019-08-31 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-18 | 2019-08-19 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-18 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-18 07:00 | 2019-09-04 | 1.38 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 1.13 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-18 | 3.13 | 5 | Brian Le | Completed | 2019-09-06 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 2.13 | 10 | Andrew Moralez | Completed | 2019-09-18 | 0.54 | 1 | Ara Sotto | Completed | 2019-09-27 | 6.71 | 2 | Ara Sotto | Completed | 2019-09-13 | 5.04 | 2 | Brian Le | Completed | 2019-09-06 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.83 | 1 |  | Completed | 2019-09-13 | 5.71 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 7.38 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-04 | 9.92 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 8.08 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 1.92 | 1 | Jill Allen | Completed | 2019-09-20 16:55 |  | 2019-09-20 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 0.33 | [11 empty] | 2019-09-20 | 2019-09-27 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28037 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28037 | https://completesolar.sugarondemand.com/#Opportunities/4a6fdfd2-cbff-11e9-afed-069e4f790264 | Just Power | Cory Hartman | 2019-08-18 | Green Road Solar Crew | 4a6fdfd2-cbff-11e9-afed-069e4f790264 | 2 | 9 | 7 | -2 | 5 | 5 | 5 | 15
28281 | PIP_APPROVED | PIP_APPROVED | 13777 Fuchsia Lane | Victorville | CA | 92392 | Rosa Manzo | 2019-08-31 19:35 | 7605137452 | rosie_isin@hotmail.com |  |  |  | 11349 | 0.138 | Bill Angevine | 2019-08-31 | 7.015 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-28 | 2019-08-31 15:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-18 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-18 07:00 | 2019-09-03 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-18 | 3.04 | 5 | Brian Le | Completed | 2019-09-06 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-10 | 2.17 | 10 | Andrew Moralez | Completed | 2019-09-18 | 0.46 | 2 | Ara Sotto | Completed | 2019-09-19 | 1.08 | 2 | Ara Sotto | Completed | 2019-09-13 | 5 | 2 | Brian Le | Completed | 2019-09-06 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.83 | 1 |  | Completed | 2019-09-12 | 5.04 | 1 | Andrew Clemons | Completed | 2019-09-27 | 7.38 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 1.58 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-09-24 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 0.96 | 1 | Noe Gomez | Completed | 2019-09-19 16:55 |  | 2019-09-19 | 0.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-20 | 2019-09-19 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28281 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28281 | https://completesolar.sugarondemand.com/#Opportunities/04079884-cc61-11e9-bd1a-022c40d974e6 | Shane Montana |  | 2019-08-28 | Power Town Solar Electric | 04079884-cc61-11e9-bd1a-022c40d974e6 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
28351 | PIP_APPROVED | PIP_APPROVED | 45314 23rd Street East | Lancaster | CA | 93535 | Cruz Sanchez | 2019-08-31 17:32 | 6619920227 | crnlchez1234@gmail.com |  |  |  | 9473.53 | 0.141 | Alex Holdridge | 2019-08-31 | 2.44 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-30 | 2019-08-31 15:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-18 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-13 07:00 | 2019-09-04 | 1.63 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-18 | 3.21 | 5 | Brian Le | Completed | 2019-09-05 | 0 | 3 | Andrew Moralez | Completed | 2019-09-06 | 1.17 | 1 | Andrew Moralez | Completed | 2019-09-18 | 3.42 | 1 | Ara Sotto | Completed | 2019-10-02 | 9.79 | 2 | Ara Sotto | Completed | 2019-09-09 | 2.83 | 2 | Brian Le | Completed | 2019-09-04 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 0.75 | 1 |  | Completed | 2019-09-10 | 4 | 1 | Jeremiah Liend | Completed | 2019-09-18 | 3.54 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-26 | 5 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 7.92 | 2 | Ashley Rockwood | Completed |  | 9.13 | 2 | Darlynn Lacap | Current |  | 9.09 | 1 | Andrew Clemons | Current | 2019-09-17 16:45 | 2019-09-25 | 2019-09-19 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 3.75 | [11 empty] | 2019-09-06 | 2019-10-01 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28351 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28351 | https://completesolar.sugarondemand.com/#Opportunities/ed5b66ee-cc4f-11e9-a874-0630baf9dcb8 | Henry Garcia |  | 2019-08-30 | JK Solar | ed5b66ee-cc4f-11e9-a874-0630baf9dcb8 | 1 | 14 | 10 | -2 | 5 | 5 | 5 | 18
28388 | PIP_APPROVED | PIP_APPROVED | 20317 Osseo Road | Apple Valley | CA | 92308 | Linda Salazar | 2019-09-05 16:54 | 8054408281 | llsalazar6@gmail.com | Daniel Salazar | 8054408282 |  | 11030 | 0.145 | Shaun Labelle | 2019-09-05 | 6.405 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-09-02 | 2019-09-05 11:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-18 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-17 07:00 | 2019-09-09 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0.25 | 2 | Daniel Speegle | Completed | 2019-09-11 | 1.71 | 1 | Ara Sotto | Completed | 2019-09-18 | 1.83 | 5 | Brian Le | Completed | 2019-09-12 | 1.92 | 3 | Andrew Moralez | Completed | 2019-09-12 | 0 | 14 | Andrew Moralez | Completed | 2019-09-18 | 0.96 | 2 | Ara Sotto | Completed | 2019-09-18 | 0.08 | 2 | Ara Sotto | Completed | 2019-09-16 | 3.92 | 2 | Brian Le | Completed | 2019-09-10 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 0.96 | 1 |  | Completed | 2019-09-13 | 3.67 | 1 | Andrew Clemons | Completed | 2019-09-17 | 0.21 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 2.96 | 2 | Jeremiah Liend | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-03 16:57 |  |  | 23.29 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-10-02 | 2019-09-18 | APPLE VALLEY | Apple Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=28388 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28388 | https://completesolar.sugarondemand.com/#Opportunities/69c3d964-d038-11e9-9f41-02ae981fbade | CUIC Inc | Cody Booth | 2019-09-02 | HDM Electric Inc | 69c3d964-d038-11e9-9f41-02ae981fbade | 33 | 0 | -25 | 5 | 5 | 5 | 5 | -10
26019 | PIP_APPROVED | PIP_APPROVED | 630 Olive Street | Menlo Park | CA | 94025 | Tom Foody | 2019-07-26 15:53 | 6502692267 | tom@hps.llc |  |  |  | 12260 |  | Ricardo Virgen | 2019-07-22 | 8.845 | Christina Horton | PACE Avenue | Darlynn Lacap | 2019-07-15 | 2019-07-19 10:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-09-17 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-09-16 07:00 | 2019-07-26 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-29 | 1.75 | 2 | Jethro Andal | Completed | 2019-08-06 | 8.33 | 1 | Christina Horton | Completed | 2019-09-16 | 3 | 5 | Brian Le | Completed | 2019-08-09 | 11.09 | 3 | Andrew Moralez | Completed | 2019-09-11 | 21.79 | 10 | Andrew Moralez | Completed | 2019-09-17 | 1.42 | 2 | Christina Horton | Completed | 2019-10-11 | 17.88 | 2 | Christina Horton | Completed | 2019-09-11 | 22.83 | 2 | Brian Le | Completed | 2019-08-06 | 4.25 | 2 | Darlynn Lacap | Completed | 2019-07-29 | 0.21 | 1 |  | Completed | 2019-08-28 | 24.34 | 1 | Andrew Clemons | Completed | 2019-09-24 | 6.46 | 1 | Darlynn Lacap | Completed | 2019-10-18 | 5 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-04 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5.79 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-10-18 | 4.13 | 1 | Andrew Clemons | Completed | 2019-09-30 17:03 |  | 2019-09-30 | 9 | 2 | Christina Horton | Completed | [10 empty] | 22.42 | [11 empty] | 2019-08-23 | 2019-10-11 | MENLO PARK | Menlo Park | https://heliotrack.completesolar.com/job.php?action=review&jobID=26019 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26019 | https://completesolar.sugarondemand.com/#Opportunities/43d400c4-acea-11e9-9cfc-02ae981fbade | Micah Myers |  | 2019-05-30 | OSullivan Green Solar | 43d400c4-acea-11e9-9cfc-02ae981fbade | 13 | 24 | -15 | -2 | 5 | 5 | 5 | -7
26149 | PIP_APPROVED | PIP_APPROVED | 3630 Tumbleweed Drive | Palmdale | CA | 93550 | Ricardo Espinosa | 2019-08-05 12:21 | 6615337346 | ricardo-e@sbcglobal.net | Lucy Espinosa | 6614334236 |  | 7885 | 0.132 | Bill Angevine | 2019-08-05 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-05 | 2019-06-08 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-17 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-16 07:00 | 2019-08-21 | 11.92 | 2 | Marcia Garay | Completed | 2019-08-22 | 1.13 | 2 | Daniel Speegle | Completed | 2019-09-09 | 10.79 | 1 | Ara Sotto | Completed | 2019-09-17 | 5.75 | 5 | Brian Le | Completed | 2019-08-29 | 3.96 | 3 | Ernesto Enriquez | Completed | 2019-09-06 | 5.21 | 0 | Ernesto Enriquez | Completed | 2019-09-17 | 2.42 | 1 | Ara Sotto | Completed | 2019-10-01 | 10.54 | 2 | Ara Sotto | Completed | 2019-09-09 | 7.75 | 2 | Brian Le | Completed | 2019-08-27 | 3.17 | 2 | Marcia Garay | Completed | 2019-08-23 | 0.79 | 1 |  | Completed | 2019-08-30 | 5.75 | 1 | Jeremiah Liend | Completed |  | 26.79 | 1 | Marcia Garay | Current | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 7.04 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.96 | 1 | Jeremiah Liend | Completed | 2019-09-18 16:50 | 2019-08-27 | 2019-09-19 | 2.25 | 2 | Ara Sotto | Completed | [10 empty] | 11.42 | [11 empty] | 2019-08-29 | 2019-10-01 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26149 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26149 | https://completesolar.sugarondemand.com/#Opportunities/1494a206-b7b6-11e9-accc-022c40d974e6 | Solar Raze | Emily Bowden | 2019-06-04 | JK Solar | 1494a206-b7b6-11e9-accc-022c40d974e6 | 2 | 14 | 7 | -2 | 5 | 5 | 5 | 15
27562 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 67799 20th Avenue | Desert Hot Springs | CA | 92241 | Ismara S Luevano | 2019-08-08 14:56 | 7609729856 | socorro270@msn.com | Joe Luevano | 7609729856 |  | 15940 | 0.13 | Chris Peaslee | 2019-08-08 | 8.54 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-31 | 2019-08-08 15:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-09-17 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-13 07:00 | 2019-08-13 | 2.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 2.17 | 2 | Daniel Speegle | Completed | 2019-09-06 | 14.88 | 1 | Ara Sotto | Completed | 2019-09-17 | 7 | 5 | Brian Le | Completed | 2019-08-20 | 1.96 | 3 | Andrew Moralez | Completed | 2019-09-06 | 11.88 | 14 | Ernesto Enriquez | Completed | 2019-09-17 | 2.46 | 2 | Ara Sotto | Completed |  | 24.08 | 2 | Ara Sotto | Current | 2019-09-06 | 11.96 | 2 | Brian Le | Completed | 2019-08-20 | 2.96 | 2 | Marcia Garay | Completed | 2019-08-16 | 0.96 | 1 |  | Completed | 2019-08-26 | 6.79 | 1 | Andrew Clemons | Completed | 2019-10-16 | 23.42 | 1 | Marcia Garay | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 12.75 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-16 16:42 | 2019-09-16 | 2019-09-17 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 11.33 | [11 empty] | 2019-09-10 |  | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=27562 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27562 | https://completesolar.sugarondemand.com/#Opportunities/3e47b5d4-ba27-11e9-878b-069e4f790264 | PJB Division |  | 2019-07-31 | Zachary Noah Gamez | 3e47b5d4-ba27-11e9-878b-069e4f790264 | 0 | 34 | 10 | -2 | 5 | 5 | 5 | 18
27732 | PIP_APPROVED | PIP_APPROVED | 446 Buckingham Drive | San Jacinto | CA | 92583 | Primitivo Pedroza | 2019-08-27 19:14 | 9512590248 | primitivopedroza@yahoo.com | Luz Villalpando |  |  | 8665 | 0.145 | Alex Holdridge | 2019-08-15 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-07 | 2019-08-09 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-17 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-17 | 2019-08-28 | 1.63 | 2 | Marcia Garay | Completed | 2019-08-29 | 1.92 | 2 | Daniel Speegle | Completed | 2019-09-05 | 7.63 | 1 | Ara Sotto | Completed | 2019-09-17 | 2.04 | 5 | Brian Le | Completed | 2019-09-05 | 6.05 | 3 | Ernesto Enriquez | Completed | 2019-09-10 | 2.96 | 10 | Ernesto Enriquez | Completed | 2019-09-17 | 0.55 | 1 | Ara Sotto | Completed | 2019-09-18 | 0.96 | 2 | Ara Sotto | Completed | 2019-09-13 | 12.83 | 2 | Brian Le | Completed | 2019-08-28 | 1 | 2 | Marcia Garay | Completed | 2019-08-30 | 1.75 | 1 |  | Completed | 2019-09-16 | 14.83 | 1 | Andrew Clemons | Completed |  | 24.71 | 1 | Marcia Garay | Current | 2019-09-19 | 0.79 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 5.08 | 2 | Marcia Garay | Completed | 2019-09-26 | 1.04 | 1 | Andrew Clemons | Completed | 2019-09-18 16:46 | 2019-09-19 | 2019-09-19 | 2.04 | 2 | Ara Sotto | Completed | [10 empty] | 11.24 | [11 empty] | 2019-09-19 | 2019-09-18 | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27732 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27732 | https://completesolar.sugarondemand.com/#Opportunities/74e4a9e2-bfb5-11e9-8f81-0630baf9dcb8 | SCES Division | JW Pitchford | 2019-08-07 | Green Road Solar Crew | 74e4a9e2-bfb5-11e9-8f81-0630baf9dcb8 | 2 | 1 | 7 | 5 | 5 | 5 | 5 | 22
27764 | SP APPROVED |  | 8035 Marilyn Street | San Bernardino | CA | 92410 | Fennina Espinoza | 2019-08-20 17:14 | 9098005349 | fenespinoza@yahoo.com | Hernando Espinoza | 9098005430 |  | 9979 | 0.17 | Alex Holdridge | 2019-08-20 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-15 | 2019-08-16 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-17 | HelioDesk Rework | SunRun Monthly | [6 empty] | 2019-09-16 07:00 | 2019-08-28 | 6 | 2 | Marcia Garay | Completed | 2019-08-23 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-13 | 10.67 | 1 | Ara Sotto | Completed | 2019-09-17 | 1.79 | 5 | Brian Le | Completed | 2019-08-29 | 0.67 | 3 | Andrew Moralez | Completed | 2019-09-10 | 7.08 | 14 | Andrew Moralez | Completed | 2019-09-17 | 1.17 | 2 | Ara Sotto | Completed |  | 24.29 | 2 | Ara Sotto | Current | 2019-09-13 | 8.92 | 2 | Brian Le | Completed | 2019-08-30 | 1.88 | 2 | Marcia Garay | Completed | 2019-08-27 | 0.08 | 1 |  | Completed |  | 34.75 | 1 | Andrew Clemons | Current |  | 23.33 | 1 | Marcia Garay | Current |  | 0 | 2 |  | Inactive | [16 empty] | 22.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-19 16:50 | 2019-09-13 | 2019-09-19 | 0.16 | 2 | Ara Sotto | Completed | [10 empty] | 27.88 | [11 empty] | 2019-09-19 |  | HIGHLAND | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=27764 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27764 | https://completesolar.sugarondemand.com/#Opportunities/802220b8-c3a8-11e9-9399-0630baf9dcb8 | Summit Marketing Inc | Matt Cox | 2019-08-08 | Power Town Solar Electric | 802220b8-c3a8-11e9-9399-0630baf9dcb8 | 2 | 34 | 7 | -2 | 5 | 5 | 5 | 15
27950 | PIP_APPROVED | PIP_APPROVED | 2923 Luciernaga Street | Carlsbad | CA | 92009 | Paula Kalustian | 2019-08-17 16:16 | 6195495081 | kalustia@sdsu.edu |  |  |  | 5350 | 0.181 | Alex Holdridge | 2019-08-17 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-16 | 2019-08-17 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Other | NO | 2019-09-17 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-17 12:00 | 2019-08-19 | 0.5 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.92 | 2 | Jethro Andal | Completed | 2019-09-09 | 9.96 | 1 | Christina Horton | Completed | 2019-09-17 | 10.8 | 5 | Brian Le | Completed | 2019-08-22 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-22 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-17 | 0.42 | 1 | Christina Horton | Completed | 2019-10-04 | 13 | 2 | Christina Horton | Completed | 2019-08-21 | 0.08 | 2 | Brian Le | Completed | 2019-08-22 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 0.08 | 1 |  | Completed | 2019-09-16 | 14.5 | 1 | Andrew Clemons | Completed | 2019-09-17 | 0.5 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-26 | 3.79 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 4.88 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Noe Gomez | Completed | 2019-09-20 11:19 |  | 2019-09-20 | 3.04 | 2 | Christina Horton | Completed | [10 empty] | 14.83 | [11 empty] | 2019-09-13 | 2019-10-04 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=27950 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27950 | https://completesolar.sugarondemand.com/#Opportunities/07baf362-c145-11e9-87f1-0630baf9dcb8 | Perry Ustick |  | 2019-08-14 | Infinity Energy Inc | 07baf362-c145-11e9-87f1-0630baf9dcb8 | 3 | 17 | 0 | -2 | 5 | 5 | 5 | 8
28217 | PIP_APPROVED | PIP_APPROVED | 3995 North Golden Avenue | San Bernardino | CA | 92404 | Darrel Batey | 2019-08-31 13:32 | 9097232518 | melaniebatey532@gmail.com | MELANIE L BATEY | 9096596871 |  | 9220 | 0.176 | Michael Marlaire | 2019-08-29 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-27 | 2019-08-29 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-17 07:00 | 2019-08-31 | 0.66 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 3 | 2 | Daniel Speegle | Completed | 2019-09-11 | 2.75 | 1 | Ara Sotto | Completed | 2019-09-17 | 1.96 | 5 | Brian Le | Completed | 2019-09-10 | 1.92 | 3 | Ernesto Enriquez | Completed | 2019-09-10 | 0 | 1 | Ernesto Enriquez | Completed | 2019-09-17 | 0.38 | 2 | Ara Sotto | Completed | 2019-09-20 | 3 | 2 | Ara Sotto | Completed | 2019-09-13 | 2.83 | 2 | Brian Le | Completed | 2019-09-10 | 2.13 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 1 |  | Completed | 2019-09-10 | 2.13 | 1 | Andrew Clemons | Completed | 2019-09-27 | 8.33 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 2.75 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.04 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 3 | 1 | Jeremiah Liend | Completed | 2019-09-19 16:53 |  | 2019-09-17 | 0.13 | 2 | Ara Sotto | Completed | [10 empty] | 3.7 | [11 empty] | 2019-09-11 | 2019-09-20 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=28217 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28217 | https://completesolar.sugarondemand.com/#Opportunities/3d04bcda-cacb-11e9-9d26-022c40d974e6 | 300 Stars Inc | Oscar Hernandez | 2019-08-27 | Power Town Solar Electric | 3d04bcda-cacb-11e9-9d26-022c40d974e6 | 0 | 3 | 10 | 2 | 5 | 5 | 5 | 22
28236 | PIP_APPROVED | PIP_APPROVED | 12741 Pacoima Road | Victorville | CA | 92392 | Laurie Angel | 2019-08-28 17:00 | 7144603889 | sunflowerlove247@gmail.com |  |  |  | 10898 | 0.114 | Bill Angevine | 2019-08-28 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-27 | 2019-08-28 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-16 07:00 | 2019-08-29 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 3.92 | 2 | Daniel Speegle | Completed | 2019-09-17 | 7.79 | 1 | Ara Sotto | Completed | 2019-09-17 | 1.75 | 5 | Brian Le | Completed | 2019-09-06 | 0 | 3 | Andrew Moralez | Completed | 2019-09-10 | 2.17 | 10 | Andrew Moralez | Completed | 2019-09-17 | 1.17 | 2 | Ara Sotto | Completed | 2019-09-26 | 7.08 | 2 | Ara Sotto | Completed | 2019-09-13 | 3.29 | 2 | Brian Le | Completed | 2019-09-06 | 1 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.88 | 1 |  | Completed | 2019-09-10 | 3.13 | 1 | Jill Allen | Completed | 2019-09-18 | 2.54 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 2.96 | 1 | Andrew Clemons | Completed | 2019-09-18 16:47 | 2019-09-30 | 2019-09-19 | 2.21 | 2 | Ara Sotto | Completed | [10 empty] | 2.87 | [11 empty] | 2019-09-20 | 2019-09-26 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=28236 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28236 | https://completesolar.sugarondemand.com/#Opportunities/e895dcaa-c9ef-11e9-9598-02ae981fbade | SCES Division | Cody Booth | 2019-08-27 | HDM Electric Inc | e895dcaa-c9ef-11e9-9598-02ae981fbade | 2 | 9 | 7 | -2 | 5 | 5 | 5 | 15
28290 | PIP_APPROVED | PIP_APPROVED | 11 Shasta Court | Oceanside | CA | 92057 | David Kissinger | 2019-09-06 09:33 | 7608280217 | dgkissinger@gmail.com | Patricia Kissinger | 7604457883 |  | 5630 |  | Chad Malloy | 2019-09-06 | 4.27 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-09-03 | 2019-09-04 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-17 | PTO Received | Cash | [6 empty] | 2019-09-16 07:00 | 2019-09-06 | 0 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 1 | 2 | Daniel Speegle | Completed | 2019-09-11 | 2.08 | 1 | Christina Horton | Completed | 2019-09-16 | 1.04 | 5 | Brian Le | Completed | 2019-09-09 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-11 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-17 | 1.13 | 1 | Christina Horton | Completed | 2019-10-21 | 24.33 | 2 | Christina Horton | Completed | 2019-09-10 | 0.88 | 2 | Brian Le | Completed | 2019-09-09 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-09-09 | 0.08 | 1 |  | Completed | 2019-09-11 | 2.08 | 1 | Andrew Clemons | Completed | 2019-09-19 | 3.17 | 1 | Darlynn Lacap | Completed |  | 0.04 | 2 | Noe Gomez | Current | [15 empty] | 2019-09-19 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 1.17 | 2 | Ashley Rockwood | Completed |  | 21.08 | 2 | Darlynn Lacap | Current |  | 21.08 | 1 | Noe Gomez | Current |  | 2019-10-07 | 2019-09-17 | 0.29 | 2 | Christina Horton | Completed | [10 empty] | 3 | [11 empty] | 2019-09-25 | 2019-10-08 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=28290 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28290 | https://completesolar.sugarondemand.com/#Opportunities/07420216-d0c4-11e9-abd2-0630baf9dcb8 | Alan Moberg |  | 2019-08-29 | Infinity Energy Inc | 07420216-d0c4-11e9-abd2-0630baf9dcb8 | 0 | 34 | 10 | -2 | 5 | 5 | 5 | 18
28292 | PIP_APPROVED | PIP_APPROVED | 2695 Cincinnati Street West | San Bernardino | CA | 92407 | Joseph D Busby | 2019-08-31 11:13 | 9098380068 | sandybusby16@verizon.net | Sandra Busby | 9098385154 |  | 5369 | 0.155 | Alex Holdridge | 2019-08-31 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-30 | 2019-08-31 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-17 07:00 | 2019-09-03 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-09-05 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-11 | 3.71 | 1 | Ara Sotto | Completed | 2019-09-17 | 2.04 | 5 | Brian Le | Completed | 2019-09-10 | 2.08 | 3 | Ernesto Enriquez | Completed | 2019-09-10 | 0.08 | 1 | Ernesto Enriquez | Completed | 2019-09-17 | 0.38 | 1 | Ara Sotto | Completed | 2019-09-24 | 5.25 | 2 | Ara Sotto | Completed | 2019-09-13 | 5.79 | 2 | Brian Le | Completed | 2019-09-05 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-06 | 0.75 | 1 |  | Completed | 2019-09-10 | 3.04 | 1 | Jill Allen | Completed | 2019-09-18 | 1.54 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.08 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 2.96 | 1 | Noe Gomez | Completed | 2019-09-17 16:52 | 2019-09-25 | 2019-09-19 | 2.04 | 2 | Ara Sotto | Completed | [10 empty] | 0.13 | [11 empty] | 2019-09-11 | 2019-09-24 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=28292 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28292 | https://completesolar.sugarondemand.com/#Opportunities/fd76091a-cc1a-11e9-96b0-0630baf9dcb8 | 300 Stars Inc | Oscar Hernandez | 2019-08-29 | Green Road Solar Crew | fd76091a-cc1a-11e9-96b0-0630baf9dcb8 | 2 | 7 | 7 | -2 | 5 | 5 | 5 | 15
24435 | PIP_APPROVED | PIP_APPROVED | 15761 Joshua Road | Apple Valley | CA | 92307 | Elizabeth Keith | 2019-04-10 08:37 | 7604906411 | lizkeith7690@gmail.com | Rocky Keith | 7602472080 |  | 13191 | 0.118 | Bill Angevine | 2019-04-10 | 7.015 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-04-08 | 2019-04-09 14:00 | Q.PEAK-G4.1 305 | 305 | 23 | Hanwha Q CELLS | SolarEdge | SE6000H-US RGM | Ground Mount | Line-side Tap | 2019-09-16 | Final Permit | SunRun Monthly |  | 0 |  |  |  |  | 2019-08-30 07:00 | 2019-04-15 | 3.04 | 2 | Marcia Garay | Completed | 2019-04-18 | 3.13 | 2 | Daniel Speegle | Completed | 2019-04-12 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-16 | 59.96 | 5 | Brian Le | Completed | 2019-04-30 | 5.75 | 3 | Ernesto Enriquez | Completed | 2019-08-21 | 73.21 | 14 | Ernesto Enriquez | Completed | 2019-09-16 | 19.84 | 2 | Ara Sotto | Completed | 2019-09-18 | 2 | 2 | Ara Sotto | Completed | 2019-06-20 | 42.88 | 2 | Brian Le | Completed | 2019-04-19 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-04-22 | 2.13 | 1 |  | Completed | 2019-04-26 | 6.04 | 1 | Noe Gomez | Completed | 2019-08-30 | 5.14 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.88 | 2 | Jeremiah Liend | Completed | [16 empty] | 6.92 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-24 15:25 |  | 2019-09-26 | 2.75 | 2 | Ara Sotto | Completed | 2019-09-23 | 15.46 | 1 | Ara Sotto | Completed | 2019-08-29 | 0.79 | 2 | Darlynn Lacap | Completed | 30.8 | [11 empty] | 2019-05-30 | 2019-09-18 | APPLE VALLEY | Apple Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=24435 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24435 | https://completesolar.sugarondemand.com/#Opportunities/861173e4-5ba6-11e9-ada9-022c40d974e6 | SCES Division | Cody Booth | 2019-04-08 | HDM Electric Inc | 861173e4-5ba6-11e9-ada9-022c40d974e6 | 3 | 2 | 0 | 4 | 5 | 5 | 5 | 14
27251 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 7240 Mimosa Drive | Carlsbad | CA | 92011 | Blaine Staggs | 2019-08-14 12:33 | 5209758066 | blainestaggs@yahoo.com | Sarah Staggs | 6198847755 |  | 4630 | 0.183 | Chad Malloy | 2019-08-14 | 3.355 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-24 | 2019-07-31 12:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | EDPM Membrane | NO | 2019-09-16 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-16 07:00 | 2019-08-15 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 1.21 | 2 | Jethro Andal | Completed | 2019-09-03 | 10.79 | 1 | Ara Sotto | Completed | 2019-09-16 | 10 | 5 | Brian Le | Completed | 2019-08-19 | 0.54 | 3 | Andrew Moralez | Completed | 2019-08-19 | 0 | 15 | Andrew Moralez | Completed | 2019-09-16 | 0.92 | 1 | Ara Sotto | Completed |  | 25.04 | 2 | Ara Sotto | Current | 2019-09-10 | 3.08 | 2 | Brian Le | Completed | 2019-08-26 | 1.91 | 2 | Darlynn Lacap | Completed | 2019-08-17 | 0.33 | 1 |  | Completed | 2019-08-26 | 5.63 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 8.83 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-23 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.83 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1.79 | 1 | Andrew Clemons | Completed | 2019-09-19 16:06 |  | 2019-09-19 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 11.42 | [11 empty] | 2019-09-10 |  | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=27251 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27251 | https://completesolar.sugarondemand.com/#Opportunities/3796c14c-beca-11e9-b1e0-0630baf9dcb8 | Perry Ustick |  | 2019-07-18 | Zachary Noah Gamez | 3796c14c-beca-11e9-b1e0-0630baf9dcb8 | 3 | 35 | 0 | -2 | 5 | 5 | 5 | 8
27338 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 301 Yacon Street | Vista | CA | 92083 | Jose Camacho | 2019-07-24 16:41 | 7606660496 | jose55187@gmail.com | Magdalena Camacho | 760 666 0496 | camachomalena.55@gmail.com | 7997 | 0.145 | Chad Malloy | 2019-07-24 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-23 | 2019-07-24 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-09-16 | Installation Complete | SunRun Monthly | 0 | 0 | 0 |  | 0 | 1 | 2019-09-16 07:00 | 2019-07-25 | 0.75 | 2 | Marcia Garay | Completed | 2019-07-29 | 2 | 2 | Daniel Speegle | Completed | 2019-08-06 | 3.21 | 1 | Christina Horton | Completed | 2019-09-16 | 23.14 | 5 | Brian Le | Completed | 2019-08-28 | 19.08 | 3 | Andrew Moralez | Completed | 2019-08-28 | 0.08 | 0 | Andrew Moralez | Completed | 2019-09-16 | 0.46 | 2 | Christina Horton | Completed |  | 25.08 | 2 | Christina Horton | Current | 2019-08-05 | 2.08 | 2 | Brian Le | Completed | 2019-08-01 | 0 | 2 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 1 |  | Completed | 2019-08-01 | 0.04 | 1 | Andrew Clemons | Completed | 2019-10-15 | 21.46 | 1 | Marcia Garay | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 17.25 | 1 | Christina Horton | Inactive | 2019-07-29 | 0.04 | 2 | Marcia Garay | Completed | 20.26 | [11 empty] | 2019-08-28 |  | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27338 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27338 | https://completesolar.sugarondemand.com/#Opportunities/7548033e-ae6c-11e9-911c-022c40d974e6 | Alexis Cain |  | 2019-07-22 | Infinity Energy Inc | 7548033e-ae6c-11e9-911c-022c40d974e6 |  | 35 | -25 | -2 | 5 | 5 | 5 | -17
27928 | PIP_APPROVED | PIP_APPROVED | 303 Magdalena Drive | Oceanside | CA | 92057 | Luis Rodriguez | 2019-08-22 12:28 | 7604728993 | Jenrodriguez807@gmail.com |  |  |  | 5611.8 |  | Chad Malloy | 2019-08-22 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-08-20 | 2019-08-22 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000A-US RGM | Composite | NO | 2019-09-16 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-16 07:00 | 2019-08-22 | 0 | 2 | Marcia Garay | Completed | 2019-08-26 | 2.04 | 2 | Daniel Speegle | Completed | 2019-09-09 | 6.38 | 1 | Christina Horton | Completed | 2019-09-16 | 4.59 | 5 | Brian Le | Completed | 2019-08-27 | 0 | 3 | Andrew Moralez | Completed | 2019-08-28 | 1.08 | 10 | Andrew Moralez | Completed | 2019-09-16 | 0.42 | 1 | Christina Horton | Completed | 2019-09-17 | 1 | 2 | Christina Horton | Completed | 2019-08-28 | 0.08 | 2 | Brian Le | Completed | 2019-09-09 | 3.96 | 2 | Marcia Garay | Completed | 2019-08-27 | 0.88 | 1 |  | Completed | 2019-08-30 | 3.71 | 1 | Andrew Clemons | Completed |  | 25.54 | 1 | Marcia Garay | Current | 2019-09-19 | 1.71 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-09-23 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 4.92 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 4.88 | 2 | Marcia Garay | Completed | 2019-10-03 | 2.83 | 1 | Andrew Clemons | Completed |  | 2019-09-23 | 2019-09-17 | 1 | 2 | Christina Horton | Completed | [10 empty] | 5.33 | [11 empty] | 2019-09-11 | 2019-09-17 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27928 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27928 | https://completesolar.sugarondemand.com/#Opportunities/00e8e73e-c513-11e9-bbb7-0630baf9dcb8 | Brett Martinez |  | 2019-08-14 | Infinity Energy Inc | 00e8e73e-c513-11e9-bbb7-0630baf9dcb8 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27187 | PIP_APPROVED | PIP_APPROVED | 4924 Siesta Drive | Oceanside | CA | 92057 | Patrick Mcintyre | 2019-08-14 15:30 | 7605294217 | Patrick.w.mcintyre@gmail.com |  |  |  | 7791 | 0.185 | Michael Marlaire | 2019-07-24 | 4.88 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-20 | 2019-07-23 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-14 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-14 07:00 | 2019-08-15 | 6.92 | 2 | Marcia Garay | Completed | 2019-08-19 | 2.16 | 2 | Daniel Speegle | Completed | 2019-08-26 | 4.96 | 1 | Christina Horton | Completed | 2019-09-14 | 17.38 | 5 | Brian Le | Completed | 2019-08-19 | 0 | 3 | Andrew Moralez | Completed | 2019-08-26 | 5.13 | 10 | Andrew Moralez | Completed | 2019-09-14 | 0.58 | 1 | Christina Horton | Completed | 2019-10-15 | 19.67 | 2 | Christina Horton | Completed | 2019-08-20 | 0.08 | 2 | Brian Le | Completed | 2019-08-20 | 1.08 | 2 | Marcia Garay | Completed | 2019-08-19 | 0 | 1 |  | Completed | 2019-08-29 | 8.17 | 1 | Jill Allen | Completed | 2019-09-24 | 7.04 | 1 | Marcia Garay | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-19 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.71 | 2 | Marcia Garay | Completed |  | 21.08 | 1 | Andrew Clemons | Current |  | 2019-09-20 | 2019-09-17 | 1.58 | 2 | Christina Horton | Completed | [10 empty] | 17.95 | [11 empty] | 2019-09-03 | 2019-10-15 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27187 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27187 | https://completesolar.sugarondemand.com/#Opportunities/e7e791dc-ae23-11e9-8a36-0630baf9dcb8 | Brett Martinez |  | 2019-07-17 | Infinity Energy Inc | e7e791dc-ae23-11e9-8a36-0630baf9dcb8 | 3 | 31 | 0 | -2 | 5 | 5 | 5 | 8
27424 | SP APPROVED |  | 1962 El Prado Avenue | Lemon Grove | CA | 91945 | Israel Tantiangco | 2019-07-31 11:20 | 6199445574 | iszyt@yahoo.com | Mialyn Medina |  |  | 6054 | 0.161 | Chad Malloy | 2019-07-28 | 3.965 | Christina Horton | Solar Power Marketing | Marcia Garay | 2019-07-24 | 2019-07-27 09:30 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-14 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-14 07:00 | 2019-07-31 | 1.29 | 2 | Marcia Garay | Completed | 2019-08-02 | 2.38 | 2 | Daniel Speegle | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-14 | 0.08 | 5 | Brian Le | Completed | 2019-08-06 | 2.29 | 3 | Andrew Moralez | Completed | 2019-08-28 | 16 | 0 | Andrew Moralez | Completed | 2019-09-14 | 0.08 | 1 | Christina Horton | Completed |  | 25.71 | 2 | Christina Horton | Current | 2019-08-29 | 17 | 2 | Brian Le | Completed | 2019-08-06 | 2.38 | 2 | Marcia Garay | Completed | 2019-08-02 | 0.25 | 1 |  | Completed | 2019-08-07 | 3.29 | 1 | Andrew Clemons | Completed |  | 25.71 | 1 | Marcia Garay | Current | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-11 |  | 8.37 | 2 | Christina Horton | Inactive | [10 empty] | 33.76 | [11 empty] | 2019-08-06 |  | LEMON GROVE | Lemon Grove | https://heliotrack.completesolar.com/job.php?action=review&jobID=27424 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27424 | https://completesolar.sugarondemand.com/#Opportunities/01e1e6dc-b202-11e9-88d2-069e4f790264 | Solar Power Marketing |  | 2019-07-24 | Greenday Electric Solar | 01e1e6dc-b202-11e9-88d2-069e4f790264 | 37 | 37 | -25 | -2 | 5 | 5 | 5 | -17
25983 | PIP_APPROVED | PIP_APPROVED | 3864 119th Place | Hawthorne | CA | 90250 | Martin Bernal | 2019-06-07 16:37 | 3103866114 | martinbernal50@yahoo.com |  |  |  | 6556 | 0.126 | Chris Peaslee | 2019-06-04 | 3.965 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-05-29 | 2019-06-03 17:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-13 | PTO Received | SunRun Monthly |  | 0 |  |  | 0 |  | 2019-09-13 07:00 | 2019-06-07 | 2.54 | 2 | Darlynn Lacap | Completed | 2019-06-14 | 4.83 | 2 | Daniel Speegle | Completed | 2019-07-29 | 27.91 | 1 | Ara Sotto | Completed | 2019-09-13 | 3 | 5 | Brian Le | Completed | 2019-06-21 | 2.83 | 3 | Ernesto Enriquez | Completed | 2019-09-09 | 54.08 | 0 | Andrew Moralez | Completed | 2019-09-13 | 2.75 | 1 | Ara Sotto | Completed | 2019-09-18 | 2.79 | 2 | Ara Sotto | Completed | 2019-09-10 | 53.83 | 2 | Brian Le | Completed | 2019-06-24 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 0.08 | 1 |  | Completed | 2019-06-18 | 0 | 1 | Andrew Clemons | Completed | 2019-09-26 | 11.54 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.92 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-02 | 4 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 3.96 | 2 | Ashley Rockwood | Completed |  | 9.29 | 2 | Darlynn Lacap | Current | 2019-10-09 | 0.96 | 1 | Jeremiah Liend | Completed | 2019-09-17 15:26 |  | 2019-09-26 | 8.75 | 2 | Ara Sotto | Completed | [10 empty] | 13.38 | [11 empty] | 2019-06-21 | 2019-09-18 | HAWTHORNE | Hawthorne | https://heliotrack.completesolar.com/job.php?action=review&jobID=25983 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25983 | https://completesolar.sugarondemand.com/#Opportunities/bcb2b056-8735-11e9-a64c-0630baf9dcb8 | CUIC Inc | Marco Valdizan | 2019-05-28 | Green Road Solar Crew | bcb2b056-8735-11e9-a64c-0630baf9dcb8 | 13 | 5 | -15 | -2 | 5 | 5 | 5 | -7
26352 | PIP_APPROVED | PIP_APPROVED | 3028 Calle Juarez | San Clemente | CA | 92673 | Laurie Jacobs | 2019-08-19 15:30 | 9499736087 | lauriejacobs@cox.net | Manuel Bojorquez | 9493618463 |  | 8899 | 0.174 | Ryan Malloy | 2019-06-14 | 7.32 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-13 | 2019-06-14 09:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-09-13 | PTO Received | SunRun Monthly | 1 | 0 |  | 1 | 1 | 1 | 2019-09-13 07:00 | 2019-08-19 | 0.25 | 2 | Darlynn Lacap | Completed | 2019-08-20 | 2.71 | 2 | Daniel Speegle | Completed | 2019-08-29 | 30.71 | 1 | Christina Horton | Completed | 2019-09-13 | 40.67 | 5 | Brian Le | Completed | 2019-08-22 | 8.21 | 3 | Andrew Moralez | Completed | 2019-08-22 | 0 | 1 | Andrew Moralez | Completed | 2019-09-13 | 0.5 | 2 | Christina Horton | Completed | 2019-09-24 | 7.38 | 2 | Christina Horton | Completed | 2019-08-21 | 4.04 | 2 | Brian Le | Completed | 2019-08-19 | 2.08 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 1.58 | 1 |  | Completed | 2019-08-28 | 14.42 | 1 | Andrew Clemons | Completed | 2019-09-25 | 8.09 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-27 | 5.92 | 4 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 5 | Darlynn Lacap | Completed | 2019-08-29 | 13.75 | 12 | Darlynn Lacap | Completed | 2019-09-26 | 1.21 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 6 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Jill Allen | Completed | 2019-09-24 14:48 |  | 2019-09-25 | 7.83 | 2 | Christina Horton | Completed | [10 empty] | 16.79 | 2019-09-05 | 11.83 | 14 | James Fernandez | Completed | 2019-09-03 | 2019-09-05 | 2.38 | 1 | James Fernandez | Completed | 2019-08-23 | 2019-09-24 | SAN CLEMENTE | San Clemente | https://heliotrack.completesolar.com/job.php?action=review&jobID=26352 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26352 | https://completesolar.sugarondemand.com/#Opportunities/f539e9fa-8ee0-11e9-9e59-069e4f790264 | Laura Rea |  | 2019-06-12 | Infinity Energy Inc | f539e9fa-8ee0-11e9-9e59-069e4f790264 | 12 | 11 | -15 | -2 | 5 | 5 | 5 | -7
26523 | PIP_APPROVED | PIP_APPROVED | 84 Providence Street | Worcester | MA | 1604 | Israel Fernandez | 2019-06-21 09:48 | 5084259662 | zinaivelisse@hotmail.com | Zina Fernandez |  | solara solar | 9318 | 0.002 | Hiram Velez | 2019-06-21 | 7.93 | Christina Horton | Solara Solar | Darlynn Lacap | 2019-06-20 | 2019-06-21 09:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE7600H-US RGM | Other | NO | 2019-09-13 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-09-11 07:00 | 2019-06-21 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-06-28 | 3.83 | 2 | Daniel Speegle | Completed | 2019-08-19 | 33.92 | 1 | Christina Horton | Completed | 2019-09-03 | 0.08 | 5 | Christina Horton | Completed | 2019-07-09 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-07-10 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-13 | 5.58 | 2 | Christina Horton | Completed | 2019-09-23 | 6 | 2 | Christina Horton | Completed | 2019-09-12 | 47.58 | 2 | Brian Le | Completed | 2019-07-05 | 3.13 | 2 | Darlynn Lacap | Completed | 2019-07-06 | 2.54 | 1 |  | Completed | 2019-07-05 | 2.79 | 1 | Andrew Clemons | Completed | 2019-09-26 | 11.21 | 1 | Darlynn Lacap | Completed | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-08 | 0.88 | 2 | Ashley Rockwood | Completed |  | 9.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-26 08:29 |  | 2019-09-26 | 0.08 | 2 | Christina Horton | Completed | [10 empty] | 63.47 | 2019-08-06 | 23.42 | 14 | James Fernandez | Completed | 2019-08-20 | 2019-08-28 | 15.92 | 1 | James Fernandez | Completed | 2019-07-24 | 2019-09-23 | Default | Worcester | https://heliotrack.completesolar.com/job.php?action=review&jobID=26523 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26523 | https://completesolar.sugarondemand.com/#Opportunities/4b5801ce-9444-11e9-b953-02ae981fbade | Solara Solar | Von Ayers | 2019-06-18 | Skyline Solar | 4b5801ce-9444-11e9-b953-02ae981fbade | 13 | 10 | -15 | -2 | 5 | 5 | 5 | -7
26917 | PIP_APPROVED | PIP_APPROVED | 8808 Duncan Road | San Diego | CA | 92126 | Yu Yeh | 2019-08-13 17:27 | 6193987514 | yufongyeh@gmail.com |  |  |  | 3484 | 0.2 | Chad Malloy | 2019-08-13 | 2.135 |  | Wilder Jordan | Darlynn Lacap | 2019-07-05 | 2019-07-06 12:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | NO | 2019-09-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-12 07:00 | 2019-08-14 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 1.96 | 2 | Daniel Speegle | Completed | 2019-09-04 | 11.88 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.17 | 5 | Brian Le | Completed | 2019-08-23 | 2.79 | 3 | Ernesto Enriquez | Completed | 2019-08-23 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-13 | 1.5 | 1 | Ara Sotto | Completed | 2019-09-18 | 2.92 | 2 | Ara Sotto | Completed | 2019-09-04 | 11.08 | 2 | Brian Le | Completed | 2019-08-19 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-20 | 2 | 1 |  | Completed | 2019-08-26 | 6 | 1 | Jill Allen | Completed | 2019-09-27 | 11.38 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.75 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-09-23 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 4.92 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 3.92 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Jill Allen | Completed |  | 2019-09-19 | 2019-09-13 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 3.79 | [11 empty] | 2019-09-16 | 2019-09-18 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26917 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26917 | https://completesolar.sugarondemand.com/#Opportunities/2867e16a-be2a-11e9-b855-022c40d974e6 | Wilder Jordan |  | 2019-07-05 | iEnergy ElectricSolar | 2867e16a-be2a-11e9-b855-022c40d974e6 | 0 | 5 | 10 | -2 | 5 | 5 | 5 | 18
27068 | PIP_APPROVED | PIP_APPROVED | 1520 Josephine Court | Madera | CA | 93638 | Leonides Cruz | 2019-07-15 12:51 | 5594745652 | cruzleonides74@yahoo.com | Maria Cruz | 559-871-6531 |  | 6013.8 |  | Abraham SiteTech Vazquez | 2019-07-15 | 3.965 | Christina Horton | Sunmatter Inc | Marcia Garay | 2019-07-11 | 2019-07-12 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-13 | NEM Submitted | Sunlight Financial Loan | 0 | 0 |  |  | 0 | 1 | 2019-09-13 07:00 | 2019-07-17 | 2.08 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.96 | 2 | Daniel Speegle | Completed | 2019-07-26 | 5.92 | 1 | Christina Horton | Completed | 2019-09-13 | 24.59 | 5 | Brian Le | Completed | 2019-07-22 | 2 | 3 | Andrew Moralez | Completed | 2019-08-28 | 26.88 | 0 | Andrew Moralez | Completed | 2019-09-13 | 0.25 | 1 | Christina Horton | Completed | 2019-10-03 | 14.17 | 2 | Christina Horton | Completed | 2019-08-08 | 13.96 | 2 | Brian Le | Completed | 2019-07-19 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-18 | 0 | 1 |  | Completed | 2019-07-20 | 1.38 | 1 | Andrew Clemons | Completed | 2019-09-18 | 3.21 | 1 | Marcia Garay | Completed | 2019-09-19 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-24 | 1 | 2 | Ashley Rockwood | Completed |  | 19.08 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-23 09:20 |  | 2019-09-23 | 6.17 | 2 | Christina Horton | Completed | [10 empty] | 3.87 | [11 empty] | 2019-07-22 | 2019-10-03 | MADERA | Madera | https://heliotrack.completesolar.com/job.php?action=review&jobID=27068 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27068 | https://completesolar.sugarondemand.com/#Opportunities/df781382-a739-11e9-a4ad-0630baf9dcb8 | People Builders |  | 2019-07-11 | Anley Electric | df781382-a739-11e9-a4ad-0630baf9dcb8 | 10 | 20 | -5 | -2 | 5 | 5 | 5 | 3
27128 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 29894 Camino Delores | Menifee | CA | 92586 | John Holmes | 2019-08-06 15:50 | 9512642220 | jbhausner@hotmail.com |  | 9516793722 |  | 6486 | 0.13 | Michael Marlaire | 2019-07-29 | 3.66 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-15 | 2019-07-16 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-13 | PTO Received | SunRun Monthly |  | 0 |  |  |  |  | 2019-09-13 | 2019-08-07 | 0.88 | 2 | Marcia Garay | Completed | 2019-08-14 | 6.33 | 2 | Daniel Speegle | Completed | 2019-08-30 | 14.38 | 1 | Christina Horton | Completed | 2019-09-13 | 14.29 | 5 | Brian Le | Completed | 2019-08-19 | 2.29 | 3 | Andrew Moralez | Completed | 2019-08-29 | 8.96 | 0 | Andrew Moralez | Completed | 2019-09-13 | 0.5 | 1 | Christina Horton | Completed |  | 26.04 | 2 | Christina Horton | Current | 2019-08-20 | 2.87 | 2 | Brian Le | Completed | 2019-08-15 | 3.09 | 2 | Marcia Garay | Completed | 2019-08-15 | 0.87 | 1 |  | Completed | 2019-08-26 | 9.92 | 1 | Andrew Clemons | Completed |  | 26.54 | 1 | Marcia Garay | Current | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-24 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 5 | 2 | Marcia Garay | Completed | 2019-09-26 | 0.96 | 1 | Jeremiah Liend | Completed | 2019-09-20 11:21 | 2019-09-20 | 2019-09-20 | 4.92 | 2 | Christina Horton | Completed | [10 empty] | 7.09 | [11 empty] | 2019-08-19 |  | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27128 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27128 | https://completesolar.sugarondemand.com/#Opportunities/3fbb21d2-b183-11e9-bb07-0630baf9dcb8 | Lindsey Lange | Michael Foster | 2019-07-15 | Infinity Energy Inc | 3fbb21d2-b183-11e9-bb07-0630baf9dcb8 | 7 | 38 | -5 | -2 | 5 | 5 | 5 | 3
27199 | PIP_APPROVED | PIP_APPROVED | 2357 Louise Court | El Cajon | CA | 92020 | Janice Wakefield | 2019-08-13 14:42 | 6194641086 | jwakefield.home@gmail.com |  | 6197266052 |  | 5449 | 0.18 | Ryan Malloy | 2019-07-24 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-19 | 2019-07-22 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000A-US RGM | Composite | NO | 2019-09-13 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-09-13 07:00 | 2019-08-13 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 9.87 | 2 | Jethro Andal | Completed | 2019-08-26 | 9.96 | 1 | Christina Horton | Completed | 2019-09-13 | 15.3 | 5 | Brian Le | Completed | 2019-08-16 | 0.17 | 3 | Ernesto Enriquez | Completed | 2019-09-04 | 14.09 | 0 | Ernesto Enriquez | Completed | 2019-09-13 | 0.46 | 1 | Christina Horton | Completed | 2019-09-25 | 7.92 | 2 | Christina Horton | Completed | 2019-08-20 | 2.87 | 2 | Brian Le | Completed | 2019-08-15 | 3.13 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 1.83 | 1 |  | Completed | 2019-08-26 | 9.67 | 1 | Jill Allen | Completed | 2019-09-27 | 10.33 | 1 | Darlynn Lacap | Completed |  | 18.13 | 2 | Noe Gomez | Current | [15 empty] | 2019-10-09 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-10-15 | 1.04 | 2 | Darlynn Lacap | Completed |  | 5.29 | 1 | Jeremiah Liend | Current | 2019-10-07 14:48 |  | 2019-10-07 | 4.87 | 2 | Christina Horton | Completed | [10 empty] | 23.01 | [11 empty] | 2019-08-16 | 2019-09-18 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=27199 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27199 | https://completesolar.sugarondemand.com/#Opportunities/d1a000c8-ae5d-11e9-b09b-0630baf9dcb8 | Robert Blessing |  | 2019-07-17 | Infinity Energy Inc | d1a000c8-ae5d-11e9-b09b-0630baf9dcb8 | 24 | 12 | -25 | -2 | 5 | 5 | 5 | -17
27227 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 432 Everett Drive | Danville | CA | 94526 | Michael Webb | 2019-07-30 08:24 | 9259894744 | michaelcwebb@comcast.net | Lori Webb |  | loriwebb6@yahoo.com | 16964 | 0.105 | Ricardo Virgen | 2019-07-30 | 10.37 | Christina Horton | CS Direct | Darlynn Lacap |  | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 34 | LONGi Solar | SolarEdge | SE10000A-US RGM | Composite | MPU | 2019-09-13 | Final Permit | SunRun Monthly | 0 | 0 |  | 1 |  | 1 | 2019-09-09 07:00 | 2019-07-30 | 0.08 | 2 | Marcia Garay | Completed | 2019-08-05 | 2.21 | 2 | Jethro Andal | Completed | 2019-09-03 | 9.79 | 1 | Christina Horton | Completed | 2019-09-13 | 6.79 | 5 | Brian Le | Completed | 2019-08-07 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-07 | 0.08 | 1 | Andrew Moralez | Completed | 2019-09-13 | 4.08 | 3 | Christina Horton | Completed |  | 23.58 | 2 | Christina Horton | Current | 2019-09-04 | 6.71 | 2 | Brian Le | Completed | 2019-08-23 | 4.13 | 2 | Darlynn Lacap | Completed | 2019-08-05 | 0.08 | 1 |  | Completed | 2019-08-22 | 2.88 | 1 | Noe Gomez | Completed | 2019-09-17 | 6.46 | 1 | Darlynn Lacap | Completed | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 7.2 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-30 14:50 |  | 2019-09-30 | 3.66 | 2 | Christina Horton | Completed | 2019-09-20 | 2.54 | 1 | Christina Horton | Completed | 2019-08-21 | 2 | 2 | Marcia Garay | Completed | 30.14 | [11 empty] | 2019-08-08 |  | DANVILLE | Danville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27227 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27227 | https://completesolar.sugarondemand.com/#Opportunities/060b7020-b2de-11e9-aa9e-022c40d974e6 | Josh Webb |  | 2019-07-18 | Golden Gate Electric Service | 060b7020-b2de-11e9-aa9e-022c40d974e6 | 10 | 38 | -5 | -2 | 5 | 5 | 5 | 3
27448 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 6736 Corintia Street | Carlsbad | CA | 92009 | Amanda Gretsch | 2019-08-07 14:49 | 7605253201 | chodgk2890@yahoo.com | Christopher Hodgkins |  |  | 7075 | 0.19 | Ryan Malloy | 2019-07-27 | 4.575 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-25 | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE5000H-US RGM | EDPM Membrane | NO | 2019-09-13 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-12 07:00 | 2019-08-07 | 2.42 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.37 | 2 | Jethro Andal | Completed | 2019-08-20 | 12.59 | 1 | Christina Horton | Completed | 2019-09-13 | 6.95 | 5 | Brian Le | Completed | 2019-08-13 | 2.59 | 3 | Andrew Moralez | Completed | 2019-08-13 | 0.08 | 15 | Ernesto Enriquez | Completed | 2019-09-13 | 1.46 | 2 | Christina Horton | Completed |  | 24.21 | 2 | Christina Horton | Current | 2019-08-20 | 0.87 | 2 | Brian Le | Completed | 2019-08-19 | 8.84 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 3.79 | 1 |  | Completed | 2019-09-06 | 20.72 | 1 | Andrew Clemons | Completed | 2019-09-27 | 11.33 | 1 | Darlynn Lacap | Completed | 2019-09-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-25 | 2.75 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Andrew Clemons | Completed | 2019-09-20 10:18 |  | 2019-09-20 | 3.67 | 2 | Christina Horton | Completed | [10 empty] | 26.71 | [11 empty] | 2019-09-04 |  | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=27448 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27448 | https://completesolar.sugarondemand.com/#Opportunities/a28c703c-b0a1-11e9-8f54-02ae981fbade | Perry Ustick |  | 2019-07-25 | Infinity Energy Inc | a28c703c-b0a1-11e9-8f54-02ae981fbade | 7 | 38 | -5 | -2 | 5 | 5 | 5 | 3
27909 | PIP_APPROVED | PIP_APPROVED | 136 North 1st Street | Los Banos | CA | 93635 | Emigdio Gonzalez | 2019-08-17 10:17 | 4084826976 | xpoblano741@gmail.com | Luz Campos | 2095099771 |  | 8076 |  | Ricardo Virgen | 2019-08-17 | 5.49 | Christina Horton | Sunmatter Inc | Marcia Garay | 2019-08-13 | 2019-08-15 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-13 | PTO Received | CalFirst SunRun Prepaid | 0 | 0 |  |  | 0 | 1 | 2019-09-12 | 2019-08-20 | 1.38 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.04 | 2 | Jethro Andal | Completed | 2019-09-04 | 8.92 | 1 | Christina Horton | Completed | 2019-09-12 | 0.17 | 5 | Brian Le | Completed | 2019-08-27 | 4.04 | 3 | Andrew Moralez | Completed | 2019-09-03 | 3.75 | 0 | Andrew Moralez | Completed | 2019-09-13 | 1.38 | 2 | Christina Horton | Completed | 2019-09-25 | 8.04 | 2 | Christina Horton | Completed | 2019-09-04 | 8 | 2 | Brian Le | Completed | 2019-08-22 | 1.04 | 2 | Marcia Garay | Completed | 2019-08-21 | 0.08 | 1 |  | Completed | 2019-08-26 | 2.96 | 1 | Andrew Clemons | Completed | 2019-09-19 | 5.38 | 1 | Marcia Garay | Completed | 2019-09-26 | 0.71 | 2 | Jill Allen | Completed | [15 empty] | 2019-10-03 | 7 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 6.92 | 2 | Ashley Rockwood | Completed |  | 3.04 | 2 | Marcia Garay | Inactive | 2019-10-16 | 2.21 | 1 | Andrew Clemons | Completed | 2019-09-24 10:24 |  | 2019-09-24 | 6.79 | 2 | Christina Horton | Completed | [10 empty] | 13.12 | [11 empty] | 2019-08-27 | 2019-09-25 | LOS BANOS | Los Banos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27909 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27909 | https://completesolar.sugarondemand.com/#Opportunities/c723ec50-c112-11e9-9bf1-02ae981fbade | Sunmatter Inc |  | 2019-08-13 | Peak Energy Electric | c723ec50-c112-11e9-9bf1-02ae981fbade | 11 | 12 | -15 | -2 | 5 | 5 | 5 | -7
28036 | PIP_APPROVED | PIP_APPROVED | 2838 Cebu Court | Carlsbad | CA | 92009 | Laurie Kushner | 2019-08-29 08:26 | 4086210930 | dennytk@aol.com | Dennis Kushner | 7608142773 |  | 5687 | 0.18 | Chris Peaslee | 2019-08-29 | 3.66 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-08-23 | 2019-08-27 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-09-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-13 07:00 | 2019-08-29 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 2.17 | 2 | Daniel Speegle | Completed | 2019-09-05 | 1.67 | 1 | Christina Horton | Completed | 2019-09-13 | 1.58 | 5 | Brian Le | Completed | 2019-09-04 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-04 | 0 | 15 | Andrew Moralez | Completed | 2019-09-13 | 0.33 | 1 | Ara Sotto | Completed | 2019-10-08 | 17.42 | 2 | Ara Sotto | Completed | 2019-09-06 | 0.17 | 2 | Brian Le | Completed | 2019-09-04 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.96 | 1 |  | Completed | 2019-09-10 | 5.04 | 1 | Jill Allen | Completed | 2019-09-27 | 10.25 | 1 | Darlynn Lacap | Completed | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-03 | 4.17 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 5.51 | 2 | Ashley Rockwood | Completed |  | 2.13 | 2 | Darlynn Lacap | Current | 2019-10-18 | 0.71 | 1 | Noe Gomez | Completed | 2019-09-26 13:15 |  | 2019-09-27 | 9.09 | 2 | Ara Sotto | Completed | [10 empty] | 14.49 | [11 empty] | 2019-09-25 | 2019-10-08 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=28036 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28036 | https://completesolar.sugarondemand.com/#Opportunities/4ce40408-ca71-11e9-b663-022c40d974e6 | Perry Ustick |  | 2019-08-17 | Zachary Noah Gamez | 4ce40408-ca71-11e9-b663-022c40d974e6 | 14 | 25 | -15 | -2 | 5 | 5 | 5 | -7
28149 | PIP_APPROVED | PIP_APPROVED | 1019 East Avenue J7 | Lancaster | CA | 93535 | Kristin Luxmore | 2019-08-27 20:27 | 6619659482 | kristin.luxmore@gmail.com |  |  |  | 5875 | 0.131 | Bill Angevine | 2019-08-27 | 3.05 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-23 | 2019-08-27 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-13 | Final Permit | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-13 07:00 | 2019-08-28 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 3.04 | 2 | Daniel Speegle | Completed | 2019-09-04 | 0.83 | 1 | Ara Sotto | Completed | 2019-09-13 | 0.96 | 5 | Brian Le | Completed | 2019-09-05 | 0.96 | 3 | Andrew Moralez | Completed | 2019-09-06 | 1.17 | 1 | Ernesto Enriquez | Completed | 2019-09-13 | 0.5 | 1 | Ara Sotto | Completed | 2019-09-19 | 4.08 | 2 | Ara Sotto | Completed | 2019-09-09 | 0.08 | 2 | Brian Le | Completed | 2019-09-12 | 7.04 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.92 | 1 |  | Completed | 2019-09-06 | 3.08 | 1 | Jill Allen | Completed | 2019-09-26 | 9.5 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 1.83 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-17 16:26 |  | 2019-09-17 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 32.12 | [11 empty] | 2019-09-06 | 2019-09-19 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28149 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28149 | https://completesolar.sugarondemand.com/#Opportunities/9e60e8de-c943-11e9-8297-02ae981fbade | Kevin Adams | Emily Bowden | 2019-08-23 | JK Solar | 9e60e8de-c943-11e9-8297-02ae981fbade | 4 | 6 | 0 | -2 | 5 | 5 | 5 | 8
24981 | PIP_APPROVED | PIP_APPROVED | 1302 Calvin Lane | Escondido | CA | 92025 | Richard Hall | 2019-04-29 11:44 | 7602132484 | kjeanhall@gmail.com | Kara Hall | 760-715-3538 |  | 11701 | 0.223 | Ryan Malloy | 2019-04-29 | 7.93 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-04-24 | 2019-04-26 09:00 | Q.PEAK-G4.1 305 | 305 | 26 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Composite | MPU | 2019-09-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-09-12 07:00 | 2019-04-29 | 0.08 | 2 | Marcia Garay | Completed | 2019-05-20 | 1.87 | 2 | Jethro Andal | Completed | 2019-06-04 | 9.96 | 1 | Christina Horton | Completed | 2019-09-12 | 78.05 | 5 | Ara Sotto | Completed | 2019-08-16 | 0.21 | 3 | Andrew Moralez | Completed | 2019-08-16 | 0 | 15 | Andrew Moralez | Completed | 2019-09-12 | 0.46 | 2 | Christina Horton | Completed | 2019-09-20 | 5.83 | 2 | Christina Horton | Completed | 2019-05-21 | 0.08 | 2 | Brittany Faconti | Completed | 2019-05-21 | 1.13 | 2 | Marcia Garay | Completed | 2019-08-16 | 5.92 | 1 |  | Completed | 2019-05-28 | 4.96 | 1 | Andrew Clemons | Completed | 2019-09-13 | 1.5 | 1 | Marcia Garay | Completed | 2019-09-17 | 0.08 | 2 | Jill Allen | Completed | [15 empty] | 2019-10-01 | 4.67 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 3 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 5.08 | 2 | Marcia Garay | Completed | 2019-10-09 | 2.88 | 1 | Jill Allen | Completed | 2019-09-20 11:43 |  | 2019-09-18 | 1.92 | 2 | Christina Horton | Completed | 2019-09-16 | 3.79 | 1 | Christina Horton | Completed | 2019-05-21 | 0.92 | 2 | Marcia Garay | Completed | 93.55 | 2019-08-05 | 5 | 14 | James Fernandez | Completed | 2019-08-05 | 2019-08-05 | 0.08 | 1 | James Fernandez | Completed | 2019-09-09 | 2019-09-20 | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=24981 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24981 | https://completesolar.sugarondemand.com/#Opportunities/c61eed92-6aae-11e9-a6d1-069e4f790264 | Jordan Maya | Robert Blessing | 2019-04-24 | Infinity Energy Inc | c61eed92-6aae-11e9-a6d1-069e4f790264 | 2 | 8 | 7 | -2 | 5 | 5 | 5 | 15
26022 | SP APPROVED |  | 11598 Wordsworth Road | Moreno Valley | CA | 92557 | Robert Montejano (add on) | 2019-08-21 15:54 | 9514485593 | hikinginwater@gmail.com |  |  |  | 7900 | 0.175 | Shaun Labelle | 2019-08-21 | 6.1 | Ara Sotto | Total HomeSolar | Marcia Garay | 2019-08-19 | 2019-08-21 12:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM |  | MPU | 2019-09-12 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-12 07:00 | 2019-08-21 | 0.04 | 2 | Marcia Garay | Completed | 2019-08-23 | 1.79 | 2 | Daniel Speegle | Completed | 2019-09-04 | 6.83 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.17 | 5 | Brian Le | Completed | 2019-08-27 | 1.13 | 3 | Andrew Moralez | Completed | 2019-09-05 | 5.75 | 25 | Andrew Moralez | Completed | 2019-09-12 | 0.42 | 2 | Ara Sotto | Completed |  | 27.08 | 2 | Ara Sotto | Current | 2019-09-06 | 8.42 | 2 | Brian Le | Completed | 2019-08-24 | 0.46 | 2 | Marcia Garay | Completed | 2019-08-26 | 0.96 | 1 |  | Completed | 2019-08-29 | 4.13 | 1 | Andrew Clemons | Completed |  | 27.54 | 1 | Marcia Garay | Current | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-14 |  | 0 | 2 |  | Inactive |  | 3.54 | 1 | Ara Sotto | Current | 2019-08-28 | 2.79 | 2 | Marcia Garay | Completed | 0.17 | [11 empty] | 2019-10-02 |  | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26022 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26022 | https://completesolar.sugarondemand.com/#Opportunities/8e8b6cf4-c466-11e9-8889-0630baf9dcb8 | Total HomeSolar |  | 2019-05-30 | Zachary Noah Gamez | 8e8b6cf4-c466-11e9-8889-0630baf9dcb8 |  | 39 | -25 | -2 | 5 | 5 | 5 | -17
26830 | PIP_APPROVED | PIP_APPROVED | 52 Surrey Lane | Clifton | NJ | 7012 | Megan Hener | 2019-07-05 11:28 | 8455499146 | meg.hener@gmail.com |  |  |  | 7765.28 |  | Andrew Weber | 2019-07-05 | 7.93 | Christina Horton | Sunlogic Power | Marcia Garay | 2019-07-01 | 2019-07-05 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-09-12 | NEM Submitted | Helioloan Sunlight Financial Loan | 0 | 0 |  |  | 0 |  | 2019-09-12 07:00 | 2019-07-05 | 0.08 | 2 | Marcia Garay | Completed | 2019-07-09 | 1.88 | 2 | Daniel Speegle | Completed | 2019-08-16 | 28.08 | 1 | Christina Horton | Completed | 2019-09-12 | 0.25 | 5 | Brian Le | Completed | 2019-07-15 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-08-14 | 22.17 | 10 | Ernesto Enriquez | Completed | 2019-09-12 | 0.46 | 2 | Christina Horton | Completed | 2019-09-25 | 8.88 | 2 | Christina Horton | Completed | 2019-09-12 | 37.88 | 2 | Brian Le | Completed | 2019-07-10 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-15 | 3.92 | 1 |  | Completed | 2019-07-08 | 0.08 | 1 | Andrew Clemons | Completed | 2019-09-19 | 5.42 | 1 | Marcia Garay | Completed |  | 18.21 | 2 | Andrew Clemons | Current | [15 empty] | 2019-10-18 | 10.96 | 2 | Ashley Rockwood | Completed |  | 1.29 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-30 | 2019-10-03 | 9.38 | 2 | Christina Horton | Completed | [10 empty] | 18.46 | [11 empty] | 2019-07-29 | 2019-09-13 | Default | Clifton | https://heliotrack.completesolar.com/job.php?action=review&jobID=26830 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26830 | https://completesolar.sugarondemand.com/#Opportunities/a3d12c72-9f52-11e9-b42e-02ae981fbade | Anthony Fowler |  | 2019-07-01 | Skyline Solar | a3d12c72-9f52-11e9-b42e-02ae981fbade | 21 | 13 | -25 | -2 | 5 | 5 | 5 | -17
26863 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 26727 Saint Andrews Drive | Menifee | CA | 92586 | Daniel Horn | 2019-08-21 14:51 | 9517044400 | myharleybike1@gmail.com |  |  |  | 6344 | 0.13 | Chris Peaslee | 2019-07-31 | 3.66 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-02 | 2019-07-05 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-09-12 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-12 07:00 | 2019-08-21 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 6.67 | 2 | Daniel Speegle | Completed | 2019-09-03 | 4.92 | 1 | Ara Sotto | Completed |  | 28.17 | 5 | Brian Le | Current | 2019-08-30 | 3.59 | 3 | Andrew Moralez | Completed | 2019-09-06 | 4.29 | 0 | Andrew Moralez | Completed | 2019-09-12 | 1.84 | 1 | Ara Sotto | Completed |  | 27.04 | 2 | Ara Sotto | Current | 2019-09-11 | 4 | 2 | Brian Le | Completed | 2019-09-06 | 2.13 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 1 | 1 |  | Completed | 2019-08-28 | 3.09 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.71 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-12 |  | 0 | 2 |  | Inactive |  | 28.92 | 1 | Ara Sotto | Current | 2019-08-29 | 0.71 | 2 | Darlynn Lacap | Completed | 22.11 | [11 empty] | 2019-08-30 |  | MENIFEE | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=26863 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26863 | https://completesolar.sugarondemand.com/#Opportunities/8c548720-b3c9-11e9-864e-02ae981fbade | PHNX Power |  | 2019-07-02 | Green Road Solar Crew | 8c548720-b3c9-11e9-864e-02ae981fbade |  | 39 | -25 | -2 | 5 | 5 | 5 | -17
27089 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3251 Marbrisa Court | San Jose | CA | 95135 | Charles Mu | 2019-07-15 16:12 | 4083077088 | theachievecenter@gmail.com |  |  |  | 10835 | 0.16 | Ricardo Virgen | 2019-07-15 | 7.015 | Christina Horton | RayoSun Solar | Marcia Garay | 2019-07-12 | 2019-07-13 16:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-11 07:00 | 2019-07-16 | 0.83 | 2 | Marcia Garay | Completed | 2019-07-17 | 1.13 | 2 | Jethro Andal | Completed | 2019-08-19 | 0.79 | 1 | Christina Horton | Completed | 2019-09-11 | 2.92 | 5 | Brian Le | Completed | 2019-07-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-18 | 0.08 | 1 | Andrew Moralez | Completed | 2019-09-12 | 1.5 | 2 | Christina Horton | Completed |  | 27.04 | 2 | Christina Horton | Current | 2019-08-28 | 3.17 | 2 | Brian Le | Completed | 2019-08-23 | 4.67 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.08 | 1 |  | Completed | 2019-08-20 | 1.83 | 1 | Jill Allen | Completed |  | 28.54 | 1 | Marcia Garay | Current | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-03 | 5 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 6.79 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 4.08 | 2 | Marcia Garay | Completed | 2019-10-16 | 2.25 | 1 | Andrew Clemons | Completed | 2019-09-25 10:20 | 2019-09-25 | 2019-09-26 | 9.83 | 2 | Christina Horton | Completed | [10 empty] | 33.37 | [11 empty] | 2019-07-19 |  | SAN JOSE | San Jose | https://heliotrack.completesolar.com/job.php?action=review&jobID=27089 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27089 | https://completesolar.sugarondemand.com/#Opportunities/f3d4500e-a755-11e9-97b7-0630baf9dcb8 | RayoSun Solar |  | 2019-07-12 | OSullivan Green Solar | f3d4500e-a755-11e9-97b7-0630baf9dcb8 | 14 | 39 | -15 | -2 | 5 | 5 | 5 | -7
27444 | PIP_APPROVED | PIP_APPROVED | 1122 East Avenue J5 | Lancaster | CA | 93535 | Cyndi Porteus | 2019-07-26 16:15 | 6616748627 | cndbakes419@yahoo.com |  |  |  | 8261 | 0.135 | Bill Angevine | 2019-07-26 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-25 | 2019-07-26 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | NO | 2019-09-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-09-12 07:00 | 2019-07-29 | 0.71 | 2 | Marcia Garay | Completed | 2019-07-30 | 1.13 | 2 | Daniel Speegle | Completed | 2019-07-30 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.21 | 5 | Brian Le | Completed | 2019-07-31 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-01 | 0.08 | 1 | Andrew Moralez | Completed | 2019-09-12 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-16 | 1.88 | 2 | Ara Sotto | Completed | 2019-09-06 | 19.96 | 2 | Brian Le | Completed | 2019-08-08 | 1.5 | 2 | Marcia Garay | Completed | 2019-07-31 | 0.87 | 1 |  | Completed | 2019-08-09 | 2.58 | 1 | Andrew Clemons | Completed |  | 27.54 | 1 | Marcia Garay | Current | 2019-09-17 | 0.88 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-20 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.92 | 2 | Ashley Rockwood | Completed |  | 20.25 | 2 | Marcia Garay | Current | 2019-09-26 | 2.96 | 1 | Jill Allen | Completed | 2019-09-18 16:48 | 2019-08-19 | 2019-09-19 | 4.96 | 2 | Ara Sotto | Completed | [10 empty] | 6.08 | 2019-09-04 | 9.13 | 14 | James Fernandez | Completed | 2019-08-30 | 2019-09-04 | 6.88 | 1 | James Fernandez | Completed | 2019-08-02 | 2019-09-15 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27444 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27444 | https://completesolar.sugarondemand.com/#Opportunities/1fbf9fe0-affb-11e9-bfc7-022c40d974e6 | SCES Division | Cody Booth | 2019-07-25 | HDM Electric Inc | 1fbf9fe0-affb-11e9-bfc7-022c40d974e6 | 7 | 4 | -5 | 0 | 5 | 5 | 5 | 5
27612 | PIP_APPROVED | PIP_APPROVED | 29372 Via Acaso Drive | Laguna Niguel | CA | 92677 | Michael Day | 2019-08-27 14:51 | 9496130099 | mbday11@gmail.com | MACKENZIE L DAY | 9496130100 |  | 11362 | 0.19 | Shaun Labelle | 2019-08-07 | 7.93 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-08-02 | 2019-08-07 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE6000H-US RGM |  | MPU | 2019-09-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-12 07:00 | 2019-08-27 | 1.88 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 3.83 | 2 | Daniel Speegle | Completed | 2019-09-11 | 8.12 | 1 | Ara Sotto | Completed | 2019-09-12 | 0.17 | 5 | Brian Le | Completed | 2019-08-29 | 2.21 | 3 | Ernesto Enriquez | Completed | 2019-08-29 | 7 | 5 | Ernesto Enriquez | Completed | 2019-09-12 | 6.26 | 2 | Ara Sotto | Completed | 2019-09-13 | 1.04 | 2 | Ara Sotto | Completed | 2019-09-12 | 17.96 | 2 | Brian Le | Completed | 2019-08-27 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 0.83 | 1 |  | Completed | 2019-09-12 | 14.8 | 1 | Andrew Clemons | Completed | 2019-09-27 | 15.1 | 1 | Darlynn Lacap | Completed | 2019-09-16 | 0.63 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-18 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-09-20 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-09-26 | 0.08 | 2 | Zedel Morgan | Completed |  | 0 | 1 |  | Inactive |  | 2019-08-30 | 2019-09-13 | 0.08 | 2 | Ara Sotto | Completed |  | 29.96 | 1 | Ara Sotto | Current | 2019-08-29 | 0 | 2 | Darlynn Lacap | Completed | 3.04 | [11 empty] | 2019-08-29 | 2019-09-13 | LAGUNA NIGUEL | Laguna Niguel | https://heliotrack.completesolar.com/job.php?action=review&jobID=27612 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27612 | https://completesolar.sugarondemand.com/#Opportunities/46d59cfe-b97b-11e9-a84f-069e4f790264 | Peyton Bennett |  | 2019-08-02 | Power Town Solar Electric | 46d59cfe-b97b-11e9-a84f-069e4f790264 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27943 | SP APPROVED |  | 4760 Zelda Avenue | La Mesa | CA | 91942 | Gerald Cox | 2019-08-21 16:21 | 6197970488 | gdc2013@cox.net | Lynn Cox | 6194600116 |  | 5667 | 0.19 | Ryan Malloy | 2019-08-21 | 3.355 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-08-16 | 2019-08-21 12:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-12 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-12 07:00 | 2019-08-22 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 0.79 | 2 | Daniel Speegle | Completed | 2019-09-04 | 6.96 | 1 | Ara Sotto | Completed | 2019-09-12 | 10.04 | 5 | Brian Le | Completed | 2019-08-26 | 1.08 | 3 | Andrew Moralez | Completed | 2019-08-26 | 0 | 5 | Andrew Moralez | Completed | 2019-09-12 | 0.29 | 1 | Ara Sotto | Completed |  | 27.21 | 2 | Ara Sotto | Current | 2019-09-05 | 2.75 | 2 | Brian Le | Completed | 2019-08-23 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 0 | 1 |  | Completed | 2019-08-29 | 3.71 | 1 | Jill Allen | Completed | 2019-09-27 | 10.13 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-04 |  | 19.29 | 2 | Ara Sotto | Current | [10 empty] | 11.97 | [11 empty] | 2019-09-03 |  | LA MESA | La Mesa | https://heliotrack.completesolar.com/job.php?action=review&jobID=27943 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27943 | https://completesolar.sugarondemand.com/#Opportunities/59888c40-c46a-11e9-b17e-069e4f790264 | Blake Sanders | Thomas Noble | 2019-08-14 | Zachary Noah Gamez | 59888c40-c46a-11e9-b17e-069e4f790264 | 39 | 39 | -25 | -2 | 5 | 5 | 5 | -17
28080 | PIP_APPROVED | PIP_APPROVED | 37129 Agate Court | Palmdale | CA | 93550 | Kenneth Casper | 2019-08-22 14:46 | 6619927079 | ken6670@att.net |  | 6612721346 |  | 7337 | 0.15 | Bill Angevine | 2019-08-22 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-20 | 2019-08-22 12:00 | LR6-60PE-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-11 12:00 | 2019-08-23 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 1.13 | 2 | Daniel Speegle | Completed | 2019-09-11 | 7.63 | 1 | Ara Sotto | Completed | 2019-09-12 | 2.08 | 5 | Brian Le | Completed | 2019-08-29 | 1.75 | 3 | Andrew Moralez | Completed | 2019-09-06 | 2.04 | 5 | Ernesto Enriquez | Completed | 2019-09-12 | 1.42 | 1 | Ara Sotto | Completed | 2019-09-26 | 9.92 | 2 | Ara Sotto | Completed | 2019-09-09 | 3.04 | 2 | Brian Le | Completed | 2019-08-27 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.96 | 1 |  | Completed | 2019-08-29 | 3 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.33 | 1 | Darlynn Lacap | Completed | 2019-09-16 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-19 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 8 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1 | 1 | Noe Gomez | Completed | 2019-09-16 14:55 |  | 2019-09-17 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 6 | [11 empty] | 2019-09-11 | 2019-09-26 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=28080 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28080 | https://completesolar.sugarondemand.com/#Opportunities/3f5acbaa-c526-11e9-a246-069e4f790264 | SCES Division |  | 2019-08-20 | JK Solar | 3f5acbaa-c526-11e9-a246-069e4f790264 | 5 | 14 | -5 | -2 | 5 | 5 | 5 | 3
24861 | PIP_APPROVED | PIP_APPROVED | 641 Taper Drive | Seal Beach | CA | 90740 | Mike Wurmlinger | 2019-07-12 15:06 | 5624139008 | mikewurmlinger@yahoo.com | Kim Wurmlinger | 5625378787 |  | 7953 |  | Alex Holdridge | 2019-06-18 | 4.88 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-13 | 2019-06-17 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | MPU | 2019-09-11 | PTO Received | SVN Loan | 0 | 0 |  |  | 1 | 1 | 2019-09-11 07:00 | 2019-07-15 | 3.71 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 3.08 | 2 | Daniel Speegle | Completed | 2019-08-27 | 29.96 | 1 | Christina Horton | Completed | 2019-09-11 | 33.25 | 5 | Brian Le | Completed | 2019-07-25 | 5.79 | 3 | Andrew Moralez | Completed | 2019-08-27 | 23.17 | 0 | Andrew Moralez | Completed | 2019-09-11 | 0.58 | 1 | Christina Horton | Completed | 2019-09-18 | 4.67 | 2 | Christina Horton | Completed | 2019-07-25 | 6.67 | 2 | Brian Le | Completed | 2019-07-16 | 0.16 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 0.92 | 1 |  | Completed | 2019-07-20 | 3.29 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.38 | 1 | Darlynn Lacap | Completed |  | 23.25 | 2 | Andrew Clemons | Current | [15 empty] | 2019-10-07 | 4.92 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 5 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 4.88 | 2 | Darlynn Lacap | Completed |  | 5.04 | 1 | Andrew Clemons | Current | 2019-09-30 11:17 |  | 2019-09-30 | 5.92 | 2 | Christina Horton | Completed | 2019-09-20 | 7.54 | 1 | Christina Horton | Completed | 2019-07-17 | 0.87 | 2 | Darlynn Lacap | Completed | 22 | 2019-08-02 | 0 | 14 | James Fernandez | Completed | 2019-08-02 | 2019-08-02 | 0 | 1 | James Fernandez | Completed | 2019-07-25 | 2019-09-11 | SEAL BEACH | Seal Beach | https://heliotrack.completesolar.com/job.php?action=review&jobID=24861 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24861 | https://completesolar.sugarondemand.com/#Opportunities/ff9dc216-9211-11e9-8e4a-0630baf9dcb8 | Laura Rea |  | 2019-04-20 | Infinity Energy Inc | ff9dc216-9211-11e9-8e4a-0630baf9dcb8 | 10 | 7 | -5 | -2 | 5 | 5 | 5 | 3
25856 | PIP_APPROVED | PIP_APPROVED | 28 Sachem Avenue | Worcester | MA | 1606 | Christopher Naples | 2019-07-19 20:29 | 5087977599 | christopher.naples@gmail.com | Meagan Naples | 774-253-2319 |  | 9209 |  | Hiram Velez | 2019-06-01 | 9.15 | Christina Horton | Solara Solar | Marcia Garay | 2019-05-29 | 2019-06-01 15:00 | LR6-60PB-305M | 305 | 30 | LONGi Solar | SolarEdge | SE7600H-US RGM |  | NO | 2019-09-11 | NEM Submitted | Sunlight Financial Loan |  | 0 |  |  | 0 |  | 2019-09-11 07:00 | 2019-07-22 | 2.88 | 2 | Marcia Garay | Completed | 2019-07-19 | 0.08 | 2 | Jethro Andal | Completed | 2019-08-19 | 21.29 | 1 | Christina Horton | Completed | 2019-09-05 | 0.08 | 5 | Christina Horton | Completed | 2019-07-24 | 6.04 | 3 | Andrew Moralez | Completed | 2019-07-24 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-11 | 1.88 | 2 | Christina Horton | Completed | 2019-09-18 | 4.83 | 2 | Christina Horton | Completed | 2019-10-18 | 46.92 | 2 | Brian Le | Completed | 2019-07-22 | 6.08 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.88 | 1 |  | Completed | 2019-07-27 | 4.8 | 1 | Andrew Clemons | Completed |  | 30 | 1 | Marcia Garay | Current | 2019-10-03 | 10.96 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-18 | 24.96 | 2 | Ashley Rockwood | Completed |  | 1.38 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  | 2019-09-13 | 1.75 | 2 | Christina Horton | Completed | [10 empty] | 32.4 | [11 empty] | 2019-08-07 | 2019-09-12 | Default | Worcester | https://heliotrack.completesolar.com/job.php?action=review&jobID=25856 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25856 | https://completesolar.sugarondemand.com/#Opportunities/c027ddfc-8612-11e9-9067-0630baf9dcb8 | Solara Solar |  | 2019-05-23 | Skyline Solar | c027ddfc-8612-11e9-9067-0630baf9dcb8 | 2 | 7 | 7 | -2 | 5 | 5 | 5 | 15
26111 | PIP_APPROVED | PIP_APPROVED | 3147 Blythe Avenue | Highland | CA | 92346 | Yvonne Padilla | 2019-08-15 16:12 | 9095575112 | yvonne.padilla50@gmail.com |  |  |  | 9914 | 0.217 | Shaun Labelle | 2019-07-25 | 6.1 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-23 | 2019-07-25 11:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-11 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-11 07:00 | 2019-08-15 | 3.58 | 2 | Marcia Garay | Completed | 2019-08-28 | 0.83 | 2 | Daniel Speegle | Completed | 2019-09-06 | 5.66 | 1 | Ara Sotto | Completed | 2019-09-11 | 0.08 | 5 | Ara Sotto | Completed | 2019-09-03 | 2.25 | 3 | Andrew Moralez | Completed | 2019-09-03 | 0.16 | 1 | Andrew Moralez | Completed | 2019-09-11 | 0.46 | 2 | Ara Sotto | Completed | 2019-09-16 | 2.96 | 2 | Ara Sotto | Completed | 2019-09-06 | 0.08 | 2 | Brian Le | Completed | 2019-09-06 | 5.54 | 2 | Marcia Garay | Completed | 2019-08-29 | 1.41 | 1 |  | Completed | 2019-09-04 | 4.54 | 1 | Andrew Clemons | Completed |  | 28.54 | 1 | Marcia Garay | Current | 2019-09-16 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-24 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 0.79 | 2 | Ashley Rockwood | Completed |  | 18.25 | 2 | Marcia Garay | Current | 2019-09-26 | 0.96 | 1 | Jeremiah Liend | Completed |  | 2019-09-17 | 2019-09-20 | 7 | 2 | Ara Sotto | Completed | [10 empty] | 32.12 | [11 empty] | 2019-09-04 | 2019-09-15 | SAN BERNARDINO | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=26111 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26111 | https://completesolar.sugarondemand.com/#Opportunities/e4162bc2-af40-11e9-88f8-022c40d974e6 | Summit Marketing Inc |  | 2019-06-01 | HDM Electric Inc | e4162bc2-af40-11e9-88f8-022c40d974e6 | 9 | 5 | -5 | -2 | 5 | 5 | 5 | 3
27582 | PIP_APPROVED | PIP_APPROVED | 1428 Highridge Drive | Oceanside | CA | 92056 | Jennifer Secker | 2019-08-05 17:53 | 7604149771 | Jennifersecker39@att.net | Roy Leafgrcn | 7602658505 |  | 4480 | 0.198 | Michael Marlaire | 2019-08-05 | 2.745 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-08-02 | 2019-08-05 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-11 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-11 07:00 | 2019-08-06 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 3.5 | 2 | Jethro Andal | Completed | 2019-09-06 | 18.5 | 1 | Ara Sotto | Completed | 2019-09-11 | 20.13 | 5 | Brian Le | Completed | 2019-08-10 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-14 | 2.13 | 10 | Andrew Moralez | Completed | 2019-09-11 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-27 | 11.71 | 2 | Ara Sotto | Completed | 2019-08-13 | 0.88 | 2 | Brian Le | Completed | 2019-08-12 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 0.08 | 1 |  | Completed | 2019-08-15 | 3.54 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.33 | 1 | Darlynn Lacap | Completed | 2019-09-16 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-14 | 6.08 | 4 | Darlynn Lacap | Completed | 2019-09-03 | 13 | 5 | Darlynn Lacap | Completed | 2019-09-03 | 0.08 | 12 | Darlynn Lacap | Completed | 2019-09-18 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 2.54 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 4.08 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 0.96 | 1 | Andrew Clemons | Completed |  | 2019-09-17 | 2019-09-17 | 3.75 | 2 | Ara Sotto | Completed | [10 empty] | 8.08 | [11 empty] | 2019-08-26 | 2019-09-27 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27582 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27582 | https://completesolar.sugarondemand.com/#Opportunities/75b03d88-b7e4-11e9-8092-069e4f790264 | Lee Allison |  | 2019-07-31 | Zachary Noah Gamez | 75b03d88-b7e4-11e9-8092-069e4f790264 | 6 | 16 | -5 | -2 | 5 | 5 | 5 | 3
27593 | PIP_APPROVED | PIP_APPROVED | 39356 Landmark Court | Palmdale | CA | 93551 | Martinette Hockman | 2019-08-02 17:08 | 16614784262 | martigirl_47@hotmail.com | Erick Hockman | 6619920690 |  | 16270 | 0.193 | Shaun Labelle | 2019-08-02 | 10.37 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-01 | 2019-08-02 12:00 | LR6-60PB-305M | 305 | 34 | LONGi Solar | SolarEdge | SE10000A-US RGM | Tile Concrete | MPU | 2019-09-11 | NEM Submitted | SunRun Monthly | [6 empty] | 2019-09-09 07:00 | 2019-08-07 | 2.67 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 7 | 2 | Daniel Speegle | Completed | 2019-08-19 | 0.92 | 1 | Ara Sotto | Completed | 2019-09-11 | 7.75 | 5 | Brian Le | Completed | 2019-08-30 | 7 | 3 | Andrew Moralez | Completed | 2019-08-30 | 0 | 0 | Andrew Moralez | Completed | 2019-09-11 | 3.5 | 3 | Ara Sotto | Completed | 2019-10-09 | 20.21 | 2 | Ara Sotto | Completed | 2019-08-29 | 0.17 | 2 | Brian Le | Completed | 2019-08-29 | 2.79 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 0.17 | 1 |  | Completed | 2019-08-21 | 2.96 | 1 | Andrew Clemons | Completed | 2019-09-13 | 5.54 | 1 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-18 | 1 | 2 | Ashley Rockwood | Completed |  | 1.13 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-28 | 2019-10-17 | 0 | 2 | Ara Sotto | Completed | 2019-10-17 | 29.63 | 1 | Ara Sotto | Completed | 2019-08-16 | 0.17 | 2 | Darlynn Lacap | Completed | 9.66 | [11 empty] | 2019-08-30 | 2019-10-09 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27593 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27593 | https://completesolar.sugarondemand.com/#Opportunities/b35f6564-b582-11e9-8db3-069e4f790264 | SCES Division |  | 2019-08-01 | JK Solar | b35f6564-b582-11e9-8db3-069e4f790264 | 0 | 28 | 10 | -2 | 5 | 5 | 5 | 18
27813 | PIP_APPROVED | PIP_APPROVED | 7200 Colony Road | La Mesa | CA | 91942 | Kimya Mahzad | 2019-08-17 07:55 | 5203435334 | rep.kimya@gmail.com |  |  |  | 6165 | 0.18 | Ryan Malloy | 2019-08-17 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-08-13 | 2019-08-16 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-11 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-11 12:00 | 2019-08-20 | 1.33 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.21 | 2 | Jethro Andal | Completed | 2019-08-23 | 2.08 | 1 | Christina Horton | Completed | 2019-09-11 | 13.59 | 5 | Brian Le | Completed | 2019-08-22 | 0.92 | 3 | Ernesto Enriquez | Completed | 2019-08-22 | 0 | 0 | Ernesto Enriquez | Completed | 2019-09-11 | 0.46 | 1 | Christina Horton | Completed | 2019-09-12 | 1.13 | 2 | Christina Horton | Completed | 2019-08-21 | 0.04 | 2 | Brian Le | Completed | 2019-08-21 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 0.04 | 1 |  | Completed | 2019-08-26 | 2.79 | 1 | Andrew Clemons | Completed | 2019-09-27 | 11.88 | 1 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-25 | 9 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 2.83 | 1 | Andrew Clemons | Completed |  | 2019-09-11 | 2019-09-12 | 0.83 | 2 | Christina Horton | Completed | [10 empty] | 1.54 | [11 empty] | 2019-08-22 | 2019-09-12 | LA MESA | La Mesa | https://heliotrack.completesolar.com/job.php?action=review&jobID=27813 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27813 | https://completesolar.sugarondemand.com/#Opportunities/01191106-c0ff-11e9-a57a-022c40d974e6 | Blake Sanders |  | 2019-08-10 | Infinity Energy Inc | 01191106-c0ff-11e9-a57a-022c40d974e6 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27890 | PIP_APPROVED | PIP_APPROVED | 11816 Darby Avenue | Los Angeles | CA | 91326 | Rani Mouchamel | 2019-08-20 07:58 | 8186185724 | rmouchamel@gmail.com |  |  |  | 10772 | 0.131 | Bill Angevine | 2019-08-20 | 7.015 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-08-13 | 2019-08-16 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-11 | Final Permit | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-11 07:00 | 2019-08-20 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 1.92 | 2 | Daniel Speegle | Completed | 2019-09-11 | 13.25 | 1 | Ara Sotto | Completed |  | 36.29 | 5 | Brian Le | Current | 2019-08-27 | 3.04 | 3 | Ernesto Enriquez | Completed | 2019-08-27 | 0 | 0 | Andrew Moralez | Completed | 2019-09-11 | 0.46 | 2 | Ara Sotto | Completed | 2019-09-19 | 6.17 | 2 | Ara Sotto | Completed | 2019-08-29 | 4.92 | 2 | Brian Le | Completed | 2019-08-22 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 1 |  | Completed | 2019-08-28 | 4.17 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.38 | 1 | Darlynn Lacap | Completed | 2019-09-19 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-20 | 0 | 4 | Darlynn Lacap | Completed | 2019-08-20 | 0 | 5 | Darlynn Lacap | Completed | 2019-08-20 | 0 | 12 | Darlynn Lacap | Completed |  | 26.04 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-12 09:46 |  | 2019-09-13 | 2 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-27 | 2019-09-19 | LOS ANGELES | Porter Ranch | https://heliotrack.completesolar.com/job.php?action=review&jobID=27890 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27890 | https://completesolar.sugarondemand.com/#Opportunities/e0983250-c35a-11e9-be54-02ae981fbade | Jordan Litrownik |  | 2019-08-13 | Blalock Electric&Solar | e0983250-c35a-11e9-be54-02ae981fbade | 2 | 8 | 7 | -2 | 5 | 5 | 5 | 15
27901 | PIP_APPROVED | PIP_APPROVED | 5318 Kenyon Avenue | Bakersfield | CA | 93309 | David Gonzalez | 2019-08-15 09:23 | 6613022354 | tacomix91@gmail.com |  |  |  | 7495 | 0.162 | Bill Angevine | 2019-08-15 | 4.575 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-08-13 | 2019-08-14 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-11 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-11 07:00 | 2019-08-15 | 0.25 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 1.96 | 2 | Jethro Andal | Completed | 2019-08-26 | 4.79 | 1 | Christina Horton | Completed | 2019-09-11 | 2 | 5 | Brian Le | Completed | 2019-08-21 | 1.96 | 3 | Andrew Moralez | Completed | 2019-08-29 | 5.83 | 0 | Andrew Moralez | Completed | 2019-09-11 | 0.5 | 1 | Christina Horton | Completed | 2019-09-13 | 2 | 2 | Christina Horton | Completed | 2019-09-09 | 13 | 2 | Brian Le | Completed | 2019-08-20 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0 | 1 |  | Completed | 2019-08-26 | 4.75 | 1 | Andrew Clemons | Completed | 2019-09-27 | 12.33 | 1 | Darlynn Lacap | Completed | 2019-09-16 | 0.63 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-26 | 0.67 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 3.33 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 1.04 | 1 | Noe Gomez | Completed | 2019-09-25 10:22 |  | 2019-09-25 | 10 | 2 | Christina Horton | Completed | [10 empty] | 0 | [11 empty] | 2019-08-21 | 2019-09-13 | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=27901 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27901 | https://completesolar.sugarondemand.com/#Opportunities/fbd88316-bf78-11e9-890c-022c40d974e6 | SCES ADMIN | Ryan Wilcox | 2019-08-13 | Peak Energy Electric | fbd88316-bf78-11e9-890c-022c40d974e6 | 14 | 2 | -15 | 4 | 5 | 5 | 5 | -1
27920 | PIP_APPROVED | PIP_APPROVED | 6986 Mountain Avenue | Highland | CA | 92346 | Todd Churchill | 2019-08-19 13:11 | 5414417348 | toddchurchill28@gmail.com |  |  |  | 11867 | 0.14 | Chris Peaslee | 2019-08-19 | 7.625 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-14 | 2019-08-17 09:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-11 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-11 07:00 | 2019-08-20 | 0.83 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.21 | 2 | Jethro Andal | Completed | 2019-08-19 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-11 | 3.08 | 5 | Brian Le | Completed | 2019-08-26 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-29 | 0.08 | 14 | Andrew Moralez | Completed | 2019-09-11 | 0.46 | 2 | Ara Sotto | Completed | 2019-09-17 | 3.83 | 2 | Ara Sotto | Completed | 2019-09-06 | 9.96 | 2 | Brian Le | Completed | 2019-08-22 | 0.88 | 2 | Marcia Garay | Completed | 2019-08-22 | 0.75 | 1 |  | Completed | 2019-08-27 | 3.63 | 1 | Andrew Clemons | Completed |  | 28.54 | 1 | Marcia Garay | Current | 2019-09-16 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 3.88 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 9 | 2 | Marcia Garay | Completed | 2019-09-26 | 2.96 | 1 | Jeremiah Liend | Completed | 2019-09-12 15:16 |  | 2019-09-16 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 7.71 | [11 empty] | 2019-09-19 | 2019-09-17 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=27920 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27920 | https://completesolar.sugarondemand.com/#Opportunities/82673548-c2bd-11e9-a425-02ae981fbade | Oscar Hernandez |  | 2019-08-14 | Power Town Solar Electric | 82673548-c2bd-11e9-a425-02ae981fbade | 5 | 6 | -5 | -2 | 5 | 5 | 5 | 3
28021 | PIP_APPROVED | PIP_APPROVED | 44251 Maria Circle | Lancaster | CA | 93535 | Marlene Rosales | 2019-08-19 18:55 | 6619986061 | marlen.rosales@hotmail.com |  |  |  | 9109 | 0.13 | Bill Angevine | 2019-08-19 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-17 | 2019-08-19 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-11 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-06 07:00 | 2019-08-20 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 1.04 | 2 | Jethro Andal | Completed | 2019-09-06 | 10.33 | 1 | Ara Sotto | Completed | 2019-09-11 | 0.08 | 5 | Ara Sotto | Completed | 2019-08-22 | 0 | 3 | Andrew Moralez | Completed | 2019-08-30 | 5.83 | 1 | Andrew Moralez | Completed | 2019-09-11 | 3.33 | 1 | Ara Sotto | Completed | 2019-09-27 | 11.88 | 2 | Ara Sotto | Completed |  | 39.96 | 2 | Brian Le | Current | 2019-08-23 | 2.08 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 0.92 | 1 |  | Completed | 2019-08-28 | 4.92 | 1 | Jeremiah Liend | Completed | 2019-09-11 | 3.21 | 1 | Darlynn Lacap | Completed | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.83 | 1 | Jill Allen | Completed | 2019-09-11 16:57 | 2019-09-11 | 2019-09-13 | 2.13 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-23 | 2019-09-26 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=28021 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28021 | https://completesolar.sugarondemand.com/#Opportunities/83ff20e8-c2ed-11e9-90f8-02ae981fbade | Henry Garcia |  | 2019-08-17 | JK Solar | 83ff20e8-c2ed-11e9-90f8-02ae981fbade | 2 | 16 | 7 | -2 | 5 | 5 | 5 | 15
28077 | PIP_APPROVED | PIP_APPROVED | 2097 Sequoia Crest | Vista | CA | 92081 | Rod Steger | 2019-08-21 17:27 | 7604450504 | rod.steger@roadrunner.com |  |  |  | 6803 | 0.185 | Chad Malloy | 2019-08-21 | 4.575 | Ara Sotto | Revo Home Solutions | Marcia Garay | 2019-08-20 | 2019-08-21 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-11 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-09-11 12:00 | 2019-08-22 | 0.79 | 2 | Marcia Garay | Completed | 2019-08-23 | 1.13 | 2 | Daniel Speegle | Completed | 2019-09-04 | 6.71 | 1 | Ara Sotto | Completed | 2019-09-11 | 5.62 | 5 | Brian Le | Completed | 2019-08-27 | 1.08 | 3 | Andrew Moralez | Completed | 2019-09-03 | 4 | 5 | Andrew Moralez | Completed | 2019-09-11 | 0.46 | 1 | Ara Sotto | Completed | 2019-10-08 | 19.25 | 2 | Ara Sotto | Completed | 2019-09-06 | 0.12 | 2 | Brian Le | Completed | 2019-08-28 | 0.83 | 2 | Marcia Garay | Completed | 2019-08-26 | 0.79 | 1 |  | Completed | 2019-08-30 | 4.63 | 1 | Andrew Clemons | Completed | 2019-09-17 | 3.79 | 1 | Marcia Garay | Completed | 2019-09-16 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-28 | 3.88 | 4 | Marcia Garay | Completed | 2019-08-28 | 0 | 5 | Marcia Garay | Completed | 2019-09-04 | 3.96 | 12 | Marcia Garay | Completed | 2019-09-26 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2.13 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 8.92 | 2 | Marcia Garay | Completed | 2019-10-03 | 2.83 | 1 | Andrew Clemons | Completed | 2019-09-25 17:36 |  | 2019-09-25 | 9.79 | 2 | Ara Sotto | Completed | [10 empty] | 8.51 | [11 empty] | 2019-09-04 | 2019-10-08 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=28077 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=28077 | https://completesolar.sugarondemand.com/#Opportunities/88d82dda-c473-11e9-9d1e-0630baf9dcb8 | Alexis Cain | Lauren Wimsatt | 2019-08-20 | Zachary Noah Gamez | 88d82dda-c473-11e9-9d1e-0630baf9dcb8 | 14 | 27 | -15 | -2 | 5 | 5 | 5 | -7
22731 | PIP_APPROVED | PIP_APPROVED | 8120 Trailside Road | San Diego | CA | 92127 | Mahmoud Zarei | 2019-09-10 10:00 | 7608457644 | mbz@meponline.com | Gita Zarei | 7608453514 |  | 10962 | 0.205 | Ryan Malloy | 2019-02-21 | 9.15 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-02-16 | 2019-02-18 11:00 | Q.PEAK-G4.1 305 | 305 | 30 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Ground Mount | NO | 2019-09-10 | PTO Received | SunRun Monthly | 0 |  |  | 0 |  |  | 2019-09-10 | 2019-09-10 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 4.21 | 2 | Daniel Speegle | Completed | 2019-09-10 | 9.08 | 1 | Ara Sotto | Completed |  | 31.96 | 5 | Brian Le | Current | 2019-09-10 | 26.7 | 3 | Ernesto Enriquez | Completed | 2019-09-10 | 48.41 | 1 | Andrew Moralez | Completed | 2019-09-10 | 8.8 | 2 | Ara Sotto | Completed | 2019-09-24 | 10.42 | 2 | Ara Sotto | Completed | 2019-09-16 | 88.01 | 2 | Brian Le | Completed | 2019-09-11 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 5.54 | 1 |  | Completed | 2019-09-17 | 21.21 | 1 | Jeremiah Liend | Completed | 2019-09-27 | 19.72 | 1 | Darlynn Lacap | Completed | 2019-09-17 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-26 | 12.17 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 1.92 | 2 | Ashley Rockwood | Completed |  | 7.79 | 2 | Darlynn Lacap | Inactive | 2019-10-03 | 2.83 | 1 | Andrew Clemons | Completed |  | 2019-09-12 | 2019-09-10 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 62.12 | [11 empty] | 2019-09-10 | 2019-09-24 | SAN DIEGO COUNTY | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=22731 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=22731 | https://completesolar.sugarondemand.com/#Opportunities/e92f41c2-35f4-11e9-8945-022c40d974e6 | Jordan Litrownik |  | 2019-02-16 | Blalock Electric&Solar | e92f41c2-35f4-11e9-8945-022c40d974e6 | 0 | 14 | 10 | -2 | 5 | 5 | 5 | 18
26433 | PIP_APPROVED | PIP_APPROVED | 561 Fifth Avenue | River Edge | NJ | 7661 | Larentina Carberry | 2019-06-17 14:17 | 2015275825 | larentina.carberry@gmail.com | Thomas Carberry | 2019677392 |  | 9177.52 |  | Andrew Weber | 2019-06-17 | 8.235 | Christina Horton | Sunlogic Power | Marcia Garay | 2019-06-15 | 2019-06-17 12:00 | LR6-60PB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE7600H-US RGM |  | NO | 2019-09-10 | Installation Complete | Sunlight Financial Loan | 0 | 0 |  | 0 | 1 | 0 | 2019-09-10 07:00 | 2019-06-19 | 1.75 | 2 | Marcia Garay | Completed | 2019-06-26 | 5.21 | 2 | Jethro Andal | Completed | 2019-08-12 | 31.13 | 1 | Christina Horton | Completed | 2019-09-10 | 0.08 | 5 | Christina Horton | Completed | 2019-07-09 | 6 | 3 | Andrew Moralez | Completed | 2019-08-09 | 23.17 | 10 | Andrew Moralez | Completed | 2019-09-10 | 0.38 | 2 | Christina Horton | Completed | 2019-09-12 | 1.88 | 2 | Christina Horton | Completed |  | 70.01 | 2 | Brian Le | Current | 2019-06-28 | 1 | 2 | Marcia Garay | Completed | 2019-06-28 | 0.92 | 1 |  | Completed | 2019-07-02 | 3 | 1 | Andrew Clemons | Completed | 2019-09-16 | 4.29 | 1 | Marcia Garay | Completed | 2019-09-12 | 0.08 | 2 | Andrew Clemons | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 21.08 | 2 | Christina Horton | Current | [10 empty] | 37.16 | 2019-08-06 | 24.42 | 14 | James Fernandez | Completed | 2019-08-16 | 2019-08-16 | 10.46 | 1 | James Fernandez | Completed | 2019-07-23 | 2019-09-12 | Default | River Edge | https://heliotrack.completesolar.com/job.php?action=review&jobID=26433 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26433 | https://completesolar.sugarondemand.com/#Opportunities/2cde5c2c-9145-11e9-9c21-069e4f790264 | Anthony Fowler |  | 2019-06-15 | Skyline Solar | 2cde5c2c-9145-11e9-9c21-069e4f790264 | 41 | 2 | -25 | 4 | 5 | 5 | 5 | -11
26478 | PIP_APPROVED | PIP_APPROVED | 15296 Cerritos Street | Fontana | CA | 92336 | Jose Jimenez | 2019-08-06 17:02 | 9095246187 | jjimenez40@live.com |  |  |  | 10360 | 0.155 | Shaun Labelle | 2019-08-06 | 7.015 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-06-17 | 2019-06-18 12:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-10 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-06 07:00 | 2019-08-06 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 4.75 | 2 | Jethro Andal | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-10 | 7 | 5 | Brian Le | Completed | 2019-08-14 | 0.25 | 3 | Ernesto Enriquez | Completed | 2019-08-28 | 9.88 | 12 | Ernesto Enriquez | Completed | 2019-09-10 | 2.25 | 2 | Ara Sotto | Completed | 2019-09-16 | 4.13 | 2 | Ara Sotto | Completed | 2019-08-29 | 11.79 | 2 | Brian Le | Completed | 2019-08-13 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 0.88 | 1 |  | Completed | 2019-08-21 | 6.08 | 1 | Jill Allen | Completed | 2019-09-27 | 15.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-18 | 2.08 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.96 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1.92 | 1 | Jill Allen | Completed | 2019-09-09 20:20 |  | 2019-09-10 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 4.83 | [11 empty] | 2019-08-30 | 2019-09-16 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=26478 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26478 | https://completesolar.sugarondemand.com/#Opportunities/97b4555a-b8a6-11e9-b854-02ae981fbade | Dominic Labadie |  | 2019-06-17 | Blalock Electric&Solar | 97b4555a-b8a6-11e9-b854-02ae981fbade | 0 | 6 | 10 | -2 | 5 | 5 | 5 | 18
26882 | PIP_APPROVED | PIP_APPROVED | 4484 Craigie Street | San Diego | CA | 92102 | Monica C Morales | 2019-07-24 13:18 | 6198842306 | mcuevas85@ymail.com |  |  |  | 4484 | 0.18 | Ryan Malloy | 2019-07-24 | 3.05 |  | UpGrid Inc | Marcia Garay | 2019-07-02 | 2019-07-03 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-10 07:00 | 2019-07-25 | 0.96 | 2 | Marcia Garay | Completed | 2019-07-29 | 1.88 | 2 | Jethro Andal | Completed | 2019-08-30 | 16.84 | 1 | Christina Horton | Completed | 2019-09-10 | 2.09 | 5 | Brian Le | Completed | 2019-08-20 | 1.21 | 3 | Andrew Moralez | Completed | 2019-08-20 | 0.08 | 15 | Ernesto Enriquez | Completed | 2019-09-10 | 0.38 | 1 | Christina Horton | Completed | 2019-09-20 | 8 | 2 | Christina Horton | Completed | 2019-09-04 | 16.59 | 2 | Brian Le | Completed | 2019-07-31 | 2.21 | 2 | Marcia Garay | Completed | 2019-08-20 | 6.37 | 1 |  | Completed | 2019-09-06 | 20.55 | 1 | Andrew Clemons | Completed | 2019-10-10 | 22.38 | 1 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-16 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 2.04 | 2 | Ashley Rockwood | Completed |  | 7.75 | 2 | Marcia Garay | Inactive | 2019-09-23 | 2.79 | 1 | Andrew Clemons | Completed |  |  | 2019-09-12 | 2.04 | 2 | Christina Horton | Completed | [10 empty] | 39.02 | [11 empty] | 2019-09-11 | 2019-09-20 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26882 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26882 | https://completesolar.sugarondemand.com/#Opportunities/220bc852-ae50-11e9-9ae5-022c40d974e6 | Josh Gonzales |  | 2019-07-02 | iEnergy ElectricSolar | 220bc852-ae50-11e9-9ae5-022c40d974e6 | 2 | 10 | 7 | -2 | 5 | 5 | 5 | 15
27551 | PIP_APPROVED | PIP_APPROVED | 13672 Elm Street | Hesperia | CA | 92344 | Francisco Ortiz | 2019-08-01 21:47 | 7608679042 | ortiz_fco@yahoo.com | Erica tuinonez | 9095593208 |  | 6724 | 0.12 | Chris Peaslee | 2019-07-31 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-30 | 2019-07-31 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-09-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-10 07:00 | 2019-08-02 | 1.5 | 2 | Marcia Garay | Completed | 2019-08-08 | 4.79 | 2 | Jethro Andal | Completed | 2019-09-10 | 21.71 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.5 | 5 | Brian Le | Completed | 2019-08-10 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-09-03 | 15.42 | 14 | Ernesto Enriquez | Completed | 2019-09-10 | 0.88 | 1 | Ara Sotto | Completed | 2019-09-12 | 2 | 2 | Ara Sotto | Completed | 2019-09-06 | 17.67 | 2 | Brian Le | Completed | 2019-08-12 | 1.83 | 2 | Marcia Garay | Completed | 2019-08-10 | 1.08 | 1 |  | Completed | 2019-08-15 | 4.46 | 1 | Andrew Clemons | Completed | 2019-09-27 | 13.83 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-16 | 1.54 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 4.83 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.13 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 3.04 | 1 | Andrew Clemons | Completed | 2019-09-11 13:00 |  | 2019-09-12 | 2.38 | 2 | Ara Sotto | Completed | [10 empty] | 0.46 | [11 empty] | 2019-08-30 | 2019-09-12 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=27551 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27551 | https://completesolar.sugarondemand.com/#Opportunities/bf6e42ca-b3c1-11e9-a8a6-069e4f790264 | Jorge Bahena | Shane Montana | 2019-07-30 | HDM Electric Inc | bf6e42ca-b3c1-11e9-a8a6-069e4f790264 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
27560 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 27091 La Fuente | Mission Viejo | CA | 92692 | Donna De Los Santos | 2019-08-02 17:07 | 9499814648 | philip_menez192@yahoo.com | Phillip Menez | 9497849197 |  | 7338 | 0.128 | Chris Peaslee | 2019-08-02 | 4.27 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-30 | 2019-08-02 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-10 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-10 07:00 | 2019-08-05 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 3.92 | 2 | Jethro Andal | Completed | 2019-08-12 | 1.04 | 1 | Christina Horton | Completed | 2019-09-10 | 2.08 | 5 | Brian Le | Completed | 2019-08-27 | 5.92 | 3 | Ernesto Enriquez | Completed | 2019-09-04 | 4.96 | 10 | Andrew Moralez | Completed | 2019-09-10 | 0.38 | 1 | Ara Sotto | Completed |  | 29.17 | 2 | Ara Sotto | Current | 2019-09-06 | 12.8 | 2 | Brian Le | Completed | 2019-08-12 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 1.04 | 1 |  | Completed | 2019-08-30 | 9.92 | 1 | Andrew Clemons | Completed | 2019-09-27 | 13.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-06 | 0.96 | 4 | Darlynn Lacap | Completed | 2019-08-20 | 4.87 | 5 | Darlynn Lacap | Completed | 2019-08-21 | 1 | 12 | Darlynn Lacap | Completed | 2019-10-08 | 2.21 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 1 | 2 | Ashley Rockwood | Completed |  | 8.04 | 2 | Darlynn Lacap | Current | 2019-10-11 | 1.83 | 1 | Jeremiah Liend | Completed | 2019-10-02 21:11 |  | 2019-10-04 | 17.83 | 2 | Ara Sotto | Completed | [10 empty] | 12.83 | [11 empty] | 2019-09-11 |  | MISSION VIEJO | Mission Viejo | https://heliotrack.completesolar.com/job.php?action=review&jobID=27560 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27560 | https://completesolar.sugarondemand.com/#Opportunities/9b6a35a6-b582-11e9-8bc4-022c40d974e6 | Peyton Bennett |  | 2019-07-30 | Zachary Noah Gamez | 9b6a35a6-b582-11e9-8bc4-022c40d974e6 | 24 | 41 | -25 | -2 | 5 | 5 | 5 | -17
27797 | PIP_APPROVED | PIP_APPROVED | 38058 Riviera Court | Palmdale | CA | 93552 | Jesus Gonzales | 2019-08-12 19:28 | 6614353702 | gjeanelly@gmail.com | Hilda Gonzales | 6614353707 |  | 9790 | 0.116 | Shaun Labelle | 2019-08-12 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-09 | 2019-08-12 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-10 | Final Permit | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-09 07:00 | 2019-08-13 | 0.54 | 2 | Marcia Garay | Completed | 2019-08-15 | 2.08 | 2 | Jethro Andal | Completed | 2019-09-03 | 11.88 | 1 | Ara Sotto | Completed | 2019-09-10 | 4.96 | 5 | Brian Le | Completed | 2019-08-21 | 2.92 | 3 | Ernesto Enriquez | Completed | 2019-08-30 | 6.88 | 0 | Ernesto Enriquez | Completed | 2019-09-10 | 3.63 | 2 | Ara Sotto | Completed | 2019-09-30 | 13.79 | 2 | Ara Sotto | Completed | 2019-09-03 | 1.92 | 2 | Brian Le | Completed | 2019-08-29 | 10.17 | 2 | Marcia Garay | Completed | 2019-08-16 | 1.08 | 1 |  | Completed | 2019-08-22 | 5.04 | 1 | Andrew Clemons | Completed |  | 32.79 | 1 | Marcia Garay | Current | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 26.75 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-12 14:50 |  | 2019-09-12 | 2.33 | 2 | Ara Sotto | Completed | [10 empty] | 2.21 | [11 empty] | 2019-08-21 | 2019-09-30 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27797 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27797 | https://completesolar.sugarondemand.com/#Opportunities/017f9a2e-bd72-11e9-ac1b-022c40d974e6 | SCES Division | Henry Garcia | 2019-08-09 | JK Solar | 017f9a2e-bd72-11e9-ac1b-022c40d974e6 | 2 | 20 | 7 | -2 | 5 | 5 | 5 | 15
27814 | SP APPROVED |  | 13039 Cactus Drive | Desert Hot Springs | CA | 92240 | Nicanor Rojas Espinoza | 2019-08-13 13:38 | 8054989170 | socalleakdetection@gmail.com | Armando Gomez | 7608955959 |  | 14754 | 0.13 | Shaun Labelle | 2019-08-13 | 8.54 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-10 | 2019-08-13 09:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-09-10 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-10 07:00 | 2019-08-23 | 3.88 | 2 | Marcia Garay | Completed | 2019-08-20 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-06 | 8.33 | 1 | Ara Sotto | Completed | 2019-09-10 | 2.08 | 5 | Brian Le | Completed | 2019-08-23 | 0.08 | 3 | Andrew Moralez | Completed | 2019-09-04 | 6.79 | 14 | Andrew Moralez | Completed | 2019-09-10 | 0.38 | 2 | Ara Sotto | Completed |  | 29.17 | 2 | Ara Sotto | Current | 2019-09-06 | 5.87 | 2 | Brian Le | Completed | 2019-08-28 | 2.79 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 0.08 | 1 |  | Completed | 2019-09-04 | 6.83 | 1 | Andrew Clemons | Completed |  | 29.54 | 1 | Marcia Garay | Current | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-04 | 10.92 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 6.04 | 2 | Ashley Rockwood | Completed |  | 5.08 | 2 | Marcia Garay | Current |  | 5.08 | 1 | Jill Allen | Current | 2019-09-19 16:49 | 2019-09-19 | 2019-09-19 | 7.08 | 2 | Ara Sotto | Completed | [10 empty] | 4.17 | [11 empty] | 2019-09-13 |  | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=27814 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27814 | https://completesolar.sugarondemand.com/#Opportunities/fbbe1afa-be09-11e9-a4e7-022c40d974e6 | PJB Division |  | 2019-08-10 | Zachary Noah Gamez | fbbe1afa-be09-11e9-a4e7-022c40d974e6 | 9 | 41 | -5 | -2 | 5 | 5 | 5 | 3
27886 | PIP_APPROVED | PIP_APPROVED | 15081 Milford Avenue | Adelanto | CA | 92301 | Sarah Williams | 2019-08-23 13:14 | 7605534451 | traciemahone@gmail.com | Tracy Mahone | 7602466085 | laddiihazel1@gmail.com | 9534 | 0.149 | Shaun Labelle | 2019-08-15 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-13 | 2019-08-14 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-09 07:00 | 2019-08-26 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 2 | 2 | Daniel Speegle | Completed | 2019-09-09 | 8.04 | 1 | Ara Sotto | Completed | 2019-09-10 | 2.08 | 5 | Brian Le | Completed | 2019-08-29 | 4.59 | 3 | Andrew Moralez | Completed | 2019-09-06 | 5 | 10 | Andrew Moralez | Completed | 2019-09-10 | 1.08 | 2 | Ara Sotto | Completed | 2019-09-10 | 0 | 2 | Ara Sotto | Completed | 2019-09-06 | 9.54 | 2 | Brian Le | Completed | 2019-08-27 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 1.09 | 1 |  | Completed | 2019-09-06 | 10.66 | 1 | Jill Allen | Completed | 2019-09-27 | 14.08 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 1 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-09-11 | 0.17 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 9.17 | 2 | Darlynn Lacap | Completed |  | 27.25 | 1 | Andrew Clemons | Current | 2019-09-10 12:45 |  | 2019-09-11 | 0.88 | 2 | Ara Sotto | Completed | [10 empty] | 1.21 | [11 empty] | 2019-09-13 | 2019-09-10 | ADELANTO | Adelanto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27886 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27886 | https://completesolar.sugarondemand.com/#Opportunities/e16d386a-bfc7-11e9-b3f8-02ae981fbade | Christopher Cellini |  | 2019-08-13 | Power Town Solar Electric | e16d386a-bfc7-11e9-b3f8-02ae981fbade | 1 | 0 | 10 | 5 | 5 | 5 | 5 | 25
27908 | PIP_APPROVED | PIP_APPROVED | 38470 Desert Flower Drive | Palmdale | CA | 93551 | Michael Fisk | 2019-08-15 16:58 | 6612722771 | mfisk2011@hotmail.com |  |  |  | 6224 | 0.137 | Bill Angevine | 2019-08-15 | 3.66 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-13 | 2019-08-15 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-10 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-10 07:00 | 2019-08-16 | 0.75 | 2 | Marcia Garay | Completed | 2019-08-19 | 1.13 | 2 | Jethro Andal | Completed | 2019-09-10 | 14.92 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.5 | 5 | Brian Le | Completed | 2019-08-23 | 2.75 | 3 | Ernesto Enriquez | Completed | 2019-09-04 | 7.04 | 0 | Ernesto Enriquez | Completed | 2019-09-10 | 0.59 | 1 | Ara Sotto | Completed | 2019-09-26 | 11.96 | 2 | Ara Sotto | Completed | 2019-09-06 | 10.79 | 2 | Brian Le | Completed | 2019-08-21 | 1.92 | 2 | Marcia Garay | Completed | 2019-08-20 | 1 | 1 |  | Completed | 2019-08-26 | 4.67 | 1 | Jill Allen | Completed |  | 29.75 | 1 | Marcia Garay | Current | 2019-09-30 | 2.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-07 | 16.46 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 7.04 | 2 | Marcia Garay | Completed | 2019-10-09 | 0.88 | 1 | Noe Gomez | Completed | 2019-09-12 15:01 |  | 2019-09-12 | 2.38 | 2 | Ara Sotto | Completed | [10 empty] | 1.17 | [11 empty] | 2019-08-23 | 2019-09-26 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27908 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27908 | https://completesolar.sugarondemand.com/#Opportunities/74ce42e4-bfb8-11e9-bd95-02ae981fbade | SCES Division |  | 2019-08-13 | JK Solar | 74ce42e4-bfb8-11e9-bd95-02ae981fbade | 2 | 16 | 7 | -2 | 5 | 5 | 5 | 15
26716 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 5507 Sulphur Drive | Jurupa Valley | CA | 91752 | Roberta Hoodward | 2019-07-23 11:46 | 7142732580 | hoodward@sbcglobal.net | Andrew Hoodward | 7142731746 | roberta.hoodward@gmail.com | 18320 | 0.2 | Shaun Labelle | 2019-07-23 | 11.59 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-08 | 2019-07-19 09:00 | LR6-60PB-305M | 305 | 38 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | Line-side Tap | 2019-09-07 | PTO Received | SunRun Monthly | [6 empty] | 2019-09-07 07:00 | 2019-07-26 | 2.83 | 2 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-16 | 14.17 | 1 | Christina Horton | Completed | 2019-09-06 | 22.79 | 5 | Brian Le | Completed | 2019-08-02 | 3.88 | 3 | Ernesto Enriquez | Completed | 2019-08-14 | 8.33 | 0 | Andrew Moralez | Completed | 2019-09-07 | 0.37 | 3 | Christina Horton | Completed |  | 30.71 | 2 | Christina Horton | Current | 2019-08-05 | 2.25 | 2 | Brian Le | Completed | 2019-08-01 | 2.83 | 2 | Marcia Garay | Completed | 2019-07-29 | 0.13 | 1 |  | Completed | 2019-08-01 | 2.88 | 1 | Andrew Clemons | Completed | 2019-10-02 | 18 | 1 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-07 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-10-10 | 2.67 | 2 | Ashley Rockwood | Completed |  | 7.38 | 2 | Marcia Garay | Current | 2019-10-11 | 1.17 | 1 | Jeremiah Liend | Completed | 2019-10-02 11:59 |  | 2019-10-02 | 10 | 2 | Christina Horton | Completed | 2019-09-07 | 0.37 | 1 | Christina Horton | Completed | 2019-07-26 | 0.17 | 2 | Marcia Garay | Completed | 16.54 | [11 empty] | 2019-08-02 |  | MIRA LOMA | Mira Loma | https://heliotrack.completesolar.com/job.php?action=review&jobID=26716 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26716 | https://completesolar.sugarondemand.com/#Opportunities/0f4963c2-ad7a-11e9-a62b-022c40d974e6 | Lindsey Lange | Alyson Drago | 2019-06-26 | Infinity Energy Inc | 0f4963c2-ad7a-11e9-a62b-022c40d974e6 | 25 | 44 | -25 | -2 | 5 | 5 | 5 | -17
27423 | SP APPROVED |  | 34251 Canyon Rim Drive | Lake Elsinore | CA | 92532 | Albert Hernandez | 2019-08-03 15:48 | 9519664051 | bankwithvic@gmail.com | Vicky Hernandez | 909 276 9836 |  | 9767 | 0.12 | Ryan Malloy | 2019-08-03 | 5.49 | Ara Sotto | Blue Prime Energy | Darlynn Lacap | 2019-08-01 | 2019-08-03 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-07 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-07 07:00 | 2019-08-05 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 3.04 | 2 | Daniel Speegle | Completed | 2019-08-15 | 4.92 | 1 | Ara Sotto | Completed | 2019-09-07 | 14.46 | 5 | Brian Le | Completed | 2019-08-09 | 0.17 | 3 | Andrew Moralez | Completed | 2019-08-14 | 3.08 | 1 | Andrew Moralez | Completed | 2019-09-07 | 0.08 | 2 | Ara Sotto | Completed |  | 30.71 | 2 | Ara Sotto | Current | 2019-08-16 | 3.92 | 2 | Brian Le | Completed | 2019-08-12 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.79 | 1 |  | Completed | 2019-08-13 | 2.83 | 1 | Andrew Clemons | Completed | 2019-09-27 | 14.5 | 1 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-06 | 1.04 | 4 | Darlynn Lacap | Completed | 2019-08-14 | 6.08 | 5 | Darlynn Lacap | Completed | 2019-09-12 | 16.75 | 12 | Darlynn Lacap | Completed | 2019-09-13 | 3.17 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.88 | 1 | Andrew Clemons | Completed |  | 2019-08-28 | 2019-09-10 | 1.38 | 2 | Ara Sotto | Completed | [10 empty] | 4.05 | [11 empty] | 2019-08-14 |  | LAKE ELSINORE | Lake Elsinore | https://heliotrack.completesolar.com/job.php?action=review&jobID=27423 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27423 | https://completesolar.sugarondemand.com/#Opportunities/ac835502-b640-11e9-8f35-022c40d974e6 | Blue Prime Energy |  | 2019-07-24 | Zachary Noah Gamez | ac835502-b640-11e9-8f35-022c40d974e6 | 3 | 44 | 0 | -2 | 5 | 5 | 5 | 8
27668 | SP APPROVED |  | 12803 El Moro Avenue | La Mirada | CA | 90638 | Rogelio Esparza | 2019-08-07 13:55 | 3234492735 | derogelio27@yahoo.com |  |  |  | 7622 | 0.174 | Alex Holdridge | 2019-08-07 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-05 | 2019-08-07 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-09-07 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-06 07:00 | 2019-08-07 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 2.92 | 2 | Jethro Andal | Completed | 2019-09-10 | 20 | 1 | Christina Horton | Completed |  | 36.29 | 5 | Brian Le | Current | 2019-08-21 | 5.04 | 3 | Andrew Moralez | Completed | 2019-08-29 | 5.83 | 2 | Ernesto Enriquez | Completed | 2019-09-07 | 0.79 | 2 | Ara Sotto | Completed |  | 30.71 | 2 | Ara Sotto | Current | 2019-08-29 | 11.71 | 2 | Brian Le | Completed | 2019-08-13 | 0.12 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 1.83 | 1 |  | Completed | 2019-08-16 | 3.79 | 1 | Noe Gomez | Completed | 2019-09-27 | 15.38 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-17 16:48 | 2019-08-30 |  | 0 | 2 |  | Inactive |  | 31.54 | 1 | Ara Sotto | Current | 2019-08-13 | 0.71 | 2 | Darlynn Lacap | Completed | 1.04 | [11 empty] | 2019-08-23 |  | LA MIRADA | La Mirada | https://heliotrack.completesolar.com/job.php?action=review&jobID=27668 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27668 | https://completesolar.sugarondemand.com/#Opportunities/84fa26b0-b955-11e9-afe5-022c40d974e6 | Cesar Valdizan | Solar Raze | 2019-08-05 | HDM Electric Inc | 84fa26b0-b955-11e9-afe5-022c40d974e6 |  | 44 | -25 | -2 | 5 | 5 | 5 | -17
27773 | PIP_APPROVED | PIP_APPROVED | 8749 Bridgeport | Hesperia | CA | 92344 | Edward Moyers | 2019-08-26 15:09 | 9092630244 | callmepapaed@gmail.com |  |  |  | 9744 | 0.14 | Shaun Labelle | 2019-08-13 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-08 | 2019-08-13 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-07 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-07 07:00 | 2019-08-26 | 3.71 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 0.12 | 2 | Daniel Speegle | Completed | 2019-09-03 | 4.71 | 1 | Ara Sotto | Completed | 2019-09-07 | 3.38 | 5 | Brian Le | Completed | 2019-08-30 | 1.88 | 3 | Andrew Moralez | Completed | 2019-08-30 | 0 | 14 | Andrew Moralez | Completed | 2019-09-07 | 0.08 | 2 | Ara Sotto | Completed | 2019-09-12 | 3.54 | 2 | Ara Sotto | Completed | 2019-09-03 | 2.25 | 2 | Brian Le | Completed | 2019-08-29 | 2.58 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.83 | 1 |  | Completed | 2019-08-29 | 2.92 | 1 | Andrew Clemons | Completed | 2019-09-12 | 3.63 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-25 15:03 |  |  | 30.71 | 2 | Ara Sotto | Current | [10 empty] | 6.16 | [11 empty] | 2019-09-20 | 2019-09-08 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=27773 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27773 | https://completesolar.sugarondemand.com/#Opportunities/23e3d79e-be38-11e9-856f-02ae981fbade | Christopher Cellini |  | 2019-08-08 | HDM Electric Inc | 23e3d79e-be38-11e9-856f-02ae981fbade | 44 | 5 | -25 | -2 | 5 | 5 | 5 | -17
25225 | PIP_APPROVED | PIP_APPROVED | 811 Casa De Oro Place | Escondido | CA | 92025 | Can Chau | 2019-08-22 08:34 | 7606584484 | chaucan@cox.net |  |  |  | 8039 | 0.17 | Ryan Malloy | 2019-05-13 | 5.49 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-09 | 2019-05-13 13:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-06 | PTO Received | SunRun Monthly |  | 0 |  |  | 0 |  | 2019-09-05 12:00 | 2019-08-22 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2 | 2 | Jethro Andal | Completed | 2019-08-26 | 13.92 | 1 | Christina Horton | Completed | 2019-09-06 | 11.72 | 5 | Brian Le | Completed | 2019-08-22 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-22 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-06 | 1.17 | 2 | Christina Horton | Completed | 2019-10-11 | 25.5 | 2 | Christina Horton | Completed | 2019-08-22 | 6.04 | 2 | Brian Le | Completed | 2019-08-22 | 1.75 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 1 |  | Completed | 2019-09-05 | 18 | 1 | Noe Gomez | Completed | 2019-09-27 | 16.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 6.88 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 7.96 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 5.96 | 1 | Jill Allen | Completed |  | 2019-09-04 | 2019-09-06 | 0.21 | 2 | Christina Horton | Completed | [10 empty] | 31.25 | [11 empty] | 2019-09-13 | 2019-10-11 | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=25225 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25225 | https://completesolar.sugarondemand.com/#Opportunities/b47b41c4-75cd-11e9-a793-069e4f790264 | Robert Blessing |  | 2019-05-01 | Infinity Energy Inc | b47b41c4-75cd-11e9-a793-069e4f790264 | 0 | 35 | 10 | -2 | 5 | 5 | 5 | 18
26240 | PIP_APPROVED | PIP_APPROVED | 811 East Jackson Street | Rialto | CA | 92376 | Gustavo Gomez | 2019-06-14 16:42 | 9092603424 | georginagomez91@gmail.com |  |  |  | 5425 | 0.17 | Alex Holdridge | 2019-06-14 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-10 | 2019-06-14 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-09-06 07:00 | 2019-06-18 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-06-24 | 3.04 | 2 | Jethro Andal | Completed | 2019-06-17 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-06 | 38.08 | 5 | Brian Le | Completed | 2019-06-28 | 2.88 | 3 | Ernesto Enriquez | Completed | 2019-07-23 | 15.96 | 7 | Ernesto Enriquez | Completed | 2019-09-06 | 11.05 | 1 | Ara Sotto | Completed | 2019-09-12 | 4.08 | 2 | Ara Sotto | Completed | 2019-07-12 | 12 | 2 | Brian Le | Completed | 2019-06-25 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-06-25 | 1.08 | 1 |  | Completed | 2019-06-30 | 4.46 | 1 | Jill Allen | Completed | 2019-09-11 | 14.01 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.12 | 2 | Andrew Clemons | Completed | 2019-07-08 | 1.92 | 4 | Darlynn Lacap | Completed | 2019-07-08 | 0 | 5 | Darlynn Lacap | Completed | 2019-08-29 | 29.83 | 12 | Darlynn Lacap | Completed | 2019-09-16 | 1.54 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 6.04 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 1.83 | 1 | Andrew Clemons | Completed | 2019-09-09 16:48 |  | 2019-09-12 | 4.25 | 2 | Ara Sotto | Completed | [10 empty] | 23.17 | [11 empty] | 2019-07-10 | 2019-09-12 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26240 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26240 | https://completesolar.sugarondemand.com/#Opportunities/0831f72e-8efe-11e9-b28e-02ae981fbade | 300 Stars Inc |  | 2019-06-07 | Green Road Solar Crew | 0831f72e-8efe-11e9-b28e-02ae981fbade | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
26467 | PIP_APPROVED | PIP_APPROVED | 2860 Via Bellota | San Clemente | CA | 92673 | Lisa MacLean | 2019-07-18 19:07 | 9499228993 | Lance_lisa_maclean@hotmail.com | Lance MacLean | 9496838993 |  | 8011 |  | Chris Peaslee | 2019-07-18 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-06 | 2019-07-11 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | Cash | 1 | 0 |  |  |  |  | 2019-09-05 07:00 | 2019-07-19 | 0.75 | 2 | Marcia Garay | Completed | 2019-07-22 | 1 | 2 | Daniel Speegle | Completed | 2019-08-20 | 20.96 | 1 | Christina Horton | Completed | 2019-09-06 | 26.33 | 5 | Brian Le | Completed | 2019-07-30 | 4.08 | 3 | Andrew Moralez | Completed | 2019-07-30 | 0 | 1 | Ernesto Enriquez | Completed | 2019-09-06 | 1.17 | 2 | Christina Horton | Completed | 2019-09-18 | 8.25 | 2 | Christina Horton | Completed | 2019-07-30 | 0.58 | 2 | Brian Le | Completed | 2019-07-30 | 5.75 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.88 | 1 |  | Completed | 2019-08-06 | 11.13 | 1 | Andrew Clemons | Completed | 2019-10-10 | 25.58 | 1 | Marcia Garay | Completed |  | 23.08 | 2 | Jeremiah Liend | Current | 2019-08-12 | 16 | 4 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 5 | Marcia Garay | Completed | 2019-08-20 | 6.04 | 12 | Marcia Garay | Completed | 2019-09-19 | 3.67 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 3.17 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 0.79 | 2 | Marcia Garay | Completed |  | 19.08 | 1 | Jill Allen | Current |  |  | 2019-09-13 | 5.33 | 2 | Christina Horton | Completed | [10 empty] | 0 | [11 empty] | 2019-07-31 | 2019-09-18 | SAN CLEMENTE | San Clemente | https://heliotrack.completesolar.com/job.php?action=review&jobID=26467 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26467 | https://completesolar.sugarondemand.com/#Opportunities/e008b18e-a9c9-11e9-a47c-02ae981fbade | Laura Rea | Laura Rea | 2019-06-17 | Infinity Energy Inc | e008b18e-a9c9-11e9-a47c-02ae981fbade | 7 | 12 | -5 | -2 | 5 | 5 | 5 | 3
26619 | PIP_APPROVED | PIP_APPROVED | 11 Faas Court | West Orange | NJ | 7052 | Renee Locricchio | 2019-06-24 10:56 | 9082403559 | damienlocricchio@yahoo.com | Damien | 9082403558 |  | 11491.95 |  | Andrew Weber | 2019-06-24 | 10.37 | Christina Horton | Sunlogic Power | Darlynn Lacap | 2019-06-22 | 2019-06-24 09:00 | LR6-60PB-305M | 305 | 34 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-09-06 | NEM Submitted | Sunlight Financial Loan |  | 0 |  | 0 | 0 |  | 2019-09-04 07:00 | 2019-06-27 | 2.88 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 4.08 | 2 | Jethro Andal | Completed | 2019-08-14 | 28.83 | 1 | Christina Horton | Completed | 2019-09-06 | 0 | 5 | Brian Le | Completed | 2019-07-12 | 2.63 | 3 | Andrew Moralez | Completed | 2019-07-31 | 13 | 10 | Andrew Moralez | Completed | 2019-09-06 | 2.17 | 3 | Christina Horton | Completed | 2019-09-06 | 0.08 | 2 | Christina Horton | Completed | 2019-09-06 | 17.25 | 2 | Brian Le | Completed | 2019-07-09 | 2.25 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 2.29 | 1 |  | Completed | 2019-07-08 | 2.08 | 1 | Noe Gomez | Completed | 2019-09-04 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-10-18 | 15.79 | 2 | Ashley Rockwood | Completed |  | 1.29 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-10-18 | 2019-09-26 | 14.17 | 2 | Christina Horton | Completed | [10 empty] | 44.63 | [11 empty] | 2019-07-26 | 2019-09-06 | Default | West Orange | https://heliotrack.completesolar.com/job.php?action=review&jobID=26619 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26619 | https://completesolar.sugarondemand.com/#Opportunities/4044169e-96a9-11e9-a606-0630baf9dcb8 | Anthony Fowler |  | 2019-06-22 | Skyline Solar | 4044169e-96a9-11e9-a606-0630baf9dcb8 | 20 | 0 | -15 | 5 | 5 | 5 | 5 | 0
27278 | PIP_APPROVED | PIP_APPROVED | 4861 69th Place | San Diego | CA | 92115 | Robert Weas | 2019-08-06 14:45 | 6198404285 | palmrobaw@yahoo.com | Amy Weas | 6195407861 |  | 5361 | 0.002 | Ryan Malloy | 2019-08-06 | 3.66 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-19 | 2019-07-23 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  |  | 2019-09-06 07:00 | 2019-08-07 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 3.04 | 2 | Jethro Andal | Completed | 2019-09-03 | 15 | 1 | Ara Sotto | Completed | 2019-09-06 | 12.17 | 5 | Brian Le | Completed | 2019-08-23 | 2.79 | 3 | Ernesto Enriquez | Completed | 2019-08-23 | 0 | 15 | Andrew Moralez | Completed | 2019-09-06 | 0.42 | 1 | Ara Sotto | Completed | 2019-10-08 | 22.25 | 2 | Ara Sotto | Completed | 2019-08-20 | 0.67 | 2 | Brian Le | Completed | 2019-08-19 | 2.12 | 2 | Darlynn Lacap | Completed | 2019-08-20 | 6.13 | 1 |  | Completed | 2019-09-06 | 15.63 | 1 | Noe Gomez | Completed | 2019-09-27 | 14.92 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-16 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.75 | 2 | Darlynn Lacap | Completed |  | 21.08 | 1 | Jeremiah Liend | Current |  | 2019-09-12 | 2019-09-12 | 3.96 | 2 | Ara Sotto | Completed | [10 empty] | 14.97 | [11 empty] | 2019-09-16 | 2019-10-08 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27278 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27278 | https://completesolar.sugarondemand.com/#Opportunities/6a268756-b893-11e9-acd6-02ae981fbade | Blake Sanders |  | 2019-07-19 | Zachary Noah Gamez | 6a268756-b893-11e9-acd6-02ae981fbade | 6 | 32 | -5 | -2 | 5 | 5 | 5 | 3
27441 | PIP_APPROVED | PIP_APPROVED | 17734 Randall Avenue | Fontana | CA | 92335 | Rudolph R Lopez | 2019-08-06 13:49 | 9095494018 | rudolphr84@yahoo.com |  |  |  | 7171 | 0.178 | Shaun Labelle | 2019-07-26 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-25 | 2019-07-26 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | MPU | 2019-09-06 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-05 07:00 | 2019-08-07 | 2.46 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 6.21 | 2 | Ernesto Enriquez | Completed | 2019-08-15 | 4.87 | 1 | Ara Sotto | Completed | 2019-09-06 | 5 | 5 | Brian Le | Completed | 2019-08-14 | 3.21 | 3 | Ernesto Enriquez | Completed | 2019-08-30 | 11.75 | 12 | Ernesto Enriquez | Completed | 2019-09-06 | 1.25 | 2 | Ara Sotto | Completed | 2019-09-06 | 0.17 | 2 | Ara Sotto | Completed | 2019-08-29 | 14.83 | 2 | Brian Le | Completed | 2019-08-08 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.92 | 1 |  | Completed | 2019-08-13 | 3.17 | 1 | Andrew Clemons | Completed | 2019-09-27 | 16.38 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 2.96 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-28 |  | 0 | 2 |  | Inactive |  | 32.54 | 1 | Ara Sotto | Current | 2019-08-09 | 0.79 | 2 | Darlynn Lacap | Completed | 3.8 | [11 empty] | 2019-08-30 | 2019-09-06 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=27441 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27441 | https://completesolar.sugarondemand.com/#Opportunities/869c42f8-b00b-11e9-b610-02ae981fbade | Oscar Hernandez |  | 2019-07-25 | HDM Electric Inc | 869c42f8-b00b-11e9-b610-02ae981fbade |  | 0 | -25 | 5 | 5 | 5 | 5 | -10
27533 | SP APPROVED |  | 2573 Gum tree Lane | Fallbrook | CA | 92028 | Joseph A Edgman | 2019-08-28 20:30 | 6193704271 | edgmanja@cox.net | Martha Edgman | 6195183703 |  | 10830 | 0.186 | Ryan Malloy | 2019-07-31 | 7.625 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-29 | 2019-07-31 09:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-06 07:00 | 2019-08-29 | 1.58 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 9.33 | 2 | Daniel Speegle | Completed | 2019-09-06 | 4.04 | 1 | Ara Sotto | Completed | 2019-09-06 | 0.17 | 5 | Brian Le | Completed | 2019-09-03 | 0.91 | 3 | Andrew Moralez | Completed | 2019-09-03 | 0.08 | 1 | Andrew Moralez | Completed | 2019-09-06 | 0.17 | 2 | Ara Sotto | Completed |  | 31.08 | 2 | Ara Sotto | Current | 2019-09-06 | 5.91 | 2 | Brian Le | Completed | 2019-08-30 | 5.16 | 2 | Darlynn Lacap | Completed | 2019-08-30 | 0.21 | 1 |  | Completed | 2019-09-06 | 11.21 | 1 | Andrew Clemons | Completed | 2019-09-11 | 3.21 | 1 | Darlynn Lacap | Completed | 2019-09-10 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-04 | 9.17 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-10-16 | 6.04 | 2 | Darlynn Lacap | Completed | 2019-10-09 | 1.04 | 1 | Jill Allen | Completed | 2019-09-19 16:57 | 2019-09-13 | 2019-09-23 | 10.75 | 2 | Ara Sotto | Completed | [10 empty] | 16.41 | [11 empty] | 2019-09-04 |  | SAN DIEGO COUNTY | Fallbrook | https://heliotrack.completesolar.com/job.php?action=review&jobID=27533 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27533 | https://completesolar.sugarondemand.com/#Opportunities/efbcce72-b3e6-11e9-876b-02ae981fbade | Tremaine Consulting | Jimmy Evans | 2019-07-29 | Zachary Noah Gamez | efbcce72-b3e6-11e9-876b-02ae981fbade | 17 | 45 | -15 | -2 | 5 | 5 | 5 | -7
27635 | PIP_APPROVED | PIP_APPROVED | 37952 Boxthorn Street | Palmdale | CA | 93552 | Luz M Kellerman | 2019-08-06 18:16 | 6616746940 | lmkellerman@yahoo.com |  |  |  | 11117 | 0.14 | Shaun Labelle | 2019-08-06 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-03 | 2019-08-06 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-05 07:00 | 2019-08-07 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 5.08 | 2 | Jethro Andal | Completed | 2019-09-03 | 12.88 | 1 | Ara Sotto | Completed | 2019-09-06 | 4.79 | 5 | Brian Le | Completed | 2019-08-21 | 2.88 | 3 | Andrew Moralez | Completed | 2019-08-29 | 5.83 | 0 | Andrew Moralez | Completed | 2019-09-06 | 1.25 | 2 | Ara Sotto | Completed | 2019-09-27 | 15.08 | 2 | Ara Sotto | Completed | 2019-08-29 | 9.96 | 2 | Brian Le | Completed | 2019-08-15 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 2.13 | 1 |  | Completed | 2019-08-20 | 4 | 1 | Jill Allen | Completed | 2019-09-26 | 15.46 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-11 | 0.21 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 4.67 | 2 | Ashley Rockwood | Completed |  | 22.46 | 2 | Darlynn Lacap | Current |  | 23.33 | 1 | Andrew Clemons | Current | 2019-09-10 16:56 | 2019-08-29 | 2019-09-11 | 2.96 | 2 | Ara Sotto | Completed | [10 empty] | 2.88 | [11 empty] | 2019-08-21 | 2019-09-27 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27635 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27635 | https://completesolar.sugarondemand.com/#Opportunities/ed22344e-b8b0-11e9-9919-02ae981fbade | SCES Division |  | 2019-08-03 | JK Solar | ed22344e-b8b0-11e9-9919-02ae981fbade | 5 | 21 | -5 | -2 | 5 | 5 | 5 | 3
27636 | PIP_APPROVED | PIP_APPROVED | 27958 Starfall Way | Murrieta | CA | 92563 | Benjamin Franklin | 2019-08-08 12:45 | 7606134204 | im2frank4u@hotmail.com | Angela Franklin | 7606131990 |  | 13592 | 0.134 | Chris Peaslee | 2019-08-08 | 7.625 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-08-03 | 2019-08-08 09:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-08 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 3.08 | 2 | Jethro Andal | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-06 | 10.83 | 5 | Brian Le | Completed | 2019-08-19 | 3.17 | 3 | Ernesto Enriquez | Completed | 2019-08-21 | 1.96 | 1 | Ernesto Enriquez | Completed | 2019-09-06 | 4.25 | 2 | Ara Sotto | Completed | 2019-09-13 | 5.21 | 2 | Ara Sotto | Completed | 2019-08-21 | 4.21 | 2 | Brian Le | Completed | 2019-08-15 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 0.71 | 1 |  | Completed | 2019-08-16 | 2.75 | 1 | Noe Gomez | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-12 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-19 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 7.08 | 2 | Ashley Rockwood | Completed |  | 15.17 | 2 | Darlynn Lacap | Current | 2019-10-03 | 2.79 | 1 | Noe Gomez | Completed | 2019-09-17 14:12 |  | 2019-09-17 | 7.17 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-20 | 2019-09-13 | MURRIETA | Murrieta | https://heliotrack.completesolar.com/job.php?action=review&jobID=27636 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27636 | https://completesolar.sugarondemand.com/#Opportunities/ec37f0cc-ba14-11e9-bcf4-02ae981fbade | Tier1 Power | Ryan Ostronic | 2019-08-03 | Blalock Electric&Solar | ec37f0cc-ba14-11e9-bcf4-02ae981fbade | 11 | 7 | -15 | -2 | 5 | 5 | 5 | -7
27691 | PIP_APPROVED | PIP_APPROVED | 6315 Guthrie Street | San Bernardino | CA | 92404 | Alfonso Gomez Banda | 2019-08-12 06:14 | 9093147587 | alexisgomez71@yahoo.com | Alexis Gomez |  |  | 9015 | 0.163 | Alex Holdridge | 2019-08-10 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-09 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-09-06 | Final Permit | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-06 07:00 | 2019-08-13 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 3 | 2 | Jethro Andal | Completed | 2019-08-14 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-06 | 3.04 | 5 | Brian Le | Completed | 2019-08-20 | 1.17 | 3 | Andrew Moralez | Completed | 2019-08-28 | 4.21 | 1 | Andrew Moralez | Completed | 2019-09-06 | 0.5 | 2 | Ara Sotto | Completed | 2019-09-10 | 1.88 | 2 | Ara Sotto | Completed | 2019-09-03 | 0.92 | 2 | Brian Le | Completed | 2019-08-30 | 2.08 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 1 | 1 |  | Completed | 2019-08-22 | 4.08 | 1 | Andrew Clemons | Completed | 2019-09-27 | 15.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.96 | 2 | Andrew Clemons | Completed | [16 empty] | 0.92 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-19 15:04 |  | 2019-09-19 | 0 | 2 | Ara Sotto | Completed | 2019-09-19 | 6.92 | 1 | Ara Sotto | Completed | 2019-08-18 | 0.5 | 2 | Darlynn Lacap | Completed | 30.41 | [11 empty] | 2019-08-28 | 2019-09-09 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=27691 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27691 | https://completesolar.sugarondemand.com/#Opportunities/f8c404d4-bd02-11e9-a6d6-0630baf9dcb8 | 300 Stars Inc | Oscar Hernandez | 2019-08-06 | Power Town Solar Electric | f8c404d4-bd02-11e9-a6d6-0630baf9dcb8 | 0 | 4 | 10 | 0 | 5 | 5 | 5 | 20
27695 | PIP_APPROVED | PIP_APPROVED | 37941 Wesley Court | Palmdale | CA | 93552 | Joe Delgado | 2019-08-09 18:50 | 6619168912 | olddelgados@yahoo.com | Cecilia Delgado | 6619167939 |  | 9937 | 0.136 | Shaun Labelle | 2019-08-09 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-09 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-09-06 | 2019-08-12 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 2.04 | 2 | Daniel Speegle | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-06 | 4.08 | 5 | Brian Le | Completed | 2019-08-21 | 2.88 | 3 | Andrew Moralez | Completed | 2019-08-30 | 6.88 | 0 | Andrew Moralez | Completed | 2019-09-06 | 0 | 2 | Ara Sotto | Completed | 2019-09-12 | 3.88 | 2 | Ara Sotto | Completed | 2019-08-30 | 10.88 | 2 | Brian Le | Completed | 2019-08-15 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 2 | 1 |  | Completed | 2019-08-30 | 11.88 | 1 | Noe Gomez | Completed | 2019-09-18 | 8 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.04 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 2.96 | 1 | Jeremiah Liend | Completed | 2019-09-19 15:17 |  | 2019-09-19 | 9 | 2 | Ara Sotto | Completed | [10 empty] | 0.96 | [11 empty] | 2019-08-21 | 2019-09-12 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27695 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27695 | https://completesolar.sugarondemand.com/#Opportunities/1e1b8782-bb11-11e9-a756-069e4f790264 | SCES Division | Henry Garcia | 2019-08-06 | HDM Electric Inc | 1e1b8782-bb11-11e9-a756-069e4f790264 | 13 | 6 | -15 | -2 | 5 | 5 | 5 | -7
27966 | PIP_APPROVED | PIP_APPROVED | 11005 Willow Way | Adelanto | CA | 92301 | Eva Bright | 2019-08-22 14:33 | 7604909694 | eva.bright87@gmail.com | Diana Bright | 6463773090 |  | 7513 | 0.155 | Alex Holdridge | 2019-08-22 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-15 | 2019-08-22 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-05 07:00 | 2019-08-26 | 2 | 2 | Marcia Garay | Completed | 2019-08-26 | 0.04 | 2 | Daniel Speegle | Completed | 2019-09-03 | 4.71 | 1 | Ara Sotto | Completed | 2019-09-06 | 2.83 | 5 | Brian Le | Completed | 2019-08-28 | 0.96 | 3 | Andrew Moralez | Completed | 2019-08-29 | 0.92 | 10 | Andrew Moralez | Completed | 2019-09-06 | 1.25 | 1 | Ara Sotto | Completed | 2019-09-09 | 0.92 | 2 | Ara Sotto | Completed | 2019-09-03 | 3 | 2 | Brian Le | Completed | 2019-08-28 | 1.88 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.92 | 1 |  | Completed | 2019-09-04 | 5.63 | 1 | Andrew Clemons | Completed | 2019-09-27 | 16.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 2.17 | 2 | Jill Allen | Completed | [15 empty] | 2019-09-11 | 1.17 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 7.04 | 2 | Darlynn Lacap | Completed |  | 27.29 | 1 | Andrew Clemons | Current | 2019-09-09 17:03 | 2019-09-23 | 2019-09-10 | 1.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-12 | 2019-09-09 | ADELANTO | Adelanto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27966 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27966 | https://completesolar.sugarondemand.com/#Opportunities/6171234e-c524-11e9-ad34-069e4f790264 | CSA Division | Christopher Cellini | 2019-08-15 | Green Road Solar Crew | 6171234e-c524-11e9-ad34-069e4f790264 | 4 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26729 | PIP_APPROVED | PIP_APPROVED | 211 Clearcreek Place | Santee | CA | 92071 | Kathleen Luci (#2) | 2019-07-19 13:44 | 6198043003 | kluci200@gmail.com |  |  |  | 7710.57 |  | Ryan Malloy | 2019-07-19 | 4.575 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-15 | 2019-07-17 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-05 | PTO Received | Cash | 1 | 0 |  |  | 0 | 1 | 2019-09-04 07:00 | 2019-07-31 | 2.17 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.08 | 2 | Daniel Speegle | Completed | 2019-09-03 | 22.92 | 1 | Christina Horton | Completed | 2019-09-05 | 23.34 | 5 | Brian Le | Completed | 2019-07-25 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-26 | 0.08 | 10 | Andrew Moralez | Completed | 2019-09-05 | 1.08 | 1 | Christina Horton | Completed | 2019-09-05 | 0.13 | 2 | Christina Horton | Completed | 2019-07-30 | 0.08 | 2 | Brian Le | Completed | 2019-08-01 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.08 | 1 |  | Completed | 2019-08-06 | 4.17 | 1 | Andrew Clemons | Completed | 2019-09-19 | 11.5 | 1 | Marcia Garay | Completed |  | 32.29 | 2 | Noe Gomez | Current | 2019-08-01 | 1.13 | 4 | Marcia Garay | Completed | 2019-08-27 | 17.75 | 5 | Marcia Garay | Completed | 2019-09-03 | 4.04 | 12 | Marcia Garay | Completed | 2019-09-25 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 8.88 | 2 | Marcia Garay | Completed |  | 15.17 | 1 | Noe Gomez | Current |  |  | 2019-09-20 | 6.34 | 2 | Christina Horton | Completed | [10 empty] | 13.41 | [11 empty] | 2019-08-09 | 2019-09-05 | SANTEE | Santee | https://heliotrack.completesolar.com/job.php?action=review&jobID=26729 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26729 | https://completesolar.sugarondemand.com/#Opportunities/f52360ae-aa65-11e9-b2e9-069e4f790264 | Robert Blessing |  | 2019-06-26 | Infinity Energy Inc | f52360ae-aa65-11e9-b2e9-069e4f790264 | 15 | 0 | -15 | 5 | 5 | 5 | 5 | 0
26833 | PIP_APPROVED | PIP_APPROVED | 3415 Genevieve Street North | San Bernardino | CA | 92405 | Louis Reyes | 2019-08-20 13:39 | 6267823810 | louisreyes01@gmail.com |  |  |  | 6923 | 0.18 | Shaun Labelle | 2019-08-07 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-01 | 2019-07-02 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-09-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-05 07:00 | 2019-08-20 | 3.26 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 2.79 | 2 | Daniel Speegle | Completed | 2019-09-05 | 11.91 | 1 | Ara Sotto | Completed | 2019-09-05 | 4.08 | 5 | Brian Le | Completed | 2019-08-29 | 4.92 | 3 | Andrew Moralez | Completed | 2019-08-29 | 0 | 1 | Andrew Moralez | Completed | 2019-09-05 | 0.38 | 1 | Ara Sotto | Completed | 2019-10-11 | 26.29 | 2 | Ara Sotto | Completed | 2019-08-29 | 2.88 | 2 | Brian Le | Completed | 2019-08-26 | 4.91 | 2 | Darlynn Lacap | Completed | 2019-08-26 | 2.92 | 1 |  | Completed | 2019-08-30 | 8.75 | 1 | Noe Gomez | Completed | 2019-09-27 | 16.38 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-12 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 4.08 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 7.96 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.79 | 1 | Andrew Clemons | Completed | 2019-09-09 17:00 | 2019-09-04 | 2019-09-10 | 2.83 | 2 | Ara Sotto | Completed | [10 empty] | 6.84 | [11 empty] | 2019-08-30 | 2019-10-11 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=26833 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26833 | https://completesolar.sugarondemand.com/#Opportunities/12b1d542-b934-11e9-9408-069e4f790264 | Summit Marketing Inc |  | 2019-07-01 | Zachary Noah Gamez | 12b1d542-b934-11e9-9408-069e4f790264 | 5 | 36 | -5 | -2 | 5 | 5 | 5 | 3
27469 | PIP_APPROVED | PIP_APPROVED | 1267 West Kildare Street | Lancaster | CA | 93534 | Sara Stanton | 2019-08-09 17:13 | 6612815254 | red3horn@gmail.com |  |  |  | 16128 | 0.14 | Bill Angevine | 2019-07-29 | 10.065 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-26 | 2019-07-29 15:00 | LR6-60PB-305M | 305 | 33 | LONGi Solar | SolarEdge | SE10000A-US RGM | Composite | NO | 2019-09-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-05 | 2019-08-12 | 1.87 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 11.17 | 2 | Daniel Speegle | Completed | 2019-08-14 | 0.16 | 1 | Ara Sotto | Completed | 2019-09-05 | 8.83 | 5 | Brian Le | Completed | 2019-08-19 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-30 | 8.75 | 1 | Ernesto Enriquez | Completed | 2019-09-05 | 0 | 3 | Ara Sotto | Completed | 2019-09-06 | 1.04 | 2 | Ara Sotto | Completed | 2019-08-21 | 0.08 | 2 | Brian Le | Completed | 2019-08-22 | 3.17 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.13 | 1 |  | Completed | 2019-08-21 | 1.92 | 1 | Andrew Clemons | Completed | 2019-09-27 | 15.96 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 2.96 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-12 | 3.71 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 4 | 2 | Ashley Rockwood | Completed | 2019-10-01 | 8.92 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.88 | 1 | Jeremiah Liend | Completed | 2019-09-06 13:16 |  | 2019-09-06 | 1.13 | 2 | Ara Sotto | Completed | [10 empty] | 7.94 | [11 empty] | 2019-08-20 | 2019-09-06 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27469 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27469 | https://completesolar.sugarondemand.com/#Opportunities/58bff47e-b25e-11e9-bd27-02ae981fbade | SCES Division |  | 2019-07-26 | HDM Electric Inc | 58bff47e-b25e-11e9-bd27-02ae981fbade | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27704 | PIP_APPROVED | PIP_APPROVED | 12781 4th Avenue | Victorville | CA | 92395 | Daniel Jones | 2019-08-10 16:11 | 7605142247 | dan.jonessr@safelite.com | Viola Jones | 7605083216 |  | 11234 | 0.15 | Shaun Labelle | 2019-08-10 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-10 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-05 07:00 | 2019-08-12 | 0.38 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 3.25 | 2 | Jethro Andal | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-05 | 4 | 5 | Brian Le | Completed | 2019-08-16 | 0 | 3 | Andrew Moralez | Completed | 2019-08-30 | 9.79 | 10 | Andrew Moralez | Completed | 2019-09-05 | 0.38 | 2 | Ara Sotto | Completed | 2019-09-06 | 0.96 | 2 | Ara Sotto | Completed | 2019-08-29 | 8.92 | 2 | Brian Le | Completed | 2019-08-16 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 0.92 | 1 |  | Completed | 2019-08-26 | 6.75 | 1 | Andrew Clemons | Completed | 2019-09-27 | 16.33 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 3 | 2 | Jill Allen | Completed | [15 empty] | 2019-09-12 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 5.92 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.92 | 1 | Jill Allen | Completed |  | 2019-09-12 | 2019-09-09 | 2 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-30 | 2019-09-06 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27704 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27704 | https://completesolar.sugarondemand.com/#Opportunities/0c9ead32-bbc4-11e9-8559-0630baf9dcb8 | Christopher Cellini |  | 2019-08-06 | Power Town Solar Electric | 0c9ead32-bbc4-11e9-8559-0630baf9dcb8 | 4 | 1 | 0 | 5 | 5 | 5 | 5 | 15
27849 | PIP_APPROVED | PIP_APPROVED | 9573 Oakfield Court | Spring Valley | CA | 91977 | Isabella Restani | 2019-08-13 15:58 | 6196077765 | fourrdi@frontiernet.net | Arnold Broden | 9164582797 |  | 7688 | 0.185 | Michael Marlaire | 2019-08-13 | 4.575 |  | Kyle Wilson | Darlynn Lacap | 2019-08-12 | 2019-08-13 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-04 | 2019-08-14 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 2 | 2 | Jethro Andal | Completed | 2019-08-19 | 0.88 | 1 | Christina Horton | Completed | 2019-09-05 | 2.58 | 5 | Brian Le | Completed | 2019-08-16 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-19 | 0.88 | 3 | Ernesto Enriquez | Completed | 2019-09-05 | 1.38 | 1 | Christina Horton | Completed | 2019-09-06 | 1 | 2 | Christina Horton | Completed | 2019-08-28 | 7 | 2 | Brian Le | Completed | 2019-08-19 | 1 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 0 | 1 |  | Completed | 2019-08-23 | 5.04 | 1 | Andrew Clemons | Completed | 2019-09-04 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 3 | 2 | Jill Allen | Completed | [15 empty] | 2019-09-12 | 2.21 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.79 | 1 | Andrew Clemons | Completed |  | 2019-09-11 | 2019-09-10 | 2.83 | 2 | Christina Horton | Completed | [10 empty] | 5.21 | [11 empty] | 2019-08-21 | 2019-09-06 | SPRING VALLEY | Spring Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27849 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27849 | https://completesolar.sugarondemand.com/#Opportunities/da98d9aa-be1d-11e9-be3f-0630baf9dcb8 | Kyle Wilson |  | 2019-08-12 | iEnergy ElectricSolar | da98d9aa-be1d-11e9-be3f-0630baf9dcb8 | 5 | 1 | -5 | 5 | 5 | 5 | 5 | 10
27857 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 5100 Pismo Court | Antioch | CA | 94531 | Carlos Velasquez | 2019-08-13 13:02 | 5105128618 | lexcruiser@sbcglobal.net | Maria Velasquez | (510) 371-1899 |  | 6285 |  | Ricardo Virgen | 2019-08-13 | 4.27 | Christina Horton | Sunwave Energy | Darlynn Lacap | 2019-08-12 | 2019-08-13 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-05 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-09-04 07:00 | 2019-08-14 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 1.21 | 2 | Jethro Andal | Completed | 2019-08-26 | 6.83 | 1 | Christina Horton | Completed | 2019-09-05 | 5.5 | 5 | Brian Le | Completed | 2019-08-16 | 1 | 3 | Ernesto Enriquez | Completed | 2019-08-16 | 0 | 2 | Andrew Moralez | Completed | 2019-09-05 | 1.08 | 1 | Christina Horton | Completed |  | 32.46 | 2 | Christina Horton | Current | 2019-08-27 | 2 | 2 | Brian Le | Completed | 2019-08-23 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0 | 1 |  | Completed | 2019-08-28 | 7.54 | 1 | Andrew Clemons | Completed | 2019-09-04 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-06 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-10 | 3.21 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 2.21 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 1.08 | 1 | Andrew Clemons | Completed |  | 2019-09-05 | 2019-09-05 | 0 | 2 | Christina Horton | Completed | [10 empty] | 5.3 | [11 empty] | 2019-08-20 |  | ANTIOCH | Antioch | https://heliotrack.completesolar.com/job.php?action=review&jobID=27857 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27857 | https://completesolar.sugarondemand.com/#Opportunities/2c5ef3fa-be05-11e9-bbba-069e4f790264 | Sunwave Energy |  | 2019-08-12 | Golden Gate Electric Service | 2c5ef3fa-be05-11e9-bbba-069e4f790264 | 0 | 46 | 10 | -2 | 5 | 5 | 5 | 18
26720 | PIP_APPROVED | PIP_APPROVED | 572 Glen Heather Drive | San Marcos | CA | 92069 | Marlene Paladino | 2019-08-10 09:34 | 6193228456 | tvcrb@hotmail.com | Roberta Paladino |  |  | 7652 | 0.163 | Michael Marlaire | 2019-07-08 | 4.88 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-06-26 | 2019-07-08 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-04 | Installation Complete | SunRun Monthly | [6 empty] | 2019-09-04 07:00 | 2019-08-10 | 3.83 | 2 | Marcia Garay | Completed | 2019-08-14 | 2.54 | 2 | Daniel Speegle | Completed | 2019-09-04 | 5.71 | 1 | Ara Sotto | Completed | 2019-09-04 | 3.13 | 5 | Brian Le | Completed | 2019-08-16 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-16 | 0.08 | 0 | Andrew Moralez | Completed | 2019-09-04 | 0.38 | 1 | Ara Sotto | Completed | 2019-09-18 | 9.79 | 2 | Ara Sotto | Completed | 2019-08-29 | 2.71 | 2 | Brian Le | Completed | 2019-08-22 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 0.08 | 1 |  | Completed | 2019-08-28 | 1.79 | 1 | Andrew Clemons | Completed |  | 33.54 | 1 | Marcia Garay | Current | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-10 13:59 |  |  | 33.13 | 2 | Ara Sotto | Current | [10 empty] | 23.79 | [11 empty] | 2019-08-16 | 2019-09-18 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=26720 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26720 | https://completesolar.sugarondemand.com/#Opportunities/c6c8cede-a1cc-11e9-bdcd-022c40d974e6 | Jordan Litrownik |  | 2019-06-26 | Blalock Electric&Solar | c6c8cede-a1cc-11e9-bdcd-022c40d974e6 | 47 | 14 | -25 | -2 | 5 | 5 | 5 | -17
27071 | PIP_APPROVED | PIP_APPROVED | 40815 Siltstone Court | Palmdale | CA | 93551 | Maria Umana | 2019-07-15 12:02 | 8055388828 | mariahenry821@gmail.com | Delmy Umana | 7146091205 |  | 9264 | 0.136 | Bill Angevine | 2019-07-15 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-13 | 2019-07-15 08:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-09-04 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-04 07:00 | 2019-07-29 | 9.04 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-05 | 4.83 | 1 | Ara Sotto | Completed | 2019-09-04 | 3.17 | 5 | Brian Le | Completed | 2019-07-23 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-25 | 0.08 | 0 | Andrew Moralez | Completed | 2019-09-04 | 0.84 | 1 | Ara Sotto | Completed | 2019-09-26 | 15.92 | 2 | Ara Sotto | Completed | 2019-08-29 | 22.88 | 2 | Brian Le | Completed | 2019-07-29 | 0 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.08 | 1 |  | Completed | 2019-08-07 | 6.96 | 1 | Andrew Clemons | Completed | 2019-10-08 | 24.67 | 1 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-14 | 12.08 | 4 | Marcia Garay | Completed | 2019-08-14 | 0 | 5 | Marcia Garay | Completed | 2019-08-29 | 9 | 12 | Marcia Garay | Completed | 2019-10-08 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-10-09 | 0.88 | 2 | Ashley Rockwood | Completed |  | 8.29 | 2 | Marcia Garay | Current | 2019-10-10 | 1.13 | 1 | Andrew Clemons | Completed | 2019-09-10 16:55 |  | 2019-10-08 | 23.92 | 2 | Ara Sotto | Completed | [10 empty] | 31.97 | [11 empty] | 2019-07-25 | 2019-09-26 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27071 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27071 | https://completesolar.sugarondemand.com/#Opportunities/11c1b020-a733-11e9-8b7f-069e4f790264 | Solar Raze | Emily Bowden | 2019-07-11 | JK Solar | 11c1b020-a733-11e9-8b7f-069e4f790264 | 34 | 22 | -25 | -2 | 5 | 5 | 5 | -17
27330 | PIP_APPROVED | PIP_APPROVED | 17465 Cabela Drive | San Diego | CA | 92127 | Kenneth Gongon | 2019-07-29 15:02 | 8587227125 | kgongon@yahoo.com | Jantzen Gongon | 6198945949 |  | 7283 | 0.222 | Michael Marlaire | 2019-07-25 | 5.185 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-22 | 2019-07-23 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-09-04 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-09-04 07:00 | 2019-07-29 | 1.21 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 1.75 | 2 | Jethro Andal | Completed | 2019-08-07 | 5.91 | 1 | Ara Sotto | Completed | 2019-09-04 | 3.13 | 5 | Brian Le | Completed | 2019-08-05 | 2.29 | 3 | Ernesto Enriquez | Completed | 2019-08-05 | 0 | 15 | Andrew Moralez | Completed | 2019-09-04 | 0.59 | 1 | Ara Sotto | Completed | 2019-09-17 | 8.92 | 2 | Ara Sotto | Completed | 2019-08-29 | 20.92 | 2 | Brian Le | Completed | 2019-07-31 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 2.08 | 1 |  | Completed | 2019-08-02 | 3 | 1 | Noe Gomez | Completed | 2019-09-04 | 0.59 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-31 | 2.75 | 4 | Darlynn Lacap | Completed | 2019-08-07 | 4.96 | 5 | Darlynn Lacap | Completed | 2019-08-26 | 12.96 | 12 | Darlynn Lacap | Completed | 2019-09-12 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 6.04 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.88 | 1 | Andrew Clemons | Completed | 2019-09-09 16:50 | 2019-08-30 | 2019-09-10 | 4 | 2 | Ara Sotto | Completed | [10 empty] | 2.21 | [11 empty] | 2019-08-26 | 2019-09-17 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27330 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27330 | https://completesolar.sugarondemand.com/#Opportunities/7878975a-aef1-11e9-af32-02ae981fbade | Jordan Litrownik | Nakul Pandya | 2019-07-22 | Blalock Electric&Solar | 7878975a-aef1-11e9-af32-02ae981fbade | 6 | 13 | -5 | -2 | 5 | 5 | 5 | 3
27474 | PIP_APPROVED | PIP_APPROVED | 3405 Robin Street | San Diego | CA | 92115 | Kenny Huynh | 2019-08-01 17:51 | 6194717701 | kennyhuynh118@yahoo.com | Cathy Huynh | 6194717502 |  | 4212 | 0.18 | Chad Malloy | 2019-08-01 | 2.745 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-29 | 2019-08-01 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-09-04 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 0 | 2019-09-04 | 2019-08-02 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 3.75 | 2 | Jethro Andal | Completed | 2019-08-20 | 8 | 1 | Christina Horton | Completed | 2019-09-04 | 13.96 | 5 | Brian Le | Completed | 2019-08-19 | 0.17 | 3 | Ernesto Enriquez | Completed | 2019-08-19 | 0 | 15 | Ernesto Enriquez | Completed | 2019-09-04 | 0.42 | 1 | Christina Horton | Completed | 2019-09-13 | 6.88 | 2 | Christina Horton | Completed | 2019-08-13 | 2.83 | 2 | Brian Le | Completed | 2019-08-08 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.92 | 1 |  | Completed | 2019-08-15 | 4.88 | 1 | Andrew Clemons | Completed | 2019-09-04 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-16 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 7 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 1.88 | 1 | Andrew Clemons | Completed |  | 2019-09-13 | 2019-09-13 | 6.88 | 2 | Christina Horton | Completed | [10 empty] | 8.5 | [11 empty] | 2019-09-10 | 2019-09-13 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27474 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27474 | https://completesolar.sugarondemand.com/#Opportunities/a3c3541c-b4bf-11e9-a634-0630baf9dcb8 | Blake Sanders | Shalan Pieroni | 2019-07-26 | Infinity Energy Inc | a3c3541c-b4bf-11e9-a634-0630baf9dcb8 | 9 | 9 | -5 | -2 | 5 | 5 | 5 | 3
27646 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 37902 50th Street East | Palmdale | CA | 93552 | Maria Ramos | 2019-08-06 15:15 | 8187995344 | anguie45@hotmail.com |  |  |  | 8376 | 0.132 | Chris Peaslee | 2019-08-06 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-04 | 2019-08-06 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-09-04 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-03 07:00 | 2019-08-07 | 0.96 | 2 | Marcia Garay | Completed | 2019-08-10 | 2.38 | 2 | Daniel Speegle | Completed | 2019-08-09 | 0.08 | 1 | Ara Sotto | Completed | 2019-09-04 | 3.17 | 5 | Brian Le | Completed | 2019-08-15 | 1.33 | 3 | Andrew Moralez | Completed | 2019-08-27 | 8 | 0 | Andrew Moralez | Completed | 2019-09-04 | 1.42 | 1 | Ara Sotto | Completed |  | 33.08 | 2 | Ara Sotto | Current | 2019-08-29 | 13 | 2 | Brian Le | Completed | 2019-08-12 | 0.38 | 2 | Marcia Garay | Completed | 2019-08-14 | 2.54 | 1 |  | Completed | 2019-08-15 | 3.38 | 1 | Andrew Clemons | Completed |  | 34.54 | 1 | Marcia Garay | Current | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-11 | 0.17 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 5.13 | 2 | Marcia Garay | Completed |  | 27.25 | 1 | Andrew Clemons | Current | 2019-09-10 16:52 | 2019-08-28 | 2019-09-11 | 4.83 | 2 | Ara Sotto | Completed | [10 empty] | 1 | [11 empty] | 2019-08-15 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27646 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27646 | https://completesolar.sugarondemand.com/#Opportunities/a53054b8-b897-11e9-9fc1-0630baf9dcb8 | SCES Division | Henry Garcia | 2019-08-04 | JK Solar | a53054b8-b897-11e9-9fc1-0630baf9dcb8 | 7 | 47 | -5 | -2 | 5 | 5 | 5 | 3
27902 | PIP_APPROVED | PIP_APPROVED | 6593 Mesada Street | Rancho Cucamonga | CA | 91737 | Jorge Alvarado | 2019-08-16 12:08 | 3233141666 | jorgealvarado91730@gmail.com | Sofia Alvarado | 5629650696 |  | 10411 | 0.15 | Shaun Labelle | 2019-08-16 | 6.405 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-13 | 2019-08-15 09:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 |  | MPU | 2019-09-04 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-04 07:00 | 2019-08-20 | 1.88 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.04 | 2 | Jethro Andal | Completed | 2019-09-04 | 9.04 | 1 | Ara Sotto | Completed | 2019-09-04 | 3.17 | 5 | Brian Le | Completed | 2019-08-22 | 0.92 | 3 | Andrew Moralez | Completed | 2019-08-26 | 2.08 | 15 | Ernesto Enriquez | Completed | 2019-09-04 | 0.38 | 2 | Ara Sotto | Completed | 2019-09-06 | 1.96 | 2 | Ara Sotto | Completed | 2019-08-29 | 4.79 | 2 | Brian Le | Completed | 2019-08-22 | 1.04 | 2 | Marcia Garay | Completed | 2019-08-21 | 0.13 | 1 |  | Completed | 2019-08-26 | 3.17 | 1 | Andrew Clemons | Completed |  | 25.25 | 1 | Marcia Garay | Current | 2019-09-11 | 3 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-12 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 21 | 2 | Marcia Garay | Completed | 2019-09-16 | 0.96 | 1 | Andrew Clemons | Completed | 2019-09-09 17:03 | 2019-09-25 | 2019-09-10 | 2.88 | 2 | Ara Sotto | Completed | 2019-09-10 | 0.92 | 1 | Ara Sotto | Completed | 2019-09-09 | 0.17 | 2 | Marcia Garay | Completed | 10.75 | [11 empty] | 2019-09-13 | 2019-09-06 | RANCHO CUCAMONGA | Rancho Cucamonga | https://heliotrack.completesolar.com/job.php?action=review&jobID=27902 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27902 | https://completesolar.sugarondemand.com/#Opportunities/31ec6946-c059-11e9-838d-069e4f790264 | Summit Marketing Inc | Martha Reyes | 2019-08-13 | Power Town Solar Electric | 31ec6946-c059-11e9-838d-069e4f790264 | 0 | 2 | 10 | 4 | 5 | 5 | 5 | 24
27435 | PIP_APPROVED | PIP_APPROVED | 936 South Rancho Santa Fe Road | San Marcos | CA | 92078 | Maellen Shepherd | 2019-07-26 19:48 | 7607270545 | grammael@ymail.com | Shawn Shepherd | 7608779186 |  | 7028 | 0.151 | Michael Marlaire | 2019-07-26 | 4.27 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-25 | 2019-07-26 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | NO | 2019-09-03 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-09-03 07:00 | 2019-07-30 | 1.54 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 8.04 | 2 | Jethro Andal | Completed | 2019-08-27 | 1.08 | 1 | Christina Horton | Completed | 2019-09-03 | 2.5 | 5 | Brian Le | Completed | 2019-08-09 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-09 | 0.08 | 0 | Andrew Moralez | Completed | 2019-09-03 | 0.42 | 1 | Christina Horton | Completed | 2019-09-17 | 9.83 | 2 | Christina Horton | Completed | 2019-08-12 | 0.08 | 2 | Brian Le | Completed | 2019-08-12 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 1 |  | Completed | 2019-08-14 | 0.08 | 1 | Andrew Clemons | Completed | 2019-09-03 | 0.38 | 1 | Darlynn Lacap | Completed |  | 24.25 | 2 | Andrew Clemons | Current | [15 empty] | 2019-09-18 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 8 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 3.83 | 1 | Andrew Clemons | Completed |  | 2019-09-17 | 2019-09-17 | 5.75 | 2 | Christina Horton | Completed | [10 empty] | 20.46 | [11 empty] | 2019-08-09 | 2019-09-17 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27435 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27435 | https://completesolar.sugarondemand.com/#Opportunities/f06f89da-b018-11e9-8f11-02ae981fbade | Lindsey Lange |  | 2019-07-25 | Infinity Energy Inc | f06f89da-b018-11e9-8f11-02ae981fbade | 14 | 14 | -15 | -2 | 5 | 5 | 5 | -7
27812 | PIP_APPROVED | PIP_APPROVED | 2169 Paradise Hills Road | San Diego | CA | 92114 | Naomi Tantiango | 2019-08-15 14:03 | 6192526883 | naomijan@yahoo.com |  |  |  | 9284 | 0.165 | Ryan Malloy | 2019-08-15 | 7.015 | Ara Sotto | Solar Power Marketing | Marcia Garay | 2019-08-10 | 2019-08-15 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-09-03 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-09-03 07:00 | 2019-08-15 | 0.04 | 2 | Marcia Garay | Completed | 2019-08-16 | 1.04 | 2 | Jethro Andal | Completed | 2019-08-20 | 1.75 | 1 | Christina Horton | Completed | 2019-09-03 | 1.75 | 5 | Brian Le | Completed | 2019-08-23 | 0.83 | 3 | Andrew Moralez | Completed | 2019-08-23 | 0.08 | 15 | Andrew Moralez | Completed | 2019-09-03 | 0.33 | 2 | Ara Sotto | Completed | 2019-09-24 | 11.88 | 2 | Ara Sotto | Completed | 2019-08-28 | 4 | 2 | Brian Le | Completed | 2019-08-22 | 3.83 | 2 | Marcia Garay | Completed | 2019-08-22 | 3.92 | 1 |  | Completed | 2019-08-26 | 5.92 | 1 | Andrew Clemons | Completed | 2019-09-03 | 0.46 | 1 | Marcia Garay | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-25 | 9 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 6.88 | 2 | Marcia Garay | Completed | 2019-10-03 | 2.83 | 1 | Jill Allen | Completed | 2019-09-04 14:06 |  | 2019-09-06 | 2.88 | 2 | Ara Sotto | Completed | [10 empty] | 13.06 | [11 empty] | 2019-09-16 | 2019-09-24 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27812 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27812 | https://completesolar.sugarondemand.com/#Opportunities/082cba66-bfa0-11e9-b4db-0630baf9dcb8 | Solar Power Marketing |  | 2019-08-10 | Zachary Noah Gamez | 082cba66-bfa0-11e9-b4db-0630baf9dcb8 | 3 | 21 | 0 | -2 | 5 | 5 | 5 | 8
25592 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3003 Jackson Street | San Francisco | CA | 94115 | Will Stegall | 2019-06-14 17:37 | 4157966800 | WStegall@routeonepartners.com |  |  |  | 15447.14 |  | Ricardo Virgen | 2019-06-14 | 10.22 | Christina Horton |  | Darlynn Lacap |  | 2019-05-23 12:00 | LG 365W | 365 | 28 | LG | SolarEdge Technologies | SE10000H-US | Rolled Roofing / Torchdown | NO | 2019-08-31 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-08-26 07:00 | 2019-06-17 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 6.84 | 2 | Daniel Speegle | Completed | 2019-07-26 | 20.17 | 1 | Christina Horton | Completed | 2019-08-27 | 3.96 | 5 | Brian Le | Completed | 2019-07-02 | 3.96 | 3 | Andrew Moralez | Completed | 2019-07-24 | 14.26 | 5 | Andrew Moralez | Completed | 2019-08-31 | 4.79 | 3 | Christina Horton | Completed |  | 34.71 | 2 | Christina Horton | Current | 2019-08-21 | 29.92 | 2 | Brian Le | Completed | 2019-07-01 | 2.16 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 0 | 1 |  | Completed | 2019-07-18 | 14.26 | 1 | Noe Gomez | Completed | 2019-08-28 | 2.38 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [15 empty] | 2019-09-19 | 3.79 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 2.79 | 2 | Ashley Rockwood | Completed |  | 19.33 | 2 | Darlynn Lacap | Current |  | 19.33 | 1 | Noe Gomez | Current | 2019-09-06 19:58 |  | 2019-09-06 | 3.54 | 2 | Christina Horton | Completed | [10 empty] | 14.26 | [11 empty] | 2019-07-11 |  | SAN FRANCISCO | San Francisco | https://heliotrack.completesolar.com/job.php?action=review&jobID=25592 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25592 | https://completesolar.sugarondemand.com/#Opportunities/bcc96738-8f05-11e9-9877-022c40d974e6 | Josh Webb |  | 2019-05-31 | All Bay Solar | bcc96738-8f05-11e9-9877-022c40d974e6 | 6 | 51 | -5 | -2 | 5 | 5 | 5 | 3
27642 | PIP_APPROVED | PIP_APPROVED | 204 Umber Court | San Diego | CA | 92114 | Mialyn Medina | 2019-08-10 11:39 | 6197018594 | meyzys@yahoo.com | Nellie Reyes | 6197334503 |  | 4753 | 0.138 | Ryan Malloy | 2019-08-10 | 2.745 |  | Solar Power Marketing | Darlynn Lacap | 2019-08-03 | 2019-08-10 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-31 07:00 | 2019-08-12 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 2.04 | 2 | Daniel Speegle | Completed | 2019-08-26 | 7.88 | 1 | Christina Horton | Completed | 2019-08-31 | 1.29 | 5 | Brian Le | Completed | 2019-08-23 | 2 | 3 | Ernesto Enriquez | Completed | 2019-08-23 | 0 | 15 | Andrew Moralez | Completed | 2019-08-31 | 0.08 | 1 | Christina Horton | Completed | 2019-09-03 | 0.38 | 2 | Christina Horton | Completed | 2019-08-29 | 3.16 | 2 | Brian Le | Completed | 2019-08-20 | 3 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 4.83 | 1 |  | Completed | 2019-08-26 | 7.79 | 1 | Noe Gomez | Completed | 2019-09-03 | 0.54 | 1 | Darlynn Lacap | Completed |  | 34.33 | 2 | Andrew Clemons | Current | [15 empty] | 2019-09-09 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 7.04 | 2 | Ashley Rockwood | Completed | 2019-10-01 | 9.13 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.79 | 1 | Jeremiah Liend | Completed | 2019-09-05 08:41 |  | 2019-09-05 | 2.54 | 2 | Christina Horton | Completed | [10 empty] | 10.99 | [11 empty] | 2019-09-16 | 2019-09-03 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27642 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27642 | https://completesolar.sugarondemand.com/#Opportunities/2ca6f7a4-bb9e-11e9-847c-0630baf9dcb8 | Solar Power Marketing |  | 2019-08-03 | iEnergy ElectricSolar | 2ca6f7a4-bb9e-11e9-847c-0630baf9dcb8 | 5 | 3 | -5 | 2 | 5 | 5 | 5 | 7
26216 | PIP_APPROVED | PIP_APPROVED | 6 Coppel Drive | Tenafly | NJ | 7670 | Michael Lin | 2019-06-28 16:35 | 9174782703 | mlin1974@yahoo.com | Cecilia Chan | 9173357850 | ceciliaechan@gmail.com | 14032.18 |  | Andrew Weber | 2019-06-08 | 12.505 | Christina Horton | Sunlogic Power | Darlynn Lacap | 2019-06-06 | 2019-06-08 12:00 | LR6-60PB-305M | 305 | 41 | LONGi Solar | SolarEdge | SE11400A-US RGM |  | NO | 2019-08-30 | NEM Submitted | Sunlight Financial Loan | 0 | 0 |  | 0 | 0 | 1 | 2019-08-29 07:00 | 2019-06-28 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 8.46 | 2 | Daniel Speegle | Completed | 2019-08-15 | 26.75 | 1 | Christina Horton | Completed | 2019-08-29 | 0.08 | 5 | Christina Horton | Completed | 2019-07-15 | 3.67 | 3 | Andrew Moralez | Completed | 2019-07-22 | 5.04 | 10 | Andrew Moralez | Completed | 2019-08-30 | 1.17 | 3 | Christina Horton | Completed | 2019-08-30 | 0.25 | 2 | Christina Horton | Completed | 2019-08-30 | 11.96 | 2 | Brian Le | Completed | 2019-07-09 | 2.83 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 3.21 | 1 |  | Completed | 2019-07-24 | 13.79 | 1 | Jeremiah Liend | Completed | 2019-08-29 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-09-03 | 0.67 | 2 | Jill Allen | Completed | [15 empty] | 2019-10-18 | 11.63 | 2 | Ashley Rockwood | Completed |  | 1.29 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-09-30 | 2019-09-24 | 6.58 | 2 | Christina Horton | Completed | [10 empty] | 55.67 | [11 empty] | 2019-07-29 | 2019-08-30 | Default | Tenafly | https://heliotrack.completesolar.com/job.php?action=review&jobID=26216 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26216 | https://completesolar.sugarondemand.com/#Opportunities/c89e9f4c-8b9a-11e9-b799-02ae981fbade | Anthony Fowler |  | 2019-06-06 | Skyline Solar | c89e9f4c-8b9a-11e9-b799-02ae981fbade | 25 | 0 | -25 | 5 | 5 | 5 | 5 | -10
26578 | PIP_APPROVED | PIP_APPROVED | 212 Pardee Street | San Diego | CA | 92102 | Wesley D McGowan | 2019-07-06 07:31 | 6198927705 | mcgowanvee.sd@gmail.com |  |  |  | 7451 | 0.2 | Ryan Malloy | 2019-07-06 | 5.185 |  | UpGrid Inc | Marcia Garay | 2019-06-21 | 2019-06-22 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-08-30 | Installation Complete | SunRun Monthly |  | 0 |  |  | 0 |  | 2019-08-29 07:00 | 2019-08-07 | 3.63 | 2 | Marcia Garay | Completed | 2019-07-19 | 0.16 | 2 | Daniel Speegle | Completed | 2019-08-22 | 10.5 | 1 | Christina Horton | Completed | 2019-08-29 | 0 | 5 | Brian Le | Completed | 2019-08-23 | 6.75 | 3 | Andrew Moralez | Completed | 2019-08-23 | 0 | 15 | Andrew Moralez | Completed | 2019-08-30 | 1.21 | 2 | Christina Horton | Completed | 2019-09-04 | 2.08 | 2 | Christina Horton | Completed | 2019-08-23 | 6.71 | 2 | Brian Le | Completed | 2019-08-14 | 4.71 | 2 | Marcia Garay | Completed | 2019-07-19 | 0.08 | 1 |  | Completed | 2019-08-01 | 0.08 | 1 | Andrew Clemons | Completed |  | 36.54 | 1 | Marcia Garay | Current | 2019-09-04 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 28.13 | 1 | Christina Horton | Inactive | 2019-08-08 | 0.88 | 2 | Marcia Garay | Completed | 41.47 | [11 empty] | 2019-09-16 | 2019-09-04 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26578 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26578 | https://completesolar.sugarondemand.com/#Opportunities/a5532944-9ffa-11e9-b7c8-022c40d974e6 | Josh Gonzales |  | 2019-06-21 | iEnergy ElectricSolar | a5532944-9ffa-11e9-b7c8-022c40d974e6 |  | 5 | -25 | -2 | 5 | 5 | 5 | -17
26681 | PIP_APPROVED | PIP_APPROVED | 324 Nettleton Road | Vista | CA | 92083 | Loreto Ramirez | 2019-08-07 14:35 | 7607170494 | loretoramirez324@yahoo.com | Maria Ramirez | 7608409624 |  | 5262 | 0.185 | Michael Marlaire | 2019-07-10 | 3.66 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-29 | 2019-07-01 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-30 | PTO Received | SunRun Monthly |  |  |  |  | 1 | 1 | 2019-08-30 07:00 | 2019-08-07 | 2.66 | 2 | Marcia Garay | Completed | 2019-08-13 | 5.75 | 2 | Jethro Andal | Completed | 2019-08-19 | 9.34 | 1 | Christina Horton | Completed | 2019-08-29 | 18.8 | 5 | Brian Le | Completed | 2019-08-15 | 3.29 | 3 | Andrew Moralez | Completed | 2019-08-15 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-30 | 0.58 | 1 | Christina Horton | Completed | 2019-09-24 | 16.17 | 2 | Christina Horton | Completed | 2019-08-13 | 0.16 | 2 | Brian Le | Completed | 2019-08-13 | 5.26 | 2 | Marcia Garay | Completed | 2019-08-14 | 1.96 | 1 |  | Completed | 2019-08-19 | 9.26 | 1 | Andrew Clemons | Completed | 2019-09-10 | 6.75 | 1 | Marcia Garay | Completed | 2019-09-04 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 1.58 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 7.83 | 2 | Marcia Garay | Completed | 2019-09-23 | 2.79 | 1 | Jill Allen | Completed |  | 2019-09-19 | 2019-09-14 | 4.62 | 2 | Christina Horton | Completed | [10 empty] | 44.21 | 2019-08-12 | 2.79 | 14 | James Fernandez | Completed | 2019-08-12 | 2019-08-12 | 0.08 | 1 | James Fernandez | Completed | 2019-08-15 | 2019-09-24 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=26681 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26681 | https://completesolar.sugarondemand.com/#Opportunities/ad0ef430-a377-11e9-a74a-0630baf9dcb8 | Brett Martinez | Xavier Kimbrough | 2019-06-24 | Infinity Energy Inc | ad0ef430-a377-11e9-a74a-0630baf9dcb8 | 15 | 25 | -15 | -2 | 5 | 5 | 5 | -7
27057 | PIP_APPROVED | PIP_APPROVED | 4935 Calvin Avenue | Los Angeles | CA | 91356 | Rick Mechammil | 2019-07-17 11:10 | 8189709139 | rickm1986@gmail.com |  |  |  | 13205 | 0.19 | Chris Peaslee | 2019-07-17 | 10.675 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-11 | 2019-07-12 15:00 | LR6-60PB-305M | 305 | 35 | LONGi Solar | SolarEdge | SE10000A-US RGM |  | NO | 2019-08-30 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-28 07:00 | 2019-07-18 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-07 | 11.16 | 2 | Jethro Andal | Completed | 2019-07-30 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-30 | 7.04 | 5 | Brian Le | Completed | 2019-08-19 | 6.75 | 3 | Ernesto Enriquez | Completed | 2019-08-19 | 0 | 0 | Andrew Moralez | Completed | 2019-08-30 | 4.17 | 3 | Ara Sotto | Completed | 2019-09-04 | 1.83 | 2 | Ara Sotto | Completed | 2019-08-21 | 5.88 | 2 | Brian Le | Completed | 2019-08-08 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.13 | 1 |  | Completed | 2019-08-15 | 5.88 | 1 | Andrew Clemons | Completed | 2019-08-28 | 0.8 | 1 | Darlynn Lacap | Completed |  | 22.87 | 2 | Andrew Clemons | Current | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-09 16:49 |  |  | 35 | 2 | Ara Sotto | Current | [10 empty] | 27.87 | [11 empty] | 2019-08-19 | 2019-09-04 | TARZANA | Tarzana | https://heliotrack.completesolar.com/job.php?action=review&jobID=27057 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27057 | https://completesolar.sugarondemand.com/#Opportunities/083116b8-a8be-11e9-9f09-0630baf9dcb8 | Tier1 Power | Jordan Litrownik | 2019-07-11 | Blalock Electric&Solar | 083116b8-a8be-11e9-9f09-0630baf9dcb8 | 52 | 5 | -25 | -2 | 5 | 5 | 5 | -17
27076 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1316 Sicard Street | Marysville | CA | 95901 | Cody Turner | 2019-08-01 18:31 | 5309335532 | ct16@live.com | Laurie | 916-271-0431 | cturnercalifornia@gmail.com | 10419 | 0.179 | Ricardo Virgen | 2019-08-01 | 7.625 | Christina Horton | Blue Bright | Darlynn Lacap | 2019-07-27 | 2019-08-01 15:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-29 07:00 | 2019-08-02 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-07 | 2.96 | 2 | Jethro Andal | Completed | 2019-08-13 | 3.96 | 1 | Christina Horton | Completed | 2019-08-29 | 3.96 | 5 | Brian Le | Completed | 2019-08-22 | 9.71 | 3 | Ernesto Enriquez | Completed | 2019-08-22 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-30 | 1.21 | 2 | Christina Horton | Completed |  | 35.29 | 2 | Christina Horton | Current | 2019-08-23 | 9.63 | 2 | Brian Le | Completed | 2019-08-09 | 2.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1 | 1 |  | Completed | 2019-08-22 | 10.88 | 1 | Jeremiah Liend | Completed | 2019-08-29 | 0.33 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-05 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 3.79 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 10 | 2 | Darlynn Lacap | Completed | 2019-09-12 | 1.29 | 1 | Jill Allen | Completed | 2019-09-03 10:05 |  | 2019-09-03 | 1.21 | 2 | Christina Horton | Completed | [10 empty] | 1.25 | [11 empty] | 2019-08-22 |  | MARYSVILLE | Marysville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27076 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27076 | https://completesolar.sugarondemand.com/#Opportunities/2ae1039a-b4c5-11e9-9d1c-069e4f790264 | Blue Bright |  | 2019-07-12 | Sepac EnergySystems | 2ae1039a-b4c5-11e9-9d1c-069e4f790264 | 4 | 52 | 0 | -2 | 5 | 5 | 5 | 8
27336 | PIP_APPROVED | PIP_APPROVED | 24651 Leafwood Drive | Murrieta | CA | 92562 | Veronica Gomez | 2019-08-14 06:20 | 9519079513 | sportsplus110@msn.com | Manuel Gomez | 9519079514 | bcbgomez@msn.com | 8559 | 0.172 | Chris Peaslee | 2019-08-13 | 5.795 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-22 | 2019-07-23 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-29 07:00 | 2019-08-14 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-08-16 | 2.13 | 2 | Daniel Speegle | Completed | 2019-08-22 | 3.92 | 1 | Christina Horton | Completed | 2019-08-29 | 4.04 | 5 | Brian Le | Completed | 2019-08-19 | 0.04 | 3 | Andrew Moralez | Completed | 2019-08-21 | 2.04 | 1 | Andrew Moralez | Completed | 2019-08-30 | 1.21 | 2 | Christina Horton | Completed | 2019-09-24 | 16.46 | 2 | Christina Horton | Completed | 2019-08-21 | 1.92 | 2 | Brian Le | Completed | 2019-08-19 | 1 | 2 | Darlynn Lacap | Completed | 2019-08-19 | 0.83 | 1 |  | Completed | 2019-08-26 | 5.71 | 1 | Andrew Clemons | Completed | 2019-08-29 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-25 | 0.13 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-08 | 8 | 2 | Darlynn Lacap | Completed | 2019-10-03 | 5 | 1 | Jill Allen | Completed | 2019-09-24 15:19 |  | 2019-09-25 | 13.21 | 2 | Christina Horton | Completed | [10 empty] | 6.68 | [11 empty] | 2019-08-20 | 2019-09-24 | MURRIETA | Murrieta | https://heliotrack.completesolar.com/job.php?action=review&jobID=27336 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27336 | https://completesolar.sugarondemand.com/#Opportunities/2ac09a9e-be96-11e9-b776-0630baf9dcb8 | Lindsey Lange | Alyson Drago | 2019-07-22 | Infinity Energy Inc | 2ac09a9e-be96-11e9-b776-0630baf9dcb8 | 26 | 25 | -25 | -2 | 5 | 5 | 5 | -17
27491 | PIP_APPROVED | PIP_APPROVED | 6215 Dixie Drive | La Mesa | CA | 91942 | Anthony Alameda | 2019-08-02 18:02 | 8086303329 | apcalameda@gmail.com | Ami Alameda | 8086303330 | emiko.808@gmail.com | 4468 | 0.2 | Ryan Malloy | 2019-08-02 | 2.745 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-29 | 2019-08-02 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-06 | 1.92 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 3.79 | 2 | Daniel Speegle | Completed | 2019-08-19 | 4.54 | 1 | Christina Horton | Completed | 2019-08-30 | 10.17 | 5 | Brian Le | Completed | 2019-08-13 | 1.13 | 3 | Ernesto Enriquez | Completed | 2019-08-13 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-30 | 0.29 | 1 | Christina Horton | Completed | 2019-09-23 | 15.04 | 2 | Christina Horton | Completed | 2019-08-13 | 0.08 | 2 | Brian Le | Completed | 2019-08-13 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 0 | 1 |  | Completed | 2019-08-22 | 4.88 | 1 | Noe Gomez | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-25 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 11.84 | 2 | Ashley Rockwood | Completed |  | 5.29 | 2 | Darlynn Lacap | Current | 2019-10-16 | 2.21 | 1 | Andrew Clemons | Completed | 2019-09-24 16:19 |  | 2019-09-23 | 4.71 | 2 | Christina Horton | Completed | [10 empty] | 19.33 | [11 empty] | 2019-08-13 | 2019-09-23 | LA MESA | La Mesa | https://heliotrack.completesolar.com/job.php?action=review&jobID=27491 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27491 | https://completesolar.sugarondemand.com/#Opportunities/3e38a7c0-b58a-11e9-9969-069e4f790264 | Chad Bright | Robert Blessing | 2019-07-27 | Infinity Energy Inc | 3e38a7c0-b58a-11e9-9969-069e4f790264 | 24 | 24 | -25 | -2 | 5 | 5 | 5 | -17
27545 | PIP_APPROVED | PIP_APPROVED | 6837 Rosefield Drive | La Mesa | CA | 91942 | Richard Arneson | 2019-08-02 12:03 | 6197338506 | arniesue333@outlook.com |  |  |  | 6262 | 0.188 | Ryan Malloy | 2019-08-02 | 4.27 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-30 | 2019-08-02 09:00 | LR6-60PE-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-02 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 3.92 | 2 | Jethro Andal | Completed | 2019-08-15 | 5 | 1 | Christina Horton | Completed | 2019-08-30 | 10.04 | 5 | Brian Le | Completed | 2019-08-13 | 2 | 3 | Ernesto Enriquez | Completed | 2019-08-13 | 0.21 | 0 | Ernesto Enriquez | Completed | 2019-08-30 | 0.46 | 1 | Christina Horton | Completed | 2019-09-04 | 1.92 | 2 | Christina Horton | Completed | 2019-08-13 | 0.83 | 2 | Brian Le | Completed | 2019-08-12 | 2.08 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.92 | 1 |  | Completed | 2019-08-20 | 7.92 | 1 | Andrew Clemons | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-04 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-05 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 11.88 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 5.67 | 1 | Andrew Clemons | Completed | 2019-09-04 15:49 |  | 2019-09-04 | 1.92 | 2 | Christina Horton | Completed | [10 empty] | 4.71 | [11 empty] | 2019-08-13 | 2019-09-04 | LA MESA | La Mesa | https://heliotrack.completesolar.com/job.php?action=review&jobID=27545 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27545 | https://completesolar.sugarondemand.com/#Opportunities/16d6b2e4-b558-11e9-880e-02ae981fbade | Blake Sanders |  | 2019-07-30 | Infinity Energy Inc | 16d6b2e4-b558-11e9-880e-02ae981fbade | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
27590 | PIP_APPROVED | PIP_APPROVED | 27226 Clifton Street | Highland | CA | 92346 | Misael Elias | 2019-08-08 17:11 | 9096705088 | misaelelias83@gmail.com | Brenda Elias | 9092622140 |  | 5322 | 0.18 | Alex Holdridge | 2019-08-08 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-08-06 | 2019-08-08 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-09 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 2.92 | 2 | Jethro Andal | Completed | 2019-08-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-30 | 5.21 | 5 | Brian Le | Completed | 2019-08-15 | 0.25 | 3 | Andrew Moralez | Completed | 2019-08-21 | 3.96 | 14 | Andrew Moralez | Completed | 2019-08-30 | 0.46 | 1 | Ara Sotto | Completed | 2019-09-03 | 0.96 | 2 | Ara Sotto | Completed | 2019-08-23 | 3.75 | 2 | Brian Le | Completed | 2019-08-19 | 3.08 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.75 | 1 |  | Completed | 2019-08-26 | 7.88 | 1 | Jeremiah Liend | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-06 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 5.92 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.71 | 1 | Andrew Clemons | Completed |  | 2019-09-13 | 2019-09-05 | 2.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-05 | 2019-09-03 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=27590 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27590 | https://completesolar.sugarondemand.com/#Opportunities/1e4646c0-ba3a-11e9-b6a8-069e4f790264 | 300 Stars Inc |  | 2019-08-01 | HDM Electric Inc | 1e4646c0-ba3a-11e9-b6a8-069e4f790264 | 6 | 4 | -5 | 0 | 5 | 5 | 5 | 5
27614 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 5101 Pismo Court | Antioch | CA | 94531 | Tara Jaber | 2019-08-05 11:13 | 9258583410 | jaberlivermore@aol.com |  |  |  | 10532 | 0.131 | Ricardo Virgen | 2019-08-05 | 6.71 | Christina Horton | Sunwave Energy | Darlynn Lacap | 2019-08-02 | 2019-08-05 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-05 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 3.92 | 2 | Jethro Andal | Completed | 2019-08-14 | 3.04 | 1 | Christina Horton | Completed | 2019-08-30 | 4.92 | 5 | Brian Le | Completed | 2019-08-13 | 1.17 | 3 | Andrew Moralez | Completed | 2019-08-13 | 0 | 2 | Ernesto Enriquez | Completed | 2019-08-30 | 0.46 | 2 | Christina Horton | Completed |  | 35.04 | 2 | Christina Horton | Current | 2019-08-22 | 7.92 | 2 | Brian Le | Completed | 2019-08-12 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 1 |  | Completed | 2019-08-20 | 6.92 | 1 | Jill Allen | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-09-04 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-09 | 2.17 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 3.75 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 6.13 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.96 | 1 | Andrew Clemons | Completed | 2019-09-04 18:21 |  | 2019-09-05 | 2.71 | 2 | Christina Horton | Completed | [10 empty] | 5.34 | [11 empty] | 2019-08-15 |  | ANTIOCH | Antioch | https://heliotrack.completesolar.com/job.php?action=review&jobID=27614 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27614 | https://completesolar.sugarondemand.com/#Opportunities/b450d6de-b7ac-11e9-88f7-069e4f790264 | Sunwave Energy |  | 2019-08-02 | Golden Gate Electric Service | b450d6de-b7ac-11e9-88f7-069e4f790264 | 6 | 52 | -5 | -2 | 5 | 5 | 5 | 3
27696 | PIP_APPROVED | PIP_APPROVED | 430 West Redondo Drive | Oceanside | CA | 92057 | David Dielman | 2019-08-09 19:12 | 7603106584 | ddielman@cox.net |  |  |  | 6771 | 0.197 | Michael Marlaire | 2019-08-09 | 4.575 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-08-06 | 2019-08-09 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-29 07:00 | 2019-08-14 | 2.58 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-22 | 5.88 | 1 | Christina Horton | Completed | 2019-08-30 | 5.71 | 5 | Brian Le | Completed | 2019-08-14 | 0 | 3 | Andrew Moralez | Completed | 2019-08-20 | 3.96 | 10 | Andrew Moralez | Completed | 2019-08-30 | 1.21 | 1 | Ara Sotto | Completed | 2019-08-30 | 0.13 | 2 | Ara Sotto | Completed | 2019-08-23 | 3.71 | 2 | Brian Le | Completed | 2019-08-15 | 1 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 0.04 | 1 |  | Completed | 2019-08-19 | 2.88 | 1 | Noe Gomez | Completed | 2019-08-29 | 0.33 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.13 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-05 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 7.75 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 5.13 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 3.88 | 1 | Andrew Clemons | Completed |  | 2019-09-10 | 2019-09-04 | 2.17 | 2 | Ara Sotto | Completed | [10 empty] | 2.34 | [11 empty] | 2019-08-28 | 2019-08-30 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27696 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27696 | https://completesolar.sugarondemand.com/#Opportunities/3e8cafc0-bb14-11e9-84c5-069e4f790264 | Brett Martinez | Omar Jackson | 2019-08-06 | Zachary Noah Gamez | 3e8cafc0-bb14-11e9-84c5-069e4f790264 | 5 | 0 | -5 | 5 | 5 | 5 | 5 | 10
27708 | PIP_APPROVED | PIP_APPROVED | 26951 Messina Street | Highland | CA | 92346 | Yosmara L Martinez | 2019-08-08 12:16 | 9096720829 | yoric92@gmail.com |  |  |  | 8131 | 0.14 | Alex Holdridge | 2019-08-08 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-08-07 | 2019-08-08 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-08-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-30 07:00 | 2019-08-09 | 0.88 | 2 | Marcia Garay | Completed | 2019-08-14 | 3.04 | 2 | Jethro Andal | Completed | 2019-08-14 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-30 | 3 | 5 | Brian Le | Completed | 2019-08-21 | 4.04 | 3 | Andrew Moralez | Completed | 2019-08-26 | 3.08 | 14 | Andrew Moralez | Completed | 2019-08-30 | 0.38 | 2 | Ara Sotto | Completed | 2019-09-05 | 2.96 | 2 | Ara Sotto | Completed | 2019-08-27 | 9 | 2 | Brian Le | Completed | 2019-08-14 | 0 | 2 | Marcia Garay | Completed | 2019-08-15 | 0.92 | 1 |  | Completed | 2019-08-19 | 2.92 | 1 | Andrew Clemons | Completed | 2019-09-04 | 2.5 | 1 | Marcia Garay | Completed | 2019-09-04 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-06 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-10 | 1.71 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 7.17 | 2 | Marcia Garay | Completed | 2019-09-11 | 1.17 | 1 | Andrew Clemons | Completed |  | 2019-09-16 | 2019-09-05 | 0 | 2 | Ara Sotto | Completed | 2019-09-05 | 3.46 | 1 | Ara Sotto | Completed | 2019-08-14 | 0.17 | 2 | Marcia Garay | Completed | 1 | [11 empty] | 2019-09-11 | 2019-09-05 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=27708 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27708 | https://completesolar.sugarondemand.com/#Opportunities/e79306be-ba10-11e9-98d8-069e4f790264 | Oscar Hernandez |  | 2019-08-06 | Green Road Solar Crew | e79306be-ba10-11e9-98d8-069e4f790264 | 0 | 6 | 10 | -2 | 5 | 5 | 5 | 18
27728 | PIP_APPROVED | PIP_APPROVED | 2530 Hollywood Drive | Campo | CA | 91906 | Macho Rosa | 2019-08-13 13:55 | 9092633178 | macho.rosa2010@gmail.com | Erin Rosa | 9092634178 |  | 7167.31 |  | Ryan Malloy | 2019-08-13 | 5.49 | Ara Sotto | LaDon Daniels | Darlynn Lacap | 2019-08-07 | 2019-08-13 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-30 | NEM Submitted | Dividend | 0 | 0 |  |  |  | 1 | 2019-08-30 07:00 | 2019-08-14 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 1.17 | 2 | Jethro Andal | Completed | 2019-08-14 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-30 | 5.13 | 5 | Brian Le | Completed | 2019-08-15 | 0 | 3 | Andrew Moralez | Completed | 2019-08-16 | 1 | 0 | Andrew Moralez | Completed | 2019-08-30 | 0.38 | 2 | Ara Sotto | Completed | 2019-10-21 | 35 | 2 | Ara Sotto | Completed | 2019-08-23 | 4.92 | 2 | Brian Le | Completed | 2019-08-16 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0 | 1 |  | Completed | 2019-10-02 | 27.96 | 1 | Andrew Clemons | Completed | 2019-08-30 | 0.38 | 1 | Darlynn Lacap | Completed |  | 0.08 | 2 | Noe Gomez | Current | [15 empty] | 2019-10-16 | 18.79 | 2 | Ashley Rockwood | Completed |  | 3.17 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-09 09:06 |  | 2019-09-10 | 6 | 2 | Ara Sotto | Completed | [10 empty] | 14.05 | [11 empty] | 2019-08-15 | 2019-10-08 | CAMPO | Campo | https://heliotrack.completesolar.com/job.php?action=review&jobID=27728 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27728 | https://completesolar.sugarondemand.com/#Opportunities/9b52e576-be0c-11e9-9832-069e4f790264 | LaDon Daniels |  | 2019-08-07 | Zachary Noah Gamez | 9b52e576-be0c-11e9-9832-069e4f790264 | 11 | 52 | -15 | -2 | 5 | 5 | 5 | -7
24314 | PIP_APPROVED | PIP_APPROVED | 6543 Verdon Street | Palmdale | CA | 93552 | Manuel Ramos | 2019-07-17 09:27 | 3234490525 | manuel.ramos11.mr@gmail.com |  |  | mramos5622@gmail.com | 5930 | 0.143 | Bill Angevine | 2019-04-23 | 3.05 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-04-03 | 2019-04-20 16:00 | Q.PEAK-G4.1 305 | 305 | 10 | Hanwha Q CELLS | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-29 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 0 | 2019-08-28 07:00 | 2019-07-17 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-17 | 1.79 | 2 | Daniel Speegle | Completed | 2019-08-01 | 19.84 | 1 | Ara Sotto | Completed |  | 36.04 | 5 | Brian Le | Current | 2019-07-17 | 4.75 | 3 | Andrew Moralez | Completed | 2019-07-17 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-29 | 1.46 | 1 | Ara Sotto | Completed | 2019-09-20 | 14.88 | 2 | Ara Sotto | Completed | 2019-08-29 | 64.84 | 2 | Brian Le | Completed | 2019-07-17 | 0.5 | 2 | Marcia Garay | Completed | 2019-07-17 | 0.13 | 1 |  | Completed | 2019-07-17 | 23.25 | 1 | Jeremiah Liend | Completed |  | 37.54 | 1 | Marcia Garay | Current | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-17 | 28.41 | 30 | Marcia Garay | Completed | 2019-07-17 | 0 | 5 | Marcia Garay | Completed | 2019-08-21 | 24.92 | 12 | Marcia Garay | Completed | 2019-09-05 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 9 | 2 | Marcia Garay | Completed | 2019-09-11 | 2.92 | 1 | Jill Allen | Completed |  |  | 2019-09-04 | 2.92 | 2 | Ara Sotto | Completed | [10 empty] | 18.2 | [11 empty] | 2019-07-17 | 2019-09-20 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=24314 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24314 | https://completesolar.sugarondemand.com/#Opportunities/ee22dffe-660a-11e9-b1e1-0630baf9dcb8 | Kevin Adams | Emily Bowden | 2019-04-03 | JK Solar | ee22dffe-660a-11e9-b1e1-0630baf9dcb8 | 6 | 22 | -5 | -2 | 5 | 5 | 5 | 3
26796 | PIP_APPROVED | PIP_APPROVED | 6146 Wolfstar Court | San Diego | CA | 92122 | Guillermo Adame | 2019-08-01 18:14 | 6199932308 | gadame@gmail.com |  |  |  | 9869.99 | 0.181 | Michael Marlaire | 2019-07-01 | 8.235 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-29 | 2019-07-01 15:00 | LR6-60PB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-08-29 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-08-29 07:00 | 2019-08-01 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-07 | 6.42 | 2 | Daniel Speegle | Completed | 2019-08-14 | 9.96 | 1 | Christina Horton | Completed | 2019-08-29 | 7.08 | 5 | Brian Le | Completed | 2019-08-19 | 6.29 | 3 | Ernesto Enriquez | Completed | 2019-08-19 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-29 | 0.33 | 2 | Christina Horton | Completed | 2019-08-30 | 1.04 | 2 | Christina Horton | Completed | 2019-08-13 | 2.91 | 2 | Brian Le | Completed | 2019-08-08 | 4.12 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 6.84 | 1 |  | Completed | 2019-08-14 | 9.96 | 1 | Andrew Clemons | Completed | 2019-08-29 | 0.33 | 1 | Darlynn Lacap | Completed |  | 35.13 | 2 | Noe Gomez | Current | [15 empty] | 2019-09-17 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 0 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 1.04 | 2 | Darlynn Lacap | Completed |  | 24.17 | 1 | Andrew Clemons | Current |  | 2019-09-16 | 2019-09-16 | 11.04 | 2 | Christina Horton | Completed | 2019-08-08 | 0.08 | 1 | Christina Horton | Completed | 2019-08-08 | 1.05 | 2 | Darlynn Lacap | Completed | 29.06 | [11 empty] | 2019-09-10 | 2019-08-30 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26796 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26796 | https://completesolar.sugarondemand.com/#Opportunities/5c8c839c-9c65-11e9-9e89-0630baf9dcb8 | Robert Blessing |  | 2019-06-28 | Infinity Energy Inc | 5c8c839c-9c65-11e9-9e89-0630baf9dcb8 | 18 | 1 | -15 | 5 | 5 | 5 | 5 | 0
26872 | PIP_APPROVED | PIP_APPROVED | 3207 Hebron Lane | Stockton | CA | 95206 | Rigoberto Jacobo | 2019-07-30 17:20 | 5593898852 | jacrigs77@yahoo.com |  |  |  | 7184 |  | Ricardo Virgen | 2019-07-23 | 4.27 | Christina Horton | PACE Avenue | Marcia Garay | 2019-07-02 | 2019-07-08 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-29 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  | 1 | 1 | 2019-08-29 07:00 | 2019-07-30 | 0.75 | 2 | Marcia Garay | Completed | 2019-07-31 | 2.58 | 2 | Jethro Andal | Completed | 2019-08-08 | 7.01 | 1 | Christina Horton | Completed | 2019-08-29 | 0.13 | 5 | Brian Le | Completed | 2019-08-12 | 5.37 | 3 | Ernesto Enriquez | Completed | 2019-08-12 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-29 | 0.46 | 1 | Christina Horton | Completed | 2019-09-04 | 2.96 | 2 | Christina Horton | Completed | 2019-08-23 | 10 | 2 | Brian Le | Completed | 2019-08-02 | 3.01 | 2 | Marcia Garay | Completed | 2019-08-01 | 1.88 | 1 |  | Completed | 2019-08-21 | 9.34 | 1 | Andrew Clemons | Completed | 2019-09-03 | 2.46 | 1 | Marcia Garay | Completed | 2019-09-03 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-09 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 3.71 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 2.08 | 2 | Marcia Garay | Completed | 2019-09-17 | 2.04 | 1 | Jill Allen | Completed | 2019-09-04 18:19 |  | 2019-09-04 | 1.08 | 2 | Christina Horton | Completed | [10 empty] | 15.11 | 2019-08-05 | 6.96 | 14 | James Fernandez | Completed | 2019-08-05 | 2019-08-05 | 0.08 | 1 | James Fernandez | Completed | 2019-08-12 | 2019-09-04 | STOCKTON | Stockton | https://heliotrack.completesolar.com/job.php?action=review&jobID=26872 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26872 | https://completesolar.sugarondemand.com/#Opportunities/52f073e2-adb4-11e9-8064-069e4f790264 | PACE Avenue |  | 2019-07-02 | Golden Gate Electric Service | 52f073e2-adb4-11e9-8064-069e4f790264 | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27272 | PIP_APPROVED | PIP_APPROVED | 3346 Gillette Street | San Diego | CA | 92102 | Juan Lopez | 2019-07-24 07:59 | 8059909671 | contodo23@gmail.com |  |  | juaanlopez3346@gmail.com | 7084 | 0.25 | Chad Malloy | 2019-07-23 | 4.575 |  | UpGrid Inc | Marcia Garay | 2019-07-19 | 2019-07-22 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-29 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-28 | 2019-07-29 | 3 | 2 | Marcia Garay | Completed | 2019-07-30 | 1.17 | 2 | Daniel Speegle | Completed | 2019-08-21 | 13.8 | 1 | Christina Horton | Completed | 2019-08-28 | 2.13 | 5 | Brian Le | Completed | 2019-08-19 | 2.25 | 3 | Andrew Moralez | Completed | 2019-08-19 | 0 | 15 | Andrew Moralez | Completed | 2019-08-29 | 1.33 | 1 | Christina Horton | Completed | 2019-08-30 | 0.96 | 2 | Christina Horton | Completed | 2019-08-26 | 7.67 | 2 | Brian Le | Completed | 2019-08-14 | 8.71 | 2 | Marcia Garay | Completed | 2019-08-15 | 1.62 | 1 |  | Completed | 2019-08-26 | 16.34 | 1 | Noe Gomez | Completed |  | 37.17 | 1 | Marcia Garay | Current | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 0.13 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 10.13 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Jill Allen | Completed |  | 2019-08-30 | 2019-08-30 | 0.92 | 2 | Christina Horton | Completed | [10 empty] | 27.96 | [11 empty] | 2019-09-10 | 2019-08-30 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27272 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27272 | https://completesolar.sugarondemand.com/#Opportunities/82d2eec2-ae23-11e9-9a60-0630baf9dcb8 | Josh Gonzales |  | 2019-07-19 | iEnergy ElectricSolar | 82d2eec2-ae23-11e9-9a60-0630baf9dcb8 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27384 | PIP_APPROVED | PIP_APPROVED | 1624 Jonathon Street | Vista | CA | 92083 | Krista Mays | 2019-08-07 20:06 | 6197421913 | Gdvibe2001@yahoo.com |  |  |  | 3978 | 0.16 | Michael Marlaire | 2019-07-27 | 2.745 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-25 | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-29 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-29 07:00 | 2019-08-08 | 2.01 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 5.5 | 2 | Daniel Speegle | Completed | 2019-08-15 | 3.63 | 1 | Christina Horton | Completed | 2019-08-29 | 12 | 5 | Brian Le | Completed | 2019-08-14 | 1.17 | 3 | Ernesto Enriquez | Completed | 2019-08-14 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-29 | 0.33 | 1 | Christina Horton | Completed | 2019-08-30 | 1.08 | 2 | Christina Horton | Completed | 2019-08-13 | 1 | 2 | Brian Le | Completed | 2019-08-12 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 1.63 | 1 |  | Completed | 2019-08-23 | 9.63 | 1 | Andrew Clemons | Completed | 2019-08-29 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-09-11 | 6.92 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-16 | 10.13 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 8 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.79 | 1 | Jeremiah Liend | Completed |  | 2019-08-22 | 2019-08-30 | 0.96 | 2 | Christina Horton | Completed | [10 empty] | 9.38 | [11 empty] | 2019-08-14 | 2019-08-30 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27384 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27384 | https://completesolar.sugarondemand.com/#Opportunities/88c26a5c-b0a2-11e9-a5df-022c40d974e6 | Xavier Kimbrough |  | 2019-07-23 | Infinity Energy Inc | 88c26a5c-b0a2-11e9-a5df-022c40d974e6 | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27512 | SP APPROVED |  | 37470 Bristol Court | Palmdale | CA | 93550 | Willie Brown | 2019-07-30 18:34 | 6617339623 | willie.brown.dominion@gmail.com | Delthine Brown | 6614703614 |  | 12425 | 0.143 | Bill Angevine | 2019-07-30 | 7.93 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-29 | 2019-07-30 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-29 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-28 07:00 | 2019-07-31 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-03 | 2.42 | 2 | Jethro Andal | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-29 | 6.08 | 5 | Brian Le | Completed | 2019-08-13 | 4.21 | 3 | Andrew Moralez | Completed | 2019-08-21 | 5.88 | 0 | Ernesto Enriquez | Completed | 2019-08-29 | 1.46 | 2 | Ara Sotto | Completed |  | 36.04 | 2 | Ara Sotto | Current | 2019-08-21 | 10.83 | 2 | Brian Le | Completed | 2019-08-06 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-08-07 | 2.42 | 1 |  | Completed | 2019-08-07 | 2.46 | 1 | Andrew Clemons | Completed | 2019-08-28 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-22 |  | 36.04 | 2 | Ara Sotto | Current | [10 empty] | 0 | [11 empty] | 2019-08-13 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27512 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27512 | https://completesolar.sugarondemand.com/#Opportunities/4e9384e0-b333-11e9-9de8-0630baf9dcb8 | Henry Garcia |  | 2019-07-29 | JK Solar | 4e9384e0-b333-11e9-9de8-0630baf9dcb8 | 53 | 53 | -25 | -2 | 5 | 5 | 5 | -17
27535 | PIP_APPROVED | PIP_APPROVED | 22982 Via Santana | Nuevo | CA | 92567 | Lindsay Marie Lewis | 2019-07-31 15:40 | 9516635491 | lindsaymariek12@yahoo.com | Christopher Lewis | 9512851049 |  | 8161 | 0.002 | Shaun Labelle | 2019-07-31 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-29 | 2019-07-31 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-29 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-29 07:00 | 2019-08-01 | 0.75 | 2 | Marcia Garay | Completed | 2019-08-02 | 0.58 | 2 | Jethro Andal | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-29 | 4.04 | 5 | Brian Le | Completed | 2019-08-06 | 1.71 | 3 | Ernesto Enriquez | Completed | 2019-08-07 | 0.92 | 0 | Andrew Moralez | Completed | 2019-08-29 | 0.33 | 1 | Ara Sotto | Completed | 2019-08-30 | 1.13 | 2 | Ara Sotto | Completed | 2019-08-23 | 13.08 | 2 | Brian Le | Completed | 2019-08-06 | 2.29 | 2 | Marcia Garay | Completed | 2019-08-02 | 0.71 | 1 |  | Completed | 2019-08-07 | 3.29 | 1 | Jill Allen | Completed | 2019-08-29 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-02 | 1.13 | 4 | Marcia Garay | Completed | 2019-08-14 | 7.17 | 5 | Marcia Garay | Completed | 2019-08-23 | 6.83 | 12 | Darlynn Lacap | Completed | 2019-09-03 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 3.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 8.04 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.17 | 1 | Andrew Clemons | Completed | 2019-08-30 09:04 |  | 2019-08-30 | 1.04 | 2 | Ara Sotto | Completed | [10 empty] | 1.75 | [11 empty] | 2019-08-06 | 2019-08-30 | NUEVO | Nuevo | https://heliotrack.completesolar.com/job.php?action=review&jobID=27535 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27535 | https://completesolar.sugarondemand.com/#Opportunities/278b9980-b3e4-11e9-a51e-02ae981fbade | PJB Division |  | 2019-07-29 | Zachary Noah Gamez | 278b9980-b3e4-11e9-a51e-02ae981fbade | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
24132 | PIP_APPROVED | PIP_APPROVED | 1962 15th Street | Olivehurst | CA | 95961 | Michael Hall | 2019-08-12 14:33 | 5307430144 | mhalltonight@gmail.com | Helen Hall | 5306822586 | helenhall530@hotmail.com | 16924 |  | Ricardo Virgen | 2019-06-06 | 10.065 | Christina Horton | Blue Bright | Darlynn Lacap | 2019-05-31 | 2019-06-06 09:00 | LR6-60PB-305M | 305 | 33 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | MPU | 2019-08-28 | PTO Received | Dividend | 0 | 0 |  | 0 | 1 | 1 | 2019-08-28 07:00 | 2019-08-13 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 7.29 | 2 | Jethro Andal | Completed | 2019-08-19 | 10.67 | 1 | Christina Horton | Completed | 2019-08-28 | 12.05 | 5 | Brian Le | Completed | 2019-08-14 | 3.54 | 3 | Andrew Moralez | Completed | 2019-08-14 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-28 | 1.13 | 3 | Christina Horton | Completed | 2019-09-05 | 4.71 | 2 | Christina Horton | Completed | 2019-08-20 | 8.95 | 2 | Brian Le | Completed | 2019-08-13 | 3.28 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 0.34 | 1 |  | Completed | 2019-08-19 | 5.24 | 1 | Andrew Clemons | Completed | 2019-08-28 | 0.97 | 1 | Darlynn Lacap | Completed |  | 32.25 | 2 | Noe Gomez | Current | [15 empty] | 2019-09-20 | 5.17 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 3.75 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2 | 2 | Darlynn Lacap | Completed |  | 17.38 | 1 | Jill Allen | Current | 2019-08-30 17:42 |  | 2019-08-30 | 1.71 | 2 | Christina Horton | Completed | 2019-08-27 | 5.63 | 1 | Christina Horton | Completed | 2019-08-15 | 1.08 | 2 | Darlynn Lacap | Completed | 31.71 | 2019-08-19 | 1.54 | 14 | James Fernandez | Completed | 2019-08-17 | 2019-08-19 | 0.42 | 1 | James Fernandez | Completed | 2019-08-14 | 2019-09-05 | OLIVEHURST | Olivehurst | https://heliotrack.completesolar.com/job.php?action=review&jobID=24132 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24132 | https://completesolar.sugarondemand.com/#Opportunities/74442764-88a2-11e9-9eab-022c40d974e6 | Blue Bright |  | 2019-05-14 | Golden Gate Electric Service | 74442764-88a2-11e9-9eab-022c40d974e6 | 2 | 8 | 7 | -2 | 5 | 5 | 5 | 15
25278 | PIP_APPROVED | PIP_APPROVED | 106-15 31st Avenue | East Elmhurst | NY | 11552 | Nadhia Powell | 2019-05-13 09:06 | 9294620592 | nadhiapowell@yahoo.com |  | 9173554566 |  | 3855 |  | Complete Solar NY Tech 1 | 2019-05-13 | 3.355 | Christina Horton | Sunlogic Power | Darlynn Lacap | 2019-05-03 | 2019-05-11 10:00 | Q.PEAK-G4.1 305 | 305 | 11 | Hanwha Q CELLS | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-28 | PTO Received | Dividend | [6 empty] | 2019-08-27 07:00 | 2019-05-31 | 2.21 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 28.79 | 2 | Jethro Andal | Completed | 2019-08-12 | 19.17 | 1 | Christina Horton | Completed | 2019-08-28 | 0 | 5 | Brian Le | Completed | 2019-07-16 | 0 | 3 | Andrew Moralez | Completed | 2019-08-07 | 15.79 | 10 | Andrew Moralez | Completed | 2019-08-28 | 1.33 | 1 | Christina Horton | Completed | 2019-10-21 | 37.08 | 2 | Christina Horton | Completed | 2019-08-28 | 18.75 | 2 | Brian Le | Completed | 2019-07-19 | 3.04 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 0 | 1 |  | Completed | 2019-07-22 | 4.13 | 1 | Andrew Clemons | Completed | 2019-08-28 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-10-03 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-18 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-10-01 | 8.71 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 14.04 | 2 | Darlynn Lacap | Completed |  | 14.33 | 1 | Noe Gomez | Current |  | 2019-10-11 | 2019-09-17 | 13.17 | 2 | Christina Horton | Completed | [10 empty] | 24.76 | [11 empty] | 2019-07-30 | 2019-10-21 | Default |  | https://heliotrack.completesolar.com/job.php?action=review&jobID=25278 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25278 | https://completesolar.sugarondemand.com/#Opportunities/fdc832a4-7598-11e9-8f77-0630baf9dcb8 | Sunlogic Power | Anthony Fowler | 2019-05-03 | Hytech Solar | fdc832a4-7598-11e9-8f77-0630baf9dcb8 | 20 | 54 | -15 | -2 | 5 | 5 | 5 | -7
27433 | PIP_APPROVED | PIP_APPROVED | 559 Gold Drive | Oceanside | CA | 92057 | Larry Howard | 2019-07-30 18:55 | 7608056078 | lh4464@aol.com |  |  |  | 5504.48 | 0.19 | Michael Marlaire | 2019-07-30 | 2.745 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-26 | 2019-07-30 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-08-28 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-28 07:00 | 2019-07-31 | 0.63 | 2 | Marcia Garay | Completed | 2019-08-07 | 5.04 | 2 | Daniel Speegle | Completed | 2019-08-14 | 4.92 | 1 | Christina Horton | Completed | 2019-08-28 | 9.38 | 5 | Brian Le | Completed | 2019-08-08 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-09 | 1.04 | 10 | Ernesto Enriquez | Completed | 2019-08-28 | 0.33 | 1 | Christina Horton | Completed | 2019-09-19 | 14.84 | 2 | Christina Horton | Completed | 2019-08-12 | 2.96 | 2 | Brian Le | Completed | 2019-08-07 | 0.08 | 2 | Marcia Garay | Completed | 2019-08-08 | 1.04 | 1 |  | Completed | 2019-08-13 | 3.79 | 1 | Andrew Clemons | Completed | 2019-08-28 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-23 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.83 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 1.79 | 1 | Noe Gomez | Completed | 2019-09-20 11:23 |  | 2019-09-19 | 0.83 | 2 | Christina Horton | Completed | 2019-09-18 | 0.67 | 1 | Christina Horton | Completed | 2019-08-08 | 0.96 | 2 | Marcia Garay | Completed | 5.5 | [11 empty] | 2019-08-22 | 2019-09-19 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27433 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27433 | https://completesolar.sugarondemand.com/#Opportunities/212b9f1c-b336-11e9-bdd5-02ae981fbade | Brett Martinez | Omar Jackson | 2019-07-25 | Infinity Energy Inc | 212b9f1c-b336-11e9-bdd5-02ae981fbade | 1 | 22 | 10 | -2 | 5 | 5 | 5 | 18
27465 | PIP_APPROVED | PIP_APPROVED | 555 Gold Drive | Oceanside | CA | 92057 | Pedro Patino | 2019-07-30 18:39 | 7605196398 | hottltnlvr@sbcglobal.net |  |  |  | 5205 | 0.18 | Michael Marlaire | 2019-07-30 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-27 | 2019-07-30 16:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | MPU | 2019-08-28 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-28 07:00 | 2019-07-31 | 0.63 | 2 | Marcia Garay | Completed | 2019-08-02 | 2.08 | 2 | Jethro Andal | Completed | 2019-08-15 | 8.96 | 1 | Christina Horton | Completed | 2019-08-28 | 7.13 | 5 | Brian Le | Completed | 2019-08-02 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-21 | 12.96 | 10 | Ernesto Enriquez | Completed | 2019-08-28 | 0.54 | 1 | Christina Horton | Completed | 2019-09-24 | 17.88 | 2 | Christina Horton | Completed | 2019-08-13 | 6.04 | 2 | Brian Le | Completed | 2019-08-05 | 0.88 | 2 | Marcia Garay | Completed | 2019-08-02 | 0.13 | 1 |  | Completed | 2019-08-06 | 1.79 | 1 | Andrew Clemons | Completed | 2019-08-28 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-18 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.83 | 2 | Darlynn Lacap | Completed |  | 21.13 | 1 | Andrew Clemons | Current | 2019-09-13 17:29 |  | 2019-09-13 | 1.88 | 2 | Christina Horton | Completed | 2019-09-11 | 0.54 | 1 | Christina Horton | Completed | 2019-08-05 | 0.92 | 2 | Marcia Garay | Completed | 6.93 | [11 empty] | 2019-08-16 | 2019-09-24 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27465 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27465 | https://completesolar.sugarondemand.com/#Opportunities/059f2680-b334-11e9-a45d-0630baf9dcb8 | Brett Martinez |  | 2019-07-26 | Infinity Energy Inc | 059f2680-b334-11e9-a45d-0630baf9dcb8 | 2 | 27 | 7 | -2 | 5 | 5 | 5 | 15
26246 | PIP_APPROVED | PIP_APPROVED | 53 Idalla Road | Worcester | MA | 1606 | Laura F Cherny | 2019-06-19 18:13 | 5084718817 | rcherny@gmail.com | Rob Cherny | 7744526747 |  | 10845 | 0.2 | Hiram Velez | 2019-06-19 | 10.98 | Christina Horton | Solara Solar | Darlynn Lacap | 2019-06-08 | 2019-06-19 15:00 | LR6-60PB-305M | 305 | 36 | LONGi Solar | SolarEdge | SE10000A-US RGM | Composite | MPU | 2019-08-27 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-23 07:00 | 2019-06-20 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-06-25 | 3.04 | 2 | Jethro Andal | Completed | 2019-08-02 | 22.96 | 1 | Christina Horton | Completed | 2019-08-23 | 0 | 5 | Brian Le | Completed | 2019-07-09 | 0.21 | 3 | Andrew Moralez | Completed | 2019-07-11 | 1.67 | 10 | Andrew Moralez | Completed | 2019-08-27 | 2.33 | 3 | Christina Horton | Completed | 2019-09-03 | 3.88 | 2 | Christina Horton | Completed | 2019-08-23 | 34.88 | 2 | Brian Le | Completed | 2019-07-02 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 4.96 | 1 |  | Completed | 2019-07-03 | 2.05 | 1 | Andrew Clemons | Completed | 2019-08-23 | 0.58 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-13 | 4.08 | 2 | Ashley Rockwood | Completed |  | 26.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-09-06 08:01 |  | 2019-09-09 | 6.79 | 2 | Christina Horton | Completed | 2019-08-27 | 2.33 | 1 | Christina Horton | Completed | 2019-08-02 | 7.91 | 2 | Darlynn Lacap | Completed | 33.79 | [11 empty] | 2019-07-23 | 2019-09-03 | Default | Worcester | https://heliotrack.completesolar.com/job.php?action=review&jobID=26246 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26246 | https://completesolar.sugarondemand.com/#Opportunities/7969e3d6-92f8-11e9-97ba-0630baf9dcb8 | Solara Solar | Von Ayers | 2019-06-07 | Skyline Solar | 7969e3d6-92f8-11e9-97ba-0630baf9dcb8 | 13 | 7 | -15 | -2 | 5 | 5 | 5 | -7
26366 | PIP_APPROVED | PIP_APPROVED | 12915 Ilene Street | Poway | CA | 92064 | Randy Bosch | 2019-06-14 11:49 | 8587353336 | susan121@cox.net |  |  |  | 14359 | 0.22 | Chad Malloy | 2019-06-14 | 8.54 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-06-12 | 2019-06-14 09:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | MPU | 2019-07-05 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-27 07:00 | 2019-06-14 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 1.96 | 2 | Daniel Speegle | Completed | 2019-06-17 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-27 | 30.96 | 5 | Brian Le | Completed | 2019-06-19 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-15 | 17 | 14 | Ernesto Enriquez | Completed | 2019-08-27 | 4.59 | 2 | Ara Sotto | Completed | 2019-09-09 | 7.96 | 2 | Ara Sotto | Completed | 2019-07-15 | 17.08 | 2 | Brian Le | Completed | 2019-06-19 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 0.08 | 1 |  | Completed | 2019-07-10 | 13.88 | 1 | Andrew Clemons | Completed | 2019-08-28 | 3.13 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 6 | 2 | Darlynn Lacap | Completed | 2019-09-16 | 0.79 | 1 | Jill Allen | Completed | 2019-08-30 10:02 |  | 2019-08-30 | 0 | 2 | Ara Sotto | Completed | 2019-08-30 | 7.71 | 1 | Ara Sotto | Completed | 2019-06-19 | 0.33 | 2 | Darlynn Lacap | Completed | 4 | [11 empty] | 2019-07-10 | 2019-09-09 | POWAY | Poway | https://heliotrack.completesolar.com/job.php?action=review&jobID=26366 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26366 | https://completesolar.sugarondemand.com/#Opportunities/eeca0282-8ed4-11e9-8b97-0630baf9dcb8 | Jordan Litrownik |  | 2019-06-12 | Blalock Electric&Solar | eeca0282-8ed4-11e9-8b97-0630baf9dcb8 | 0 | 13 | 10 | -2 | 5 | 5 | 5 | 18
27181 | PIP_APPROVED | PIP_APPROVED | 29770 Avenue De Real | Menifee | CA | 92586 | Bryan Escobedo | 2019-07-19 16:17 | 7605041204 | customelectric@gmail.com | Jessica Escobedo |  | 8582485103 | 9179 | 0.169 | Ryan Malloy | 2019-07-19 | 5.49 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-16 | 2019-07-19 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-27 07:00 | 2019-07-22 | 1 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.92 | 2 | Jethro Andal | Completed | 2019-08-09 | 12.13 | 1 | Christina Horton | Completed | 2019-08-27 | 22.04 | 5 | Brian Le | Completed | 2019-07-25 | 0.75 | 3 | Ernesto Enriquez | Completed | 2019-08-02 | 6.46 | 0 | Ernesto Enriquez | Completed | 2019-08-27 | 0.5 | 2 | Christina Horton | Completed | 2019-09-20 | 16.92 | 2 | Christina Horton | Completed | 2019-07-26 | 1.96 | 2 | Brian Le | Completed | 2019-07-24 | 0 | 2 | Marcia Garay | Completed | 2019-07-24 | 0.04 | 1 |  | Completed | 2019-07-30 | 3.79 | 1 | Andrew Clemons | Completed | 2019-09-19 | 16.46 | 1 | Marcia Garay | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-24 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 5.17 | 2 | Marcia Garay | Completed | 2019-09-26 | 0.96 | 1 | Andrew Clemons | Completed | 2019-09-20 10:19 |  | 2019-09-20 | 16.92 | 2 | Christina Horton | Completed | [10 empty] | 1 | [11 empty] | 2019-07-25 | 2019-09-20 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27181 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27181 | https://completesolar.sugarondemand.com/#Opportunities/ef5974e4-aa5e-11e9-a011-02ae981fbade | Robert Garcia | Michael Foster | 2019-07-16 | Infinity Energy Inc | ef5974e4-aa5e-11e9-a011-02ae981fbade | 24 | 24 | -25 | -2 | 5 | 5 | 5 | -17
27440 | PIP_APPROVED | PIP_APPROVED | 14126 Apple Creek Dr Victorville CA 92395 | Victorville | CA | 92395 | Jessica Ochoa | 2019-07-29 11:53 | 7608818237 | ochoajess54@yahoo.com |  |  |  | 8885 | 0.145 | Shaun Labelle | 2019-07-29 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-25 | 2019-07-29 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 |  | NO | 2019-08-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-27 07:00 | 2019-07-30 | 0.96 | 2 | Marcia Garay | Completed | 2019-08-06 | 5.17 | 2 | Daniel Speegle | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-27 | 3.88 | 5 | Brian Le | Completed | 2019-08-08 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-20 | 7.79 | 10 | Ernesto Enriquez | Completed | 2019-08-27 | 1.71 | 1 | Ara Sotto | Completed | 2019-08-28 | 0.96 | 2 | Ara Sotto | Completed | 2019-08-21 | 3.88 | 2 | Brian Le | Completed | 2019-08-15 | 4.08 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.96 | 1 |  | Completed | 2019-08-13 | 4.63 | 1 | Jill Allen | Completed | 2019-08-28 | 2.76 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.92 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-08-30 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 10.63 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 3.96 | 1 | Noe Gomez | Completed | 2019-08-27 20:54 |  | 2019-08-28 | 0.88 | 2 | Ara Sotto | Completed | [10 empty] | 2.96 | [11 empty] | 2019-08-22 | 2019-08-27 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27440 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27440 | https://completesolar.sugarondemand.com/#Opportunities/2ba98496-b22c-11e9-ac7a-02ae981fbade | Christopher Cellini | Shane Montana | 2019-07-25 | Power Town Solar Electric | 2ba98496-b22c-11e9-ac7a-02ae981fbade | 1 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27488 | PIP_APPROVED | PIP_APPROVED | 1475 Pearl Place | Escondido | CA | 92027 | Eric Gronquist | 2019-08-01 17:25 | 7607466661 | newfiewon@aol.com | Marilyn Gronquist | 7607466661 |  | 6435 | 0.12 | Ryan Malloy | 2019-08-01 | 3.965 | Christina Horton | Kyle Wilson | Darlynn Lacap | 2019-07-29 | 2019-07-31 12:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-27 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-08-27 | 2019-08-05 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 3.92 | 2 | Daniel Speegle | Completed | 2019-08-19 | 6 | 1 | Christina Horton | Completed | 2019-08-27 | 10 | 5 | Brian Le | Completed | 2019-08-16 | 4.96 | 3 | Ernesto Enriquez | Completed | 2019-08-16 | 0 | 15 | Andrew Moralez | Completed | 2019-08-27 | 0.5 | 1 | Christina Horton | Completed | 2019-09-06 | 6.88 | 2 | Christina Horton | Completed | 2019-08-13 | 0.08 | 2 | Brian Le | Completed | 2019-08-13 | 2.13 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 0.13 | 1 |  | Completed | 2019-08-20 | 6.92 | 1 | Andrew Clemons | Completed | 2019-08-28 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 6.92 | 2 | Ashley Rockwood | Completed |  | 4.83 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-29 17:13 |  | 2019-08-29 | 1.96 | 2 | Christina Horton | Completed | [10 empty] | 25.5 | [11 empty] | 2019-09-09 | 2019-09-06 | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=27488 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27488 | https://completesolar.sugarondemand.com/#Opportunities/f1b80536-b4bb-11e9-bfc1-022c40d974e6 | Kyle Wilson |  | 2019-07-27 | T.A.K. Electric | f1b80536-b4bb-11e9-bfc1-022c40d974e6 | 2 | 10 | 7 | -2 | 5 | 5 | 5 | 15
27965 | PIP_APPROVED | PIP_APPROVED | 667 Meadowview Lane | San Marcos | CA | 92069 | David Porzel | 2019-08-17 16:03 | 7607442634 | davidporzel7@gmail.com |  | 7602877452 |  | 6721 | 0.17 | Michael Marlaire | 2019-08-17 | 4.27 | Ara Sotto | Kyle Wilson | Darlynn Lacap | 2019-08-15 | 2019-08-17 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-27 07:00 | 2019-08-20 | 1.38 | 2 | Marcia Garay | Completed | 2019-08-21 | 1.04 | 2 | Jethro Andal | Completed | 2019-08-27 | 4.04 | 1 | Ara Sotto | Completed | 2019-08-27 | 0.96 | 5 | Brian Le | Completed | 2019-08-22 | 1.08 | 3 | Ernesto Enriquez | Completed | 2019-08-22 | 0.08 | 0 | Ernesto Enriquez | Completed | 2019-08-27 | 0.33 | 1 | Ara Sotto | Completed | 2019-09-25 | 20.04 | 2 | Ara Sotto | Completed | 2019-08-26 | 0.88 | 2 | Brian Le | Completed | 2019-08-23 | 2.17 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 0 | 1 |  | Completed | 2019-08-26 | 2.92 | 1 | Andrew Clemons | Completed |  | 38.54 | 1 | Marcia Garay | Current | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-18 | 6.75 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.71 | 2 | Darlynn Lacap | Completed |  | 21.13 | 1 | Andrew Clemons | Current | 2019-08-28 08:59 |  | 2019-08-29 | 2.25 | 2 | Ara Sotto | Completed | [10 empty] | 6.04 | [11 empty] | 2019-08-22 | 2019-09-25 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27965 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27965 | https://completesolar.sugarondemand.com/#Opportunities/320d752e-c143-11e9-8255-069e4f790264 | Kyle Wilson |  | 2019-08-15 | Zachary Noah Gamez | 320d752e-c143-11e9-8255-069e4f790264 | 2 | 29 | 7 | -2 | 5 | 5 | 5 | 15
26702 | PIP_APPROVED | PIP_APPROVED | 58366 Pueblo Trail | Yucca Valley | CA | 92284 | Claire Nazario | 2019-06-29 13:31 | 7606252205 | claireannph@gmail.com |  |  |  | 8165 | 0.155 | Shaun Labelle | 2019-06-29 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-25 | 2019-06-29 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-26 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-26 07:00 | 2019-07-01 | 0.5 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 4.08 | 2 | Jethro Andal | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-26 | 3 | 5 | Brian Le | Completed | 2019-07-16 | 4.88 | 3 | Andrew Moralez | Completed | 2019-08-21 | 26 | 0 | Andrew Moralez | Completed | 2019-08-26 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-30 | 3.96 | 2 | Ara Sotto | Completed | 2019-08-21 | 31.83 | 2 | Brian Le | Completed | 2019-07-08 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 0.96 | 1 |  | Completed | 2019-07-11 | 2.67 | 1 | Andrew Clemons | Completed | 2019-08-28 | 2.38 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-03 | 1.21 | 2 | Ashley Rockwood | Completed | 2019-09-10 | 4.75 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 11.96 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 1.17 | 1 | Andrew Clemons | Completed | 2019-08-28 08:55 |  | 2019-08-30 | 3.71 | 2 | Ara Sotto | Completed | [10 empty] | 9.8 | [11 empty] | 2019-07-16 | 2019-08-30 | YUCCA VALLEY | Yucca Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26702 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26702 | https://completesolar.sugarondemand.com/#Opportunities/cc8360ea-9aac-11e9-a37a-022c40d974e6 | SCES Division | Ryan Wilcox | 2019-06-25 | Power Town Solar Electric | cc8360ea-9aac-11e9-a37a-022c40d974e6 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
26958 | SP APPROVED |  | 554 Niles Street | San Bernardino | CA | 92404 | Marchetta Rogers | 2019-07-30 10:17 | 9094537351 | pinx400@msn.com |  |  |  | 8251 | 0.182 | Alex Holdridge | 2019-07-16 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-10 | 2019-07-11 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-08-26 | Installation Complete | SunRun Monthly |  | 0 |  |  |  |  | 2019-08-24 | 2019-07-30 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 2.59 | 2 | Daniel Speegle | Completed | 2019-08-02 | 2.08 | 1 | Ara Sotto | Completed | 2019-08-26 | 0.08 | 5 | Ara Sotto | Completed | 2019-08-02 | 0.96 | 3 | Ernesto Enriquez | Completed | 2019-08-02 | 0 | 1 | Andrew Moralez | Completed | 2019-08-26 | 0.33 | 2 | Ara Sotto | Completed |  | 39.33 | 2 | Ara Sotto | Current |  | 41.04 | 2 | Brian Le | Current | 2019-08-15 | 1.33 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 1.08 | 1 |  | Completed | 2019-08-02 | 2.08 | 1 | Andrew Clemons | Completed | 2019-08-28 | 2.54 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-08 |  | 0 | 2 |  | Inactive |  | 39.71 | 1 | Ara Sotto | Current | 2019-07-31 | 0.21 | 2 | Darlynn Lacap | Completed | 22.99 | [11 empty] | 2019-08-05 |  | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=26958 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26958 | https://completesolar.sugarondemand.com/#Opportunities/98ecbf7e-a7ef-11e9-a4bc-069e4f790264 | 300 Stars Inc |  | 2019-07-08 | Zachary Noah Gamez | 98ecbf7e-a7ef-11e9-a4bc-069e4f790264 |  | 56 | -25 | -2 | 5 | 5 | 5 | -17
27425 | PIP_APPROVED | PIP_APPROVED | 1152 Stephanie Court | Lancaster | CA | 93535 | Marie Paule Davenport | 2019-07-29 16:41 | 6619429490 |  |  |  |  | 10085 | 0.133 | Bill Angevine | 2019-07-29 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-26 | 2019-07-29 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-26 | PTO Received | SunRun Monthly |  | 0 |  |  |  |  | 2019-08-26 07:00 | 2019-08-12 | 5.58 | 2 | Marcia Garay | Completed | 2019-08-09 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-30 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-26 | 1.21 | 5 | Brian Le | Completed | 2019-08-16 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-22 | 3.92 | 1 | Ernesto Enriquez | Completed | 2019-08-26 | 0.96 | 2 | Ara Sotto | Completed | 2019-09-03 | 4.71 | 2 | Ara Sotto | Completed | 2019-08-23 | 5 | 2 | Brian Le | Completed | 2019-08-16 | 4 | 2 | Marcia Garay | Completed | 2019-08-16 | 4.21 | 1 |  | Completed | 2019-08-21 | 7.17 | 1 | Andrew Clemons | Completed |  | 40.04 | 1 | Marcia Garay | Current | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-03 | 1.17 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 6.21 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed | 2019-08-28 12:46 |  | 2019-08-30 | 3.71 | 2 | Ara Sotto | Completed | [10 empty] | 6.08 | [11 empty] | 2019-08-19 | 2019-08-30 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27425 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27425 | https://completesolar.sugarondemand.com/#Opportunities/4e6ef19a-b25a-11e9-9ff9-0630baf9dcb8 | SCES Division |  | 2019-07-24 | Green Road Solar Crew | 4e6ef19a-b25a-11e9-9ff9-0630baf9dcb8 | 4 | 8 | 0 | -2 | 5 | 5 | 5 | 8
24998 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3145 Chollas Road | San Diego | CA | 92105 | Albert Monfort | 2019-08-03 12:03 | 6192486138 |  | Hilda Monfort | 6196443030 |  | 6198 | 0.22 | Chad Malloy | 2019-05-29 | 4.27 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-04-25 | 2019-05-29 12:00 | Q.PEAK-G4.1 305 | 305 | 14 | Hanwha Q CELLS | SolarEdge | SE3800H-US RGM | Composite | MPU | 2019-08-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-08-23 07:00 | 2019-08-05 | 1.17 | 2 | Marcia Garay | Completed | 2019-08-06 | 3.18 | 2 | Daniel Speegle | Completed | 2019-08-08 | 18.21 | 1 | Christina Horton | Completed | 2019-08-23 | 22.33 | 5 | Ara Sotto | Completed | 2019-08-06 | 4.83 | 3 | Andrew Moralez | Completed | 2019-08-06 | 12 | 15 | Andrew Moralez | Completed | 2019-08-23 | 0.33 | 1 | Christina Horton | Completed |  | 40.21 | 2 | Christina Horton | Current | 2019-08-13 | 3.75 | 2 | Brian Le | Completed | 2019-08-12 | 4.91 | 2 | Marcia Garay | Completed | 2019-08-06 | 0 | 1 |  | Completed | 2019-08-06 | 5.17 | 1 | Andrew Clemons | Completed |  | 40.54 | 1 | Marcia Garay | Current | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 1.88 | 2 | Ashley Rockwood | Completed |  | 27.17 | 2 | Marcia Garay | Current |  | 27.17 | 1 | Andrew Clemons | Current | 2019-09-09 10:09 |  | 2019-09-09 | 3.17 | 2 | Christina Horton | Completed | 2019-09-04 | 1.29 | 1 | Christina Horton | Completed | 2019-08-08 | 1.96 | 2 | Marcia Garay | Completed | 16.85 | 2019-08-03 | 0.08 | 14 | James Fernandez | Completed | 2019-08-03 | 2019-08-03 | 0.08 | 1 | James Fernandez | Completed | 2019-08-09 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=24998 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24998 | https://completesolar.sugarondemand.com/#Opportunities/28b3f840-825a-11e9-9fbd-0630baf9dcb8 | Isiah BurksHarvey |  | 2019-04-25 | Infinity Energy Inc | 28b3f840-825a-11e9-9fbd-0630baf9dcb8 | 5 | 59 | -5 | -2 | 5 | 5 | 5 | 3
25243 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 4485 Aragon Drive | San Diego | CA | 92115 | Karen Renwick | 2019-05-03 19:03 | 6193394718 | kabobber@gmail.com |  |  |  | 9751 | 0.23 | Ryan Malloy | 2019-05-03 | 6.1 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-02 | 2019-05-03 16:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | MPU | 2019-08-23 | Installation Complete | SunRun Monthly |  | 0 |  |  | 1 |  | 2019-08-23 07:00 | 2019-05-07 | 1.58 | 2 | Darlynn Lacap | Completed | 2019-05-17 | 1.21 | 2 | Jethro Andal | Completed | 2019-05-28 | 6 | 1 | Christina Horton | Completed | 2019-08-23 | 59.42 | 5 | Ara Sotto | Completed | 2019-05-23 | 3.13 | 3 | Ernesto Enriquez | Completed | 2019-05-23 | 0 | 15 | Andrew Moralez | Completed | 2019-08-23 | 0.46 | 2 | Christina Horton | Completed |  | 33.09 | 2 | Christina Horton | Current | 2019-05-24 | 4.92 | 2 | Brittany Faconti | Completed | 2019-05-17 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-05-20 | 0.5 | 1 |  | Completed | 2019-05-24 | 4.88 | 1 | Noe Gomez | Completed | 2019-08-23 | 0.58 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 0.38 | 1 | Christina Horton | Inactive | 2019-05-30 | 1.88 | 2 | Darlynn Lacap | Completed | 83.93 | 2019-08-12 | 23.21 | 14 | James Fernandez | Completed | 2019-08-15 | 2019-08-16 | 14.46 | 1 | James Fernandez | Completed | 2019-06-14 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=25243 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25243 | https://completesolar.sugarondemand.com/#Opportunities/ab46bfee-6e10-11e9-9b5b-069e4f790264 | Brandon Seidel | Blake Sanders | 2019-05-01 | Infinity Energy Inc | ab46bfee-6e10-11e9-9b5b-069e4f790264 |  | 59 | -25 | -2 | 5 | 5 | 5 | -17
27121 | SP APPROVED |  | 15157 Zhana Drive | Moreno Valley | CA | 92551 | Luis Aguilar | 2019-07-16 18:47 | 9096440621 | laguilar4320@gmail.com |  |  |  | 6523 | 0.145 | Shaun Labelle | 2019-07-16 | 3.66 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-13 | 2019-07-16 16:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-23 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-22 | 2019-07-17 | 0.83 | 2 | Marcia Garay | Completed | 2019-07-19 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-31 | 7.88 | 1 | Ara Sotto | Completed | 2019-08-23 | 4.92 | 5 | Brian Le | Completed | 2019-07-24 | 0.17 | 3 | Andrew Moralez | Completed | 2019-07-30 | 3.92 | 25 | Ernesto Enriquez | Completed | 2019-08-23 | 1.46 | 1 | Ara Sotto | Completed |  | 40.33 | 2 | Ara Sotto | Current | 2019-07-31 | 0.08 | 2 | Brian Le | Completed | 2019-08-16 | 11 | 2 | Marcia Garay | Completed | 2019-07-24 | 2.79 | 1 |  | Completed | 2019-07-29 | 5.71 | 1 | Jeremiah Liend | Completed |  | 41.83 | 1 | Marcia Garay | Current | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-06 21:42 |  |  | 40.33 | 2 | Ara Sotto | Current | [10 empty] | 12.8 | [11 empty] | 2019-08-28 |  | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27121 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27121 | https://completesolar.sugarondemand.com/#Opportunities/bba3a60a-a834-11e9-b067-022c40d974e6 | 300 Stars Inc |  | 2019-07-13 | JK Solar | bba3a60a-a834-11e9-b067-022c40d974e6 | 59 | 59 | -25 | -2 | 5 | 5 | 5 | -17
27124 | PIP_APPROVED | PIP_APPROVED | 2867 Colgate Drive | Oceanside | CA | 92056 | Elizabeth Oakley-Austin | 2019-08-07 16:50 | 7602124444 | jacevetu@yahoo.com |  |  |  | 4597 | 0.185 | Chad Malloy | 2019-08-07 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-16 | 2019-07-20 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-23 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-08-23 07:00 | 2019-08-07 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 2.08 | 2 | Jethro Andal | Completed | 2019-08-16 | 4.63 | 1 | Christina Horton | Completed | 2019-08-23 | 3.25 | 5 | Brian Le | Completed | 2019-08-10 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-14 | 2.54 | 10 | Andrew Moralez | Completed | 2019-08-23 | 0.38 | 1 | Christina Horton | Completed | 2019-08-27 | 1.96 | 2 | Christina Horton | Completed | 2019-08-14 | 0.88 | 2 | Brian Le | Completed | 2019-08-13 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 0.08 | 1 |  | Completed | 2019-08-14 | 2.71 | 1 | Andrew Clemons | Completed | 2019-08-23 | 0.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-11 | 10.79 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 13.92 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 2.75 | 1 | Andrew Clemons | Completed | 2019-08-26 14:49 |  | 2019-08-26 | 1.08 | 2 | Christina Horton | Completed | [10 empty] | 6.13 | [11 empty] | 2019-08-26 | 2019-08-27 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27124 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27124 | https://completesolar.sugarondemand.com/#Opportunities/11c93726-b96e-11e9-b1b9-02ae981fbade | Brett Martinez |  | 2019-07-15 | T.A.K. Electric | 11c93726-b96e-11e9-b1b9-02ae981fbade | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
27496 | PIP_APPROVED | PIP_APPROVED | 214 Smilax Road | San Marcos | CA | 92069 | Christopher Jordan Itaya | 2019-07-29 12:52 | 7603319920 | jordanitaya@gmail.com | Kathryn Itaya | 7604053826 |  | 5726 | 0.17 | Ryan Malloy | 2019-07-29 | 3.355 | Ara Sotto | Revo Home Solutions | Marcia Garay | 2019-07-27 | 2019-07-29 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-23 | PTO Received | SunRun Monthly |  | 0 |  |  |  |  | 2019-08-23 07:00 | 2019-07-30 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-31 | 0.92 | 2 | Daniel Speegle | Completed | 2019-08-08 | 5.75 | 1 | Ara Sotto | Completed | 2019-08-23 | 13.88 | 5 | Brian Le | Completed | 2019-08-07 | 4 | 3 | Andrew Moralez | Completed | 2019-08-07 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-23 | 0.33 | 1 | Ara Sotto | Completed | 2019-08-26 | 1.13 | 2 | Ara Sotto | Completed | 2019-08-05 | 1.04 | 2 | Brian Le | Completed | 2019-08-02 | 2 | 2 | Marcia Garay | Completed | 2019-08-01 | 0.88 | 1 |  | Completed | 2019-08-02 | 1.92 | 1 | Andrew Clemons | Completed |  | 40.54 | 1 | Marcia Garay | Current | 2019-08-29 | 2.71 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-30 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 8.08 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed | 2019-08-26 17:21 |  | 2019-08-26 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 8.92 | [11 empty] | 2019-08-07 | 2019-08-26 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27496 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27496 | https://completesolar.sugarondemand.com/#Opportunities/5427eb8e-b23a-11e9-a225-022c40d974e6 | Trey Greenhill |  | 2019-07-27 | Zachary Noah Gamez | 5427eb8e-b23a-11e9-a225-022c40d974e6 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
27570 | PIP_APPROVED | PIP_APPROVED | 43931 Delgado Court | Lancaster | CA | 93535 | Horace Neely | 2019-08-02 16:00 | 6612362088 | dew-ace@verizon.net |  |  |  | 5924 | 0.136 | Bill Angevine | 2019-08-02 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-31 | 2019-08-02 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-19 07:00 | 2019-08-05 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-08-05 | 0.08 | 2 | Ernesto Enriquez | Completed | 2019-08-15 | 5.83 | 1 | Ara Sotto | Completed | 2019-08-23 | 5 | 5 | Brian Le | Completed | 2019-08-08 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-15 | 4.79 | 1 | Ernesto Enriquez | Completed | 2019-08-23 | 4.25 | 1 | Ara Sotto | Completed | 2019-09-20 | 19.04 | 2 | Ara Sotto | Completed | 2019-08-16 | 3.83 | 2 | Brian Le | Completed | 2019-08-12 | 3.04 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1 | 1 |  | Completed | 2019-08-12 | 3.13 | 1 | Jeremiah Liend | Completed | 2019-08-21 | 2.29 | 1 | Darlynn Lacap | Completed | 2019-08-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 10.21 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 5.13 | 2 | Darlynn Lacap | Completed | 2019-09-19 | 1 | 1 | Jeremiah Liend | Completed | 2019-08-23 14:44 |  | 2019-08-26 | 0.79 | 2 | Ara Sotto | Completed | [10 empty] | 6.92 | [11 empty] | 2019-08-09 | 2019-09-20 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27570 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27570 | https://completesolar.sugarondemand.com/#Opportunities/3519c63a-b579-11e9-bae8-02ae981fbade | SCES Division | Henry Garcia | 2019-07-31 | JK Solar | 3519c63a-b579-11e9-bae8-02ae981fbade | 3 | 28 | 0 | -2 | 5 | 5 | 5 | 8
27571 | PIP_APPROVED | PIP_APPROVED | 44023 Canyon Way | Lancaster | CA | 93535 | Roy Battles | 2019-08-02 06:23 | 6617239466 | rbattles@roadrunner.com |  | 6619174014 |  | 9494 | 0.139 | Bill Angevine | 2019-08-01 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-31 | 2019-08-01 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-23 | 2019-08-05 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-08-09 | 4.13 | 2 | Jethro Andal | Completed | 2019-08-02 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-22 | 3.17 | 5 | Brian Le | Completed | 2019-08-10 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-08-15 | 3.38 | 1 | Ernesto Enriquez | Completed | 2019-08-23 | 0.88 | 1 | Ara Sotto | Completed | 2019-08-29 | 3.75 | 2 | Ara Sotto | Completed | 2019-08-19 | 3.75 | 2 | Brian Le | Completed | 2019-08-13 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 0.42 | 1 |  | Completed | 2019-08-20 | 5.54 | 1 | Jeremiah Liend | Completed | 2019-08-23 | 1.04 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 5.79 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 3.96 | 1 | Jill Allen | Completed | 2019-08-27 14:34 |  | 2019-08-28 | 2.91 | 2 | Ara Sotto | Completed | [10 empty] | 1.17 | [11 empty] | 2019-08-13 | 2019-08-28 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27571 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27571 | https://completesolar.sugarondemand.com/#Opportunities/92539156-b528-11e9-a7c5-0630baf9dcb8 | SCES Division |  | 2019-07-31 | HDM Electric Inc | 92539156-b528-11e9-a7c5-0630baf9dcb8 | 5 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27644 | PIP_APPROVED | PIP_APPROVED | 5128 Goleta Court | Antioch | CA | 94531 | Ana Bonilla | 2019-08-07 12:45 | 9254972662 | ascencio1970@gmail.com |  |  |  | 7086.46 |  | Ricardo Virgen | 2019-08-07 | 5.185 | Christina Horton | SolarIT Inc | Darlynn Lacap | 2019-08-03 | 2019-08-06 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-23 | PTO Received | SVN Loan | [6 empty] | 2019-08-23 07:00 | 2019-08-07 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 3.96 | 2 | Jethro Andal | Completed | 2019-08-19 | 3.88 | 1 | Christina Horton | Completed | 2019-08-23 | 2.96 | 5 | Brian Le | Completed | 2019-08-16 | 3.04 | 3 | Andrew Moralez | Completed | 2019-08-16 | 0 | 2 | Andrew Moralez | Completed | 2019-08-23 | 0.42 | 2 | Christina Horton | Completed | 2019-09-12 | 12.83 | 2 | Christina Horton | Completed | 2019-08-20 | 4.08 | 2 | Brian Le | Completed | 2019-08-14 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 0 | 1 |  | Completed | 2019-08-19 | 0.92 | 1 | Jill Allen | Completed | 2019-08-23 | 0.58 | 1 | Darlynn Lacap | Completed |  | 27.25 | 2 | Andrew Clemons | Current | [15 empty] | 2019-09-09 | 6.08 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 3.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 4 | 2 | Darlynn Lacap | Completed |  | 26.33 | 1 | Jill Allen | Current | 2019-08-29 15:26 |  | 2019-08-29 | 1.96 | 2 | Christina Horton | Completed | [10 empty] | 7.37 | [11 empty] | 2019-08-20 | 2019-09-12 | ANTIOCH | Antioch | https://heliotrack.completesolar.com/job.php?action=review&jobID=27644 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27644 | https://completesolar.sugarondemand.com/#Opportunities/cba22b62-b94b-11e9-83dc-069e4f790264 | SolarIT Inc |  | 2019-08-03 | Golden Gate Electric Service | cba22b62-b94b-11e9-83dc-069e4f790264 | 6 | 20 | -5 | -2 | 5 | 5 | 5 | 3
25760 | PIP_APPROVED | PIP_APPROVED | 2223 Virginia Court | El Cajon | CA | 92020 | Kathleen A Luci | 2019-07-08 15:36 | 6199222296 | alisonazz80@gmail.com | Alison Azzarella | 6196544867 |  | 12869 | 0 | Chad Malloy | 2019-06-27 | 8.54 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-20 | 2019-05-22 09:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-22 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-08-21 07:00 | 2019-07-09 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-07-15 | 8.51 | 2 | Jethro Andal | Completed | 2019-08-07 | 19.05 | 1 | Christina Horton | Completed | 2019-08-21 | 6.38 | 5 | Brian Le | Completed | 2019-07-17 | 0.71 | 3 | Andrew Moralez | Completed | 2019-08-09 | 15.96 | 0 | Andrew Moralez | Completed | 2019-08-22 | 1.17 | 2 | Christina Horton | Completed | 2019-08-23 | 1.13 | 2 | Christina Horton | Completed | 2019-07-26 | 8.92 | 2 | Brian Le | Completed | 2019-07-15 | 1.12 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 2.21 | 1 |  | Completed | 2019-08-01 | 6.92 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-27 | 1.96 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-29 | 5 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 13.92 | 2 | Darlynn Lacap | Completed | 2019-09-03 | 0.79 | 1 | Jill Allen | Completed |  |  | 2019-08-22 | 0.13 | 2 | Christina Horton | Completed | [10 empty] | 26.38 | [11 empty] | 2019-07-18 | 2019-08-22 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=25760 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25760 | https://completesolar.sugarondemand.com/#Opportunities/20fd3136-98f1-11e9-8533-022c40d974e6 | Robert Blessing |  | 2019-05-20 | Infinity Energy Inc | 20fd3136-98f1-11e9-8533-022c40d974e6 | 0 | 1 | 10 | 5 | 5 | 5 | 5 | 25
26880 | PIP_APPROVED | PIP_APPROVED | 8755 Aquarius Drive | San Diego | CA | 92126 | Casey Ochinang | 2019-07-05 18:28 | 8582086977 | caseyochinang@gmail.com | Venus Ochinang | 8582086843 |  | 6216 | 0.2 | Michael Marlaire | 2019-07-05 | 3.66 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-03 | 2019-07-05 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-22 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-22 07:00 | 2019-07-09 | 1.63 | 2 | Marcia Garay | Completed | 2019-07-11 | 2.13 | 2 | Daniel Speegle | Completed | 2019-07-26 | 10.96 | 1 | Christina Horton | Completed | 2019-08-22 | 7.13 | 5 | Brian Le | Completed | 2019-07-22 | 6.79 | 3 | Andrew Moralez | Completed | 2019-07-22 | 0.08 | 15 | Andrew Moralez | Completed | 2019-08-22 | 0.75 | 1 | Christina Horton | Completed | 2019-08-30 | 6.13 | 2 | Christina Horton | Completed | 2019-07-25 | 9.83 | 2 | Brian Le | Completed | 2019-07-11 | 0 | 2 | Marcia Garay | Completed | 2019-07-11 | 0.08 | 1 |  | Completed | 2019-07-25 | 9.58 | 1 | Jill Allen | Completed |  | 41.79 | 1 | Marcia Garay | Current | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 3.71 | 2 | Ashley Rockwood | Completed |  | 36.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-09 15:14 |  | 2019-08-23 | 1.08 | 2 | Christina Horton | Completed | [10 empty] | 13.67 | [11 empty] | 2019-08-12 | 2019-08-30 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26880 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26880 | https://completesolar.sugarondemand.com/#Opportunities/46d2782e-9f8d-11e9-ad8e-069e4f790264 | Brandon Seidel |  | 2019-07-02 | Infinity Energy Inc | 46d2782e-9f8d-11e9-ad8e-069e4f790264 | 1 | 8 | 10 | -2 | 5 | 5 | 5 | 18
27055 | PIP_APPROVED | PIP_APPROVED | 1388 Tobias Drive | Chula Vista | CA | 91911 | Linda King | 2019-07-17 11:49 | 6195850739 | tigerbrat2@cox.net |  |  |  | 6313 | 0.15 | Chad Malloy | 2019-07-17 | 3.965 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-11 | 2019-07-17 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-22 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-22 07:00 | 2019-07-18 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 1.54 | 2 | Jethro Andal | Completed | 2019-08-16 | 19.54 | 1 | Ara Sotto | Completed | 2019-08-22 | 14.13 | 5 | Brian Le | Completed | 2019-07-24 | 0.04 | 3 | Andrew Moralez | Completed | 2019-08-09 | 12.17 | 7 | Andrew Moralez | Completed | 2019-08-22 | 0.38 | 1 | Ara Sotto | Completed | 2019-10-08 | 32.25 | 2 | Ara Sotto | Completed | 2019-07-31 | 6.96 | 2 | Brian Le | Completed | 2019-07-22 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 2.42 | 1 |  | Completed | 2019-08-19 | 20.5 | 1 | Andrew Clemons | Completed | 2019-08-23 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-24 12:26 |  |  | 41.13 | 2 | Ara Sotto | Current | [10 empty] | 2 | [11 empty] | 2019-08-02 | 2019-10-08 | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27055 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27055 | https://completesolar.sugarondemand.com/#Opportunities/834ebe2c-a8c3-11e9-a69a-022c40d974e6 | Henry Rendon | Blake Sanders | 2019-07-11 | Zachary Noah Gamez | 834ebe2c-a8c3-11e9-a69a-022c40d974e6 | 60 | 47 | -25 | -2 | 5 | 5 | 5 | -17
27212 | PIP_APPROVED | PIP_APPROVED | 3251 Cabana Lane | Lancaster | CA | 93536 | Jason Edwards | 2019-07-27 16:02 | 6618397121 | jasonleanne07@yahoo.com | Leanne Edwards |  |  | 10027 | 0.147 | Bill Angevine | 2019-07-27 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-17 | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-21 07:00 | 2019-07-29 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 2.83 | 2 | Jethro Andal | Completed | 2019-08-15 | 9.33 | 1 | Ara Sotto | Completed | 2019-08-22 | 3.83 | 5 | Brian Le | Completed | 2019-08-02 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-12 | 3.75 | 1 | Andrew Moralez | Completed | 2019-08-22 | 1.17 | 2 | Ara Sotto | Completed | 2019-08-28 | 4.29 | 2 | Ara Sotto | Completed | 2019-08-16 | 9.92 | 2 | Brian Le | Completed | 2019-08-02 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 1.08 | 1 |  | Completed | 2019-08-19 | 11.8 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 4.92 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 3.96 | 1 | Jeremiah Liend | Completed | 2019-08-28 15:50 |  | 2019-08-28 | 4.13 | 2 | Ara Sotto | Completed | [10 empty] | 5.08 | [11 empty] | 2019-08-07 | 2019-08-22 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27212 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27212 | https://completesolar.sugarondemand.com/#Opportunities/7a38eb58-b0c2-11e9-abb2-02ae981fbade | SCES Division |  | 2019-07-17 | HDM Electric Inc | 7a38eb58-b0c2-11e9-abb2-02ae981fbade | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27260 | PIP_APPROVED | PIP_APPROVED | 893 Autumn Lane | Corona | CA | 92881 | Gilbert Daniel | 2019-07-22 16:08 | 9512045164 | jennifer_m_daniel@msn.com |  |  |  | 8695 | 0.154 | Michael Marlaire | 2019-07-22 | 6.1 | Ara Sotto | Branden Williams | Darlynn Lacap | 2019-07-18 | 2019-07-22 12:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-22 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-21 07:00 | 2019-07-22 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 2.71 | 2 | Daniel Speegle | Completed | 2019-07-26 | 0.5 | 1 | Ara Sotto | Completed | 2019-08-22 | 2.75 | 5 | Brian Le | Completed | 2019-08-01 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-08-09 | 2.17 | 14 | Andrew Moralez | Completed | 2019-08-22 | 1.5 | 2 | Ara Sotto | Completed | 2019-08-23 | 1.33 | 2 | Ara Sotto | Completed | 2019-08-19 | 11.08 | 2 | Brian Le | Completed | 2019-07-26 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.08 | 1 |  | Completed | 2019-08-14 | 9.37 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.75 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-29 | 4.79 | 4 | Darlynn Lacap | Completed | 2019-07-29 | 0 | 5 | Darlynn Lacap | Completed | 2019-07-29 | 0 | 12 | Darlynn Lacap | Completed | 2019-09-04 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 8.21 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.13 | 1 | Jill Allen | Completed |  |  | 2019-08-22 | 0.17 | 2 | Ara Sotto | Completed | [10 empty] | 15.01 | [11 empty] | 2019-08-27 | 2019-08-23 | CORONA | Corona | https://heliotrack.completesolar.com/job.php?action=review&jobID=27260 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27260 | https://completesolar.sugarondemand.com/#Opportunities/99befc60-acd5-11e9-99ce-02ae981fbade | Branden Williams |  | 2019-07-18 | Power Town Solar Electric | 99befc60-acd5-11e9-99ce-02ae981fbade | 0 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27285 | PIP_APPROVED | PIP_APPROVED | 105 Prospect Street | Chula Vista | CA | 91911 | Willard Howard | 2019-07-23 12:23 | 6194227088 | willarddochoward@aol.com |  |  |  | 8398 | 0.18 | Ryan Malloy | 2019-07-23 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-20 | 2019-07-22 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-22 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-22 07:00 | 2019-07-26 | 3 | 2 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-13 | 12.17 | 1 | Christina Horton | Completed | 2019-08-22 | 13 | 5 | Brian Le | Completed | 2019-07-25 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-09 | 10.17 | 7 | Ernesto Enriquez | Completed | 2019-08-22 | 0.46 | 2 | Christina Horton | Completed | 2019-09-17 | 16.88 | 2 | Christina Horton | Completed | 2019-08-05 | 6.04 | 2 | Brian Le | Completed | 2019-07-26 | 0 | 2 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 1 |  | Completed | 2019-08-08 | 9.13 | 1 | Andrew Clemons | Completed | 2019-09-13 | 15.5 | 1 | Marcia Garay | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-18 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 2.21 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 3.88 | 2 | Marcia Garay | Completed |  | 21.13 | 1 | Jeremiah Liend | Current | 2019-09-16 13:17 |  | 2019-09-16 | 15.92 | 2 | Christina Horton | Completed | [10 empty] | 5.17 | [11 empty] | 2019-08-06 | 2019-09-17 | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27285 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27285 | https://completesolar.sugarondemand.com/#Opportunities/470a35a2-ad7f-11e9-a724-022c40d974e6 | Daniel Boyce | Henry Rendon | 2019-07-20 | Infinity Energy Inc | 470a35a2-ad7f-11e9-a724-022c40d974e6 | 25 | 26 | -25 | -2 | 5 | 5 | 5 | -17
27297 | PIP_APPROVED | PIP_APPROVED | 7967 Linares Avenue | Riverside/Jarupa Valley | CA | 92509 | Tina Sharp | 2019-07-22 19:47 | 9092266514 | billtinasharp@gmail.com | Bill Sharp | 9092248981 |  | 9111.62 | 0.125 | Michael Marlaire | 2019-07-22 | 9.15 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-21 | 2019-07-22 15:00 | LR6-60PB-305M | 305 | 30 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-22 07:00 | 2019-07-23 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-30 | 2.75 | 1 | Ara Sotto | Completed | 2019-08-22 | 1 | 5 | Brian Le | Completed | 2019-08-06 | 7 | 3 | Andrew Moralez | Completed | 2019-08-14 | 6.13 | 10 | Andrew Moralez | Completed | 2019-08-22 | 0.42 | 2 | Ara Sotto | Completed | 2019-08-26 | 2.04 | 2 | Ara Sotto | Completed | 2019-08-21 | 17.83 | 2 | Brian Le | Completed | 2019-07-26 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-26 | 0.75 | 1 |  | Completed | 2019-08-19 | 16.63 | 1 | Jill Allen | Completed | 2019-08-23 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-28 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 4.17 | 1 | Jeremiah Liend | Completed | 2019-08-23 15:49 |  | 2019-08-23 | 1.13 | 2 | Ara Sotto | Completed | [10 empty] | 2 | [11 empty] | 2019-08-20 | 2019-08-26 | RIVERSIDE | Riverside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27297 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27297 | https://completesolar.sugarondemand.com/#Opportunities/16b19ac0-acf4-11e9-b9e7-022c40d974e6 | Ryan Ostronic |  | 2019-07-21 | Blalock Electric&Solar | 16b19ac0-acf4-11e9-b9e7-022c40d974e6 | 1 | 4 | 10 | 0 | 5 | 5 | 5 | 20
27307 | PIP_APPROVED | PIP_APPROVED | 1326 Boyden Avenue | Lancaster | CA | 93534 | Gerardo Verdugo | 2019-08-06 19:20 | 3107676360 | vrdugo05@yahoo.com |  |  |  | 9955 | 0.16 | Shaun Labelle | 2019-08-06 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-31 | 2019-08-06 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-22 07:00 | 2019-08-07 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 2.54 | 2 | Daniel Speegle | Completed | 2019-08-08 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-22 | 4.13 | 5 | Brian Le | Completed | 2019-08-13 | 0 | 3 | Andrew Moralez | Completed | 2019-08-15 | 1.79 | 1 | Andrew Moralez | Completed | 2019-08-22 | 0.46 | 2 | Ara Sotto | Completed | 2019-08-29 | 4.75 | 2 | Ara Sotto | Completed | 2019-08-16 | 4.04 | 2 | Brian Le | Completed | 2019-08-12 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-08-13 | 1.58 | 1 |  | Completed | 2019-08-15 | 3.38 | 1 | Andrew Clemons | Completed | 2019-08-23 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 0.71 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 8.13 | 2 | Darlynn Lacap | Completed |  | 28.33 | 1 | Noe Gomez | Current | 2019-08-30 08:52 |  | 2019-09-06 | 10 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-14 | 2019-08-28 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27307 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27307 | https://completesolar.sugarondemand.com/#Opportunities/db87d88e-b8b9-11e9-a159-02ae981fbade | Cody Booth |  | 2019-07-22 | HDM Electric Inc | db87d88e-b8b9-11e9-a159-02ae981fbade | 15 | 7 | -15 | -2 | 5 | 5 | 5 | -7
27389 | PIP_APPROVED | PIP_APPROVED | 34276 Lupine Court | Lake Elsinore | CA | 92532 | Tracie Laplante | 2019-07-24 16:48 | 9513982904 | tracielaplante@hotmail.com | Robert Laplonte | 9515534018 |  | 12094 | 0.147 | Shaun Labelle | 2019-07-24 | 7.32 | Ara Sotto | Blue Prime Energy | Marcia Garay | 2019-07-23 | 2019-07-24 12:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-22 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-22 07:00 | 2019-07-25 | 0.96 | 2 | Marcia Garay | Completed | 2019-07-30 | 2.75 | 2 | Daniel Speegle | Completed | 2019-07-25 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-22 | 4.08 | 5 | Brian Le | Completed | 2019-08-09 | 2.04 | 3 | Andrew Moralez | Completed | 2019-08-14 | 3.21 | 1 | Andrew Moralez | Completed | 2019-08-22 | 0.46 | 2 | Ara Sotto | Completed | 2019-08-26 | 1.63 | 2 | Ara Sotto | Completed | 2019-08-16 | 11.83 | 2 | Brian Le | Completed | 2019-07-31 | 1.21 | 2 | Marcia Garay | Completed | 2019-08-07 | 6.13 | 1 |  | Completed | 2019-08-02 | 3.04 | 1 | Noe Gomez | Completed |  | 41.54 | 1 | Marcia Garay | Current | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-25 | 0 | 4 | Marcia Garay | Completed | 2019-08-21 | 16.63 | 5 | Marcia Garay | Completed | 2019-08-21 | 0.08 | 12 | Marcia Garay | Completed | 2019-08-27 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 6.96 | 2 | Marcia Garay | Completed | 2019-08-29 | 1 | 1 | Andrew Clemons | Completed | 2019-08-23 14:32 |  | 2019-08-23 | 1.04 | 2 | Ara Sotto | Completed | [10 empty] | 4.34 | [11 empty] | 2019-08-12 | 2019-08-23 | LAKE ELSINORE | Lake Elsinore | https://heliotrack.completesolar.com/job.php?action=review&jobID=27389 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27389 | https://completesolar.sugarondemand.com/#Opportunities/75d45e32-ae6d-11e9-adf0-069e4f790264 | Blue Prime Energy |  | 2019-07-23 | Power Town Solar Electric | 75d45e32-ae6d-11e9-adf0-069e4f790264 | 1 | 4 | 10 | 0 | 5 | 5 | 5 | 20
27507 | PIP_APPROVED | PIP_APPROVED | 4936 Tyler Street | Oceanside | CA | 92057 | Ross Mcdonald | 2019-08-01 17:08 | 7604739984 | r171701@gmail.com | Margarete Mcdonald | 7606447498 |  | 5533 | 0.19 | Michael Marlaire | 2019-08-01 | 3.355 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-30 | 2019-08-01 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-21 07:00 | 2019-08-02 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-08-07 | 2.88 | 2 | Jethro Andal | Completed | 2019-08-15 | 5.88 | 1 | Christina Horton | Completed | 2019-08-22 | 7.83 | 5 | Brian Le | Completed | 2019-08-08 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-09 | 1.04 | 10 | Ernesto Enriquez | Completed | 2019-08-22 | 1.38 | 1 | Ara Sotto | Completed | 2019-08-23 | 0.96 | 2 | Ara Sotto | Completed | 2019-08-12 | 0.08 | 2 | Brian Le | Completed | 2019-08-12 | 3.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 0.96 | 1 |  | Completed | 2019-08-12 | 3.17 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-29 | 4.92 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 10 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 1.83 | 1 | Jill Allen | Completed |  | 2019-08-30 | 2019-08-22 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 31.04 | [11 empty] | 2019-08-22 | 2019-08-23 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27507 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27507 | https://completesolar.sugarondemand.com/#Opportunities/84ec358c-b4b9-11e9-8e76-02ae981fbade | Brett Martinez | Omar Jackson | 2019-07-29 | Zachary Noah Gamez | 84ec358c-b4b9-11e9-8e76-02ae981fbade | 0 | 1 | 10 | 5 | 5 | 5 | 5 | 25
27559 | PIP_APPROVED | PIP_APPROVED | 334 Holiday Way | Oceanside | CA | 92057 | Daniel Williams | 2019-08-07 07:59 | 7608150978 | Dww62@live.com |  |  |  | 5816 | 0.18 | Bill Angevine | 2019-08-07 | 3.66 |  | Revo Home Solutions | Darlynn Lacap | 2019-08-05 | 2019-08-06 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-22 07:00 | 2019-08-07 | 0.29 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 2.33 | 2 | Daniel Speegle | Completed | 2019-08-16 | 4.5 | 1 | Ara Sotto | Completed | 2019-08-22 | 6.71 | 5 | Brian Le | Completed | 2019-08-10 | 0.08 | 3 | Ernesto Enriquez | Completed | 2019-08-12 | 0.67 | 10 | Ernesto Enriquez | Completed | 2019-08-22 | 0.5 | 1 | Ara Sotto | Completed | 2019-08-27 | 2.88 | 2 | Ara Sotto | Completed | 2019-08-13 | 0.79 | 2 | Brian Le | Completed | 2019-08-12 | 0.58 | 2 | Darlynn Lacap | Completed | 2019-08-10 | 0.08 | 1 |  | Completed | 2019-08-15 | 3.38 | 1 | Andrew Clemons | Completed | 2019-08-23 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 5.33 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed | 2019-08-27 08:26 |  | 2019-08-27 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 1.46 | [11 empty] | 2019-08-26 | 2019-08-27 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27559 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27559 | https://completesolar.sugarondemand.com/#Opportunities/e4fc8fbc-b923-11e9-bbe3-0630baf9dcb8 | Alan Moberg |  | 2019-07-30 | iEnergy ElectricSolar | e4fc8fbc-b923-11e9-bbe3-0630baf9dcb8 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
27567 | PIP_APPROVED | PIP_APPROVED | 734 West 5th Avenue | Escondido | CA | 92025 | Antonio Rubalcava | 2019-08-02 18:08 | 7608772731 | a.rubalcava@cox.net |  |  |  | 4855 | 0.181 | Chad Malloy | 2019-08-02 | 3.05 | Christina Horton | Kyle Wilson | Marcia Garay | 2019-07-31 | 2019-08-02 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-22 07:00 | 2019-08-05 | 0.71 | 2 | Marcia Garay | Completed | 2019-08-08 | 3.13 | 2 | Jethro Andal | Completed | 2019-08-16 | 5.92 | 1 | Ara Sotto | Completed | 2019-08-22 | 3.33 | 5 | Brian Le | Completed | 2019-08-13 | 2.17 | 3 | Ernesto Enriquez | Completed | 2019-08-13 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-22 | 0.46 | 1 | Christina Horton | Completed | 2019-09-05 | 8.92 | 2 | Christina Horton | Completed | 2019-08-16 | 4.17 | 2 | Brian Le | Completed | 2019-08-12 | 1.75 | 2 | Marcia Garay | Completed | 2019-08-09 | 0.83 | 1 |  | Completed | 2019-08-15 | 4.92 | 1 | Andrew Clemons | Completed |  | 41.54 | 1 | Marcia Garay | Current | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 5.96 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.08 | 1 | Jill Allen | Completed | 2019-08-28 15:40 |  | 2019-08-28 | 4.04 | 2 | Christina Horton | Completed | [10 empty] | 0.42 | [11 empty] | 2019-09-04 | 2019-09-05 | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=27567 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27567 | https://completesolar.sugarondemand.com/#Opportunities/1b5e0186-b58b-11e9-b3df-02ae981fbade | Kyle Wilson |  | 2019-07-31 | T.A.K. Electric | 1b5e0186-b58b-11e9-b3df-02ae981fbade | 6 | 14 | -5 | -2 | 5 | 5 | 5 | 3
26197 | PIP_APPROVED | PIP_APPROVED | 26391 Chambers Avenue | Menifee | CA | 92586 | Lorna Corazon A Sabater | 2019-07-26 14:37 | 7143079972 | ramirosabater37@yahoo.com | Ramiro T Sabater | 9514343172 |  | 7586 | 0.115 | Ryan Malloy | 2019-06-07 | 4.27 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-06-05 | 2019-06-07 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-21 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-08-21 07:00 | 2019-07-29 | 1.88 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 2.71 | 2 | Jethro Andal | Completed | 2019-08-05 | 3.96 | 1 | Ara Sotto | Completed |  | 38.29 | 5 | Brian Le | Current | 2019-08-07 | 1.75 | 3 | Ernesto Enriquez | Completed | 2019-08-14 | 5.21 | 0 | Andrew Moralez | Completed | 2019-08-21 | 0.25 | 1 | Ara Sotto | Completed | 2019-08-21 | 0.13 | 2 | Ara Sotto | Completed | 2019-08-16 | 11 | 2 | Brian Le | Completed | 2019-08-01 | 2 | 2 | Darlynn Lacap | Completed | 2019-08-05 | 4.17 | 1 |  | Completed | 2019-08-12 | 8.83 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.96 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-06 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 5.08 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.13 | 1 | Jeremiah Liend | Completed |  | 2019-09-27 | 2019-09-05 | 10.17 | 2 | Ara Sotto | Completed | [10 empty] | 14.62 | 2019-08-15 | 13.17 | 14 | James Fernandez | Completed | 2019-08-15 | 2019-08-15 | 0 | 1 | James Fernandez | Completed | 2019-08-07 | 2019-08-21 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=26197 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26197 | https://completesolar.sugarondemand.com/#Opportunities/29fdd066-897d-11e9-af36-069e4f790264 | PHNX Power |  | 2019-06-05 | Power Town Solar Electric | 29fdd066-897d-11e9-af36-069e4f790264 | 15 | 0 | -15 | 5 | 5 | 5 | 5 | 0
26584 | PIP_APPROVED | PIP_APPROVED | 6757 Bluestone Court | Corona | CA | 92880 | Desiree Diaz | 2019-06-22 12:27 | 5628328143 | desidez.34@gmail.com | Hector Diaz | 6263831759 |  | 10275 | 0.145 | Alex Holdridge | 2019-06-22 | 6.405 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-06-21 | 2019-06-22 09:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-21 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-21 07:00 | 2019-06-25 | 1.42 | 2 | Marcia Garay | Completed | 2019-06-27 | 1.96 | 2 | Daniel Speegle | Completed | 2019-06-25 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-21 | 4.88 | 5 | Brian Le | Completed | 2019-07-06 | 1.38 | 3 | Andrew Moralez | Completed | 2019-07-23 | 11.67 | 14 | Andrew Moralez | Completed | 2019-08-21 | 0.38 | 2 | Ara Sotto | Completed | 2019-08-26 | 3.29 | 2 | Ara Sotto | Completed | 2019-08-14 | 32.13 | 2 | Brian Le | Completed | 2019-06-28 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-03 | 4.13 | 1 |  | Completed | 2019-07-03 | 4.08 | 1 | Andrew Clemons | Completed |  | 42.54 | 1 | Marcia Garay | Current | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-03 | 2.08 | 4 | Marcia Garay | Completed | 2019-07-24 | 14 | 5 | Marcia Garay | Completed | 2019-08-14 | 14.88 | 12 | Marcia Garay | Completed | 2019-08-28 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 5 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 9.96 | 2 | Marcia Garay | Completed | 2019-09-11 | 4.13 | 1 | Jeremiah Liend | Completed | 2019-08-22 13:28 |  | 2019-08-22 | 0.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-26 | 2019-08-26 | CORONA | Corona | https://heliotrack.completesolar.com/job.php?action=review&jobID=26584 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26584 | https://completesolar.sugarondemand.com/#Opportunities/c22bcbf2-9523-11e9-8943-069e4f790264 | Dominic Labadie |  | 2019-06-21 | Blalock Electric&Solar | c22bcbf2-9523-11e9-8943-069e4f790264 | 1 | 5 | 10 | -2 | 5 | 5 | 5 | 18
27111 | PIP_APPROVED | PIP_APPROVED | 4835 Tacayme Drive | Oceanside | CA | 92057 | Martin Perez | 2019-07-29 18:22 | 7604701819 | clubsanjorge1964@yahoo.com |  |  |  | 4385 | 0.181 | Ryan Malloy | 2019-07-29 | 2.745 | Ara Sotto | Revo Home Solutions | Marcia Garay | 2019-07-20 | 2019-07-27 12:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-21 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-21 | 2019-08-01 | 2.71 | 2 | Marcia Garay | Completed | 2019-08-08 | 5.42 | 2 | Daniel Speegle | Completed | 2019-08-16 | 5.58 | 1 | Christina Horton | Completed | 2019-08-21 | 5.96 | 5 | Brian Le | Completed | 2019-08-09 | 0 | 3 | Andrew Moralez | Completed | 2019-08-13 | 2.17 | 10 | Andrew Moralez | Completed | 2019-08-21 | 0 | 1 | Ara Sotto | Completed | 2019-10-08 | 33.38 | 2 | Ara Sotto | Completed | 2019-08-13 | 0.96 | 2 | Brian Le | Completed | 2019-08-12 | 1.54 | 2 | Marcia Garay | Completed | 2019-08-09 | 0.54 | 1 |  | Completed | 2019-08-13 | 2.5 | 1 | Jill Allen | Completed |  | 42.25 | 1 | Marcia Garay | Current | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 5.67 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 3 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 13.04 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed |  | 2019-08-27 | 2019-08-21 | 0.21 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-23 | 2019-10-08 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27111 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27111 | https://completesolar.sugarondemand.com/#Opportunities/5cb8c966-b268-11e9-9c16-02ae981fbade | Brett Martinez |  | 2019-07-13 | Zachary Noah Gamez | 5cb8c966-b268-11e9-9c16-02ae981fbade | 0 | 48 | 10 | -2 | 5 | 5 | 5 | 18
27289 | PIP_APPROVED | PIP_APPROVED | 36826 Jenna Lane | Palmdale | CA | 93550 | Robin Goff | 2019-07-27 14:18 | 6614330826 | rgoff731@yahoo.com |  | 6612858856 |  | 10671 | 0.16 | Bill Angevine | 2019-07-27 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-20 | 2019-07-23 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-21 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-21 07:00 | 2019-07-29 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 3.13 | 2 | Daniel Speegle | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-21 | 3.04 | 5 | Brian Le | Completed | 2019-08-07 | 3.42 | 3 | Andrew Moralez | Completed | 2019-08-16 | 7.17 | 0 | Andrew Moralez | Completed | 2019-08-21 | 0.59 | 2 | Ara Sotto | Completed | 2019-09-13 | 16.08 | 2 | Ara Sotto | Completed | 2019-08-16 | 8.17 | 2 | Brian Le | Completed | 2019-08-06 | 2.67 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 0.33 | 1 |  | Completed | 2019-08-06 | 2.63 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.63 | 1 | Darlynn Lacap | Completed | 2019-09-16 | 0.67 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-16 | 13 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 4.75 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 5.13 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 3.04 | 1 | Andrew Clemons | Completed | 2019-08-26 15:52 | 2019-08-21 | 2019-08-27 | 3.96 | 2 | Ara Sotto | Completed | [10 empty] | 3.38 | [11 empty] | 2019-08-07 | 2019-09-13 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27289 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27289 | https://completesolar.sugarondemand.com/#Opportunities/f9e5f382-b0b3-11e9-9849-022c40d974e6 | SCES Division |  | 2019-07-20 | JK Solar | f9e5f382-b0b3-11e9-9849-022c40d974e6 | 6 | 23 | -5 | -2 | 5 | 5 | 5 | 3
27326 | PIP_APPROVED | PIP_APPROVED | 1420 Pluto Road | Vista | CA | 92083 | Joseph Parra | 2019-07-24 16:55 | 7608037391 | janet.parra1420@gmail.com | Janet Parra |  |  | 4973 | 0.188 | Chad Malloy | 2019-07-24 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-22 | 2019-07-24 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Composite | NO | 2019-08-21 | PTO Received | SunRun Monthly |  |  |  |  | 1 |  | 2019-08-21 07:00 | 2019-07-31 | 4.62 | 2 | Marcia Garay | Completed | 2019-07-31 | 0.13 | 2 | Jethro Andal | Completed | 2019-08-07 | 4.88 | 1 | Christina Horton | Completed | 2019-08-21 | 11.79 | 5 | Brian Le | Completed | 2019-08-05 | 2.38 | 3 | Ernesto Enriquez | Completed | 2019-08-05 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-21 | 0.42 | 1 | Christina Horton | Completed | 2019-08-26 | 2.75 | 2 | Christina Horton | Completed | 2019-08-05 | 2.08 | 2 | Brian Le | Completed | 2019-08-01 | 1 | 2 | Marcia Garay | Completed | 2019-08-01 | 1.04 | 1 |  | Completed | 2019-08-09 | 6.96 | 1 | Andrew Clemons | Completed |  | 42.54 | 1 | Marcia Garay | Current | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 2.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 11.17 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed |  |  | 2019-08-22 | 0.92 | 2 | Christina Horton | Completed | [10 empty] | 6.38 | 2019-08-06 | 4.54 | 14 | James Fernandez | Completed | 2019-08-08 | 2019-08-08 | 0.17 | 1 | James Fernandez | Completed | 2019-08-05 | 2019-08-26 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27326 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27326 | https://completesolar.sugarondemand.com/#Opportunities/655713e6-ae6e-11e9-aa08-0630baf9dcb8 | Alexis Cain |  | 2019-07-22 | Infinity Energy Inc | 655713e6-ae6e-11e9-aa08-0630baf9dcb8 | 1 | 5 | 10 | -2 | 5 | 5 | 5 | 18
27499 | PIP_APPROVED | PIP_APPROVED | 545 Emerald Drive | Vista | CA | 92083 | Erika Smith | 2019-07-31 17:18 | 7607269379 | tomramey@cox.net | Tom Ramey | 7609455859 |  | 4056 | 0.15 | Michael Marlaire | 2019-07-31 | 2.745 |  | Revo Home Solutions | Darlynn Lacap | 2019-07-27 | 2019-07-30 12:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-21 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-21 07:00 | 2019-07-31 | 0 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 1.71 | 2 | Jethro Andal | Completed | 2019-08-15 | 9.08 | 1 | Christina Horton | Completed | 2019-08-21 | 10.54 | 5 | Brian Le | Completed | 2019-08-05 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-05 | 0.08 | 0 | Andrew Moralez | Completed | 2019-08-21 | 0.46 | 1 | Christina Horton | Completed | 2019-08-23 | 1.83 | 2 | Christina Horton | Completed | 2019-08-06 | 0.71 | 2 | Brian Le | Completed | 2019-08-05 | 1.12 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 0.21 | 1 |  | Completed | 2019-08-09 | 5 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.13 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-30 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 7.08 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 5.21 | 1 | Andrew Clemons | Completed | 2019-08-27 15:08 |  | 2019-08-27 | 3.88 | 2 | Christina Horton | Completed | [10 empty] | 11.92 | [11 empty] | 2019-08-05 | 2019-08-23 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27499 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27499 | https://completesolar.sugarondemand.com/#Opportunities/d0b2cddc-b3f1-11e9-ac24-022c40d974e6 | Xavier Kimbrough |  | 2019-07-27 | iEnergy ElectricSolar | d0b2cddc-b3f1-11e9-ac24-022c40d974e6 | 6 | 2 | -5 | 4 | 5 | 5 | 5 | 9
25734 | PIP_APPROVED | PIP_APPROVED | 337 Edgehill Lane | Oceanside | CA | 92054 | Rosaly Estrada | 2019-06-19 19:05 | 7607574534 | suzieq197272@gmail.com | Suzie Estrada |  |  | 3255 | 0.175 | Michael Marlaire | 2019-06-19 | 2.135 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-18 | 2019-05-23 09:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | Enphase Energy | IQ7PLUS-72-2-US | Metal Corrugated | NO | 2019-08-20 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-20 07:00 | 2019-06-20 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-06-27 | 4.75 | 2 | Jethro Andal | Completed | 2019-07-10 | 7.88 | 1 | Christina Horton | Completed | 2019-07-17 | 3.29 | 5 | Brian Le | Completed | 2019-06-28 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-08 | 0.08 | 10 | Andrew Moralez | Completed | 2019-08-20 | 7.59 | 1 | Christina Horton | Completed | 2019-08-22 | 2 | 2 | Christina Horton | Completed | 2019-07-08 | 0.08 | 2 | Brian Le | Completed | 2019-07-09 | 3.33 | 2 | Darlynn Lacap | Completed | 2019-06-28 | 1 | 1 |  | Completed | 2019-07-02 | 3.04 | 1 | Jeremiah Liend | Completed | 2019-08-21 | 1.8 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 5.83 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-10-01 | 18.96 | 2 | Darlynn Lacap | Completed | 2019-09-27 | 7.83 | 1 | Andrew Clemons | Completed | 2019-08-21 14:17 |  | 2019-08-21 | 0.96 | 2 | Christina Horton | Completed | [10 empty] | 18.63 | [11 empty] | 2019-07-22 | 2019-08-22 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=25734 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25734 | https://completesolar.sugarondemand.com/#Opportunities/c68f1526-92ff-11e9-a30c-02ae981fbade | Brett Martinez | Chuck Sabo | 2019-05-18 | Infinity Energy Inc | c68f1526-92ff-11e9-a30c-02ae981fbade | 1 | 2 | 10 | 4 | 5 | 5 | 5 | 24
26185 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 10629 Meadow Glen Way East | Escondido | CA | 92026 | Mark Madore | 2019-08-01 06:59 | 6194544935 | markamanofgod@gmail.com |  |  |  | 9456 | 0.165 | Michael Marlaire | 2019-07-31 | 5.795 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-24 | 2019-07-26 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-20 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-08-20 07:00 | 2019-08-01 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 1.08 | 2 | Jethro Andal | Completed | 2019-08-08 | 3.79 | 1 | Ara Sotto | Completed | 2019-08-20 | 10.96 | 5 | Brian Le | Completed | 2019-08-02 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-06 | 1.88 | 15 | Ernesto Enriquez | Completed | 2019-08-20 | 0.5 | 2 | Christina Horton | Completed |  | 43.04 | 2 | Christina Horton | Current | 2019-08-05 | 0.08 | 2 | Brian Le | Completed | 2019-08-05 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 0.17 | 1 |  | Completed | 2019-08-14 | 8 | 1 | Noe Gomez | Completed | 2019-08-21 | 1.42 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | 2019-08-06 | 3 | 4 | Darlynn Lacap | Completed | 2019-08-07 | 0.92 | 5 | Darlynn Lacap | Completed | 2019-08-07 | 0.08 | 12 | Darlynn Lacap | Completed | 2019-09-19 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-10-16 | 7.75 | 2 | Ashley Rockwood | Completed |  | 3.38 | 2 | Darlynn Lacap | Current | 2019-10-18 | 1.96 | 1 | Andrew Clemons | Completed |  | 2019-09-20 | 2019-09-18 | 19.71 | 2 | Christina Horton | Completed | [10 empty] | 12.67 | [11 empty] | 2019-08-23 |  | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=26185 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26185 | https://completesolar.sugarondemand.com/#Opportunities/890e2c92-b464-11e9-8b07-022c40d974e6 | Robert Blessing |  | 2019-06-05 | Infinity Energy Inc | 890e2c92-b464-11e9-8b07-022c40d974e6 | 29 | 62 | -25 | -2 | 5 | 5 | 5 | -17
26757 | PIP_APPROVED | PIP_APPROVED | 1852 Andross Avenue | Yuba City | CA | 95993 | Kairam Mohan | 2019-07-22 17:26 | 5307131570 | dkk530@yahoo.com | Dhirag Kairam |  |  | 9575 | 0.195 | Ricardo Virgen | 2019-07-22 | 6.1 | Christina Horton | Blue Bright | Darlynn Lacap | 2019-07-19 | 2019-07-22 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-20 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-20 07:00 | 2019-07-24 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.92 | 2 | Jethro Andal | Completed | 2019-07-26 | 0.88 | 1 | Christina Horton | Completed | 2019-08-20 | 0.83 | 5 | Brian Le | Completed | 2019-08-01 | 4.79 | 3 | Andrew Moralez | Completed | 2019-08-09 | 6.29 | 0 | Andrew Moralez | Completed | 2019-08-20 | 0.42 | 2 | Christina Horton | Completed | 2019-08-22 | 1.96 | 2 | Christina Horton | Completed | 2019-08-16 | 14.92 | 2 | Brian Le | Completed | 2019-07-26 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0 | 1 |  | Completed | 2019-07-31 | 4 | 1 | Jill Allen | Completed | 2019-08-21 | 1.42 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 5.92 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 6.17 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 1.96 | 1 | Andrew Clemons | Completed | 2019-08-22 14:56 |  | 2019-08-22 | 1.83 | 2 | Christina Horton | Completed | [10 empty] | 7.5 | [11 empty] | 2019-08-01 | 2019-08-22 | YUBA CITY | Yuba City | https://heliotrack.completesolar.com/job.php?action=review&jobID=26757 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26757 | https://completesolar.sugarondemand.com/#Opportunities/7ac3220e-ace0-11e9-8a60-022c40d974e6 | Blue Bright |  | 2019-06-27 | Golden Gate Electric Service | 7ac3220e-ace0-11e9-8a60-022c40d974e6 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
27078 | PIP_APPROVED | PIP_APPROVED | 114 Norfolk Street | Worcester | MA | 1604 | Kwame A Kissi | 2019-07-16 12:44 | 7742429947 | kakissi@hotmail.com |  |  |  | 4543 |  | Hiram Velez | 2019-07-16 | 6.71 | Christina Horton | Solara Solar | Marcia Garay | 2019-07-12 | 2019-07-15 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-08-20 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  | 0 | 0 | 2019-08-19 07:00 | 2019-07-17 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-19 | 1.96 | 2 | Jethro Andal | Completed | 2019-08-02 | 9.71 | 1 | Christina Horton | Completed | 2019-08-19 | 0.08 | 5 | Christina Horton | Completed | 2019-07-24 | 0 | 3 | Andrew Moralez | Completed | 2019-07-25 | 1.04 | 10 | Andrew Moralez | Completed | 2019-08-20 | 1.17 | 2 | Christina Horton | Completed | 2019-08-22 | 2.13 | 2 | Christina Horton | Completed | 2019-08-20 | 15.88 | 2 | Brian Le | Completed | 2019-07-22 | 1 | 2 | Marcia Garay | Completed | 2019-07-24 | 2.79 | 1 |  | Completed | 2019-07-20 | 0.38 | 1 | Andrew Clemons | Completed |  | 31.83 | 1 | Marcia Garay | Current | 2019-08-27 | 0.96 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 16.08 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 9.96 | 2 | Marcia Garay | Completed | 2019-09-30 | 3.08 | 1 | Jill Allen | Completed |  | 2019-09-18 | 2019-08-28 | 5.92 | 2 | Christina Horton | Completed | [10 empty] | 49.13 | [11 empty] | 2019-08-07 | 2019-08-20 | Default | Worcester | https://heliotrack.completesolar.com/job.php?action=review&jobID=27078 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27078 | https://completesolar.sugarondemand.com/#Opportunities/06444bac-a802-11e9-9c8b-02ae981fbade | Solara Solar | Von Ayers | 2019-07-12 | Skyline Solar | 06444bac-a802-11e9-9c8b-02ae981fbade | 8 | 2 | -5 | 4 | 5 | 5 | 5 | 9
27235 | PIP_APPROVED | PIP_APPROVED | 9855 Blanchard Avenue | Fontana | CA | 92335 | Renee Mendoza | 2019-07-22 18:43 | 9513176015 | mendozapiglet13@gmail.com |  |  |  | 7700 | 0.136 | Shaun Labelle | 2019-07-22 | 4.575 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-18 | 2019-07-22 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-20 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-20 07:00 | 2019-07-23 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 2.08 | 2 | Daniel Speegle | Completed | 2019-07-24 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-20 | 0.08 | 5 | Ara Sotto | Completed | 2019-07-29 | 1 | 3 | Andrew Moralez | Completed | 2019-08-14 | 12.21 | 12 | Ernesto Enriquez | Completed | 2019-08-20 | 0.41 | 1 | Ara Sotto | Completed | 2019-08-27 | 5.04 | 2 | Ara Sotto | Completed |  | 60.96 | 2 | Brian Le | Current | 2019-07-25 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-07-26 | 0.83 | 1 |  | Completed | 2019-07-31 | 3.92 | 1 | Jill Allen | Completed | 2019-08-21 | 1.5 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-27 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 10.21 | 2 | Darlynn Lacap | Completed |  | 37.25 | 1 | Andrew Clemons | Current | 2019-08-21 18:45 |  | 2019-08-21 | 1.08 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-14 | 2019-08-27 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=27235 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27235 | https://completesolar.sugarondemand.com/#Opportunities/342fdf98-aceb-11e9-a0df-02ae981fbade | Dominic Labadie |  | 2019-07-18 | Blalock Electric&Solar | 342fdf98-aceb-11e9-a0df-02ae981fbade | 1 | 7 | 10 | -2 | 5 | 5 | 5 | 18
27319 | PIP_APPROVED | PIP_APPROVED | 1011 West 127th Street | Compton | CA | 90222 | Daniel Jean | 2019-08-04 15:53 | 9493744403 | jeandaniel3300@gmail.com |  |  |  | 5297 | 0.151 | Chris Peaslee | 2019-08-04 | 3.05 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-31 | 2019-08-03 12:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-20 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-19 07:00 | 2019-08-05 | 0.5 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 3.13 | 2 | Daniel Speegle | Completed | 2019-08-06 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-20 | 1.88 | 5 | Brian Le | Completed | 2019-08-14 | 0 | 3 | Andrew Moralez | Completed | 2019-08-14 | 0 | 1 | Andrew Moralez | Completed | 2019-08-20 | 1.08 | 1 | Ara Sotto | Completed | 2019-08-22 | 2.17 | 2 | Ara Sotto | Completed | 2019-08-16 | 5.08 | 2 | Brian Le | Completed | 2019-08-09 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-08-14 | 3.96 | 1 |  | Completed | 2019-08-19 | 2.79 | 1 | Jill Allen | Completed | 2019-08-21 | 2.29 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-13 | 0.71 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 6.75 | 2 | Darlynn Lacap | Completed |  | 22.08 | 1 | Andrew Clemons | Current | 2019-09-12 16:59 |  | 2019-09-12 | 16.5 | 2 | Ara Sotto | Completed | [10 empty] | 4.04 | [11 empty] | 2019-08-15 | 2019-08-22 | COMPTON | Compton | https://heliotrack.completesolar.com/job.php?action=review&jobID=27319 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27319 | https://completesolar.sugarondemand.com/#Opportunities/9ed55afc-b70a-11e9-aa8b-069e4f790264 | Cesar Valdizan |  | 2019-07-22 | Green Road Solar Crew | 9ed55afc-b70a-11e9-aa8b-069e4f790264 | 23 | 2 | -25 | 4 | 5 | 5 | 5 | -11
25257 | PIP_APPROVED | PIP_APPROVED | 1632 North Aspen Court | Visalia | CA | 93291 | Mary Florio | 2019-06-12 14:27 | 5592501579 | Dustin@comfort-now.com |  |  |  | 19559.67 |  | Abraham SiteTech Vazquez | 2019-06-12 | 14.03 | Christina Horton |  | Marcia Garay |  | 2019-05-06 08:00 | LR6-60PB-305M | 305 | 46 | LONGi Solar | SolarEdge | SE11400A-US RGM | Composite | Line-side Tap | 2019-08-19 | PTO Received | Cash | 1 | 0 |  |  | 0 | 0 | 2019-08-19 07:00 | 2019-06-13 | 0.83 | 2 | Marcia Garay | Completed | 2019-06-14 | 0.96 | 2 | Jethro Andal | Completed | 2019-06-27 | 9 | 1 | Christina Horton | Completed | 2019-08-19 | 10.13 | 5 | Brian Le | Completed | 2019-06-18 | 1.75 | 3 | Andrew Moralez | Completed | 2019-06-24 | 4.08 | 0 | Andrew Moralez | Completed | 2019-08-19 | 2.21 | 3 | Christina Horton | Completed | 2019-08-27 | 5.83 | 2 | Christina Horton | Completed | 2019-08-05 | 31.96 | 2 | Brian Le | Completed | 2019-06-14 | 0.04 | 2 | Marcia Garay | Completed | 2019-06-14 | 0.25 | 1 |  | Completed | 2019-06-27 | 9 | 1 | Andrew Clemons | Completed | 2019-08-22 | 5.29 | 1 | Marcia Garay | Completed |  | 38.25 | 2 | Andrew Clemons | Current | 2019-07-03 | 0.04 | 4 | Marcia Garay | Completed | 2019-07-03 | 0 | 5 | Marcia Garay | Completed | 2019-07-03 | 0.21 | 12 | Marcia Garay | Completed | 2019-08-27 | 2 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.21 | 2 | Marcia Garay | Completed |  | 35.38 | 1 | Andrew Clemons | Current | 2019-08-23 15:30 |  | 2019-08-23 | 3.92 | 2 | Christina Horton | Completed | 2019-07-23 | 0.08 | 1 | Christina Horton | Completed | 2019-06-27 | 0.33 | 2 | Marcia Garay | Completed | 2.92 | [11 empty] | 2019-06-18 | 2019-08-26 | VISALIA | Visalia | https://heliotrack.completesolar.com/job.php?action=review&jobID=25257 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25257 | https://completesolar.sugarondemand.com/#Opportunities/c957377c-8d58-11e9-86a2-069e4f790264 | Steve Walden |  | 2019-05-02 | Peak Energy Electric | c957377c-8d58-11e9-86a2-069e4f790264 | 4 | 8 | 0 | -2 | 5 | 5 | 5 | 8
26095 | PIP_APPROVED | PIP_APPROVED | 3420 Laketree Drive | Fallbrook | CA | 92028 | Rafiq Waziri | 2019-07-03 15:01 | 7608052361 | rafiwaz@hotmail.com | Gunnel Waziri | 7608053591 |  | 8915 | 0.184 | Chad Malloy | 2019-07-03 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-01 | 2019-06-10 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Spanish Tile | NO | 2019-08-19 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-19 07:00 | 2019-07-10 | 3.71 | 2 | Marcia Garay | Completed | 2019-07-04 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-24 | 10 | 1 | Christina Horton | Completed | 2019-08-19 | 20.17 | 5 | Brian Le | Completed | 2019-07-16 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-16 | 0.13 | 0 | Andrew Moralez | Completed | 2019-08-19 | 0.54 | 2 | Christina Horton | Completed | 2019-09-09 | 13.75 | 2 | Christina Horton | Completed | 2019-07-09 | 0.08 | 2 | Brian Le | Completed | 2019-07-10 | 0 | 2 | Marcia Garay | Completed | 2019-07-16 | 4.08 | 1 |  | Completed | 2019-07-22 | 8.04 | 1 | Andrew Clemons | Completed | 2019-08-29 | 8.58 | 1 | Marcia Garay | Completed | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-09 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 8.13 | 2 | Marcia Garay | Completed |  | 28.33 | 1 | Jill Allen | Current |  | 2019-09-06 | 2019-09-06 | 12.83 | 2 | Christina Horton | Completed | [10 empty] | 13.08 | [11 empty] | 2019-07-16 | 2019-09-09 | FALLBROOK | Fallbrook | https://heliotrack.completesolar.com/job.php?action=review&jobID=26095 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26095 | https://completesolar.sugarondemand.com/#Opportunities/ba58c2e2-8739-11e9-b9a5-0630baf9dcb8 | Robert Garcia |  | 2019-06-01 | Infinity Energy Inc | ba58c2e2-8739-11e9-b9a5-0630baf9dcb8 | 18 | 21 | -15 | -2 | 5 | 5 | 5 | -7
27269 | PIP_APPROVED | PIP_APPROVED | 15158 Calle Renfro | Moreno Valley | CA | 92551 | Judith Trujillo | 2019-07-30 11:43 | 9512363377 | judytrujillo@hotmail.com |  |  |  | 6989 | 0.165 | Shaun Labelle | 2019-07-30 | 4.27 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-19 | 2019-07-22 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-19 07:00 | 2019-08-02 | 3.09 | 2 | Marcia Garay | Completed | 2019-08-03 | 0.38 | 2 | Jethro Andal | Completed | 2019-08-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-19 | 0.96 | 5 | Brian Le | Completed | 2019-08-14 | 2 | 3 | Andrew Moralez | Completed | 2019-08-15 | 1 | 25 | Andrew Moralez | Completed | 2019-08-19 | 0.29 | 1 | Ara Sotto | Completed | 2019-08-23 | 4.04 | 2 | Ara Sotto | Completed | 2019-08-16 | 9.17 | 2 | Brian Le | Completed | 2019-08-05 | 0.42 | 2 | Marcia Garay | Completed | 2019-08-12 | 5.54 | 1 |  | Completed | 2019-08-26 | 15.29 | 1 | Andrew Clemons | Completed |  | 44.42 | 1 | Marcia Garay | Current | 2019-08-29 | 3.67 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-30 | 4.54 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.25 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 4.17 | 2 | Marcia Garay | Completed | 2019-09-11 | 4.04 | 1 | Jeremiah Liend | Completed | 2019-08-23 14:53 |  | 2019-08-23 | 4.13 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-19 | 2019-08-23 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27269 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27269 | https://completesolar.sugarondemand.com/#Opportunities/ca1fc694-b2f9-11e9-af0d-069e4f790264 | 300 Stars Inc |  | 2019-07-19 | Power Town Solar Electric | ca1fc694-b2f9-11e9-af0d-069e4f790264 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
27277 | PIP_APPROVED | PIP_APPROVED | 10328 Darden Road | San Diego | CA | 92126 | Francis Garcia | 2019-07-25 14:28 | 8585861379 | Cf007nassociate@yahoo.com | Crispina Garcia |  |  | 13537 | 0.17 | Ryan Malloy | 2019-07-25 | 8.845 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-22 | 2019-07-24 09:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-19 07:00 | 2019-07-30 | 3.04 | 2 | Marcia Garay | Completed | 2019-07-29 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-05 | 4 | 1 | Christina Horton | Completed | 2019-08-19 | 9.96 | 5 | Brian Le | Completed | 2019-08-01 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-01 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-19 | 0.46 | 2 | Christina Horton | Completed | 2019-08-21 | 2.04 | 2 | Christina Horton | Completed | 2019-08-05 | 3.96 | 2 | Brian Le | Completed | 2019-07-30 | 0 | 2 | Marcia Garay | Completed | 2019-08-01 | 1.75 | 1 |  | Completed | 2019-08-06 | 4.63 | 1 | Andrew Clemons | Completed |  | 44.54 | 1 | Marcia Garay | Current | 2019-08-22 | 0.88 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-29 | 5.67 | 2 | Ashley Rockwood | Completed | 2019-09-03 | 2.25 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 7 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.92 | 1 | Jill Allen | Completed | 2019-08-21 15:16 |  | 2019-08-21 | 2 | 2 | Christina Horton | Completed | [10 empty] | 0.79 | [11 empty] | 2019-08-22 | 2019-08-21 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27277 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27277 | https://completesolar.sugarondemand.com/#Opportunities/120beabc-af23-11e9-af30-022c40d974e6 | Thomas Noble |  | 2019-07-19 | Infinity Energy Inc | 120beabc-af23-11e9-af30-022c40d974e6 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
27456 | SP APPROVED |  | 27523 Camden Way | Menifee | CA | 92586 | David Phelps | 2019-07-29 06:47 | 8583544460 | davidphelps2@hotmail.com |  |  |  | 15643 | 0.15 | Michael Marlaire | 2019-07-29 | 10.37 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-26 | 2019-07-27 14:00 | LR6-60PB-305M | 305 | 34 | LONGi Solar | SolarEdge | SE10000A-US RGM | Composite | Line-side Tap | 2019-08-19 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-19 07:00 | 2019-07-29 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 1.17 | 2 | Daniel Speegle | Completed | 2019-08-06 | 2.92 | 1 | Ara Sotto | Completed | 2019-08-19 | 6 | 5 | Brian Le | Completed | 2019-08-01 | 0 | 3 | Ernesto Enriquez | Completed | 2019-08-07 | 4.08 | 0 | Ernesto Enriquez | Completed | 2019-08-19 | 0.5 | 3 | Ara Sotto | Completed |  | 44.25 | 2 | Ara Sotto | Current | 2019-08-09 | 5.96 | 2 | Brian Le | Completed | 2019-07-31 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 1 |  | Completed | 2019-08-02 | 0.96 | 1 | Andrew Clemons | Completed | 2019-08-21 | 2.63 | 1 | Darlynn Lacap | Completed | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-02 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 1.75 | 2 | Ashley Rockwood | Completed |  | 11.38 | 2 | Darlynn Lacap | Current | 2019-10-09 | 3.04 | 1 | Jeremiah Liend | Completed |  | 2019-08-22 | 2019-09-27 | 0 | 2 | Ara Sotto | Completed | 2019-09-27 | 28.71 | 1 | Ara Sotto | Completed | 2019-07-31 | 0.75 | 2 | Darlynn Lacap | Completed | 3.67 | [11 empty] | 2019-08-01 |  | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27456 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27456 | https://completesolar.sugarondemand.com/#Opportunities/59efd780-b207-11e9-81cd-069e4f790264 | PHNX Power |  | 2019-07-26 | Zachary Noah Gamez | 59efd780-b207-11e9-81cd-069e4f790264 | 0 | 63 | 10 | -2 | 5 | 5 | 5 | 18
26325 | PIP_APPROVED | PIP_APPROVED | 22691 Napoli | Laguna Hills | CA | 92653 | Soheili Asghar | 2019-06-14 13:09 | 9495178340 | jsoheili@cox.net | Jay Ashagar | 9497518032 |  | 4506 | 0.182 | Chris Peaslee | 2019-06-14 | 3.66 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-06-12 | 2019-06-14 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-08-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-16 07:00 | 2019-06-14 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 2.88 | 2 | Jethro Andal | Completed | 2019-08-08 | 35.13 | 1 | Christina Horton | Completed | 2019-08-16 | 26.17 | 5 | Brian Le | Completed | 2019-06-21 | 0 | 3 | Andrew Moralez | Completed | 2019-08-09 | 33.96 | 2 | Andrew Moralez | Completed | 2019-08-17 | 0.79 | 1 | Ara Sotto | Completed | 2019-09-20 | 23.46 | 2 | Ara Sotto | Completed | 2019-07-09 | 0.08 | 2 | Brian Le | Completed | 2019-07-11 | 3.08 | 2 | Darlynn Lacap | Completed | 2019-06-21 | 2.13 | 1 |  | Completed | 2019-07-08 | 12.08 | 1 | Andrew Clemons | Completed | 2019-08-16 | 0.54 | 1 | Darlynn Lacap | Completed | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 5 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 17.08 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 1.83 | 1 | Jill Allen | Completed |  |  | 2019-08-19 | 0.08 | 2 | Christina Horton | Completed | [10 empty] | 21.49 | [11 empty] | 2019-06-25 | 2019-09-20 | LAGUNA HILLS | Laguna Hills | https://heliotrack.completesolar.com/job.php?action=review&jobID=26325 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26325 | https://completesolar.sugarondemand.com/#Opportunities/348568e2-8ee0-11e9-8505-069e4f790264 | Robert Blessing |  | 2019-06-11 | Zachary Noah Gamez | 348568e2-8ee0-11e9-8505-069e4f790264 | 2 | 34 | 7 | -2 | 5 | 5 | 5 | 15
26585 | PIP_APPROVED | PIP_APPROVED | 261 Goettingen Street | San Francisco | CA | 94134 | Sandy Chow | 2019-07-02 16:39 | 4158125891 | sandykids2004@yahoo.com | Takwing Cheund | 4158125918 |  | 5701.57 |  | Ricardo Virgen | 2019-07-02 | 3.66 | Christina Horton | PACE Avenue | Marcia Garay | 2019-07-01 | 2019-07-02 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Rolled Roofing / Torchdown | NO | 2019-08-17 | PTO Received | Cash | 0 | 0 |  | 0 | 0 | 1 | 2019-08-17 07:00 | 2019-07-09 | 3.63 | 2 | Marcia Garay | Completed | 2019-07-10 | 1.25 | 2 | Daniel Speegle | Completed | 2019-07-17 | 4.88 | 1 | Christina Horton | Completed | 2019-08-17 | 17.26 | 5 | Brian Le | Completed | 2019-07-18 | 4.67 | 3 | Andrew Moralez | Completed | 2019-07-29 | 7.21 | 5 | Andrew Moralez | Completed | 2019-08-17 | 0.08 | 2 | Christina Horton | Completed | 2019-10-09 | 36.63 | 2 | Christina Horton | Completed | 2019-07-24 | 8.21 | 2 | Brian Le | Completed | 2019-07-11 | 0.75 | 2 | Marcia Garay | Completed | 2019-07-11 | 1.13 | 1 |  | Completed | 2019-07-22 | 8.08 | 1 | Andrew Clemons | Completed |  | 44.71 | 1 | Marcia Garay | Current |  | 8.04 | 2 | Jill Allen | Current | [15 empty] | 2019-08-30 | 4.75 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 4.96 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 24.96 | 2 | Marcia Garay | Completed |  | 30.29 | 1 | Jill Allen | Current | 2019-08-22 11:10 |  | 2019-08-23 | 4.63 | 2 | Christina Horton | Completed | [10 empty] | 1.13 | [11 empty] | 2019-07-25 | 2019-09-30 | SAN FRANCISCO | San Francisco | https://heliotrack.completesolar.com/job.php?action=review&jobID=26585 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26585 | https://completesolar.sugarondemand.com/#Opportunities/2b9b29b4-a1ce-11e9-b283-022c40d974e6 | PACE Avenue |  | 2019-06-21 | All Bay Solar | 2b9b29b4-a1ce-11e9-b283-022c40d974e6 | 6 | 53 | -5 | -2 | 5 | 5 | 5 | 3
26657 | SP APPROVED |  | 514 NAPLES ST | San Francisco | CA | 94112 | Zhan Yuan Huang | 2019-06-27 13:58 | 4153109824 | szhuang@outlook.com | Jasmine Cui |  | 4156728121 | 5986.73 |  | Ricardo Virgen | 2019-06-27 | 3.66 | Christina Horton | PACE Avenue | Darlynn Lacap | 2019-06-25 | 2019-06-27 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-17 | PTO Received | Cash | 0 | 0 |  |  |  | 1 | 2019-08-17 07:00 | 2019-06-27 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 2.71 | 2 | Daniel Speegle | Completed | 2019-07-15 | 7.88 | 1 | Christina Horton | Completed | 2019-08-16 | 15.84 | 5 | Brian Le | Completed | 2019-07-16 | 9.21 | 3 | Andrew Moralez | Completed | 2019-07-24 | 5.83 | 5 | Ernesto Enriquez | Completed | 2019-08-17 | 0.08 | 1 | Christina Horton | Completed |  | 44.71 | 2 | Christina Horton | Current | 2019-07-16 | 1.21 | 2 | Brian Le | Completed | 2019-07-12 | 1.29 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 0 | 1 |  | Completed | 2019-07-16 | 9.04 | 1 | Andrew Clemons | Completed | 2019-08-21 | 0.21 | 1 | Darlynn Lacap | Completed |  | 0 | 2 |  | Inactive | [15 empty] | 2019-08-30 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 8.83 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 18.08 | 2 | Darlynn Lacap | Completed |  | 26.33 | 1 | Andrew Clemons | Current | 2019-08-22 16:52 |  | 2019-08-23 | 4.63 | 2 | Christina Horton | Completed | [10 empty] | 26.33 | [11 empty] | 2019-07-23 |  | SAN FRANCISCO | San Francisco | https://heliotrack.completesolar.com/job.php?action=review&jobID=26657 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26657 | https://completesolar.sugarondemand.com/#Opportunities/2c4e6d0c-991e-11e9-a28d-0630baf9dcb8 | PACE Avenue |  | 2019-06-24 | All Bay Solar | 2c4e6d0c-991e-11e9-a28d-0630baf9dcb8 | 6 | 65 | -5 | -2 | 5 | 5 | 5 | 3
26745 | PIP_APPROVED | PIP_APPROVED | 10171 Shangri La Avenue | Hesperia | CA | 92345 | Bryan Herman | 2019-06-27 18:53 | 3233607079 | bhermanmail@yahoo.com |  |  |  | 6402 | 0.125 | Bill Angevine | 2019-06-27 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-26 | 2019-06-27 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-17 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-16 07:00 | 2019-07-02 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 3.08 | 2 | Daniel Speegle | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-17 | 6.5 | 5 | Brian Le | Completed | 2019-07-17 | 5.83 | 3 | Ernesto Enriquez | Completed | 2019-08-16 | 22.08 | 14 | Andrew Moralez | Completed | 2019-08-17 | 2.54 | 1 | Ara Sotto | Completed | 2019-08-20 | 1.63 | 2 | Ara Sotto | Completed | 2019-08-08 | 19.79 | 2 | Brian Le | Completed | 2019-07-11 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 0.75 | 1 |  | Completed | 2019-07-25 | 12.46 | 1 | Andrew Clemons | Completed | 2019-08-21 | 4.17 | 1 | Darlynn Lacap | Completed | 2019-08-21 | 0.71 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-30 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.13 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 11.88 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 3.96 | 1 | Andrew Clemons | Completed | 2019-08-21 12:08 |  | 2019-08-27 | 6.42 | 2 | Ara Sotto | Completed | [10 empty] | 12.92 | [11 empty] | 2019-08-06 | 2019-08-20 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=26745 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26745 | https://completesolar.sugarondemand.com/#Opportunities/791657b6-9947-11e9-a528-02ae981fbade | SCES Division |  | 2019-06-26 | HDM Electric Inc | 791657b6-9947-11e9-a528-02ae981fbade | 10 | 3 | -5 | 2 | 5 | 5 | 5 | 7
26842 | PIP_APPROVED | PIP_APPROVED | 13477 Huntington Street | Fontana | CA | 92336 | Trinidad Herrera | 2019-07-05 15:08 | 9512018597 | trinie59@gmail.com | Lia Herrera | 9092390730 |  | 13787 | 0.165 | Shaun Labelle | 2019-07-05 | 8.235 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-02 | 2019-07-05 15:00 | LR6-60PB-305M | 305 | 27 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-18 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-08-15 07:00 | 2019-07-08 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-10 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-30 | 13.79 | 1 | Ara Sotto | Completed | 2019-08-18 | 5.54 | 5 | Brian Le | Completed | 2019-07-17 | 1.04 | 3 | Ernesto Enriquez | Completed | 2019-08-06 | 14.08 | 12 | Andrew Moralez | Completed | 2019-08-17 | 2.25 | 2 | Ara Sotto | Completed | 2019-09-20 | 23.54 | 2 | Ara Sotto | Completed | 2019-08-09 | 19.83 | 2 | Brian Le | Completed | 2019-07-12 | 2.08 | 2 | Marcia Garay | Completed | 2019-07-16 | 3.88 | 1 |  | Completed | 2019-07-22 | 8 | 1 | Andrew Clemons | Completed | 2019-09-17 | 22.92 | 1 | Marcia Garay | Completed | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 13.92 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 7.96 | 2 | Marcia Garay | Completed | 2019-09-12 | 1.29 | 1 | Noe Gomez | Completed | 2019-08-19 17:40 |  | 2019-08-20 | 1.58 | 2 | Ara Sotto | Completed | [10 empty] | 11 | 2019-07-31 | 16.79 | 14 | James Fernandez | Completed | 2019-07-29 | 2019-08-07 | 7.21 | 1 | James Fernandez | Completed | 2019-08-06 | 2019-09-20 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=26842 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26842 | https://completesolar.sugarondemand.com/#Opportunities/5236d834-9f71-11e9-bfeb-069e4f790264 | 300 Stars Inc |  | 2019-07-01 | Zachary Noah Gamez | 5236d834-9f71-11e9-bfeb-069e4f790264 | 3 | 34 | 0 | -2 | 5 | 5 | 5 | 8
27100 | PIP_APPROVED | PIP_APPROVED | 363 Center Grove Way | San Jacinto | CA | 92582 | David Gonzalez | 2019-07-19 09:18 | 9512061660 | jiggaboy.david@gmail.com | Maria Castro | 9513372147 | mariemercedes1@aol.com | 12978 | 0.16 | Shaun Labelle | 2019-07-16 | 7.32 | Ara Sotto | Branden Williams | Marcia Garay | 2019-07-15 | 2019-07-16 09:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM |  | NO | 2019-08-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-15 07:00 | 2019-07-19 | 1.88 | 2 | Marcia Garay | Completed | 2019-07-19 | 1.13 | 2 | Jethro Andal | Completed | 2019-07-25 | 4.38 | 1 | Ara Sotto | Completed | 2019-08-17 | 5.54 | 5 | Brian Le | Completed | 2019-07-26 | 4.79 | 3 | Ernesto Enriquez | Completed | 2019-08-07 | 8.13 | 10 | Ernesto Enriquez | Completed | 2019-08-17 | 1.79 | 2 | Ara Sotto | Completed | 2019-09-30 | 29.33 | 2 | Ara Sotto | Completed | 2019-08-09 | 13.88 | 2 | Brian Le | Completed | 2019-07-22 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-19 | 0.04 | 1 |  | Completed | 2019-07-31 | 7.71 | 1 | Noe Gomez | Completed |  | 46.54 | 1 | Marcia Garay | Current | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-27 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 5.79 | 2 | Marcia Garay | Completed |  | 37.04 | 1 | Jill Allen | Current | 2019-08-19 17:39 | 2019-08-16 | 2019-08-23 | 4.75 | 2 | Ara Sotto | Completed | [10 empty] | 0.04 | [11 empty] | 2019-08-09 | 2019-09-27 | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=27100 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27100 | https://completesolar.sugarondemand.com/#Opportunities/4f670424-a7fc-11e9-9619-069e4f790264 | Branden Williams |  | 2019-07-12 | Zachary Noah Gamez | 4f670424-a7fc-11e9-9619-069e4f790264 | 6 | 44 | -5 | -2 | 5 | 5 | 5 | 3
27118 | PIP_APPROVED | PIP_APPROVED | 2024 Woodland Drive | Yuba City | CA | 95991 | Vikram Passi | 2019-07-16 16:17 | 5302180414 | vikram.passi@yahoo.com | Rajni Passi | 5302182417 | vikramsolar530@gmail.com | 7919 | 0.195 | Ricardo Virgen | 2019-07-16 | 5.49 | Christina Horton | Blue Bright | Marcia Garay | 2019-07-13 | 2019-07-16 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-17 07:00 | 2019-07-17 | 0.79 | 2 | Marcia Garay | Completed | 2019-07-19 | 2.13 | 2 | Jethro Andal | Completed | 2019-07-25 | 3.83 | 1 | Christina Horton | Completed | 2019-08-17 | 11.17 | 5 | Brian Le | Completed | 2019-08-01 | 8.75 | 3 | Ernesto Enriquez | Completed | 2019-08-09 | 6.33 | 0 | Ernesto Enriquez | Completed | 2019-08-17 | 0.08 | 2 | Christina Horton | Completed | 2019-08-20 | 1.58 | 2 | Christina Horton | Completed | 2019-07-31 | 6.17 | 2 | Brian Le | Completed | 2019-07-23 | 1.79 | 2 | Marcia Garay | Completed | 2019-07-19 | 0 | 1 |  | Completed | 2019-07-25 | 3.96 | 1 | Noe Gomez | Completed | 2019-08-22 | 3.63 | 1 | Marcia Garay | Completed | 2019-08-21 | 0.75 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-22 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 0.08 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 0.08 | 2 | Cynthia Morales | Completed | 2019-09-04 | 0.08 | 1 | Noe Gomez | Completed | 2019-08-20 13:52 |  | 2019-08-20 | 1.58 | 2 | Christina Horton | Completed | [10 empty] | 13.67 | [11 empty] | 2019-08-01 | 2019-08-20 | YUBA CITY | Yuba City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27118 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27118 | https://completesolar.sugarondemand.com/#Opportunities/d8abf140-a81f-11e9-878b-0630baf9dcb8 | Blue Bright |  | 2019-07-13 | Golden Gate Electric Service | d8abf140-a81f-11e9-878b-0630baf9dcb8 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
27169 | PIP_APPROVED | PIP_APPROVED | 30866 Emperor Drive | Canyon Lake | CA | 92587 | Lon Swank | 2019-07-18 10:31 | 9518052265 | capnkat@verizon.net | Kathryn Elizabeth Swank | 951-805-2264 |  | 12842 | 0.181 | Chad Malloy | 2019-07-18 | 7.625 | Ara Sotto | PHNX Power | Marcia Garay | 2019-07-16 | 2019-07-17 12:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-18 | PTO Received | SunRun Monthly | 1 | 0 |  |  | 0 | 1 | 2019-08-16 07:00 | 2019-07-22 | 2.08 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.92 | 2 | Daniel Speegle | Completed | 2019-07-22 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-18 | 9.38 | 5 | Brian Le | Completed | 2019-07-26 | 1.25 | 3 | Andrew Moralez | Completed | 2019-08-07 | 8.17 | 0 | Andrew Moralez | Completed | 2019-08-17 | 0.92 | 2 | Ara Sotto | Completed | 2019-08-22 | 3.58 | 2 | Ara Sotto | Completed | 2019-08-05 | 8.04 | 2 | Brian Le | Completed | 2019-07-24 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-25 | 1.63 | 1 |  | Completed | 2019-07-30 | 5.04 | 1 | Noe Gomez | Completed | 2019-08-22 | 4.38 | 1 | Marcia Garay | Completed | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-22 | 0.04 | 4 | Marcia Garay | Completed | 2019-07-24 | 1.92 | 5 | Marcia Garay | Completed | 2019-07-25 | 1.08 | 12 | Marcia Garay | Completed | 2019-08-22 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-08-23 | 1.29 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 4.58 | 2 | Marcia Garay | Completed | 2019-08-29 | 3.5 | 1 | Andrew Clemons | Completed |  | 2019-08-19 | 2019-08-20 | 1.54 | 2 | Ara Sotto | Completed | [10 empty] | 1.42 | [11 empty] | 2019-07-26 | 2019-08-22 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27169 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27169 | https://completesolar.sugarondemand.com/#Opportunities/c1a05a00-a981-11e9-a358-069e4f790264 | PHNX Power |  | 2019-07-16 | HDM Electric Inc | c1a05a00-a981-11e9-a358-069e4f790264 | 3 | 5 | 0 | -2 | 5 | 5 | 5 | 8
27248 | PIP_APPROVED | PIP_APPROVED | 24807 4th Street | San Bernardino | CA | 92410 | Hermelinda G Ambriz | 2019-07-22 19:12 | 9097636899 | ermelindaambriz@gmail.com | Elias Ambriz | 9099634297 |  | 7775 | 0.181 | Shaun Labelle | 2019-07-22 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-18 | 2019-07-22 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-18 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-16 | 2019-07-23 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 1.96 | 2 | Daniel Speegle | Completed | 2019-07-25 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-18 | 3.67 | 5 | Brian Le | Completed | 2019-07-26 | 0.79 | 3 | Andrew Moralez | Completed | 2019-08-01 | 3.88 | 1 | Andrew Moralez | Completed | 2019-08-17 | 0.79 | 2 | Ara Sotto | Completed | 2019-08-20 | 1.67 | 2 | Ara Sotto | Completed | 2019-08-13 | 0.5 | 2 | Brian Le | Completed | 2019-08-08 | 7.25 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.17 | 1 |  | Completed | 2019-08-09 | 11.17 | 1 | Andrew Clemons | Completed | 2019-08-21 | 3.42 | 1 | Darlynn Lacap | Completed | 2019-08-21 | 0.67 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-30 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 4.17 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 4.04 | 1 | Jill Allen | Completed |  | 2019-08-19 | 2019-08-29 | 8.38 | 2 | Ara Sotto | Completed | [10 empty] | 7.54 | [11 empty] | 2019-07-29 | 2019-08-20 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=27248 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27248 | https://completesolar.sugarondemand.com/#Opportunities/47cbe052-acef-11e9-a045-02ae981fbade | 300 Stars Inc | Oscar Hernandez | 2019-07-18 | Green Road Solar Crew | 47cbe052-acef-11e9-a045-02ae981fbade | 12 | 3 | -15 | 2 | 5 | 5 | 5 | -3
27355 | PIP_APPROVED | PIP_APPROVED | 27475 Sun City Boulevard | Menifee | CA | 92586 | Dianne Boatner | 2019-07-24 17:17 | 3104298803 | dianneboatner@gmail.com | Ivory Boatner |  |  | 7439 | 0.11 | Shaun Labelle | 2019-07-24 | 4.575 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-23 | 2019-07-24 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-17 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-16 07:00 | 2019-07-25 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-26 | 1.25 | 2 | Daniel Speegle | Completed | 2019-07-25 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-17 | 6.5 | 5 | Brian Le | Completed | 2019-07-30 | 1.25 | 3 | Andrew Moralez | Completed | 2019-08-09 | 8.08 | 0 | Ernesto Enriquez | Completed | 2019-08-17 | 0.79 | 1 | Ara Sotto | Completed | 2019-08-19 | 0.38 | 2 | Ara Sotto | Completed | 2019-08-08 | 7.96 | 2 | Brian Le | Completed | 2019-07-29 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-29 | 0.63 | 1 |  | Completed | 2019-08-02 | 4.63 | 1 | Jill Allen | Completed | 2019-08-21 | 3.42 | 1 | Darlynn Lacap | Completed | 2019-08-21 | 2 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-27 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 5.04 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 0.96 | 1 | Jeremiah Liend | Completed | 2019-08-22 16:12 |  | 2019-08-22 | 3.5 | 2 | Ara Sotto | Completed | [10 empty] | 1.83 | [11 empty] | 2019-07-30 | 2019-08-19 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27355 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27355 | https://completesolar.sugarondemand.com/#Opportunities/8c90d7c8-ae71-11e9-b512-022c40d974e6 | PHNX Power |  | 2019-07-23 | Power Town Solar Electric | 8c90d7c8-ae71-11e9-b512-022c40d974e6 | 5 | 2 | -5 | 4 | 5 | 5 | 5 | 9
25472 | PIP_APPROVED | PIP_APPROVED | 1016 San Andrade Drive | Encinitas | CA | 92024 | Nancy Martin | 2019-05-31 15:47 | 7607078778 | lefnan@yahoo.com |  |  |  | 4329 | 0.002 | Ryan Malloy | 2019-05-31 | 3.355 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-05-24 | 2019-05-28 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-16 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-16 07:00 | 2019-06-04 | 2 | 2 | Marcia Garay | Completed | 2019-06-07 | 2.92 | 2 | Jethro Andal | Completed | 2019-08-09 | 44.13 | 1 | Christina Horton | Completed | 2019-08-16 | 45.96 | 5 | Christina Horton | Completed | 2019-06-10 | 0 | 3 | Andrew Moralez | Completed | 2019-08-09 | 42.96 | 0 | Andrew Moralez | Completed | 2019-08-16 | 0 | 1 | Christina Horton | Completed | 2019-08-23 | 4.79 | 2 | Christina Horton | Completed | 2019-06-11 | 0.79 | 2 | Brittany Faconti | Completed | 2019-06-10 | 0.92 | 2 | Marcia Garay | Completed | 2019-06-10 | 0.79 | 1 |  | Completed | 2019-06-11 | 1.92 | 1 | Andrew Clemons | Completed | 2019-08-22 | 3.96 | 1 | Marcia Garay | Completed | 2019-08-21 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 4.79 | 2 | Ashley Rockwood | Completed | 2019-09-03 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 15.88 | 2 | Marcia Garay | Completed | 2019-09-04 | 0.88 | 1 | Andrew Clemons | Completed | 2019-08-23 16:54 |  | 2019-08-23 | 4.79 | 2 | Christina Horton | Completed | [10 empty] | 21.79 | [11 empty] | 2019-06-10 | 2019-08-23 | ENCINITAS | Encinitas | https://heliotrack.completesolar.com/job.php?action=review&jobID=25472 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25472 | https://completesolar.sugarondemand.com/#Opportunities/f634b646-83f5-11e9-8365-069e4f790264 | Gavin Seeberger |  | 2019-05-10 | Infinity Energy Inc | f634b646-83f5-11e9-8365-069e4f790264 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26790 | PIP_APPROVED | PIP_APPROVED | 44514 Watford Avenue | Lancaster | CA | 93535 | Harvey Valles | 2019-07-17 10:10 | 6617898847 | hvalles96@gmail.com | Maria Valles | 6619412558 |  | 9930 | 0.125 | Chris Peaslee | 2019-06-29 | 5.795 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-28 | 2019-06-29 15:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-16 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-15 07:00 | 2019-07-17 | 0.42 | 2 | Marcia Garay | Completed | 2019-07-18 | 5.46 | 2 | Jethro Andal | Completed | 2019-07-26 | 8.09 | 1 | Ara Sotto | Completed | 2019-08-16 | 11.75 | 5 | Brian Le | Completed | 2019-07-19 | 0.25 | 3 | Andrew Moralez | Completed | 2019-07-29 | 5.62 | 1 | Andrew Moralez | Completed | 2019-08-16 | 1.21 | 2 | Ara Sotto | Completed | 2019-09-17 | 21.17 | 2 | Ara Sotto | Completed | 2019-07-31 | 12.95 | 2 | Brian Le | Completed | 2019-07-19 | 0.67 | 2 | Marcia Garay | Completed | 2019-07-19 | 1.87 | 1 |  | Completed | 2019-07-31 | 13.75 | 1 | Andrew Clemons | Completed |  | 46.54 | 1 | Marcia Garay | Current | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-22 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 19.04 | 2 | Marcia Garay | Completed | 2019-08-29 | 2 | 1 | Andrew Clemons | Completed | 2019-08-16 22:45 |  | 2019-08-16 | 0.25 | 2 | Ara Sotto | Completed | [10 empty] | 11.76 | [11 empty] | 2019-07-20 | 2019-09-17 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26790 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26790 | https://completesolar.sugarondemand.com/#Opportunities/7bb5cadc-9ac9-11e9-bb3e-069e4f790264 | SCES Division | Henry Garcia | 2019-06-28 | JK Solar | 7bb5cadc-9ac9-11e9-bb3e-069e4f790264 | 0 | 32 | 10 | -2 | 5 | 5 | 5 | 18
26807 | PIP_APPROVED | PIP_APPROVED | 6973 Loma Vista Avenue | Hesperia | CA | 92345 | Sheila Voelker | 2019-07-03 17:48 | 7609876907 | cheetasv@gmail.com | Christopher Voelker | 7608855769 |  | 9174 | 0.14 | Shaun Labelle | 2019-07-01 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-29 | 2019-07-01 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-16 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-08-15 07:00 | 2019-07-03 | 2.46 | 2 | Marcia Garay | Completed | 2019-07-08 | 1.71 | 2 | Jethro Andal | Completed | 2019-07-11 | 2.71 | 1 | Ara Sotto | Completed | 2019-08-16 | 5.88 | 5 | Brian Le | Completed | 2019-07-17 | 5.58 | 3 | Andrew Moralez | Completed | 2019-08-16 | 22.08 | 14 | Andrew Moralez | Completed | 2019-08-16 | 1.42 | 1 | Ara Sotto | Completed | 2019-08-23 | 5.04 | 2 | Ara Sotto | Completed | 2019-08-08 | 18.92 | 2 | Brian Le | Completed | 2019-07-12 | 3.88 | 2 | Marcia Garay | Completed | 2019-07-09 | 1.17 | 1 |  | Completed | 2019-07-24 | 11.63 | 1 | Andrew Clemons | Completed | 2019-08-20 | 3.63 | 1 | Marcia Garay | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-03 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 11.04 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.21 | 1 | Jill Allen | Completed | 2019-08-21 12:07 |  | 2019-08-29 | 9.38 | 2 | Ara Sotto | Completed | [10 empty] | 4.08 | [11 empty] | 2019-08-06 | 2019-08-21 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=26807 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26807 | https://completesolar.sugarondemand.com/#Opportunities/78983c36-9c2c-11e9-bce3-02ae981fbade | SCES Division |  | 2019-06-29 | HDM Electric Inc | 78983c36-9c2c-11e9-bce3-02ae981fbade | 13 | 7 | -15 | -2 | 5 | 5 | 5 | -7
26931 | PIP_APPROVED | PIP_APPROVED | 3023 Leroy Street | San Bernardino | CA | 92404 | Wilhelmina Cardinal | 2019-07-15 16:11 | 9097259238 | wcardi2767@aol.com |  |  |  | 15299 | 0.193 | Shaun Labelle | 2019-07-15 | 11.59 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-08 | 2019-07-15 10:00 | LR6-60PB-305M | 305 | 38 | LONGi Solar | SolarEdge | SE11400A-US RGM | Composite | Line-side Tap | 2019-08-16 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-15 07:00 | 2019-07-17 | 1.79 | 2 | Marcia Garay | Completed | 2019-07-22 | 2.96 | 2 | Daniel Speegle | Completed | 2019-07-16 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-16 | 5.88 | 5 | Brian Le | Completed | 2019-07-25 | 1 | 3 | Ernesto Enriquez | Completed | 2019-08-07 | 8.92 | 1 | Ernesto Enriquez | Completed | 2019-08-16 | 1.21 | 3 | Ara Sotto | Completed | 2019-09-04 | 12.33 | 2 | Ara Sotto | Completed | 2019-08-08 | 10.92 | 2 | Brian Le | Completed | 2019-07-24 | 2.08 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.96 | 1 |  | Completed | 2019-07-25 | 3 | 1 | Andrew Clemons | Completed | 2019-09-03 | 12.21 | 1 | Marcia Garay | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-03 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 7.04 | 2 | Marcia Garay | Completed | 2019-09-11 | 4.17 | 1 | Andrew Clemons | Completed | 2019-08-28 08:14 |  | 2019-08-28 | 8.42 | 2 | Ara Sotto | Completed | 2019-08-16 | 1.21 | 1 | Ara Sotto | Completed | 2019-07-23 | 1 | 2 | Marcia Garay | Completed | 5.17 | [11 empty] | 2019-07-26 | 2019-09-04 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=26931 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26931 | https://completesolar.sugarondemand.com/#Opportunities/cb59bc72-a755-11e9-a47c-02ae981fbade | Oscar Hernandez |  | 2019-07-06 | Power Town Solar Electric | cb59bc72-a755-11e9-a47c-02ae981fbade | 12 | 19 | -15 | -2 | 5 | 5 | 5 | -7
26942 | PIP_APPROVED | PIP_APPROVED | 2715 Norma Street | Oceanside | CA | 92056 | Evelyn Gladfelter | 2019-07-08 12:04 | 7607241016 | evelyn.gladfelter@yahoo.com |  |  |  | 4984 | 0.19 | Chris Peaslee | 2019-07-08 | 3.355 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-06 | 2019-07-08 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-16 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-16 07:00 | 2019-07-10 | 2.08 | 2 | Marcia Garay | Completed | 2019-07-12 | 1.79 | 2 | Daniel Speegle | Completed | 2019-08-02 | 15.13 | 1 | Christina Horton | Completed | 2019-08-16 | 3.96 | 5 | Brian Le | Completed | 2019-07-12 | 0 | 3 | Andrew Moralez | Completed | 2019-07-18 | 3.96 | 10 | Andrew Moralez | Completed | 2019-08-16 | 0.42 | 1 | Christina Horton | Completed | 2019-10-15 | 40.96 | 2 | Christina Horton | Completed | 2019-07-23 | 0.08 | 2 | Brian Le | Completed | 2019-08-02 | 7.08 | 2 | Marcia Garay | Completed | 2019-07-12 | 0.21 | 1 |  | Completed | 2019-07-16 | 2.04 | 1 | Andrew Clemons | Completed | 2019-10-15 | 41.38 | 1 | Marcia Garay | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 8.08 | 2 | Marcia Garay | Completed | 2019-09-04 | 1.83 | 1 | Andrew Clemons | Completed | 2019-08-21 14:10 |  | 2019-08-23 | 5.08 | 2 | Christina Horton | Completed | [10 empty] | 15.88 | [11 empty] | 2019-07-26 | 2019-10-15 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26942 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26942 | https://completesolar.sugarondemand.com/#Opportunities/32da2272-a1b3-11e9-9574-02ae981fbade | Xavier Kimbrough |  | 2019-07-06 | Infinity Energy Inc | 32da2272-a1b3-11e9-9574-02ae981fbade | 7 | 60 | -5 | -2 | 5 | 5 | 5 | 3
27143 | PIP_APPROVED | PIP_APPROVED | 43146 Bloomingpark Street | Lancaster | CA | 93536 | Michael Vivens | 2019-07-20 17:10 | 6268408022 | mdveejazz@yahoo.com |  |  |  | 7028 |  | Bill Angevine | 2019-07-20 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-15 | 2019-07-20 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | Enphase Energy | M215-60-2LL-S22 | Tile Concrete | NO | 2019-08-16 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-08-15 07:00 | 2019-07-22 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 1.79 | 2 | Daniel Speegle | Completed | 2019-07-30 | 3.92 | 1 | Ara Sotto | Completed | 2019-08-16 | 5.88 | 5 | Brian Le | Completed | 2019-07-24 | 0 | 3 | Andrew Moralez | Completed | 2019-07-30 | 4 | 1 | Andrew Moralez | Completed | 2019-08-16 | 1.21 | 2 | Ara Sotto | Completed | 2019-08-20 | 2.29 | 2 | Ara Sotto | Completed | 2019-08-08 | 2.79 | 2 | Brian Le | Completed | 2019-08-05 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 0.17 | 1 |  | Completed | 2019-07-29 | 2.83 | 1 | Andrew Clemons | Completed | 2019-08-15 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-22 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-23 | 1.29 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 3.54 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 3.5 | 1 | Jeremiah Liend | Completed | 2019-08-16 17:32 |  | 2019-08-16 | 0.04 | 2 | Ara Sotto | Completed | [10 empty] | 9 | 2019-08-02 | 0 | 14 | James Fernandez | Completed | 2019-08-06 | 2019-08-07 | 1.38 | 1 | James Fernandez | Completed | 2019-07-30 | 2019-08-16 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27143 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27143 | https://completesolar.sugarondemand.com/#Opportunities/cfff9fae-ab4b-11e9-bfa2-022c40d974e6 | SCES Division | George Sarkis | 2019-07-15 | Green Road Solar Crew | cfff9fae-ab4b-11e9-bfa2-022c40d974e6 | 0 | 4 | 10 | 0 | 5 | 5 | 5 | 20
27229 | PIP_APPROVED | PIP_APPROVED | 8735 12th Street | San Joaquin | CA | 93660 | Cristobal Estrada (Add on) | 2019-07-19 12:30 | 5593019784 | e_alicia@rocketmail.com | Leticia Estrada | 5596939207 |  | 14574 | 0.14 | Abraham SiteTech Vazquez | 2019-07-19 | 9.76 | Christina Horton |  | Marcia Garay | 2019-07-18 | 2019-07-19 09:00 | LR6-60PB-305M | 305 | 32 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | NO | 2019-08-16 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-15 07:00 | 2019-07-22 | 1.17 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.92 | 2 | Daniel Speegle | Completed | 2019-07-26 | 2.92 | 1 | Christina Horton | Completed | 2019-08-15 | 4.88 | 5 | Brian Le | Completed | 2019-07-24 | 0.88 | 3 | Ernesto Enriquez | Completed | 2019-08-12 | 12.92 | 0 | Ernesto Enriquez | Completed | 2019-08-16 | 1.5 | 2 | Christina Horton | Completed | 2019-09-04 | 9.63 | 2 | Christina Horton | Completed | 2019-08-08 | 10.96 | 2 | Brian Le | Completed | 2019-07-24 | 0.83 | 2 | Marcia Garay | Completed | 2019-07-23 | 0 | 1 |  | Completed | 2019-07-26 | 2.92 | 1 | Noe Gomez | Completed |  | 46.54 | 1 | Marcia Garay | Current | 2019-08-22 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-20 | 10.66 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 6.13 | 2 | Ashley Rockwood | Completed | 2019-10-07 | 4.83 | 2 | Marcia Garay | Completed | 2019-10-03 | 2.83 | 1 | Jill Allen | Completed | 2019-09-03 14:13 |  | 2019-09-03 | 7.79 | 2 | Christina Horton | Completed | [10 empty] | 7.09 | [11 empty] | 2019-07-24 | 2019-09-03 | SAN JOAQUIN COUNTY | San Joaquin | https://heliotrack.completesolar.com/job.php?action=review&jobID=27229 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27229 | https://completesolar.sugarondemand.com/#Opportunities/90cf22f0-aa5b-11e9-8747-0630baf9dcb8 | Total HomeSolar |  | 2019-07-18 | Anley Electric | 90cf22f0-aa5b-11e9-8747-0630baf9dcb8 | 18 | 19 | -15 | -2 | 5 | 5 | 5 | -7
24697 | SP APPROVED |  | 40526 Tesoro Lane | Palmdale | CA | 93551 | Raymond Rodriguez | 2019-08-07 18:03 | 6612738452 | raymond2200@sbcglobal.net |  | 6619928598 |  | 14640 | 0.145 | Bill Angevine | 2019-05-31 | 7.625 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-04-17 | 2019-05-18 10:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | Line-side Tap | 2019-08-15 | Installation Complete | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-15 | 2019-08-12 | 6.71 | 2 | Marcia Garay | Completed | 2019-08-12 | 5.96 | 2 | Daniel Speegle | Completed | 2019-08-14 | 1.71 | 1 | Ara Sotto | Completed | 2019-08-15 | 0.08 | 5 | Ara Sotto | Completed | 2019-08-12 | 9.96 | 3 | Ernesto Enriquez | Completed | 2019-08-12 | 4.45 | 0 | Andrew Moralez | Completed | 2019-08-15 | 0.33 | 2 | Ara Sotto | Completed |  | 46.17 | 2 | Ara Sotto | Current | 2019-08-22 | 7.92 | 2 | Brian Le | Completed | 2019-08-12 | 9.8 | 2 | Marcia Garay | Completed | 2019-08-12 | 0.91 | 1 |  | Completed | 2019-08-14 | 15.3 | 1 | Andrew Clemons | Completed |  | 46.54 | 1 | Marcia Garay | Current | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-28 08:58 |  |  | 0 | 2 |  | Inactive |  | 46.54 | 1 | Ara Sotto | Current | 2019-08-13 | 0.63 | 2 | Marcia Garay | Completed | 19.72 | [11 empty] | 2019-08-12 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=24697 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24697 | https://completesolar.sugarondemand.com/#Opportunities/819751a8-841e-11e9-9977-0630baf9dcb8 | Kevin Adams | Emily Bowden | 2019-04-16 | JK Solar | 819751a8-841e-11e9-9977-0630baf9dcb8 |  | 67 | -25 | -2 | 5 | 5 | 5 | -17
25533 | PIP_APPROVED | PIP_APPROVED | 34 Ridge Road | Fairfax | CA | 94930 | Shai Lavie | 2019-07-11 19:43 | 4156081259 | shailavie@hotmail.com | Ivy Mayer | 4153423677 |  | 3466 |  | Ricardo Virgen | 2019-07-11 | 2.135 | Christina Horton | CS Direct | Darlynn Lacap | 2019-07-03 | 2019-07-11 09:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | Enphase Energy | IQ7PLUS-72-2-US | Composite | NO | 2019-08-15 | NEM Submitted | Cash | 0 | 0 |  |  |  | 0 | 2019-08-15 | 2019-07-12 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 2.88 | 2 | Daniel Speegle | Completed | 2019-08-08 | 15.71 | 1 | Christina Horton | Completed | 2019-08-15 | 2.67 | 5 | Brian Le | Completed | 2019-07-23 | 3.17 | 3 | Andrew Moralez | Completed | 2019-07-23 | 0.08 | 2 | Ernesto Enriquez | Completed | 2019-08-15 | 0.46 | 1 | Christina Horton | Completed | 2019-08-21 | 4.04 | 2 | Christina Horton | Completed | 2019-08-12 | 7.08 | 2 | Brian Le | Completed | 2019-08-01 | 1.62 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 0.88 | 1 |  | Completed | 2019-07-24 | 4.67 | 1 | Andrew Clemons | Completed | 2019-08-15 | 0.46 | 1 | Darlynn Lacap | Completed |  | 28.79 | 2 | Jeremiah Liend | Inactive | [15 empty] | 2019-08-30 | 9.92 | 2 | Ashley Rockwood | Completed |  | 23.96 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-15 07:39 |  | 2019-08-16 | 0.75 | 2 | Christina Horton | Completed | [10 empty] | 36 | [11 empty] | 2019-07-25 | 2019-08-21 | FAIRFAX | Fairfax | https://heliotrack.completesolar.com/job.php?action=review&jobID=25533 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25533 | https://completesolar.sugarondemand.com/#Opportunities/d1c6a430-a44e-11e9-bc49-069e4f790264 | CS Direct |  | 2019-05-13 | Golden Gate Electric Service | d1c6a430-a44e-11e9-bc49-069e4f790264 | 1 | 6 | 10 | -2 | 5 | 5 | 5 | 18
26570 | PIP_APPROVED | PIP_APPROVED | 122 Beaumont Drive | Vista | CA | 92084 | Ronald Holbrook | 2019-07-23 11:04 | 7609084644 | beau122@cox.net | Carol Holbrook |  |  | 7116 | 0.17 | Chris Peaslee | 2019-06-24 | 4.88 |  | CUIC Inc | Darlynn Lacap | 2019-06-20 | 2019-06-21 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | MPU | 2019-08-15 | PTO Received | SunRun Monthly | 0 | 0 |  | 1 | 0 | 1 | 2019-08-15 07:00 | 2019-07-23 | 0.88 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 3.05 | 2 | Daniel Speegle | Completed | 2019-07-26 | 5.84 | 1 | Christina Horton | Completed | 2019-08-15 | 4.21 | 5 | Brian Le | Completed | 2019-08-08 | 12.79 | 3 | Andrew Moralez | Completed | 2019-08-08 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-15 | 0.46 | 1 | Christina Horton | Completed | 2019-09-06 | 13.83 | 2 | Christina Horton | Completed | 2019-08-08 | 13.96 | 2 | Brian Le | Completed | 2019-07-25 | 0.91 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 2.12 | 1 |  | Completed | 2019-08-08 | 15.04 | 1 | Andrew Clemons | Completed | 2019-08-15 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 1.25 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 4.21 | 2 | Darlynn Lacap | Completed | 2019-09-23 | 2.79 | 1 | Noe Gomez | Completed |  | 2019-09-19 | 2019-09-16 | 5.71 | 2 | Christina Horton | Completed | 2019-09-06 | 8.71 | 1 | Christina Horton | Completed | 2019-07-25 | 2.59 | 2 | Darlynn Lacap | Completed | 15.17 | [11 empty] | 2019-08-08 | 2019-09-06 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=26570 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26570 | https://completesolar.sugarondemand.com/#Opportunities/89d7c4a4-96d1-11e9-bf8e-022c40d974e6 | Jimmy Evans |  | 2019-06-20 | iEnergy ElectricSolar | 89d7c4a4-96d1-11e9-bf8e-022c40d974e6 | 10 | 22 | -5 | -2 | 5 | 5 | 5 | 3
27062 | PIP_APPROVED | PIP_APPROVED | 248 Fernwood Avenue | Burlington | NJ | 8016 | Lisa Antuzzi | 2019-07-15 17:27 | 6099236604 | lantuzzi@live.com |  |  |  | 3877 | 0.145 | Andrew Weber | 2019-07-15 | 2.745 | Christina Horton | US EnergySavers | Marcia Garay | 2019-07-11 | 2019-07-12 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-15 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  |  | 2019-08-15 07:00 | 2019-07-16 | 0.83 | 2 | Marcia Garay | Completed | 2019-07-18 | 2.29 | 2 | Daniel Speegle | Completed | 2019-07-31 | 8.71 | 1 | Christina Horton | Completed | 2019-09-13 | 0.08 | 5 | Christina Horton | Completed | 2019-07-24 | 2.04 | 3 | Ernesto Enriquez | Completed | 2019-07-30 | 4.08 | 10 | Ernesto Enriquez | Completed | 2019-08-15 | 0.25 | 1 | Christina Horton | Completed | 2019-08-20 | 2.75 | 2 | Christina Horton | Completed | 2019-09-13 | 34.75 | 2 | Brian Le | Completed | 2019-07-22 | 1.63 | 2 | Marcia Garay | Completed | 2019-07-22 | 1.58 | 1 |  | Completed | 2019-07-29 | 6.42 | 1 | Noe Gomez | Completed |  | 44.05 | 1 | Marcia Garay | Current | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 2.13 | 2 | Ashley Rockwood | Completed | 2019-10-09 | 15.92 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 5.96 | 2 | Marcia Garay | Completed | 2019-10-10 | 1.13 | 1 | Andrew Clemons | Completed |  | 2019-09-13 | 2019-09-13 | 19.88 | 2 | Christina Horton | Completed | [10 empty] | 5.71 | [11 empty] | 2019-08-07 | 2019-08-20 | Default | Burlington | https://heliotrack.completesolar.com/job.php?action=review&jobID=27062 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27062 | https://completesolar.sugarondemand.com/#Opportunities/73ab5d86-a760-11e9-9abc-0630baf9dcb8 | US EnergySavers |  | 2019-07-11 | Skyline Solar | 73ab5d86-a760-11e9-9abc-0630baf9dcb8 | 29 | 5 | -25 | -2 | 5 | 5 | 5 | -17
27275 | PIP_APPROVED | PIP_APPROVED | 5136 Chateau Drive | San Diego | CA | 92117 | Judith Kincaid | 2019-07-22 13:53 | 6198718525 | kincaid.judith1@gmail.com |  |  |  | 3899 | 0.002 | Chad Malloy | 2019-07-22 | 2.44 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-20 | 2019-07-22 12:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-15 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-15 12:00 | 2019-07-22 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 1.96 | 2 | Daniel Speegle | Completed | 2019-07-26 | 1.88 | 1 | Christina Horton | Completed | 2019-08-15 | 6.92 | 5 | Brian Le | Completed | 2019-08-01 | 1.75 | 3 | Ernesto Enriquez | Completed | 2019-08-01 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-15 | 0.46 | 1 | Christina Horton | Completed | 2019-08-22 | 5.04 | 2 | Christina Horton | Completed | 2019-08-05 | 4.92 | 2 | Brian Le | Completed | 2019-07-29 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 4 | 1 |  | Completed | 2019-08-06 | 8.92 | 1 | Andrew Clemons | Completed | 2019-08-15 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 4.71 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-10 | 5.96 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 1.83 | 1 | Andrew Clemons | Completed | 2019-08-21 09:07 |  | 2019-08-22 | 5.04 | 2 | Christina Horton | Completed | [10 empty] | 6.66 | [11 empty] | 2019-08-22 | 2019-08-22 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27275 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27275 | https://completesolar.sugarondemand.com/#Opportunities/a697fcd8-acc2-11e9-bab7-02ae981fbade | Isiah BurksHarvey |  | 2019-07-19 | Infinity Energy Inc | a697fcd8-acc2-11e9-bab7-02ae981fbade | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
24437 | PIP_APPROVED | PIP_APPROVED | 5540 Via Mariposa | Yorba Linda | CA | 92887 | Robert Fumo | 2019-08-06 16:13 | 7142351219 | rfumo@sbcglobal.net |  |  |  | 9731 | 0.16 | Alex Holdridge | 2019-04-11 | 6.405 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-04-08 | 2019-04-11 13:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-14 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-14 07:00 | 2019-08-06 | 7.75 | 2 | Marcia Garay | Completed | 2019-08-12 | 6.88 | 2 | Daniel Speegle | Completed | 2019-08-09 | 0.91 | 1 | Ara Sotto | Completed | 2019-08-14 | 12.79 | 5 | Brian Le | Completed | 2019-08-15 | 4.79 | 3 | Andrew Moralez | Completed | 2019-08-15 | 0 | 12 | Andrew Moralez | Completed | 2019-08-14 | 13.67 | 2 | Ara Sotto | Completed | 2019-08-17 | 2.38 | 2 | Ara Sotto | Completed | 2019-08-23 | 11.96 | 2 | Brian Le | Completed | 2019-08-13 | 3.08 | 2 | Marcia Garay | Completed | 2019-08-13 | 2.13 | 1 |  | Completed | 2019-08-21 | 13.12 | 1 | Noe Gomez | Completed | 2019-08-21 | 18.46 | 1 | Marcia Garay | Completed | 2019-08-22 | 3.54 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-28 | 5.04 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 4.21 | 2 | Marcia Garay | Completed |  | 36.33 | 1 | Andrew Clemons | Current |  | 2019-08-19 | 2019-08-21 | 4.79 | 2 | Ara Sotto | Completed | [10 empty] | 31.88 | [11 empty] | 2019-09-03 | 2019-08-17 | YORBA LINDA | Yorba Linda | https://heliotrack.completesolar.com/job.php?action=review&jobID=24437 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24437 | https://completesolar.sugarondemand.com/#Opportunities/a0a14ffa-5cb8-11e9-8994-0630baf9dcb8 | Jake Tremaine |  | 2019-04-08 | Power Town Solar Electric | a0a14ffa-5cb8-11e9-8994-0630baf9dcb8 | 7 | 3 | -5 | 2 | 5 | 5 | 5 | 7
26336 | PIP_APPROVED | PIP_APPROVED | 2149 Dusk Drive | San Diego | CA | 92139 | Jason McFee | 2019-07-02 17:30 | 6199620766 | jason.s.mcfee@gmail.com |  |  |  | 10898 | 0.203 | Chad Malloy | 2019-06-13 | 7.32 | Christina Horton | UpGrid Inc | Marcia Garay | 2019-06-11 | 2019-06-13 15:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-14 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-13 07:00 | 2019-07-02 | 2.67 | 2 | Marcia Garay | Completed | 2019-07-05 | 4.88 | 2 | Jethro Andal | Completed | 2019-08-07 | 29.79 | 1 | Christina Horton | Completed | 2019-08-13 | 2.83 | 5 | Brian Le | Completed | 2019-07-19 | 3.04 | 3 | Ernesto Enriquez | Completed | 2019-08-07 | 12.91 | 15 | Andrew Moralez | Completed | 2019-08-14 | 1.55 | 2 | Christina Horton | Completed | 2019-08-26 | 7.83 | 2 | Christina Horton | Completed | 2019-08-08 | 24.01 | 2 | Brian Le | Completed | 2019-07-15 | 4.51 | 2 | Marcia Garay | Completed | 2019-07-09 | 2.37 | 1 |  | Completed | 2019-07-11 | 10.33 | 1 | Andrew Clemons | Completed | 2019-08-15 | 2.59 | 1 | Marcia Garay | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-09-03 | 2 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 12 | 2 | Marcia Garay | Completed | 2019-09-04 | 0.88 | 1 | Andrew Clemons | Completed | 2019-08-21 10:05 |  | 2019-08-22 | 5.71 | 2 | Christina Horton | Completed | [10 empty] | 23.21 | [11 empty] | 2019-08-09 | 2019-08-23 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26336 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26336 | https://completesolar.sugarondemand.com/#Opportunities/b344ea92-8e34-11e9-ba21-022c40d974e6 | UpGrid Inc |  | 2019-06-11 | Greenday Electric Solar | b344ea92-8e34-11e9-ba21-022c40d974e6 | 8 | 12 | -5 | -2 | 5 | 5 | 5 | 3
27034 | PIP_APPROVED | PIP_APPROVED | 13902 Sam O Reno Road | Poway | CA | 92064 | Benedicto R Diaz | 2019-07-14 10:04 | 8584422741 | diaz.bc@gmail.com | Connie Diaz | 858-442-3855 |  | 4558 | 0.16 | Chad Malloy | 2019-07-14 | 2.745 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-10 | 2019-07-12 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-14 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-14 | 2019-07-18 | 3.38 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-16 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-14 | 4.13 | 5 | Brian Le | Completed | 2019-07-26 | 4.92 | 3 | Andrew Moralez | Completed | 2019-08-01 | 4.04 | 14 | Andrew Moralez | Completed | 2019-08-14 | 0.42 | 1 | Ara Sotto | Completed | 2019-09-03 | 13 | 2 | Ara Sotto | Completed | 2019-08-08 | 13.96 | 2 | Brian Le | Completed | 2019-07-19 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 1 | 1 |  | Completed | 2019-07-31 | 8.63 | 1 | Andrew Clemons | Completed | 2019-08-14 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 6.04 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 11.08 | 2 | Darlynn Lacap | Completed |  | 38.17 | 1 | Andrew Clemons | Current | 2019-08-15 14:06 |  | 2019-08-16 | 1.75 | 2 | Ara Sotto | Completed | [10 empty] | 10.67 | [11 empty] | 2019-08-15 | 2019-09-03 | POWAY | Poway | https://heliotrack.completesolar.com/job.php?action=review&jobID=27034 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27034 | https://completesolar.sugarondemand.com/#Opportunities/4dfde3fe-a659-11e9-bb02-0630baf9dcb8 | Tier1 Power | Jordan Litrownik | 2019-07-10 | Blalock Electric&Solar | 4dfde3fe-a659-11e9-bb02-0630baf9dcb8 | 2 | 20 | 7 | -2 | 5 | 5 | 5 | 15
27339 | PIP_APPROVED | PIP_APPROVED | 14869 Alba Way | Moreno Valley | CA | 92553 | Anthony Alba | 2019-07-25 17:32 | 9515758291 | anthony.alba951@gmail.com | Valerie Cota | 9512148992 |  | 5393 | 0.176 | Chris Peaslee | 2019-07-25 | 3.05 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-23 | 2019-07-25 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-08-14 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-14 07:00 | 2019-07-30 | 2.92 | 2 | Marcia Garay | Completed | 2019-07-29 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-25 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-14 | 4.13 | 5 | Brian Le | Completed | 2019-08-01 | 0.17 | 3 | Andrew Moralez | Completed | 2019-08-07 | 3.75 | 25 | Ernesto Enriquez | Completed | 2019-08-14 | 0.42 | 1 | Ara Sotto | Completed | 2019-08-16 | 1.92 | 2 | Ara Sotto | Completed | 2019-08-08 | 4.08 | 2 | Brian Le | Completed | 2019-08-02 | 2.71 | 2 | Marcia Garay | Completed | 2019-08-01 | 1.79 | 1 |  | Completed | 2019-08-06 | 4.63 | 1 | Noe Gomez | Completed |  | 47.54 | 1 | Marcia Garay | Current | 2019-08-19 | 0.83 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-28 | 4.08 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 8.96 | 2 | Marcia Garay | Completed |  | 36.25 | 1 | Andrew Clemons | Current | 2019-08-22 09:30 |  | 2019-08-22 | 5.79 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-09-06 | 2019-08-16 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27339 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27339 | https://completesolar.sugarondemand.com/#Opportunities/d3f246da-af3c-11e9-872c-022c40d974e6 | 300 Stars Inc |  | 2019-07-22 | Green Road Solar Crew | d3f246da-af3c-11e9-872c-022c40d974e6 | 8 | 2 | -5 | 4 | 5 | 5 | 5 | 9
27345 | PIP_APPROVED | PIP_APPROVED | 9365 Corte Ganzo | Spring Valley | CA | 91977 | Steven Watson | 2019-07-29 17:47 | 6198087059 | Swatson1275@gmail.com |  |  |  | 4856 | 0.17 | Ryan Malloy | 2019-07-29 | 3.05 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-24 | 2019-07-29 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-14 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-14 07:00 | 2019-07-30 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 3.08 | 2 | Jethro Andal | Completed | 2019-08-06 | 2.17 | 1 | Christina Horton | Completed | 2019-08-14 | 3.5 | 5 | Brian Le | Completed | 2019-08-02 | 0 | 3 | Andrew Moralez | Completed | 2019-08-06 | 1.71 | 3 | Andrew Moralez | Completed | 2019-08-14 | 0.42 | 1 | Ara Sotto | Completed | 2019-08-19 | 3.08 | 2 | Ara Sotto | Completed | 2019-08-05 | 0.17 | 2 | Brian Le | Completed | 2019-08-05 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 0.13 | 1 |  | Completed | 2019-08-06 | 2.08 | 1 | Andrew Clemons | Completed | 2019-08-14 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 5 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-13 | 11.92 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 1.83 | 1 | Jeremiah Liend | Completed | 2019-08-19 09:32 |  | 2019-08-19 | 2.96 | 2 | Ara Sotto | Completed | [10 empty] | 3.42 | [11 empty] | 2019-08-07 | 2019-08-19 | SPRING VALLEY | Spring Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27345 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27345 | https://completesolar.sugarondemand.com/#Opportunities/860470f4-b263-11e9-9d9f-0630baf9dcb8 | Daniel Boyce |  | 2019-07-23 | Zachary Noah Gamez | 860470f4-b263-11e9-9d9f-0630baf9dcb8 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
27377 | PIP_APPROVED | PIP_APPROVED | 352 Salina Court | Vista | CA | 92083 | Raquel Vazquez | 2019-07-25 20:40 | 6193097685 | rql.vzqz@gmail.com | Christopher Beaudry | 5627040773 |  | 5016 | 0.185 | Michael Marlaire | 2019-07-25 | 4.88 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-23 | 2019-07-25 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-14 | NEM Submitted | SunRun Monthly | 0 | 1 |  |  |  | 1 | 2019-08-13 07:00 | 2019-07-26 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 3.92 | 2 | Jethro Andal | Completed | 2019-08-06 | 2.92 | 1 | Christina Horton | Completed | 2019-08-13 | 5.88 | 5 | Brian Le | Completed | 2019-08-05 | 2.38 | 3 | Andrew Moralez | Completed | 2019-08-05 | 0 | 0 | Andrew Moralez | Completed | 2019-08-14 | 1.42 | 1 | Ara Sotto | Completed | 2019-10-08 | 6.96 | 2 | Ara Sotto | Completed | 2019-08-05 | 1.88 | 2 | Brian Le | Completed | 2019-08-01 | 0.25 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 0.04 | 1 |  | Completed | 2019-08-06 | 2.88 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.04 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-29 | 5 | 2 | Ashley Rockwood | Completed |  | 3.54 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-19 13:58 |  | 2019-08-22 | 5.96 | 2 | Ara Sotto | Completed | [10 empty] | 77.85 | [11 empty] | 2019-08-05 | 2019-10-08 | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=27377 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27377 | https://completesolar.sugarondemand.com/#Opportunities/04291f1c-af57-11e9-8f09-0630baf9dcb8 | Alexis Cain |  | 2019-07-23 | Zachary Noah Gamez | 04291f1c-af57-11e9-8f09-0630baf9dcb8 | 8 | 55 | -5 | -2 | 5 | 5 | 5 | 3
24512 | PIP_APPROVED | PIP_APPROVED | 1679 Hillsborough Street | Chula Vista | CA | 91913 | Francis Salvador | 2019-05-17 15:03 | 8584499359 | franz_xis14@yahoo.com |  |  |  | 4608 | 0.176 | Chad Malloy | 2019-05-17 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-04-29 | 2019-05-02 09:00 | Q.PEAK-G4.1 305 | 305 | 10 | Hanwha Q CELLS | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-13 | Final Permit | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-08-13 07:00 | 2019-05-29 | 1.75 | 2 | Darlynn Lacap | Completed | 2019-05-30 | 1.04 | 2 | Daniel Speegle | Completed | 2019-06-03 | 2.04 | 1 | Christina Horton | Completed | 2019-08-13 | 46.79 | 5 | Ara Sotto | Completed | 2019-05-31 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-05 | 23.96 | 7 | Andrew Moralez | Completed | 2019-08-13 | 0.38 | 1 | Christina Horton | Completed | 2019-10-03 | 35.96 | 2 | Christina Horton | Completed | 2019-06-03 | 0.08 | 2 | Brittany Faconti | Completed | 2019-06-03 | 2 | 2 | Darlynn Lacap | Completed | 2019-05-31 | 0.88 | 1 |  | Completed | 2019-06-04 | 2.92 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-03 | 0 | 4 | Darlynn Lacap | Completed | 2019-07-08 | 2.08 | 5 | Darlynn Lacap | Completed | 2019-07-31 | 13.21 | 12 | Darlynn Lacap | Completed |  | 6.21 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-03 14:34 |  | 2019-10-03 | 35.96 | 2 | Christina Horton | Completed | [10 empty] | 18.29 | [11 empty] | 2019-06-11 | 2019-10-03 | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=24512 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24512 | https://completesolar.sugarondemand.com/#Opportunities/96b887bc-78ef-11e9-bc36-022c40d974e6 | Henry Rendon |  | 2019-04-10 | Infinity Energy Inc | 96b887bc-78ef-11e9-bc36-022c40d974e6 | 51 | 51 | -25 | -2 | 5 | 5 | 5 | -17
25866 | PIP_APPROVED | PIP_APPROVED | 3611 North Silvervale Court | Visalia | CA | 93291 | Alisha Sandidge | 2019-07-18 20:45 | 5597999044 | erenteria9@hotmail.com | Eddie Renteria | 5597996012 |  | 9524 | 0.12 | Abraham SiteTech Vazquez | 2019-07-18 | 6.71 | Christina Horton | CS Direct | Darlynn Lacap | 2019-05-29 | 2019-06-07 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-12 07:00 | 2019-07-22 | 1.75 | 2 | Darlynn Lacap | Completed | 2019-07-22 | 0 | 2 | Daniel Speegle | Completed | 2019-07-30 | 5.96 | 1 | Christina Horton | Completed | 2019-08-12 | 6.63 | 5 | Brian Le | Completed | 2019-07-25 | 2.17 | 3 | Ernesto Enriquez | Completed | 2019-08-05 | 7.04 | 0 | Andrew Moralez | Completed | 2019-08-13 | 1.38 | 2 | Christina Horton | Completed | 2019-08-16 | 3 | 2 | Christina Horton | Completed | 2019-07-31 | 3.96 | 2 | Brian Le | Completed | 2019-07-25 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 0.79 | 1 |  | Completed | 2019-07-28 | 4.33 | 1 | Jill Allen | Completed | 2019-08-13 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-19 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 18.96 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 0.88 | 1 | Andrew Clemons | Completed | 2019-08-14 15:39 |  | 2019-08-15 | 2 | 2 | Christina Horton | Completed | [10 empty] | 2.12 | [11 empty] | 2019-07-25 | 2019-08-15 | VISALIA | Visalia | https://heliotrack.completesolar.com/job.php?action=review&jobID=25866 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25866 | https://completesolar.sugarondemand.com/#Opportunities/933cb04a-a9d7-11e9-ab5f-022c40d974e6 | Christian Macias |  | 2019-05-23 | Anley Electric | 933cb04a-a9d7-11e9-ab5f-022c40d974e6 | 2 | 3 | 7 | 2 | 5 | 5 | 5 | 19
26110 | PIP_APPROVED | PIP_APPROVED | 870 Cromwell Street | Rialto | CA | 92376 | Armando Perez | 2019-07-19 20:07 | 3102916232 | normameza88@gmail.com | Norma Meza | 3102916232 |  | 7808 | 0.17 | Michael Marlaire | 2019-06-11 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-05 | 2019-06-07 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-13 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-12 07:00 | 2019-07-19 | 5.58 | 2 | Darlynn Lacap | Completed | 2019-07-22 | 0.79 | 2 | Daniel Speegle | Completed | 2019-08-08 | 12.83 | 1 | Ara Sotto | Completed | 2019-08-13 | 2.83 | 5 | Brian Le | Completed | 2019-07-24 | 1.08 | 3 | Andrew Moralez | Completed | 2019-08-06 | 9 | 7 | Andrew Moralez | Completed | 2019-08-13 | 1.55 | 1 | Ara Sotto | Completed | 2019-08-19 | 4.08 | 2 | Ara Sotto | Completed | 2019-08-08 | 12.88 | 2 | Brian Le | Completed | 2019-07-19 | 0.08 | 2 | Richard Guillen | Completed | 2019-07-23 | 0.92 | 1 |  | Completed | 2019-08-06 | 11.21 | 1 | Noe Gomez | Completed | 2019-08-13 | 1.88 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-23 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-10-01 | 5.04 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 2 | 1 | Noe Gomez | Completed |  |  | 2019-08-14 | 1.21 | 2 | Ara Sotto | Completed | [10 empty] | 41.49 | [11 empty] | 2019-08-02 | 2019-08-19 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26110 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26110 | https://completesolar.sugarondemand.com/#Opportunities/239baac0-8c8b-11e9-9695-0630baf9dcb8 | 300 Stars Inc |  | 2019-06-01 | Green Road Solar Crew | 239baac0-8c8b-11e9-9695-0630baf9dcb8 | 1 | 6 | 10 | -2 | 5 | 5 | 5 | 18
26267 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 1247 Browning Court | Vista | CA | 92083 | Steve McDowell | 2019-06-14 12:14 | 2135075809 | mcdowes@amtrak.com |  |  |  | 3634 | 0.17 | Michael Marlaire | 2019-06-14 | 2.135 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-12 | 2019-06-14 09:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | Enphase Energy | IQ7PLUS-72-2-US | Composite | NO | 2019-08-13 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-13 07:00 | 2019-06-14 | 0 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 3 | 2 | Jethro Andal | Completed | 2019-07-25 | 25.08 | 1 | Christina Horton | Completed | 2019-08-13 | 32.96 | 5 | Brian Le | Completed | 2019-06-24 | 2.42 | 3 | Ernesto Enriquez | Completed | 2019-06-24 | 0.08 | 0 | Ernesto Enriquez | Completed | 2019-08-13 | 0.38 | 1 | Christina Horton | Completed |  | 48.17 | 2 | Christina Horton | Current | 2019-06-26 | 1.79 | 2 | Brian Le | Completed | 2019-06-24 | 3.12 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 0.42 | 1 |  | Completed | 2019-07-16 | 11.16 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-08 | 1.92 | 4 | Darlynn Lacap | Completed | 2019-07-09 | 0.92 | 5 | Darlynn Lacap | Completed | 2019-07-25 | 12.13 | 12 | Darlynn Lacap | Completed | 2019-08-26 | 7.13 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 6.88 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 1.83 | 1 | Jill Allen | Completed | 2019-08-15 13:23 |  | 2019-08-15 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 15.76 | [11 empty] | 2019-06-24 |  | VISTA | Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=26267 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26267 | https://completesolar.sugarondemand.com/#Opportunities/97964558-8ed8-11e9-9f86-022c40d974e6 | Roofing 101 | Chaz Brouillette | 2019-06-08 | Infinity Energy Inc | 97964558-8ed8-11e9-9f86-022c40d974e6 | 2 | 69 | 7 | -2 | 5 | 5 | 5 | 15
26581 | PIP_APPROVED | PIP_APPROVED | 1221 Via De Maranatha | Fallbrook | CA | 92028 | Wayne Parkola | 2019-07-29 09:53 | 7602132688 | wparkola@newport-eyes.com |  |  |  | 10185 | 0.18 | Michael Marlaire | 2019-06-22 | 7.015 | Ara Sotto |  | Marcia Garay | 2019-06-21 | 2019-06-22 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | Line-side Tap | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-12 07:00 | 2019-07-29 | 0.54 | 2 | Marcia Garay | Completed | 2019-07-29 | 4.25 | 2 | Jethro Andal | Completed | 2019-07-31 | 1.83 | 1 | Ara Sotto | Completed | 2019-08-12 | 7.25 | 5 | Brian Le | Completed | 2019-07-29 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-30 | 0.83 | 0 | Andrew Moralez | Completed | 2019-08-13 | 2.51 | 2 | Ara Sotto | Completed | 2019-08-23 | 8.08 | 2 | Ara Sotto | Completed | 2019-07-31 | 0.08 | 2 | Brian Le | Completed | 2019-08-01 | 2.54 | 2 | Marcia Garay | Completed | 2019-07-29 | 0.08 | 1 |  | Completed | 2019-08-02 | 3.67 | 1 | Noe Gomez | Completed |  | 50.67 | 1 | Marcia Garay | Current | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 3.21 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 8.25 | 2 | Marcia Garay | Completed | 2019-09-11 | 2.17 | 1 | Andrew Clemons | Completed | 2019-08-27 21:44 |  | 2019-08-27 | 9.79 | 2 | Ara Sotto | Completed | 2019-08-13 | 1.38 | 1 | Ara Sotto | Completed | 2019-07-30 | 0.63 | 2 | Marcia Garay | Completed | 13.92 | [11 empty] | 2019-07-29 | 2019-08-23 | FALLBROOK | Fallbrook | https://heliotrack.completesolar.com/job.php?action=review&jobID=26581 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26581 | https://completesolar.sugarondemand.com/#Opportunities/6e89c4a2-952a-11e9-b0b4-022c40d974e6 | Jimmy Evans |  | 2019-06-21 | Zachary Noah Gamez | 6e89c4a2-952a-11e9-b0b4-022c40d974e6 | 14 | 10 | -15 | -2 | 5 | 5 | 5 | -7
26809 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 10 Date Avenue | Chula Vista | CA | 91910 | David Stump | 2019-07-02 12:29 | 6195077009 | davestump2@gmail.com |  |  |  | 6458 | 0.19 | Ryan Malloy | 2019-07-02 | 4.27 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-29 | 2019-07-02 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-13 12:00 | 2019-07-12 | 5.96 | 2 | Marcia Garay | Completed | 2019-07-09 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-25 | 9.17 | 1 | Christina Horton | Completed | 2019-08-13 | 11.46 | 5 | Brian Le | Completed | 2019-07-16 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-25 | 7 | 7 | Ernesto Enriquez | Completed | 2019-08-13 | 0.38 | 1 | Christina Horton | Completed |  | 47.17 | 2 | Christina Horton | Current | 2019-07-25 | 8.92 | 2 | Brian Le | Completed | 2019-07-12 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 2.08 | 1 |  | Completed | 2019-07-15 | 1 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.5 | 1 | Marcia Garay | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-09 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-10-14 | 3 | 2 | Ashley Rockwood | Completed |  | 5.04 | 2 | Marcia Garay | Current | 2019-10-16 | 1.96 | 1 | Andrew Clemons | Completed | 2019-10-03 14:01 |  | 2019-10-03 | 36 | 2 | Christina Horton | Completed | [10 empty] | 12.5 | [11 empty] | 2019-07-25 |  | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=26809 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26809 | https://completesolar.sugarondemand.com/#Opportunities/a0c0260a-9cff-11e9-851f-02ae981fbade | Jordan Maya | Shavonte Davis | 2019-06-29 | Infinity Energy Inc | a0c0260a-9cff-11e9-851f-02ae981fbade | 51 | 69 | -25 | -2 | 5 | 5 | 5 | -17
26964 | PIP_APPROVED | PIP_APPROVED | 6225 Estelle Street | San Diego | CA | 92115 | Dana Nielsen | 2019-07-12 13:21 | 6199178133 | danamckenna20@yahoo.com |  |  |  | 6508 | 0.189 | Ryan Malloy | 2019-07-12 | 4.27 | Ara Sotto | Revo Home Solutions | Darlynn Lacap | 2019-07-10 | 2019-07-12 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-13 07:00 | 2019-07-16 | 1.96 | 2 | Marcia Garay | Completed | 2019-07-18 | 2 | 2 | Jethro Andal | Completed | 2019-07-26 | 6 | 1 | Christina Horton | Completed | 2019-08-13 | 10 | 5 | Brian Le | Completed | 2019-07-24 | 2.83 | 3 | Andrew Moralez | Completed | 2019-07-24 | 0 | 15 | Andrew Moralez | Completed | 2019-08-13 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-16 | 3 | 2 | Ara Sotto | Completed | 2019-07-30 | 7.79 | 2 | Brian Le | Completed | 2019-07-18 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-19 | 1.08 | 1 |  | Completed | 2019-07-26 | 5.88 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 5.04 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-28 | 9.04 | 2 | Ashley Rockwood | Completed | 2019-09-03 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 21 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 5.96 | 1 | Andrew Clemons | Completed |  | 2019-08-15 | 2019-08-15 | 2.04 | 2 | Ara Sotto | Completed | [10 empty] | 2.2 | [11 empty] | 2019-08-14 | 2019-08-16 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26964 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26964 | https://completesolar.sugarondemand.com/#Opportunities/8a4490b0-a4e2-11e9-a64f-0630baf9dcb8 | Blake Sanders |  | 2019-07-08 | Zachary Noah Gamez | 8a4490b0-a4e2-11e9-a64f-0630baf9dcb8 | 2 | 3 | 7 | 2 | 5 | 5 | 5 | 19
26973 | PIP_APPROVED | PIP_APPROVED | 2068 Spice Street | Lancaster | CA | 93536 | Sandra Hernandez | 2019-07-17 14:45 | 6614781390 | sandamo215@yahoo.com | Mark Hernandez | 661-478-2273 |  | 14333 | 0.139 | Bill Angevine | 2019-07-09 | 7.625 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-08 | 2019-07-09 12:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-13 07:00 | 2019-07-17 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 4.13 | 2 | Jethro Andal | Completed | 2019-07-30 | 7.54 | 1 | Ara Sotto | Completed | 2019-08-13 | 8.92 | 5 | Brian Le | Completed | 2019-07-21 | 0.16 | 3 | Ernesto Enriquez | Completed | 2019-07-31 | 8.42 | 1 | Ernesto Enriquez | Completed | 2019-08-13 | 0.38 | 2 | Ara Sotto | Completed | 2019-08-15 | 1.96 | 2 | Ara Sotto | Completed | 2019-07-31 | 6.88 | 2 | Brian Le | Completed | 2019-07-22 | 3.13 | 2 | Darlynn Lacap | Completed | 2019-07-21 | 2.21 | 1 |  | Completed | 2019-07-24 | 5.62 | 1 | Jill Allen | Completed | 2019-08-13 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-22 | 4.21 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 3.29 | 2 | Ashley Rockwood | Completed |  | 15.17 | 2 | Darlynn Lacap | Current | 2019-10-03 | 2.83 | 1 | Jeremiah Liend | Completed | 2019-08-14 09:25 |  | 2019-08-16 | 2.75 | 2 | Ara Sotto | Completed | [10 empty] | 23.42 | [11 empty] | 2019-07-21 | 2019-08-15 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26973 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26973 | https://completesolar.sugarondemand.com/#Opportunities/fb7713c6-a2a2-11e9-a9d0-022c40d974e6 | SCES Division | Cody Booth | 2019-07-08 | Power Town Solar Electric | fb7713c6-a2a2-11e9-a9d0-022c40d974e6 | 3 | 2 | 0 | 4 | 5 | 5 | 5 | 14
27019 | PIP_APPROVED | PIP_APPROVED | 106 Polk Street | Oceanside | CA | 92057 | Amando Morelia | 2019-07-11 20:03 | 7606235313 | amandomorelia@yahoo.com | Leonila Morelia | 7606854647 |  | 4731 | 0.145 | Michael Marlaire | 2019-07-11 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-09 | 2019-07-11 16:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-13 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-13 07:00 | 2019-07-12 | 0.63 | 2 | Marcia Garay | Completed | 2019-07-16 | 2.04 | 2 | Jethro Andal | Completed | 2019-08-02 | 10.09 | 1 | Christina Horton | Completed | 2019-08-13 | 7.08 | 5 | Brian Le | Completed | 2019-07-16 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-22 | 3.71 | 10 | Ernesto Enriquez | Completed | 2019-08-13 | 0.38 | 1 | Christina Horton | Completed | 2019-08-19 | 3.83 | 2 | Christina Horton | Completed | 2019-07-23 | 4.17 | 2 | Brian Le | Completed | 2019-07-17 | 0.79 | 2 | Marcia Garay | Completed | 2019-07-16 | 0.13 | 1 |  | Completed | 2019-07-22 | 3.96 | 1 | Andrew Clemons | Completed | 2019-08-15 | 2.46 | 1 | Marcia Garay | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 5.13 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 4.08 | 2 | Marcia Garay | Completed |  | 36.21 | 1 | Andrew Clemons | Current | 2019-08-19 14:11 |  | 2019-08-19 | 3.83 | 2 | Christina Horton | Completed | [10 empty] | 8.84 | [11 empty] | 2019-07-30 | 2019-08-19 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=27019 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27019 | https://completesolar.sugarondemand.com/#Opportunities/7dc7ddce-a451-11e9-8aca-069e4f790264 | Brett Martinez |  | 2019-07-09 | Infinity Energy Inc | 7dc7ddce-a451-11e9-8aca-069e4f790264 | 6 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27136 | PIP_APPROVED | PIP_APPROVED | 24088 Augusta Drive | Corona | CA | 92883 | Lyle Glass | 2019-07-18 16:40 | 9098389537 | lyleglass@att.net | Barbara Glass |  |  | 6440 | 0.14 | Chris Peaslee | 2019-07-18 | 3.965 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-07-15 | 2019-07-16 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-08-13 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-08-13 07:00 | 2019-07-19 | 0.79 | 2 | Marcia Garay | Completed | 2019-07-22 | 1.04 | 2 | Daniel Speegle | Completed | 2019-07-25 | 3.33 | 1 | Ara Sotto | Completed | 2019-08-13 | 3.04 | 5 | Brian Le | Completed | 2019-07-29 | 3.92 | 3 | Ernesto Enriquez | Completed | 2019-08-02 | 4.5 | 14 | Ernesto Enriquez | Completed | 2019-08-13 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-15 | 2.04 | 2 | Ara Sotto | Completed | 2019-08-08 | 9.83 | 2 | Brian Le | Completed | 2019-07-25 | 3 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.88 | 1 |  | Completed | 2019-07-26 | 3.92 | 1 | Jill Allen | Completed |  | 48.54 | 1 | Marcia Garay | Current | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-19 | 0.08 | 4 | Marcia Garay | Completed | 2019-07-25 | 4.04 | 5 | Marcia Garay | Completed | 2019-08-06 | 8 | 12 | Marcia Garay | Completed | 2019-08-22 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 10.08 | 2 | Marcia Garay | Completed |  | 38.29 | 1 | Jill Allen | Current | 2019-08-14 13:11 |  | 2019-08-16 | 2.75 | 2 | Ara Sotto | Completed | [10 empty] | 0.96 | [11 empty] | 2019-08-16 | 2019-08-15 | CORONA | Corona | https://heliotrack.completesolar.com/job.php?action=review&jobID=27136 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27136 | https://completesolar.sugarondemand.com/#Opportunities/49639ed8-a9b5-11e9-ad57-022c40d974e6 | Ryan Ostronic |  | 2019-07-15 | Blalock Electric&Solar | 49639ed8-a9b5-11e9-ad57-022c40d974e6 | 3 | 2 | 0 | 4 | 5 | 5 | 5 | 14
27398 | PIP_APPROVED | PIP_APPROVED | 16041 Oak Creek Court | Victorville | CA | 92395 | Jimmy Lagao | 2019-07-27 12:48 | 7147678272 | jimmylagao@yahoo.com | Emma Lagao | 7608431815 |  | 6785 | 0.127 | Chris Peaslee | 2019-07-27 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-24 | 2019-07-27 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-13 07:00 | 2019-07-29 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-08-01 | 3.04 | 2 | Jethro Andal | Completed | 2019-07-30 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-13 | 3.08 | 5 | Brian Le | Completed | 2019-07-31 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-06 | 2.83 | 10 | Andrew Moralez | Completed | 2019-08-13 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-15 | 1 | 2 | Ara Sotto | Completed | 2019-08-08 | 3.88 | 2 | Brian Le | Completed | 2019-08-02 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 1 |  | Completed | 2019-08-06 | 2.71 | 1 | Andrew Clemons | Completed | 2019-08-13 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 1.79 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-22 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-23 | 1.38 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 8.58 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 3.5 | 1 | Noe Gomez | Completed | 2019-08-14 13:52 |  | 2019-08-16 | 2.75 | 2 | Ara Sotto | Completed | [10 empty] | 0.96 | [11 empty] | 2019-08-15 | 2019-08-15 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27398 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27398 | https://completesolar.sugarondemand.com/#Opportunities/5e04d610-b0a7-11e9-bace-022c40d974e6 | Christopher Cellini | Shane Montana | 2019-07-24 | Green Road Solar Crew | 5e04d610-b0a7-11e9-bace-022c40d974e6 | 3 | 2 | 0 | 4 | 5 | 5 | 5 | 14
27468 | PIP_APPROVED | PIP_APPROVED | 2756 Dolomite Avenue | Palmdale | CA | 93550 | Ismael Ramos | 2019-07-27 16:19 | 6614331626 | ish.ramos@icloud.com | Adriana Carrillo | 6614330941 |  | 12659 | 0.15 | Bill Angevine | 2019-07-27 | 7.015 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-26 | 2019-07-27 12:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-13 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-12 07:00 | 2019-07-29 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 1.92 | 2 | Jethro Andal | Completed | 2019-08-01 | 0.96 | 1 | Ara Sotto | Completed | 2019-08-13 | 2.13 | 5 | Brian Le | Completed | 2019-08-02 | 2.13 | 3 | Ernesto Enriquez | Completed | 2019-08-09 | 4.83 | 0 | Ernesto Enriquez | Completed | 2019-08-13 | 1.38 | 2 | Ara Sotto | Completed | 2019-08-23 | 7.96 | 2 | Ara Sotto | Completed | 2019-08-09 | 6.96 | 2 | Brian Le | Completed | 2019-07-31 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 0 | 1 |  | Completed | 2019-08-02 | 2.04 | 1 | Andrew Clemons | Completed | 2019-08-13 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-27 | 7.25 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 7.83 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 8.13 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.13 | 1 | Andrew Clemons | Completed | 2019-08-14 13:57 |  | 2019-08-16 | 2.75 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-02 | 2019-08-23 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27468 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27468 | https://completesolar.sugarondemand.com/#Opportunities/e7ba6146-b0c4-11e9-aa9a-022c40d974e6 | SCES Division | Henry Garcia | 2019-07-26 | JK Solar | e7ba6146-b0c4-11e9-aa9a-022c40d974e6 | 3 | 10 | 0 | -2 | 5 | 5 | 5 | 8
26166 | PIP_APPROVED | PIP_APPROVED | 357 Calle Burro | San Clemente | CA | 92673 | Roger Dunlap | 2019-06-12 07:57 | 9493704495 | bladeys@cox.net | Mary Dunlap | 9494986915 |  | 4629 | 0.164 | Ryan Malloy | 2019-06-12 | 3.05 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-04 | 2019-06-07 10:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 0 | 2019-08-12 07:00 | 2019-06-12 | 0.17 | 2 | Marcia Garay | Completed | 2019-06-15 | 2.46 | 2 | Daniel Speegle | Completed | 2019-06-17 | 0.33 | 1 | Ara Sotto | Completed | 2019-07-09 | 7.75 | 5 | Brian Le | Completed | 2019-07-01 | 8.25 | 3 | Andrew Moralez | Completed | 2019-07-01 | 0 | 1 | Ernesto Enriquez | Completed | 2019-08-12 | 1.25 | 1 | Christina Horton | Completed | 2019-10-14 | 15 | 2 | Christina Horton | Completed | 2019-06-25 | 5.13 | 2 | Brian Le | Completed | 2019-06-18 | 1.5 | 2 | Marcia Garay | Completed | 2019-06-18 | 0.08 | 1 |  | Completed | 2019-06-28 | 9.33 | 1 | Andrew Clemons | Completed | 2019-08-13 | 2.21 | 1 | Marcia Garay | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 6.83 | 2 | Marcia Garay | Completed |  | 38.17 | 1 | Jeremiah Liend | Current | 2019-08-20 16:57 |  | 2019-08-21 | 3.84 | 2 | Christina Horton | Completed | [10 empty] | 55.55 | 2019-07-16 | 1.71 | 14 | James Fernandez | Completed | 2019-07-16 | 2019-07-31 | 5.79 | 1 | James Fernandez | Completed | 2019-07-02 | 2019-10-14 | SAN CLEMENTE | San Clemente | https://heliotrack.completesolar.com/job.php?action=review&jobID=26166 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26166 | https://completesolar.sugarondemand.com/#Opportunities/48bc3d28-8d22-11e9-a4d1-02ae981fbade | Laura Rea |  | 2019-06-04 | Infinity Energy Inc | 48bc3d28-8d22-11e9-a4d1-02ae981fbade | 9 | 63 | -5 | -2 | 5 | 5 | 5 | 3
26475 | PIP_APPROVED | PIP_APPROVED | 412 West Cornell Drive | Rialto | CA | 92376 | Elmer A Constanza | 2019-07-16 15:32 | 9098151166 | elmer3003@live.com | Lizeth V Constanza | 626806124 |  | 11285 | 0.13 | Shaun Labelle | 2019-06-20 | 6.71 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-17 | 2019-06-18 15:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | Line-side Tap | 2019-08-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 0 | 2019-08-12 07:00 | 2019-07-16 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-18 | 8 | 2 | Daniel Speegle | Completed | 2019-07-30 | 7.66 | 1 | Ara Sotto | Completed | 2019-08-12 | 2.13 | 5 | Brian Le | Completed | 2019-07-22 | 0 | 3 | Andrew Moralez | Completed | 2019-08-09 | 13.79 | 7 | Andrew Moralez | Completed | 2019-08-12 | 0 | 2 | Ara Sotto | Completed | 2019-08-15 | 3.04 | 2 | Ara Sotto | Completed | 2019-08-08 | 13.96 | 2 | Brian Le | Completed | 2019-07-19 | 0.67 | 2 | Marcia Garay | Completed | 2019-07-22 | 2.04 | 1 |  | Completed | 2019-07-26 | 5.67 | 1 | Jill Allen | Completed | 2019-08-14 | 1.96 | 1 | Marcia Garay | Completed |  | 46 | 2 | Jill Allen | Current | [15 empty] | 2019-09-03 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-10-21 | 34.04 | 2 | Ashley Rockwood | Completed |  | 0.04 | 2 | Marcia Garay | Current |  | 0.04 | 1 | Jeremiah Liend | Current | 2019-08-27 17:36 |  | 2019-08-28 | 0 | 2 | Ara Sotto | Completed | 2019-08-28 | 12.17 | 1 | Ara Sotto | Completed | 2019-07-22 | 1.25 | 2 | Marcia Garay | Completed | 16.68 | [11 empty] | 2019-07-31 | 2019-08-14 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26475 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26475 | https://completesolar.sugarondemand.com/#Opportunities/ca350a76-9383-11e9-afb9-0630baf9dcb8 | 300 Stars Inc |  | 2019-06-17 | Power Town Solar Electric | ca350a76-9383-11e9-afb9-0630baf9dcb8 | 0 | 3 | 10 | 2 | 5 | 5 | 5 | 22
27015 | PIP_APPROVED | PIP_APPROVED | 10447 Manila Avenue | San Diego | CA | 92126 | Misako Boeker | 2019-07-22 12:06 | 7607036020 | Bachan@san.rr.com | Anita Boeker | 8583616937 |  | 3461 | 0.172 | Chad Malloy | 2019-07-22 | 2.135 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-15 | 2019-07-18 09:00 | LR6-60PB-305M | 305 | 7 | LONGi Solar | Enphase Energy | IQ7PLUS-72-2-US | Composite | NO | 2019-08-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-12 07:00 | 2019-07-22 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 1 | 2 | Daniel Speegle | Completed | 2019-08-02 | 7.75 | 1 | Christina Horton | Completed | 2019-08-12 | 10.75 | 5 | Brian Le | Completed | 2019-07-29 | 2.04 | 3 | Ernesto Enriquez | Completed | 2019-07-29 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-12 | 0.54 | 1 | Christina Horton | Completed | 2019-08-30 | 11.79 | 2 | Christina Horton | Completed | 2019-07-26 | 1.96 | 2 | Brian Le | Completed | 2019-07-24 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 0.96 | 1 |  | Completed | 2019-07-31 | 5.63 | 1 | Andrew Clemons | Completed | 2019-08-13 | 1.54 | 1 | Darlynn Lacap | Completed | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 8.88 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 4.04 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 1.83 | 1 | Noe Gomez | Completed | 2019-08-13 14:45 |  | 2019-08-13 | 0.88 | 2 | Christina Horton | Completed | [10 empty] | 5.92 | [11 empty] | 2019-08-19 | 2019-08-30 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=27015 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27015 | https://completesolar.sugarondemand.com/#Opportunities/037f9f8c-a9ad-11e9-94e3-022c40d974e6 | Thomas Noble |  | 2019-07-09 | Infinity Energy Inc | 037f9f8c-a9ad-11e9-94e3-022c40d974e6 | 1 | 18 | 10 | -2 | 5 | 5 | 5 | 18
27254 | PIP_APPROVED | PIP_APPROVED | 36467 Blacksmith Drive | Palmdale | CA | 93550 | Maria Ramirez | 2019-07-26 08:08 | 8185995780 | ramirezamelio@gmail.com | Amelio Ramirez | 8184427636 |  | 6392 | 0.13 | Bill Angevine | 2019-07-26 | 3.355 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-18 | 2019-07-20 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-12 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-12 07:00 | 2019-07-29 | 1.13 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 0.96 | 2 | Daniel Speegle | Completed | 2019-08-08 | 6.92 | 1 | Ara Sotto | Completed | 2019-08-12 | 1.08 | 5 | Brian Le | Completed | 2019-08-02 | 2.13 | 3 | Ernesto Enriquez | Completed | 2019-08-08 | 4.08 | 0 | Ernesto Enriquez | Completed | 2019-08-12 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-26 | 9.83 | 2 | Ara Sotto | Completed | 2019-08-09 | 7.96 | 2 | Brian Le | Completed | 2019-07-30 | 0 | 2 | Darlynn Lacap | Completed | 2019-07-31 | 0.92 | 1 |  | Completed | 2019-08-02 | 3 | 1 | Noe Gomez | Completed | 2019-08-13 | 1.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-22 | 4.08 | 2 | Ashley Rockwood | Completed | 2019-08-23 | 1.42 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 7.67 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 3.5 | 1 | Jill Allen | Completed | 2019-08-14 14:01 |  | 2019-08-16 | 3.75 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-02 | 2019-08-26 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=27254 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27254 | https://completesolar.sugarondemand.com/#Opportunities/241c433e-afb7-11e9-82de-02ae981fbade | SCES Division | Henry Garcia | 2019-07-18 | JK Solar | 241c433e-afb7-11e9-82de-02ae981fbade | 4 | 14 | 0 | -2 | 5 | 5 | 5 | 8
26270 | PIP_APPROVED | PIP_APPROVED | 3007 Calle Juarez | San Clemente | CA | 92673 | Lula White | 2019-06-21 11:40 | 9495102503 | dominiqueluoni@gmail.com | Dominique Luoni | 9494986713 |  | 5572 | 0.18 | Chad Malloy | 2019-06-21 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-10 | 2019-06-19 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM |  | NO | 2019-08-10 | NEM Submitted | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-08-10 07:00 | 2019-06-21 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 2.92 | 2 | Jethro Andal | Completed | 2019-07-23 | 17.88 | 1 | Ara Sotto | Completed | 2019-08-10 | 10.17 | 5 | Brian Le | Completed | 2019-07-02 | 2.88 | 3 | Andrew Moralez | Completed | 2019-07-02 | 0 | 1 | Andrew Moralez | Completed | 2019-08-10 | 0.08 | 1 | Christina Horton | Completed | 2019-10-15 | 45.5 | 2 | Christina Horton | Completed | 2019-07-23 | 15.17 | 2 | Brian Le | Completed | 2019-07-01 | 2.83 | 2 | Darlynn Lacap | Completed | 2019-06-27 | 0.96 | 1 |  | Completed | 2019-07-01 | 3 | 1 | Jill Allen | Completed | 2019-08-13 | 1.63 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-03 | 0 | 4 | Darlynn Lacap | Completed | 2019-07-03 | 0.08 | 5 | Darlynn Lacap | Completed | 2019-07-23 | 12.71 | 12 | Darlynn Lacap | Completed | 2019-08-29 | 2.96 | 2 | Ashley Rockwood | Completed |  | 11.75 | 2 | Ashley Rockwood | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-30 | 2019-08-26 | 10.58 | 2 | Christina Horton | Completed | [10 empty] | 27.83 | [11 empty] | 2019-07-03 | 2019-10-14 | SAN CLEMENTE | San Clemente | https://heliotrack.completesolar.com/job.php?action=review&jobID=26270 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26270 | https://completesolar.sugarondemand.com/#Opportunities/b9afa5be-9453-11e9-a5d7-02ae981fbade | Laura Rea |  | 2019-06-08 | Infinity Energy Inc | b9afa5be-9453-11e9-a5d7-02ae981fbade | 16 | 66 | -15 | -2 | 5 | 5 | 5 | -7
26641 | PIP_APPROVED | PIP_APPROVED | 5147 Andrew Jackson Street | Oceanside | CA | 92057 | Maximino Canseco | 2019-07-06 13:19 | 7609458761 | veronica.canseco1@gmail.com | Maria Canseco |  |  | 3922 | 0.16 | Michael Marlaire | 2019-07-06 | 2.44 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-29 | 2019-07-06 09:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000A-US RGM | Tile Concrete | NO | 2019-08-10 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-10 07:00 | 2019-07-18 | 4.46 | 2 | Marcia Garay | Completed | 2019-07-11 | 0.08 | 2 | Daniel Speegle | Completed | 2019-08-02 | 8 | 1 | Christina Horton | Completed | 2019-08-10 | 9.08 | 5 | Brian Le | Completed | 2019-07-26 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-29 | 1.04 | 10 | Ernesto Enriquez | Completed | 2019-08-10 | 0.08 | 1 | Christina Horton | Completed | 2019-08-20 | 6.58 | 2 | Christina Horton | Completed | 2019-07-26 | 1.04 | 2 | Brian Le | Completed | 2019-07-25 | 2.13 | 2 | Marcia Garay | Completed | 2019-07-26 | 3.08 | 1 |  | Completed | 2019-07-24 | 1 | 1 | Andrew Clemons | Completed | 2019-08-15 | 3.63 | 1 | Marcia Garay | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-08-29 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 16.04 | 2 | Marcia Garay | Completed |  | 36.21 | 1 | Andrew Clemons | Current |  | 2019-08-16 | 2019-08-16 | 0.41 | 2 | Christina Horton | Completed | [10 empty] | 29.93 | [11 empty] | 2019-08-09 | 2019-08-10 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26641 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26641 | https://completesolar.sugarondemand.com/#Opportunities/57270584-a02b-11e9-8d06-02ae981fbade | Brett Martinez |  | 2019-06-22 | Infinity Energy Inc | 57270584-a02b-11e9-8d06-02ae981fbade | 6 | 10 | -5 | -2 | 5 | 5 | 5 | 3
26954 | PIP_APPROVED | PIP_APPROVED | 29552 Kanan Road | Menifee | CA | 92586 | Jeremy Jones | 2019-07-11 17:04 | 9512331633 | jeremy.jones0718@gmail.com | Tracy Jones | 951-237-2855 | themoms3kids@verizon.net | 11883 | 0.167 | Michael Marlaire | 2019-07-11 | 7.93 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-10 | 2019-07-11 12:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-10 | 2019-07-12 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 2.04 | 2 | Jethro Andal | Completed | 2019-08-02 | 12.83 | 1 | Ara Sotto | Completed | 2019-08-10 | 8.5 | 5 | Brian Le | Completed | 2019-07-18 | 1 | 3 | Andrew Moralez | Completed | 2019-07-30 | 7.88 | 0 | Andrew Moralez | Completed | 2019-08-10 | 0.08 | 2 | Christina Horton | Completed | 2019-09-04 | 16.63 | 2 | Christina Horton | Completed | 2019-07-23 | 0.08 | 2 | Brian Le | Completed | 2019-07-30 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 1 | 1 |  | Completed | 2019-07-31 | 11.04 | 1 | Andrew Clemons | Completed | 2019-08-13 | 1.63 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-28 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 4.04 | 1 | Jeremiah Liend | Completed |  | 2019-08-30 | 2019-08-26 | 10.58 | 2 | Christina Horton | Completed | [10 empty] | 33.84 | [11 empty] | 2019-07-18 | 2019-09-04 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=26954 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26954 | https://completesolar.sugarondemand.com/#Opportunities/0c4bc85c-a430-11e9-9a7d-0630baf9dcb8 | Robert Garcia | Michael Foster | 2019-07-08 | Infinity Energy Inc | 0c4bc85c-a430-11e9-9a7d-0630baf9dcb8 | 16 | 25 | -15 | -2 | 5 | 5 | 5 | -7
27064 | PIP_APPROVED | PIP_APPROVED | 2537 West Avenue K 4 | Lancaster | CA | 93536 | Stephen Pearson | 2019-07-22 16:32 | 6616094880 | pearson21@earthlink.net | Noriko Pearson | (661)948-4235 |  | 13258 | 0.139 | Alex Holdridge | 2019-07-12 | 7.32 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-11 | 2019-07-12 09:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-10 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-09 07:00 | 2019-07-22 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-24 | 3.84 | 2 | Daniel Speegle | Completed | 2019-07-26 | 1.79 | 1 | Ara Sotto | Completed | 2019-08-14 | 9.08 | 5 | Brian Le | Completed | 2019-07-29 | 2.66 | 3 | Andrew Moralez | Completed | 2019-07-31 | 2.21 | 1 | Ernesto Enriquez | Completed | 2019-08-10 | 0.96 | 2 | Ara Sotto | Completed | 2019-08-16 | 4.54 | 2 | Ara Sotto | Completed | 2019-08-01 | 7 | 2 | Brian Le | Completed | 2019-07-26 | 2 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.17 | 1 |  | Completed | 2019-08-02 | 9.88 | 1 | Andrew Clemons | Completed | 2019-08-13 | 2.59 | 1 | Marcia Garay | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-19 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 12.92 | 2 | Marcia Garay | Completed | 2019-08-22 | 2.29 | 1 | Jill Allen | Completed | 2019-08-12 21:31 |  | 2019-08-14 | 2.5 | 2 | Ara Sotto | Completed | [10 empty] | 2.88 | [11 empty] | 2019-07-30 | 2019-08-15 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27064 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27064 | https://completesolar.sugarondemand.com/#Opportunities/cbd68078-a4cf-11e9-8044-069e4f790264 | SCES Division | Cody Booth | 2019-07-11 | Power Town Solar Electric | cbd68078-a4cf-11e9-8044-069e4f790264 | 4 | 6 | 0 | -2 | 5 | 5 | 5 | 8
21390 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 62 Linden Blvd | Hicksville | NY | 11801 | Loriann Odierna | 2019-04-26 12:15 | 5167901808 | lao67@aol.com |  |  |  | 9978 | 0.185 | Hiram Velez | 2019-01-23 | 9.76 | Christina Horton | Sunlogic Power | Marcia Garay |  | 2019-01-11 15:00 | Q.PEAK-G4.1 305 | 305 | 32 | Hanwha Q CELLS | SolarEdge Technologies | SE10000H-US | Composite | NO | 2019-08-09 | PTO Received | SunRun Lease | 0 |  |  | 0 |  |  | 2019-08-09 07:00 | 2019-04-27 | 0.54 | 2 | Marcia Garay | Completed | 2019-05-03 | 11.59 | 2 | Daniel Speegle | Completed | 2019-06-05 | 43.92 | 1 | Ara Sotto | Completed | 2019-08-09 | 4.17 | 5 | Brian Le | Completed | 2019-07-09 | 27.8 | 3 | Ernesto Enriquez | Completed | 2019-07-09 | 0 | 10 | Ernesto Enriquez | Completed | 2019-08-09 | 2.5 | 2 | Christina Horton | Completed |  | 49.96 | 2 | Christina Horton | Current | 2019-08-05 | 79.25 | 2 | Brian Le | Completed | 2019-05-07 | 5.87 | 2 | Marcia Garay | Completed | 2019-05-14 | 28.46 | 1 |  | Completed | 2019-05-29 | 37.42 | 1 | Jeremiah Liend | Completed |  | 52.46 | 1 | Marcia Garay | Current | 2019-08-19 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-13 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 4.17 | 2 | Marcia Garay | Completed | 2019-09-23 | 2 | 1 | Jill Allen | Completed |  | 2019-09-30 | 2019-09-10 | 10.59 | 2 | Christina Horton | Completed | [10 empty] | 51.42 | [11 empty] | 2019-07-23 |  | Default |  | https://heliotrack.completesolar.com/job.php?action=review&jobID=21390 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=21390 | https://completesolar.sugarondemand.com/#Opportunities/27eb6094-1f2f-11e9-84a3-0630baf9dcb8 | Sunlogic Power |  | 2018-12-19 | Hytech Solar | 27eb6094-1f2f-11e9-84a3-0630baf9dcb8 | 32 | 73 | -25 | -2 | 5 | 5 | 5 | -17
26676 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 6462 Burgundy Street | San Diego | CA | 92120 | Justin wei | 2019-07-02 12:27 | 6197801627 | jwei@dci-engineers.com | Tanya wei | 858-776-4873 |  | 6190 | 0.195 | Chad Malloy | 2019-07-02 | 3.66 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-24 | 2019-06-26 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-09 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-09 07:00 | 2019-07-03 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-09 | 3 | 2 | Daniel Speegle | Completed | 2019-07-26 | 13.08 | 1 | Christina Horton | Completed | 2019-08-09 | 10.67 | 5 | Brian Le | Completed | 2019-07-17 | 4 | 3 | Andrew Moralez | Completed | 2019-07-17 | 0 | 15 | Andrew Moralez | Completed | 2019-08-09 | 0.46 | 1 | Christina Horton | Completed |  | 50.04 | 2 | Christina Horton | Current | 2019-07-23 | 8.88 | 2 | Brian Le | Completed | 2019-07-10 | 1.25 | 2 | Marcia Garay | Completed | 2019-07-11 | 2 | 1 |  | Completed | 2019-07-26 | 9.87 | 1 | Andrew Clemons | Completed |  | 50.54 | 1 | Marcia Garay | Current | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 5 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 16.75 | 2 | Marcia Garay | Completed |  | 38.17 | 1 | Noe Gomez | Current | 2019-08-12 15:12 |  | 2019-08-12 | 0.96 | 2 | Christina Horton | Completed | [10 empty] | 7.37 | [11 empty] | 2019-08-07 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26676 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26676 | https://completesolar.sugarondemand.com/#Opportunities/4c8ee97c-9cff-11e9-b0cc-02ae981fbade | Valerie Jetter | Matthew McKay | 2019-06-24 | Infinity Energy Inc | 4c8ee97c-9cff-11e9-b0cc-02ae981fbade | 3 | 73 | 0 | -2 | 5 | 5 | 5 | 8
27011 | PIP_APPROVED | PIP_APPROVED | 24687 Rugby Lane | Moreno Valley | CA | 92551 | James Jones | 2019-07-13 08:28 | 9515221988 | jim_jones@roadrunner.com |  |  |  | 8085 | 0.161 | Alex Holdridge | 2019-07-12 | 4.575 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-10 | 2019-07-11 15:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-09 | PTO Received | SunRun Monthly | [6 empty] | 2019-08-08 07:00 | 2019-07-17 | 2.33 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 1.17 | 2 | Jethro Andal | Completed | 2019-07-25 | 5.38 | 1 | Ara Sotto | Completed | 2019-08-09 | 6.67 | 5 | Brian Le | Completed | 2019-07-24 | 0.17 | 3 | Ernesto Enriquez | Completed | 2019-08-02 | 6.79 | 25 | Ernesto Enriquez | Completed | 2019-08-09 | 1.13 | 1 | Ara Sotto | Completed | 2019-08-14 | 3.08 | 2 | Ara Sotto | Completed | 2019-07-31 | 7.08 | 2 | Brian Le | Completed | 2019-07-22 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 3.83 | 1 |  | Completed | 2019-07-29 | 6.75 | 1 | Andrew Clemons | Completed | 2019-08-13 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 1.04 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-08-20 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-08-21 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 6.08 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 1.33 | 1 | Andrew Clemons | Completed | 2019-08-13 14:31 |  | 2019-08-13 | 2.21 | 2 | Ara Sotto | Completed | [10 empty] | 35.17 | [11 empty] | 2019-08-28 | 2019-08-14 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27011 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27011 | https://completesolar.sugarondemand.com/#Opportunities/be5367f0-a582-11e9-9483-022c40d974e6 | 300 Stars Inc |  | 2019-07-09 | Power Town Solar Electric | be5367f0-a582-11e9-9483-022c40d974e6 | 4 | 5 | 0 | -2 | 5 | 5 | 5 | 8
27016 | PIP_APPROVED | PIP_APPROVED | 14780 Newcastle Way | Victorville | CA | 92394 | Ernesto Soto | 2019-07-13 11:01 | 9095228992 | soto.ernesto87@gmail.com | zaida Soto | 9099658519 |  | 8214 | 0.139 | Shaun Labelle | 2019-07-13 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-09 | 2019-07-13 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-09 07:00 | 2019-07-15 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 1.79 | 2 | Daniel Speegle | Completed | 2019-07-30 | 7.09 | 1 | Ara Sotto | Completed | 2019-08-09 | 10.96 | 5 | Brian Le | Completed | 2019-07-18 | 0 | 3 | Andrew Moralez | Completed | 2019-07-24 | 3.12 | 10 | Andrew Moralez | Completed | 2019-08-09 | 0.5 | 1 | Ara Sotto | Completed | 2019-08-13 | 6.96 | 2 | Ara Sotto | Completed | 2019-07-25 | 3.29 | 2 | Brian Le | Completed | 2019-07-18 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 1.13 | 1 |  | Completed | 2019-07-27 | 5.67 | 1 | Andrew Clemons | Completed | 2019-08-13 | 6.75 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 1.88 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-08-16 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 6.13 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 2 | 1 | Andrew Clemons | Completed | 2019-08-12 23:58 |  | 2019-08-12 | 6 | 2 | Ara Sotto | Completed | [10 empty] | 2.08 | [11 empty] | 2019-08-02 | 2019-08-12 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27016 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27016 | https://completesolar.sugarondemand.com/#Opportunities/361638e8-a598-11e9-b182-022c40d974e6 | Shane Montana |  | 2019-07-09 | Zachary Noah Gamez | 361638e8-a598-11e9-b182-022c40d974e6 | 3 | 4 | 0 | 0 | 5 | 5 | 5 | 10
27018 | PIP_APPROVED | PIP_APPROVED | 3104 Stevey Street | Lancaster | CA | 93536 | Don Whitt | 2019-07-12 15:21 | 6619429332 | thule53@roadrunner.com |  |  |  | 9953 | 0.124 | Bill Angevine | 2019-07-12 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-09 | 2019-07-12 12:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-09 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-08 12:00 | 2019-07-16 | 1.92 | 2 | Marcia Garay | Completed | 2019-07-17 | 1.08 | 2 | Jethro Andal | Completed | 2019-07-30 | 5.05 | 1 | Ara Sotto | Completed | 2019-08-09 | 10.71 | 5 | Brian Le | Completed | 2019-07-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-19 | 0.08 | 1 | Ernesto Enriquez | Completed | 2019-08-09 | 1.13 | 2 | Ara Sotto | Completed | 2019-08-16 | 5.29 | 2 | Ara Sotto | Completed | 2019-07-25 | 1.33 | 2 | Brian Le | Completed | 2019-07-18 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.92 | 1 |  | Completed | 2019-07-29 | 4.13 | 1 | Andrew Clemons | Completed |  | 51.54 | 1 | Marcia Garay | Current | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-16 | 4.79 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 8.17 | 2 | Marcia Garay | Completed | 2019-08-21 | 2 | 1 | Andrew Clemons | Completed | 2019-08-09 22:50 |  | 2019-08-09 | 0.25 | 2 | Ara Sotto | Completed | [10 empty] | 6.01 | [11 empty] | 2019-07-22 | 2019-08-16 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27018 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27018 | https://completesolar.sugarondemand.com/#Opportunities/536231ea-a4f3-11e9-914c-0630baf9dcb8 | SCES Division |  | 2019-07-09 | JK Solar | 536231ea-a4f3-11e9-914c-0630baf9dcb8 | 0 | 7 | 10 | -2 | 5 | 5 | 5 | 18
23896 | PIP_APPROVED | PIP_APPROVED | 538 Port Harwick | Chula Vista | CA | 91913 | Latisa Carson | 2019-05-06 16:17 | 6193414717 | lscarson@hotmail.com |  |  |  | 13447 | 0.192 | Ryan Malloy | 2019-04-03 | 9.715 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-03-28 | 2019-04-03 12:00 | LG335N1C-A5 | 335 | 29 | LG Electronics | SolarEdge | SE10000A-US RGM | Tile Concrete | NO | 2019-08-08 | PTO Received | SunRun Monthly | 1 |  |  | 0 |  |  | 2019-08-08 | 2019-05-06 | 0.71 | 2 | Marcia Garay | Completed | 2019-05-07 | 5.17 | 2 | Daniel Speegle | Completed | 2019-06-04 | 19.83 | 1 | Christina Horton | Completed | 2019-07-01 | 15 | 5 | Christina Horton | Completed | 2019-06-10 | 17.79 | 3 | Andrew Moralez | Completed | 2019-06-21 | 10.13 | 7 | Andrew Moralez | Completed | 2019-08-08 | 15.42 | 3 | Christina Horton | Completed | 2019-09-24 | 31.96 | 2 | Christina Horton | Completed | 2019-06-05 | 14.08 | 2 | Brittany Faconti | Completed | 2019-05-15 | 5.75 | 2 | Marcia Garay | Completed | 2019-05-14 | 5.16 | 1 |  | Completed | 2019-05-30 | 16.08 | 1 | Jill Allen | Completed | 2019-09-03 | 22.87 | 1 | Marcia Garay | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | 2019-07-03 | 0 | 4 | Marcia Garay | Completed | 2019-07-03 | 0 | 5 | Marcia Garay | Completed | 2019-07-03 | 0 | 12 | Marcia Garay | Completed | 2019-09-25 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 8.92 | 2 | Marcia Garay | Completed | 2019-10-03 | 2.79 | 1 | Jeremiah Liend | Completed | 2019-09-24 09:47 |  | 2019-09-24 | 12.38 | 2 | Christina Horton | Completed | [10 empty] | 41.79 | [11 empty] | 2019-06-18 | 2019-09-24 | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=23896 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=23896 | https://completesolar.sugarondemand.com/#Opportunities/e327727a-5667-11e9-8e6b-022c40d974e6 | Roofing 101 | Chris Monson | 2019-03-19 | Infinity Energy Inc | e327727a-5667-11e9-8e6b-022c40d974e6 | 47 | 47 | -25 | -2 | 5 | 5 | 5 | -17
25631 | PIP_APPROVED | PIP_APPROVED | 3633 Lorimer Lane | Encinitas | CA | 92024 | Jeff Riggs | 2019-06-24 10:25 | 7602129049 | jbriggsby@gmail.com |  |  |  | 5473 | 0.185 | Ryan Malloy | 2019-06-11 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-26 | 2019-05-31 12:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-08 | PTO Received | SunRun Monthly | 1 | 0 |  |  | 0 | 1 | 2019-08-08 07:00 | 2019-06-24 | 4.04 | 2 | Darlynn Lacap | Completed | 2019-06-27 | 6.71 | 2 | Jethro Andal | Completed | 2019-07-25 | 19.33 | 1 | Christina Horton | Completed | 2019-08-08 | 11.75 | 5 | Brian Le | Completed | 2019-07-02 | 0 | 3 | Andrew Moralez | Completed | 2019-07-11 | 6.04 | 0 | Andrew Moralez | Completed | 2019-08-08 | 0.46 | 1 | Christina Horton | Completed | 2019-08-12 | 2.17 | 2 | Christina Horton | Completed | 2019-07-23 | 2.88 | 2 | Brian Le | Completed | 2019-07-10 | 2.25 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 3 | 1 |  | Completed | 2019-07-08 | 5.92 | 1 | Andrew Clemons | Completed | 2019-08-13 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | 2019-07-03 | 0 | 4 | Darlynn Lacap | Completed | 2019-07-03 | 0 | 5 | Darlynn Lacap | Completed | 2019-07-25 | 15.21 | 12 | Darlynn Lacap | Completed | 2019-08-20 | 5.96 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 6.21 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 4.92 | 1 | Jeremiah Liend | Completed | 2019-08-12 14:57 |  | 2019-08-12 | 2 | 2 | Christina Horton | Completed | [10 empty] | 24.92 | [11 empty] | 2019-07-02 | 2019-08-08 | ENCINITAS | Encinitas | https://heliotrack.completesolar.com/job.php?action=review&jobID=25631 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25631 | https://completesolar.sugarondemand.com/#Opportunities/0a53a968-8c8c-11e9-aadf-0630baf9dcb8 | Gavin Seeberger |  | 2019-05-15 | Infinity Energy Inc | 0a53a968-8c8c-11e9-aadf-0630baf9dcb8 | 4 | 4 | 0 | 0 | 5 | 5 | 5 | 10
26725 | PIP_APPROVED | PIP_APPROVED | 25699 Vista Famoso Drive | Moreno Valley | CA | 92551 | Sokeath Bou | 2019-06-29 15:54 | 9519029927 | kmanzoni@yahoo.com |  |  |  | 13885 | 0.154 | Michael Marlaire | 2019-06-29 | 8.845 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-26 | 2019-06-29 12:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-08 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-08-08 07:00 | 2019-07-01 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 5 | 2 | Daniel Speegle | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-09 | 6.67 | 5 | Brian Le | Completed | 2019-07-24 | 0.13 | 3 | Ernesto Enriquez | Completed | 2019-07-30 | 3.96 | 25 | Andrew Moralez | Completed | 2019-08-08 | 0.71 | 2 | Ara Sotto | Completed | 2019-08-13 | 2.58 | 2 | Ara Sotto | Completed | 2019-07-31 | 14.96 | 2 | Brian Le | Completed | 2019-07-10 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-07-24 | 10.75 | 1 |  | Completed | 2019-07-29 | 13.63 | 1 | Andrew Clemons | Completed | 2019-08-13 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 1.92 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-08-20 | 4.88 | 2 | Ashley Rockwood | Completed | 2019-08-21 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 23.79 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 1.92 | 1 | Andrew Clemons | Completed | 2019-08-13 21:30 |  | 2019-08-13 | 2.58 | 2 | Ara Sotto | Completed | [10 empty] | 7.75 | [11 empty] | 2019-08-28 | 2019-08-13 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26725 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26725 | https://completesolar.sugarondemand.com/#Opportunities/cc89ea82-9ac0-11e9-bfe6-022c40d974e6 | 300 Stars Inc |  | 2019-06-26 | Power Town Solar Electric | cc89ea82-9ac0-11e9-bfe6-022c40d974e6 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
26952 | PIP_APPROVED | PIP_APPROVED | 68413 Panorama Drive | Desert Hot Springs | CA | 92240 | Jamie Summer Smith | 2019-07-08 18:00 | 7602721822 | kurrian@yahoo.com | David L Tapia | 7606766820 |  | 13823 | 0 | Chris Peaslee | 2019-07-08 | 7.32 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-07 | 2019-07-08 15:00 | LR6-60PB-305M | 305 | 24 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-08-08 | PTO Received | CalFirst SunRun Prepaid | 0 | 0 |  |  |  | 1 | 2019-08-08 07:00 | 2019-07-09 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-07-11 | 2.08 | 2 | Jethro Andal | Completed | 2019-07-09 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-08 | 5.38 | 5 | Brian Le | Completed | 2019-07-17 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-31 | 9.17 | 14 | Andrew Moralez | Completed | 2019-08-08 | 1.71 | 2 | Ara Sotto | Completed | 2019-08-15 | 4.71 | 2 | Ara Sotto | Completed | 2019-08-01 | 13.79 | 2 | Brian Le | Completed | 2019-07-12 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 0.08 | 1 |  | Completed | 2019-07-24 | 8.63 | 1 | Jill Allen | Completed | 2019-08-13 | 3.58 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-19 | 5.04 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 24.79 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2.13 | 1 | Andrew Clemons | Completed | 2019-08-12 21:47 |  | 2019-08-12 | 1.63 | 2 | Ara Sotto | Completed | [10 empty] | 7 | [11 empty] | 2019-08-07 | 2019-08-13 | DESERT HOT SPRINGS | Desert hot springs | https://heliotrack.completesolar.com/job.php?action=review&jobID=26952 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26952 | https://completesolar.sugarondemand.com/#Opportunities/d2022d82-a1e4-11e9-bc2d-022c40d974e6 | PJB Division |  | 2019-07-07 | Zachary Noah Gamez | d2022d82-a1e4-11e9-bc2d-022c40d974e6 | 4 | 7 | 0 | -2 | 5 | 5 | 5 | 8
27122 | PIP_APPROVED | PIP_APPROVED | 24348 Comfort Court | Moreno Valley | CA | 92553 | Sergio Bermudez Gonzalez | 2019-07-15 12:39 | 9512303236 | sgnzalezb63@gmail.com | Maria Cuevas | (909) 559-9846 |  | 7458 | 0.172 | Michael Marlaire | 2019-07-15 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-14 | 2019-07-15 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-08 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-08 | 2019-07-16 | 1.13 | 2 | Marcia Garay | Completed | 2019-07-18 | 1.75 | 2 | Jethro Andal | Completed | 2019-07-16 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-08 | 5.5 | 5 | Brian Le | Completed | 2019-07-24 | 1.04 | 3 | Ernesto Enriquez | Completed | 2019-07-30 | 4 | 25 | Andrew Moralez | Completed | 2019-08-08 | 0 | 1 | Ara Sotto | Completed | 2019-08-14 | 3.67 | 2 | Ara Sotto | Completed | 2019-08-01 | 8.92 | 2 | Brian Le | Completed | 2019-07-19 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-23 | 3 | 1 |  | Completed | 2019-07-31 | 9.21 | 1 | Andrew Clemons | Completed | 2019-08-13 | 2.71 | 1 | Marcia Garay | Completed | 2019-08-15 | 0.79 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-22 | 4.08 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 4.21 | 2 | Marcia Garay | Completed |  | 37.33 | 1 | Andrew Clemons | Current | 2019-08-14 21:09 |  | 2019-08-16 | 5.38 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-28 | 2019-08-08 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=27122 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27122 | https://completesolar.sugarondemand.com/#Opportunities/35b7832e-a738-11e9-8bc1-02ae981fbade | Oscar Torres | Oscar Hernandez | 2019-07-14 | HDM Electric Inc | 35b7832e-a738-11e9-8bc1-02ae981fbade | 8 | 6 | -5 | -2 | 5 | 5 | 5 | 3
27238 | PIP_APPROVED | PIP_APPROVED | 16252 Hiawatha Street | Victorville | CA | 92395 | Frank Aguon | 2019-07-22 17:40 | 7609534018 | fsaguon44@gmail.com | Mary Aguon | 7604867174 |  | 7352 | 0.15 | Bill Angevine | 2019-07-22 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-18 | 2019-07-22 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-08 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-07 07:00 | 2019-07-23 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 1.88 | 2 | Jethro Andal | Completed | 2019-07-25 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-07 | 4.92 | 5 | Brian Le | Completed | 2019-07-26 | 0.71 | 3 | Andrew Moralez | Completed | 2019-07-30 | 2.04 | 10 | Ernesto Enriquez | Completed | 2019-08-08 | 1.75 | 1 | Ara Sotto | Completed | 2019-08-08 | 0.08 | 2 | Ara Sotto | Completed | 2019-07-31 | 2.83 | 2 | Brian Le | Completed | 2019-07-26 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.17 | 1 |  | Completed | 2019-08-01 | 5.04 | 1 | Andrew Clemons | Completed | 2019-08-07 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-08-15 | 4.46 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-12 | 1.5 | 2 | Ashley Rockwood | Completed | 2019-08-13 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 12.04 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 2 | 1 | Andrew Clemons | Completed | 2019-08-07 21:26 |  | 2019-08-08 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-09 | 2019-08-07 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27238 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27238 | https://completesolar.sugarondemand.com/#Opportunities/62a045ec-ace2-11e9-8f3e-069e4f790264 | Christopher Cellini | Shane Montana | 2019-07-18 | Power Town Solar Electric | 62a045ec-ace2-11e9-8f3e-069e4f790264 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
26222 | PIP_APPROVED | PIP_APPROVED | 5150 Summerhill Drive | Oceanside | CA | 92057 | James R Hoggatt | 2019-07-16 14:56 | 7602771222 | getthog24@hotmail.com | Kristy Hoggatt | 7608400775 |  | 9344 | 0.002 | Michael Marlaire | 2019-06-11 | 5.795 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-06 | 2019-06-08 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-07 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-07 07:00 | 2019-07-16 | 1.92 | 2 | Marcia Garay | Completed | 2019-07-18 | 3.45 | 2 | Jethro Andal | Completed | 2019-07-24 | 3.88 | 1 | Christina Horton | Completed | 2019-08-07 | 13.42 | 5 | Brian Le | Completed | 2019-07-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-18 | 0.08 | 10 | Andrew Moralez | Completed | 2019-08-07 | 0.67 | 2 | Christina Horton | Completed | 2019-08-29 | 10.55 | 2 | Christina Horton | Completed | 2019-07-18 | 0.13 | 2 | Brian Le | Completed | 2019-07-18 | 0 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.08 | 1 |  | Completed | 2019-07-18 | 0.08 | 1 | Noe Gomez | Completed | 2019-08-09 | 2.5 | 1 | Marcia Garay | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-26 | 5.92 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 18.08 | 2 | Marcia Garay | Completed |  | 36.21 | 1 | Andrew Clemons | Current | 2019-08-16 13:29 |  | 2019-08-16 | 2.75 | 2 | Christina Horton | Completed | [10 empty] | 19.95 | [11 empty] | 2019-08-01 | 2019-08-29 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26222 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26222 | https://completesolar.sugarondemand.com/#Opportunities/c008caec-8c7b-11e9-95f6-022c40d974e6 | Trey Greenhill |  | 2019-06-06 | Infinity Energy Inc | c008caec-8c7b-11e9-95f6-022c40d974e6 | 9 | 22 | -5 | -2 | 5 | 5 | 5 | 3
26230 | PIP_APPROVED | PIP_APPROVED | 374 Doheny Bay Court | Oceanside | CA | 92057 | Carole Wilson | 2019-07-03 15:24 | 6195615207 | carolewilson@wildblue.net |  |  |  | 4656 | 0.182 | Ryan Malloy | 2019-06-26 | 3.05 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-06 | 2019-06-14 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-07 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-08-07 12:00 | 2019-07-03 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 4.91 | 2 | Daniel Speegle | Completed | 2019-07-29 | 15.13 | 1 | Christina Horton | Completed | 2019-08-07 | 17.25 | 5 | Brian Le | Completed | 2019-07-08 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-09 | 0.96 | 10 | Ernesto Enriquez | Completed | 2019-08-07 | 0.46 | 1 | Christina Horton | Completed | 2019-08-16 | 7 | 2 | Christina Horton | Completed | 2019-07-09 | 0.08 | 2 | Brian Le | Completed | 2019-07-09 | 1 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 0.13 | 1 |  | Completed | 2019-07-12 | 3.88 | 1 | Andrew Clemons | Completed | 2019-08-07 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | 2019-07-09 | 2.96 | 4 | Darlynn Lacap | Completed | 2019-07-24 | 11.04 | 5 | Darlynn Lacap | Completed | 2019-08-05 | 7.92 | 12 | Darlynn Lacap | Completed | 2019-08-14 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 9.17 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 3 | 1 | Andrew Clemons | Completed | 2019-08-08 16:04 |  | 2019-08-08 | 0.79 | 2 | Christina Horton | Completed | [10 empty] | 7.04 | [11 empty] | 2019-07-22 | 2019-08-15 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26230 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26230 | https://completesolar.sugarondemand.com/#Opportunities/d09fcc86-9903-11e9-8389-02ae981fbade | Alan Moberg |  | 2019-06-06 | Infinity Energy Inc | d09fcc86-9903-11e9-8389-02ae981fbade | 1 | 9 | 10 | -2 | 5 | 5 | 5 | 18
26670 | PIP_APPROVED | PIP_APPROVED | 7487 Chippewa Trail | Yucca Valley | CA | 92284 | David Adolphson | 2019-06-25 20:52 | 8647062462 | dsatanks@hotmail.com | Matthew Adolphson | 8647069410 |  | 11576.8 |  | Shaun Labelle | 2019-06-25 | 6.405 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-24 | 2019-06-25 15:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-08-07 | PTO Received | Sunlight Financial Loan | 0 | 0 |  |  |  | 1 | 2019-08-07 07:00 | 2019-06-26 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-01 | 3.08 | 2 | Daniel Speegle | Completed | 2019-06-26 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-07 | 4.13 | 5 | Brian Le | Completed | 2019-07-25 | 3.04 | 3 | Ernesto Enriquez | Completed | 2019-07-31 | 4.13 | 0 | Andrew Moralez | Completed | 2019-08-07 | 2.63 | 2 | Ara Sotto | Completed | 2019-08-13 | 4 | 2 | Ara Sotto | Completed | 2019-08-01 | 20.67 | 2 | Brian Le | Completed | 2019-07-02 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-07-22 | 13.75 | 1 |  | Completed | 2019-07-08 | 3.92 | 1 | Andrew Clemons | Completed | 2019-08-07 | 2.54 | 1 | Darlynn Lacap | Completed |  | 48.08 | 2 | Noe Gomez | Current | [15 empty] | 2019-08-23 | 10.33 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 0.54 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 3.04 | 2 | Darlynn Lacap | Completed | 2019-08-27 | 0.92 | 1 | Andrew Clemons | Completed | 2019-08-08 21:32 |  | 2019-08-09 | 1.96 | 2 | Ara Sotto | Completed | [10 empty] | 12.25 | [11 empty] | 2019-07-25 | 2019-08-13 | YUCCA VALLEY | Yucca Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26670 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26670 | https://completesolar.sugarondemand.com/#Opportunities/b08d9444-97c5-11e9-8f84-069e4f790264 | Ryan Wilcox |  | 2019-06-24 | Power Town Solar Electric | b08d9444-97c5-11e9-8f84-069e4f790264 | 2 | 6 | 7 | -2 | 5 | 5 | 5 | 15
26907 | PIP_APPROVED | PIP_APPROVED | 12956 Gate Drive | Poway | CA | 92064 | Adrian Ismaili | 2019-07-08 08:33 | 2082404036 | adrianbismaili@gmail.com | Taylor Ismaili | 607-345-5516 |  | 6711 | 0.18 | Michael Marlaire | 2019-07-08 | 4.27 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-03 | 2019-07-05 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-07 | Initial Customer Contact | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-07 07:00 | 2019-07-18 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 1.21 | 2 | Jethro Andal | Completed | 2019-07-08 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-07 | 1.96 | 5 | Brian Le | Completed | 2019-07-26 | 4.67 | 3 | Andrew Moralez | Completed | 2019-08-01 | 4.04 | 14 | Andrew Moralez | Completed | 2019-08-07 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-19 | 7.96 | 2 | Ara Sotto | Completed | 2019-08-05 | 10.17 | 2 | Brian Le | Completed | 2019-07-22 | 0.42 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 0.08 | 1 |  | Completed | 2019-07-29 | 5.63 | 1 | Andrew Clemons | Completed | 2019-08-07 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-19 | 3.71 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 8 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 1 | 1 | Jill Allen | Completed | 2019-08-08 13:18 |  | 2019-08-08 | 1.33 | 2 | Ara Sotto | Completed | [10 empty] | 9.83 | [11 empty] | 2019-08-15 | 2019-08-19 | POWAY | Poway | https://heliotrack.completesolar.com/job.php?action=review&jobID=26907 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26907 | https://completesolar.sugarondemand.com/#Opportunities/a07d7a4a-a195-11e9-b03d-069e4f790264 | Mario Washington | Jordan Litrownik | 2019-07-03 | Blalock Electric&Solar | a07d7a4a-a195-11e9-b03d-069e4f790264 | 1 | 12 | 10 | -2 | 5 | 5 | 5 | 18
26910 | PIP_APPROVED | PIP_APPROVED | 29948 Gifhorn Road | Menifee | CA | 92584 | Nigel Johnson | 2019-07-19 09:46 | 6197507893 | Nrjohnson619@gmail.com | Delia Johnson | 6192514211 |  | 6541 | 0.142 | Chad Malloy | 2019-07-19 | 3.66 | Ara Sotto | Blue Prime Energy | Darlynn Lacap | 2019-07-15 | 2019-07-17 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-07 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-06 07:00 | 2019-07-19 | 0.25 | 2 | Darlynn Lacap | Completed | 2019-07-22 | 0.92 | 2 | Jethro Andal | Completed | 2019-07-29 | 2.71 | 1 | Ara Sotto | Completed | 2019-08-07 | 1.96 | 5 | Brian Le | Completed | 2019-08-02 | 6.17 | 3 | Ernesto Enriquez | Completed | 2019-08-02 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-07 | 1.38 | 1 | Ara Sotto | Completed | 2019-08-12 | 3.04 | 2 | Ara Sotto | Completed | 2019-08-05 | 7.13 | 2 | Brian Le | Completed | 2019-07-25 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 0.08 | 1 |  | Completed | 2019-08-08 | 10.58 | 1 | Andrew Clemons | Completed | 2019-08-06 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-13 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 6.17 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 5.04 | 1 | Andrew Clemons | Completed |  |  | 2019-08-07 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 3.04 | [11 empty] | 2019-08-02 | 2019-08-08 | MENIFEE | Menifee | https://heliotrack.completesolar.com/job.php?action=review&jobID=26910 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26910 | https://completesolar.sugarondemand.com/#Opportunities/a4f5d150-aa44-11e9-a9ee-022c40d974e6 | Blue Prime Energy |  | 2019-07-05 | Green Road Solar Crew | a4f5d150-aa44-11e9-a9ee-022c40d974e6 | 0 | 5 | 10 | -2 | 5 | 5 | 5 | 18
27166 | PIP_APPROVED | PIP_APPROVED | 2821 West Milling Street | Lancaster | CA | 93536 | Amy Brouwer | 2019-07-17 14:38 | 6613059908 | amybrouwer25@gmail.com |  |  |  | 8257 | 0.142 | Bill Angevine | 2019-07-17 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-16 | 2019-07-17 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-07 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-07 07:00 | 2019-07-19 | 1.75 | 2 | Marcia Garay | Completed | 2019-07-22 | 1.17 | 2 | Jethro Andal | Completed | 2019-07-30 | 5.79 | 1 | Ara Sotto | Completed | 2019-08-07 | 3.17 | 5 | Brian Le | Completed | 2019-07-24 | 0.08 | 3 | Andrew Moralez | Completed | 2019-08-01 | 2.92 | 1 | Andrew Moralez | Completed | 2019-08-07 | 0.38 | 2 | Ara Sotto | Completed | 2019-08-26 | 12.96 | 2 | Ara Sotto | Completed | 2019-08-02 | 5.79 | 2 | Brian Le | Completed | 2019-07-25 | 0.08 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.91 | 1 |  | Completed | 2019-07-28 | 4.42 | 1 | Andrew Clemons | Completed |  | 52.54 | 1 | Marcia Garay | Current | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-29 | 13.29 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 4.08 | 2 | Ashley Rockwood | Completed |  | 32.25 | 2 | Marcia Garay | Current | 2019-09-11 | 4.17 | 1 | Andrew Clemons | Completed | 2019-08-09 22:44 |  | 2019-08-11 | 2.42 | 2 | Ara Sotto | Completed | [10 empty] | 19.29 | [11 empty] | 2019-07-30 | 2019-08-26 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27166 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27166 | https://completesolar.sugarondemand.com/#Opportunities/180fe4e8-a8db-11e9-bb4b-069e4f790264 | SCES Division | George Sarkis | 2019-07-16 | JK Solar | 180fe4e8-a8db-11e9-bb4b-069e4f790264 | 4 | 19 | 0 | -2 | 5 | 5 | 5 | 8
27266 | PIP_APPROVED | PIP_APPROVED | 1347 West Avenue H14 | Lancaster | CA | 93534 | Maria Hernandez | 2019-07-22 09:18 | 8182339789 | ethiktattoos@yahoo.com | Jesus Chavez | 6617288776 |  | 10680 | 0.144 | Bill Angevine | 2019-07-22 | 6.71 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-19 | 2019-07-20 10:30 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-08-07 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-07 07:00 | 2019-07-22 | 0 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 3.04 | 2 | Jethro Andal | Completed | 2019-07-30 | 2.88 | 1 | Ara Sotto | Completed | 2019-08-07 | 2.13 | 5 | Brian Le | Completed | 2019-07-26 | 0.75 | 3 | Ernesto Enriquez | Completed | 2019-08-01 | 4.17 | 1 | Andrew Moralez | Completed | 2019-08-07 | 0 | 2 | Ara Sotto | Completed | 2019-09-17 | 28 | 2 | Ara Sotto | Completed | 2019-08-05 | 5.67 | 2 | Brian Le | Completed | 2019-07-26 | 1.25 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 0.17 | 1 |  | Completed | 2019-07-30 | 2.88 | 1 | Andrew Clemons | Completed | 2019-08-07 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-14 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-08-15 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 10.08 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 3.96 | 1 | Andrew Clemons | Completed | 2019-08-09 22:51 |  | 2019-08-09 | 1.96 | 2 | Ara Sotto | Completed | [10 empty] | 0.83 | [11 empty] | 2019-07-29 | 2019-09-17 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27266 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27266 | https://completesolar.sugarondemand.com/#Opportunities/318eede6-ac9c-11e9-b060-022c40d974e6 | SCES Division | Henry Garcia | 2019-07-19 | JK Solar | 318eede6-ac9c-11e9-b060-022c40d974e6 | 2 | 41 | 7 | -2 | 5 | 5 | 5 | 15
25535 | PIP_APPROVED | PIP_APPROVED | 26262 Stallion Road | Moreno Valley | CA | 92555 | Marx Garcia | 2019-06-10 07:53 | 7604051181 | marx.garcia@icloud.com |  |  |  | 6264.87 |  | Michael Marlaire | 2019-06-10 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-06 | 2019-06-08 15:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-06 | PTO Received | Sunlight Financial Loan | 1 | 0 |  |  | 0 | 1 | 2019-08-06 07:00 | 2019-06-12 | 2.25 | 2 | Darlynn Lacap | Completed | 2019-06-17 | 2.92 | 2 | Daniel Speegle | Completed | 2019-07-25 | 26.96 | 1 | Christina Horton | Completed | 2019-08-06 | 26.92 | 5 | Brian Le | Completed | 2019-06-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-06-21 | 3.08 | 25 | Andrew Moralez | Completed | 2019-08-06 | 0.33 | 1 | Christina Horton | Completed | 2019-08-23 | 12.92 | 2 | Christina Horton | Completed | 2019-06-27 | 4.08 | 2 | Brian Le | Completed | 2019-06-21 | 2.91 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 0.88 | 1 |  | Completed | 2019-07-02 | 10.92 | 1 | Andrew Clemons | Completed | 2019-08-06 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 4.17 | 2 | Andrew Clemons | Completed | 2019-07-03 | 0 | 4 | Darlynn Lacap | Completed | 2019-07-08 | 2.04 | 5 | Darlynn Lacap | Completed | 2019-07-25 | 12.92 | 12 | Darlynn Lacap | Completed | 2019-08-28 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 0.83 | 2 | Ashley Rockwood | Completed |  | 36.33 | 2 | Darlynn Lacap | Current | 2019-09-04 | 3 | 1 | Andrew Clemons | Completed | 2019-08-22 13:28 |  | 2019-08-22 | 12 | 2 | Christina Horton | Completed | [10 empty] | 38.38 | [11 empty] | 2019-07-24 | 2019-08-21 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=25535 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25535 | https://completesolar.sugarondemand.com/#Opportunities/5ed328b8-8b8f-11e9-ace7-069e4f790264 | Lindsey Lange |  | 2019-06-06 | Infinity Energy Inc | 5ed328b8-8b8f-11e9-ace7-069e4f790264 | 16 | 17 | -15 | -2 | 5 | 5 | 5 | -7
26237 | PIP_APPROVED | PIP_APPROVED | 809 Genoa Way | San Marcos | CA | 92078 | Li Tian | 2019-06-19 11:40 | 7602188351 | tianl@hotmail.com |  |  |  | 5405 | 0.162 | Chad Malloy | 2019-06-19 | 3.355 |  | 1Up Solar | Marcia Garay | 2019-06-07 | 2019-06-08 12:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 1 | 0 |  |  | 0 | 1 | 2019-08-06 07:00 | 2019-06-24 | 2.92 | 2 | Marcia Garay | Completed | 2019-06-28 | 4.17 | 2 | Jethro Andal | Completed | 2019-07-31 | 21.96 | 1 | Christina Horton | Completed | 2019-08-06 | 2.67 | 5 | Brian Le | Completed | 2019-07-02 | 1.46 | 3 | Ernesto Enriquez | Completed | 2019-07-02 | 0 | 0 | Ernesto Enriquez | Completed | 2019-08-06 | 0.42 | 1 | Christina Horton | Completed | 2019-08-15 | 7.08 | 2 | Christina Horton | Completed | 2019-07-31 | 21 | 2 | Brian Le | Completed | 2019-07-01 | 1 | 2 | Marcia Garay | Completed | 2019-06-29 | 0.38 | 1 |  | Completed | 2019-07-02 | 1.83 | 1 | Andrew Clemons | Completed | 2019-08-14 | 6.21 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-15 | 0 | 4 | Marcia Garay | Completed | 2019-07-30 | 10.88 | 5 | Marcia Garay | Completed | 2019-07-31 | 0.96 | 12 | Marcia Garay | Completed | 2019-08-15 | 3.17 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 2.75 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 7.08 | 2 | Marcia Garay | Completed | 2019-08-22 | 2.33 | 1 | Jill Allen | Completed | 2019-08-12 14:15 |  | 2019-08-12 | 3.79 | 2 | Christina Horton | Completed | [10 empty] | 2.42 | [11 empty] | 2019-07-02 | 2019-08-15 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=26237 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26237 | https://completesolar.sugarondemand.com/#Opportunities/9c796806-92c1-11e9-9550-022c40d974e6 | Sasha1UPSolar Dearinger |  | 2019-06-06 | iEnergy ElectricSolar | 9c796806-92c1-11e9-9550-022c40d974e6 | 6 | 9 | -5 | -2 | 5 | 5 | 5 | 3
26543 | PIP_APPROVED | PIP_APPROVED | 1869 Wedgemere Road | El Cajon | CA | 92020 | John Roberts | 2019-07-03 09:14 | 6198615456 | rbertsb@cox.net | Marrulue Roberts | 6192043213 |  | 4631 | 0.176 | Ryan Malloy | 2019-07-03 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-28 | 2019-07-01 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-05 12:00 | 2019-07-05 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-09 | 1.92 | 2 | Jethro Andal | Completed | 2019-08-01 | 17.08 | 1 | Christina Horton | Completed | 2019-08-05 | 12.92 | 5 | Brian Le | Completed | 2019-07-10 | 1.13 | 3 | Ernesto Enriquez | Completed | 2019-07-29 | 12.79 | 0 | Ernesto Enriquez | Completed | 2019-08-06 | 1.13 | 1 | Christina Horton | Completed | 2019-09-04 | 18.5 | 2 | Christina Horton | Completed | 2019-07-15 | 2 | 2 | Brian Le | Completed | 2019-07-11 | 2.13 | 2 | Marcia Garay | Completed | 2019-07-09 | 0.17 | 1 |  | Completed | 2019-07-14 | 3.54 | 1 | Andrew Clemons | Completed | 2019-08-13 | 6.21 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-21 | 6 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 8.08 | 2 | Marcia Garay | Completed | 2019-08-29 | 4.88 | 1 | Noe Gomez | Completed | 2019-08-13 11:57 |  | 2019-08-13 | 5.17 | 2 | Christina Horton | Completed | [10 empty] | 4.8 | [11 empty] | 2019-07-10 | 2019-09-04 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=26543 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26543 | https://completesolar.sugarondemand.com/#Opportunities/90a3e38e-9dad-11e9-96e5-069e4f790264 | Chad Bright | Robert Blessing | 2019-06-19 | Infinity Energy Inc | 90a3e38e-9dad-11e9-96e5-069e4f790264 | 7 | 29 | -5 | -2 | 5 | 5 | 5 | 3
26647 | PIP_APPROVED | PIP_APPROVED | 6360 Essex Street | Riverside | CA | 92504 | Solyna H Nash | 2019-06-25 16:18 | 6262354422 | narciso.calderon32@yahoo.com | Narcisco Nash | 6262354422 |  | 9069.23 |  | Alex Holdridge | 2019-06-25 | 5.49 | Ara Sotto | Solar Power Marketing | Darlynn Lacap | 2019-06-23 | 2019-06-25 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-06 | PTO Received | Sunlight Financial Loan | 0 | 0 | 1 |  |  | 1 | 2019-08-05 07:00 | 2019-07-09 | 2.96 | 2 | Darlynn Lacap | Completed | 2019-07-11 | 2.08 | 2 | Daniel Speegle | Completed | 2019-06-26 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-06 | 3.88 | 5 | Brian Le | Completed | 2019-07-22 | 1.08 | 3 | Andrew Moralez | Completed | 2019-07-31 | 6.92 | 10 | Andrew Moralez | Completed | 2019-08-06 | 1.71 | 2 | Ara Sotto | Completed | 2019-08-06 | 0 | 2 | Ara Sotto | Completed | 2019-07-31 | 12.88 | 2 | Brian Le | Completed | 2019-07-12 | 0.79 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 0.96 | 1 |  | Completed | 2019-07-20 | 6.08 | 1 | Andrew Clemons | Completed | 2019-08-05 | 0.92 | 1 | Darlynn Lacap | Completed | 2019-08-28 | 15.75 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-28 | 12.71 | 2 | Ashley Rockwood | Completed | 2019-08-28 | 0 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 15.17 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 1.08 | 1 | Andrew Clemons | Completed | 2019-08-07 21:17 |  | 2019-08-09 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 16.09 | [11 empty] | 2019-08-05 | 2019-08-06 | RIVERSIDE | Riverside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26647 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26647 | https://completesolar.sugarondemand.com/#Opportunities/6b58425a-979f-11e9-a5ca-069e4f790264 | Solar Power Marketing |  | 2019-06-23 | Power Town Solar Electric | 6b58425a-979f-11e9-a5ca-069e4f790264 | 3 | 0 | 0 | 5 | 5 | 5 | 5 | 15
26767 | PIP_APPROVED | PIP_APPROVED | 3965 Dove Tree Avenue | Rialto | CA | 92377 | Laura Taylor | 2019-07-03 12:05 | 9093573739 | lauraleetaylor@att.net |  |  |  | 8168 | 0.155 | Shaun Labelle | 2019-07-03 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-01 | 2019-07-02 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | Line-side Tap | 2019-08-06 | Installation Complete | SunRun Monthly | 0 | 1 |  |  | 0 | 1 | 2019-08-06 07:00 | 2019-07-08 | 1.88 | 2 | Marcia Garay | Completed | 2019-07-05 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-05 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-06 | 4 | 5 | Brian Le | Completed | 2019-07-16 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-29 | 9 | 7 | Ernesto Enriquez | Completed | 2019-08-06 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-13 | 4.71 | 2 | Ara Sotto | Completed | 2019-07-31 | 12.21 | 2 | Brian Le | Completed | 2019-07-15 | 5 | 2 | Marcia Garay | Completed | 2019-07-16 | 6.04 | 1 |  | Completed | 2019-07-08 | 0.21 | 1 | Andrew Clemons | Completed | 2019-08-06 | 0.42 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 |  | Inactive |  | 53.54 | 1 | Ara Sotto | Current | 2019-07-08 | 0.21 | 2 | Marcia Garay | Completed | 7.42 | [11 empty] | 2019-07-25 | 2019-08-09 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26767 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26767 | https://completesolar.sugarondemand.com/#Opportunities/6eed27e2-9dc5-11e9-bcf5-022c40d974e6 | 300 Stars Inc |  | 2019-06-27 | Power Town Solar Electric | 6eed27e2-9dc5-11e9-bcf5-022c40d974e6 |  | 7 | -25 | -2 | 5 | 5 | 5 | -17
26812 | PIP_APPROVED | PIP_APPROVED | 9024 Rosecrest Drive | Fontana | CA | 92335 | Tycia Alarcon | 2019-07-08 06:07 | 5623317560 | tycia.alarcon@gmail.com |  |  |  | 6635 | 0.162 | Alex Holdridge | 2019-07-07 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-03 | 2019-07-05 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-06 07:00 | 2019-07-08 | 0.38 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 1 | 2 | Daniel Speegle | Completed | 2019-07-25 | 12.29 | 1 | Ara Sotto | Completed | 2019-08-06 | 4 | 5 | Brian Le | Completed | 2019-07-17 | 5.54 | 3 | Ernesto Enriquez | Completed | 2019-07-29 | 8.04 | 12 | Ernesto Enriquez | Completed | 2019-08-06 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-12 | 4.21 | 2 | Ara Sotto | Completed | 2019-07-31 | 11.75 | 2 | Brian Le | Completed | 2019-07-15 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 0.17 | 1 |  | Completed | 2019-07-23 | 9.67 | 1 | Andrew Clemons | Completed | 2019-08-06 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-13 | 2.71 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 6.08 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 5 | 1 | Noe Gomez | Completed | 2019-08-08 21:18 |  | 2019-08-08 | 2.25 | 2 | Ara Sotto | Completed | [10 empty] | 2.13 | [11 empty] | 2019-08-02 | 2019-08-08 | FONTANA | Fontana | https://heliotrack.completesolar.com/job.php?action=review&jobID=26812 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26812 | https://completesolar.sugarondemand.com/#Opportunities/4e33210e-a181-11e9-9db2-069e4f790264 | 300 Stars Inc |  | 2019-06-29 | Power Town Solar Electric | 4e33210e-a181-11e9-9db2-069e4f790264 | 2 | 6 | 7 | -2 | 5 | 5 | 5 | 15
27099 | PIP_APPROVED | PIP_APPROVED | 3110 Softwood Court | Lancaster | CA | 93536 | Zachary Kash | 2019-07-13 16:30 | 6618868500 | kashrichard87@gmail.com |  |  |  | 10116 | 0.128 | Bill Angevine | 2019-07-13 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-12 | 2019-07-13 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-08-05 07:00 | 2019-07-17 | 2.33 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 1.13 | 2 | Daniel Speegle | Completed | 2019-07-30 | 7.83 | 1 | Ara Sotto | Completed | 2019-08-06 | 3.92 | 5 | Brian Le | Completed | 2019-07-19 | 1 | 3 | Andrew Moralez | Completed | 2019-07-30 | 6.79 | 1 | Ernesto Enriquez | Completed | 2019-08-06 | 2.63 | 2 | Ara Sotto | Completed | 2019-08-15 | 7.08 | 2 | Ara Sotto | Completed | 2019-07-31 | 8.08 | 2 | Brian Le | Completed | 2019-07-19 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 0.33 | 1 |  | Completed | 2019-07-25 | 4.67 | 1 | Andrew Clemons | Completed | 2019-08-05 | 1.79 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-14 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 21.67 | 2 | Ashley Rockwood | Completed | 2019-09-30 | 10.08 | 2 | Darlynn Lacap | Completed | 2019-09-17 | 0.96 | 1 | Andrew Clemons | Completed | 2019-08-07 22:43 |  | 2019-08-09 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 12.08 | [11 empty] | 2019-07-22 | 2019-08-15 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27099 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27099 | https://completesolar.sugarondemand.com/#Opportunities/0cf90da4-a5c6-11e9-ab47-069e4f790264 | SCES Division |  | 2019-07-12 | JK Solar | 0cf90da4-a5c6-11e9-ab47-069e4f790264 | 3 | 9 | 0 | -2 | 5 | 5 | 5 | 8
27167 | PIP_APPROVED | PIP_APPROVED | 3629 Pumalo Street | Highland | CA | 92346 | Ron Daugherty | 2019-07-26 11:25 | 9517120885 | rondaugherty11@yahoo.com |  |  |  | 11071 | 0.2 | Bill Angevine | 2019-07-22 | 6.405 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-16 | 2019-07-22 15:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-06 07:00 | 2019-07-26 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-29 | 3.79 | 2 | Daniel Speegle | Completed | 2019-08-01 | 2.75 | 1 | Ara Sotto | Completed | 2019-08-06 | 3 | 5 | Brian Le | Completed | 2019-08-01 | 1.96 | 3 | Andrew Moralez | Completed | 2019-08-01 | 0 | 14 | Andrew Moralez | Completed | 2019-08-06 | 0.33 | 2 | Ara Sotto | Completed | 2019-10-08 | 44.33 | 2 | Ara Sotto | Completed | 2019-08-01 | 1.08 | 2 | Brian Le | Completed | 2019-07-31 | 1.83 | 2 | Darlynn Lacap | Completed | 2019-07-30 | 0.79 | 1 |  | Completed | 2019-08-07 | 6.88 | 1 | Andrew Clemons | Completed | 2019-08-06 | 0.46 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-13 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 11 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.96 | 1 | Jeremiah Liend | Completed | 2019-08-07 21:46 |  | 2019-08-07 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 2 | [11 empty] | 2019-08-21 | 2019-10-08 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=27167 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27167 | https://completesolar.sugarondemand.com/#Opportunities/ad9b6920-ace5-11e9-8f6a-069e4f790264 | Gary Stephan | Summit Marketing Inc | 2019-07-16 | Zachary Noah Gamez | ad9b6920-ace5-11e9-8f6a-069e4f790264 | 1 | 63 | 10 | -2 | 5 | 5 | 5 | 18
27210 | PIP_APPROVED | PIP_APPROVED | 43819 Elm Avenue | Lancaster | CA | 93534 | Patsy McGuirk | 2019-07-20 17:43 | 6615445270 | pjmc57@verizon.net |  |  |  | 4352 | 0.144 | Bill Angevine | 2019-07-20 | 2.745 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-18 | 2019-07-20 15:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000A-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-06 07:00 | 2019-07-22 | 0.5 | 2 | Marcia Garay | Completed | 2019-07-24 | 1.88 | 2 | Jethro Andal | Completed | 2019-07-31 | 5.04 | 1 | Ara Sotto | Completed | 2019-08-06 | 3.92 | 5 | Brian Le | Completed | 2019-07-24 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-30 | 0.08 | 1 | Andrew Moralez | Completed | 2019-08-06 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-17 | 8.42 | 2 | Ara Sotto | Completed | 2019-07-31 | 5.08 | 2 | Brian Le | Completed | 2019-07-24 | 0.08 | 2 | Marcia Garay | Completed | 2019-07-24 | 0.21 | 1 |  | Completed | 2019-07-28 | 2.54 | 1 | Andrew Clemons | Completed | 2019-08-16 | 8.38 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-15 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-04 | 12.79 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 11.08 | 2 | Marcia Garay | Completed | 2019-09-11 | 5.25 | 1 | Andrew Clemons | Completed | 2019-08-07 22:44 |  | 2019-08-09 | 3 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-31 | 2019-08-17 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27210 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27210 | https://completesolar.sugarondemand.com/#Opportunities/6c8d0d44-ab50-11e9-902f-069e4f790264 | SCES Division | George Sarkis | 2019-07-17 | JK Solar | 6c8d0d44-ab50-11e9-902f-069e4f790264 | 3 | 11 | 0 | -2 | 5 | 5 | 5 | 8
27271 | PIP_APPROVED | PIP_APPROVED | 12975 Autumnwood Drive | Victorville | CA | 92395 | Florence Scobie | 2019-07-24 08:11 | 9096884719 | f_scobie@sbcglobal.net |  |  |  | 9102.32 | 0.14 | Shaun Labelle | 2019-07-24 | 2.44 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-19 | 2019-07-23 09:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-06 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-06 07:00 | 2019-07-24 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-25 | 1.17 | 2 | Daniel Speegle | Completed | 2019-07-25 | 0.33 | 1 | Ara Sotto | Completed | 2019-08-06 | 3.08 | 5 | Brian Le | Completed | 2019-07-26 | 0.71 | 3 | Andrew Moralez | Completed | 2019-07-31 | 3 | 10 | Andrew Moralez | Completed | 2019-08-06 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-26 | 14.08 | 2 | Ara Sotto | Completed | 2019-08-01 | 2.83 | 2 | Brian Le | Completed | 2019-07-29 | 1.92 | 2 | Marcia Garay | Completed | 2019-07-25 | 0.04 | 1 |  | Completed | 2019-07-31 | 3.67 | 1 | Andrew Clemons | Completed |  | 53.54 | 1 | Marcia Garay | Current | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-12 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-08-13 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 16.08 | 2 | Marcia Garay | Completed |  | 48.17 | 1 | Andrew Clemons | Current | 2019-08-07 22:46 |  | 2019-08-07 | 0.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-09 | 2019-08-26 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=27271 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27271 | https://completesolar.sugarondemand.com/#Opportunities/367545d2-ae25-11e9-a434-02ae981fbade | Christopher Cellini | Shane Montana | 2019-07-19 | JK Solar | 367545d2-ae25-11e9-a434-02ae981fbade | 1 | 20 | 10 | -2 | 5 | 5 | 5 | 18
25514 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3035 Palmer Street | National City | CA | 91950 | Brian Norris | 2019-05-29 15:06 | 6193482320 | roadsidesniper@yahoo.com |  |  |  | 8616 | 0.205 | Ryan Malloy | 2019-05-25 | 5.49 | Christina Horton | UpGrid Inc | Marcia Garay | 2019-05-14 | 2019-05-17 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-08-05 | Installation Complete | SunRun Monthly | 0 | 1 |  |  | 0 | 1 | 2019-08-05 07:00 | 2019-05-29 | 1.38 | 2 | Marcia Garay | Completed | 2019-06-04 | 4 | 2 | Jethro Andal | Completed | 2019-06-05 | 1.25 | 1 | Christina Horton | Completed | 2019-08-02 | 3.8 | 5 | Brian Le | Completed | 2019-06-06 | 1.04 | 3 | Ernesto Enriquez | Completed | 2019-07-17 | 21.16 | 0 | Ernesto Enriquez | Completed | 2019-08-05 | 0.8 | 2 | Christina Horton | Completed |  | 50.08 | 2 | Christina Horton | Current | 2019-07-25 | 5.04 | 2 | Brian Le | Completed | 2019-07-18 | 8.54 | 2 | Marcia Garay | Completed | 2019-06-05 | 0.92 | 1 |  | Completed | 2019-06-10 | 3.67 | 1 | Andrew Clemons | Completed | 2019-08-13 | 6.71 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-10-22 14:15 |  |  | 7.05 | 2 | Christina Horton | Current | 2019-10-11 | 33.22 | 1 | Christina Horton | Completed | 2019-06-05 | 0.63 | 2 | Marcia Garay | Completed | 51.51 | [11 empty] | 2019-07-17 |  | NATIONAL CITY | National City | https://heliotrack.completesolar.com/job.php?action=review&jobID=25514 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25514 | https://completesolar.sugarondemand.com/#Opportunities/c21f7230-7ef8-11e9-adb8-069e4f790264 | UpGrid Inc |  | 2019-05-13 | Greenday Electric Solar | c21f7230-7ef8-11e9-adb8-069e4f790264 | 10 | 77 | -5 | -2 | 5 | 5 | 5 | 3
26304 | PIP_ITEMS_MISSING | PIP_ITEMS_MISSING | 3743 Texas Street | San Diego | CA | 92104 | Kristen Arrivee | 2019-06-13 13:51 | 6198407107 | fleurgal@mac.com | Patrick W Edwards | 6197080864 |  | 3416 | 0.18 | Michael Marlaire | 2019-06-13 | 2.44 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-10 | 2019-06-11 15:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-08-05 | PTO Received | SunRun Monthly | 0 | 0 |  | 1 | 0 | 1 | 2019-08-05 07:00 | 2019-06-13 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-06-15 | 1.33 | 2 | Daniel Speegle | Completed | 2019-07-24 | 26.5 | 1 | Christina Horton | Completed | 2019-10-14 | 65.38 | 5 | Brian Le | Completed | 2019-06-18 | 0 | 3 | Andrew Moralez | Completed | 2019-07-22 | 23 | 15 | Andrew Moralez | Completed | 2019-08-05 | 0.8 | 1 | Christina Horton | Completed |  | 51.08 | 2 | Christina Horton | Current | 2019-07-09 | 14.88 | 2 | Brian Le | Completed | 2019-06-17 | 0.5 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 0.16 | 1 |  | Completed | 2019-06-24 | 5.29 | 1 | Andrew Clemons | Completed | 2019-08-05 | 0.96 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 5.08 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 22.75 | 2 | Ashley Rockwood | Completed | 2019-10-04 | 6.88 | 2 | Darlynn Lacap | Completed | 2019-09-26 | 0.83 | 1 | Noe Gomez | Completed |  | 2019-08-12 | 2019-08-13 | 5.92 | 2 | Christina Horton | Completed | [10 empty] | 7.97 | [11 empty] | 2019-07-10 |  | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26304 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26304 | https://completesolar.sugarondemand.com/#Opportunities/efe89894-8e1c-11e9-bed0-0630baf9dcb8 | Domingo Beddingfield | Lisa Mcdermott | 2019-06-10 | Infinity Energy Inc | efe89894-8e1c-11e9-bed0-0630baf9dcb8 | 8 | 77 | -5 | -2 | 5 | 5 | 5 | 3
26743 | PIP_APPROVED | PIP_APPROVED | 22 Stagecoach Drive | Pomona | CA | 91766 | Anjannet Morgan | 2019-07-12 10:13 | 9097189210 | anjannetmorgan@gmail.com | Anjannet Morgan | 909-967-0623 | klevonmorgan2002@yahoo.com | 10547 | 0 | Alex Holdridge | 2019-06-28 | 6.1 | Ara Sotto | Solar Power Marketing | Darlynn Lacap | 2019-06-26 | 2019-06-27 15:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-08-05 | PTO Received | Sunlight Financial Loan |  | 0 |  |  |  |  | 2019-08-05 07:00 | 2019-07-12 | 0.96 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 4.67 | 2 | Daniel Speegle | Completed | 2019-07-25 | 5.5 | 1 | Ara Sotto | Completed | 2019-08-05 | 2.96 | 5 | Brian Le | Completed | 2019-07-19 | 0.79 | 3 | Ernesto Enriquez | Completed | 2019-08-01 | 8.75 | 0 | Ernesto Enriquez | Completed | 2019-08-05 | 0.42 | 2 | Ara Sotto | Completed | 2019-08-14 | 7 | 2 | Ara Sotto | Completed | 2019-07-31 | 8.04 | 2 | Brian Le | Completed | 2019-07-19 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 0.38 | 1 |  | Completed | 2019-07-22 | 1.62 | 1 | Andrew Clemons | Completed | 2019-08-05 | 0.54 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-28 | 13.33 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 5.21 | 2 | Ashley Rockwood | Completed | 2019-09-06 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-09-10 | 2.83 | 1 | Andrew Clemons | Completed | 2019-08-07 21:49 |  | 2019-08-08 | 3.33 | 2 | Ara Sotto | Completed | [10 empty] | 11.46 | [11 empty] | 2019-07-19 | 2019-08-08 | POMONA | Pomona | https://heliotrack.completesolar.com/job.php?action=review&jobID=26743 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26743 | https://completesolar.sugarondemand.com/#Opportunities/5e894440-99cd-11e9-93a4-022c40d974e6 | Solar Power Marketing |  | 2019-06-26 | Zachary Noah Gamez | 5e894440-99cd-11e9-93a4-022c40d974e6 | 3 | 9 | 0 | -2 | 5 | 5 | 5 | 8
26795 | PIP_APPROVED | PIP_APPROVED | 4185 Thomas Street | Oceanside | CA | 92056 | Terry Mayer | 2019-07-11 09:38 | 7604190166 | Tmtkmayer@cox.net |  |  |  | 6594 | 0.18 | Michael Marlaire | 2019-07-11 | 3.965 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-07-02 | 2019-07-06 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-05 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-05 07:00 | 2019-07-12 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 2.04 | 2 | Jethro Andal | Completed | 2019-07-26 | 7.83 | 1 | Christina Horton | Completed | 2019-08-05 | 5.83 | 5 | Brian Le | Completed | 2019-07-18 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-18 | 0 | 10 | Ernesto Enriquez | Completed | 2019-08-05 | 0.38 | 1 | Christina Horton | Completed | 2019-08-12 | 3.01 | 2 | Christina Horton | Completed | 2019-07-23 | 2.17 | 2 | Brian Le | Completed | 2019-07-19 | 2.71 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 1.96 | 1 |  | Completed | 2019-07-25 | 6.54 | 1 | Andrew Clemons | Completed | 2019-08-05 | 0.54 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-15 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 2.75 | 2 | Ashley Rockwood | Completed |  | 43.33 | 2 | Darlynn Lacap | Current | 2019-08-22 | 2.33 | 1 | Jeremiah Liend | Completed | 2019-08-12 14:23 |  | 2019-08-12 | 4.96 | 2 | Christina Horton | Completed | [10 empty] | 27.92 | [11 empty] | 2019-08-01 | 2019-08-12 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26795 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26795 | https://completesolar.sugarondemand.com/#Opportunities/2b596f5a-a3fa-11e9-8554-0630baf9dcb8 | Xavier Kimbrough |  | 2019-06-28 | Infinity Energy Inc | 2b596f5a-a3fa-11e9-8554-0630baf9dcb8 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26900 | PIP_APPROVED | PIP_APPROVED | 903 Diamond Drive | Chula Vista | CA | 91911 | Kiyoko Johnson | 2019-07-05 12:35 | 9169957871 | katjomail@aol.com |  |  |  | 4608 | 0.185 | Chad Malloy | 2019-07-05 | 3.05 |  | UpGrid Inc | Marcia Garay | 2019-07-03 | 2019-07-05 09:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-08-05 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-05 07:00 | 2019-07-05 | 0 | 2 | Marcia Garay | Completed | 2019-07-09 | 1.88 | 2 | Jethro Andal | Completed | 2019-07-24 | 11.04 | 1 | Christina Horton | Completed | 2019-08-05 | 2.88 | 5 | Brian Le | Completed | 2019-07-10 | 1.13 | 3 | Ernesto Enriquez | Completed | 2019-07-24 | 9.67 | 7 | Ernesto Enriquez | Completed | 2019-08-05 | 0.38 | 1 | Christina Horton | Completed | 2019-08-14 | 7.21 | 2 | Christina Horton | Completed | 2019-07-31 | 14 | 2 | Brian Le | Completed | 2019-07-11 | 2.13 | 2 | Marcia Garay | Completed | 2019-07-09 | 0.17 | 1 |  | Completed | 2019-07-15 | 4.13 | 1 | Andrew Clemons | Completed |  | 54.54 | 1 | Marcia Garay | Current | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-04 | 1.96 | 2 | Ashley Rockwood | Completed |  | 10.83 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-20 13:47 |  | 2019-08-20 | 11.04 | 2 | Christina Horton | Completed | [10 empty] | 41.97 | [11 empty] | 2019-07-19 | 2019-08-13 | CHULA VISTA | Chula Vista | https://heliotrack.completesolar.com/job.php?action=review&jobID=26900 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26900 | https://completesolar.sugarondemand.com/#Opportunities/fcb15c6e-9f5b-11e9-890a-02ae981fbade | Josh Gonzales |  | 2019-07-03 | iEnergy ElectricSolar | fcb15c6e-9f5b-11e9-890a-02ae981fbade | 15 | 9 | -15 | -2 | 5 | 5 | 5 | -7
27201 | PIP_APPROVED | PIP_APPROVED | 34358 Auberry Road | Auberry | CA | 93602 | Frances E Ward | 2019-07-18 14:37 | 5598558537 | mynoondayk@gmail.com | Kristy Smithson | 5592701838 | kristy_smithson@yahoo.com | 11194 | 0.15 | Abraham SiteTech Vazquez | 2019-07-18 | 8.54 | Christina Horton | Sunmatter Inc | Marcia Garay | 2019-07-17 | 2019-07-18 09:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-05 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-05 07:00 | 2019-07-23 | 3 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-26 | 2.83 | 1 | Christina Horton | Completed | 2019-08-05 | 2.88 | 5 | Brian Le | Completed | 2019-07-24 | 0.96 | 3 | Ernesto Enriquez | Completed | 2019-07-26 | 1.83 | 0 | Ernesto Enriquez | Completed | 2019-08-05 | 0.54 | 2 | Christina Horton | Completed | 2019-09-23 | 32 | 2 | Christina Horton | Completed | 2019-07-31 | 2.13 | 2 | Brian Le | Completed | 2019-07-29 | 3.88 | 2 | Marcia Garay | Completed | 2019-07-23 | 0.08 | 1 |  | Completed | 2019-07-26 | 2.92 | 1 | Andrew Clemons | Completed | 2019-09-17 | 30.42 | 1 | Marcia Garay | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-04 | 14 | 2 | Ashley Rockwood | Completed |  | 28.96 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive | 2019-08-07 14:58 |  | 2019-08-07 | 1.79 | 2 | Christina Horton | Completed | [10 empty] | 12.05 | [11 empty] | 2019-07-24 | 2019-09-23 | AUBERRY | Auberry | https://heliotrack.completesolar.com/job.php?action=review&jobID=27201 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27201 | https://completesolar.sugarondemand.com/#Opportunities/19c35080-a9a4-11e9-8796-0630baf9dcb8 | Sunmatter Inc |  | 2019-07-17 | Peak Energy Electric | 19c35080-a9a4-11e9-8796-0630baf9dcb8 | 2 | 49 | 7 | -2 | 5 | 5 | 5 | 15
25135 | PIP_APPROVED | PIP_APPROVED | 20201 Nicholas Road | Clovis | CA | 93619 | Miguel Sanchez | 2019-07-08 08:45 | 5592846585 | lacey.sanchez@sbcglobal.net | Lacey Sanchez | 5592846585 | lsanchez@fresnofamilylaw.com | 11580.8 |  | Abraham SiteTech Vazquez | 2019-05-20 | 7.32 | Christina Horton | Sunmatter Inc | Darlynn Lacap | 2019-05-17 | 2019-05-20 17:00 | Q.PEAK-G4.1 305 | 305 | 24 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-08-02 | PTO Received | Cash |  | 0 |  |  | 0 |  | 2019-08-02 07:00 | 2019-07-08 | 0.46 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 3.96 | 2 | Jethro Andal | Completed | 2019-07-16 | 9.88 | 1 | Christina Horton | Completed | 2019-08-02 | 16.13 | 5 | Ara Sotto | Completed | 2019-07-10 | 3.13 | 3 | Andrew Moralez | Completed | 2019-07-26 | 27.79 | 0 | Ernesto Enriquez | Completed | 2019-08-02 | 1.25 | 2 | Christina Horton | Completed | 2019-08-06 | 2 | 2 | Christina Horton | Completed | 2019-07-17 | 12.42 | 2 | Brian Le | Completed | 2019-07-08 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 0.75 | 1 |  | Completed | 2019-07-23 | 10.62 | 1 | Andrew Clemons | Completed | 2019-08-05 | 2.46 | 1 | Darlynn Lacap | Completed |  | 52.04 | 2 | Jill Allen | Current | [15 empty] | 2019-08-08 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-10-16 | 23.75 | 2 | Ashley Rockwood | Completed | 2019-10-17 | 1.04 | 2 | Darlynn Lacap | Completed |  | 3.29 | 1 | Andrew Clemons | Current | 2019-08-06 09:35 |  | 2019-08-07 | 3 | 2 | Christina Horton | Completed | [10 empty] | 53.8 | [11 empty] | 2019-07-10 | 2019-08-05 | CLOVIS | Clovis | https://heliotrack.completesolar.com/job.php?action=review&jobID=25135 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25135 | https://completesolar.sugarondemand.com/#Opportunities/538f7afa-7bcd-11e9-a787-022c40d974e6 | Russ Smithson | Sunmatter Inc | 2019-04-29 | Peak Energy Electric | 538f7afa-7bcd-11e9-a787-022c40d974e6 | 5 | 4 | -5 | 0 | 5 | 5 | 5 | 5
25674 | PIP_APPROVED | PIP_APPROVED | 9318 Van Andel Way | Santee | CA | 92071 | Lance Rawlings | 2019-06-07 16:09 | 6199951376 | lance.g.rawlings@gmail.com | Terrie kohler | 6199951159 |  | 8331 | 0.197 | Chad Malloy | 2019-06-07 | 4.88 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-20 | 2019-05-24 15:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-08-02 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-02 07:00 | 2019-06-07 | 0 | 2 | Darlynn Lacap | Completed | 2019-06-17 | 2.96 | 2 | Daniel Speegle | Completed | 2019-07-24 | 25.83 | 1 | Christina Horton | Completed | 2019-08-02 | 16.71 | 5 | Brian Le | Completed | 2019-06-25 | 4.08 | 3 | Ernesto Enriquez | Completed | 2019-07-23 | 19.25 | 10 | Andrew Moralez | Completed | 2019-08-02 | 0.46 | 1 | Christina Horton | Completed | 2019-08-05 | 1.13 | 2 | Christina Horton | Completed | 2019-07-09 | 13.67 | 2 | Brian Le | Completed | 2019-06-18 | 1.17 | 2 | Darlynn Lacap | Completed | 2019-06-17 | 0.08 | 1 |  | Completed | 2019-07-16 | 19.92 | 1 | Andrew Clemons | Completed | 2019-08-05 | 0.59 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 2.5 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-07 | 2 | 2 | Ashley Rockwood | Completed | 2019-08-07 | 0 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 15.96 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 0.71 | 1 | Andrew Clemons | Completed | 2019-08-05 08:58 |  | 2019-08-05 | 0.88 | 2 | Christina Horton | Completed | 2019-07-10 | 0.08 | 1 | Christina Horton | Completed | 2019-06-18 | 0.79 | 2 | Darlynn Lacap | Completed | 16.8 | [11 empty] | 2019-07-10 | 2019-08-05 | SANTEE | Santee | https://heliotrack.completesolar.com/job.php?action=review&jobID=25674 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25674 | https://completesolar.sugarondemand.com/#Opportunities/49979aa0-8979-11e9-894a-0630baf9dcb8 | Roofing 101 | Graham Dessert | 2019-05-16 | Infinity Energy Inc | 49979aa0-8979-11e9-894a-0630baf9dcb8 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26629 | PIP_APPROVED | PIP_APPROVED | 852 Hurstland Avenue | Beaumont | CA | 92223 | Paulino Santoyo | 2019-06-26 13:28 | 9098000521 | jnsautorepair@gmail.com | Anna Montiel | 909-528-5671 |  | 15648 | 0.207 | Alex Holdridge | 2019-06-26 | 8.845 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-22 | 2019-06-26 09:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | MPU | 2019-08-02 | PTO Received | SunRun Monthly |  | 0 |  |  |  |  | 2019-08-01 07:00 | 2019-07-01 | 2.83 | 2 | Marcia Garay | Completed | 2019-07-10 | 4.71 | 2 | Jethro Andal | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-02 | 6.92 | 5 | Brian Le | Completed | 2019-07-11 | 0.79 | 3 | Ernesto Enriquez | Completed | 2019-07-23 | 8.13 | 10 | Andrew Moralez | Completed | 2019-08-02 | 1.33 | 2 | Ara Sotto | Completed | 2019-08-05 | 1.29 | 2 | Ara Sotto | Completed | 2019-07-24 | 9.96 | 2 | Brian Le | Completed | 2019-07-10 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-10 | 0.17 | 1 |  | Completed | 2019-07-15 | 2.88 | 1 | Jill Allen | Completed | 2019-08-06 | 3.5 | 1 | Marcia Garay | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-13 | 2.71 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 6.04 | 2 | Marcia Garay | Completed | 2019-08-21 | 4.96 | 1 | Jeremiah Liend | Completed | 2019-08-08 16:18 | 2019-08-05 | 2019-08-08 | 4.42 | 2 | Ara Sotto | Completed | 2019-08-02 | 0.75 | 1 | Ara Sotto | Completed | 2019-07-17 | 5.04 | 2 | Marcia Garay | Completed | 9.33 | [11 empty] | 2019-07-25 | 2019-08-05 | BEAUMONT | Beaumont | https://heliotrack.completesolar.com/job.php?action=review&jobID=26629 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26629 | https://completesolar.sugarondemand.com/#Opportunities/d1ea0ea2-9850-11e9-84e5-02ae981fbade | Summit Marketing Inc | Tiburon Mike Weber | 2019-06-22 | Power Town Solar Electric | d1ea0ea2-9850-11e9-84e5-02ae981fbade | 6 | 3 | -5 | 2 | 5 | 5 | 5 | 7
26929 | PIP_APPROVED | PIP_APPROVED | 40524 Colina Court | Palmdale | CA | 93551 | Sean Wolf | 2019-07-06 14:07 | 6613171770 | sean_m_wolf@yahoo.com | Amanda Matt | 805-444-4451 |  | 8867 | 0.146 | Shaun Labelle | 2019-07-06 | 4.88 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-05 | 2019-07-06 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM |  | NO | 2019-08-02 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-31 07:00 | 2019-07-09 | 1.67 | 2 | Darlynn Lacap | Completed | 2019-07-11 | 2.17 | 2 | Daniel Speegle | Completed | 2019-07-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-01 | 4.17 | 5 | Brian Le | Completed | 2019-07-23 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-25 | 0.04 | 0 | Andrew Moralez | Completed | 2019-08-02 | 2.29 | 1 | Ara Sotto | Completed | 2019-08-12 | 6.42 | 2 | Ara Sotto | Completed | 2019-07-26 | 4.67 | 2 | Brian Le | Completed | 2019-07-19 | 2 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 5.5 | 1 |  | Completed | 2019-07-19 | 5.46 | 1 | Andrew Clemons | Completed | 2019-08-01 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-13 | 2.67 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.92 | 1 | Andrew Clemons | Completed | 2019-08-08 15:24 | 2019-08-06 | 2019-08-08 | 4.54 | 2 | Ara Sotto | Completed | [10 empty] | 14.87 | [11 empty] | 2019-07-25 | 2019-08-09 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26929 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26929 | https://completesolar.sugarondemand.com/#Opportunities/0887120a-a032-11e9-839f-0630baf9dcb8 | Emily Bowden | Kevin Adams | 2019-07-05 | JK Solar | 0887120a-a032-11e9-839f-0630baf9dcb8 | 6 | 10 | -5 | -2 | 5 | 5 | 5 | 3
26966 | PIP_APPROVED | PIP_APPROVED | 644 West Morgan Street | Rialto | CA | 92376 | Guadalupe Zamora | 2019-07-09 16:39 | 9092658583 | guadalupe.nava0824@gmail.com | Marco Nava | 9092652746 |  | 7411 | 0.158 | Michael Marlaire | 2019-07-09 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-08 | 2019-07-09 12:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-02 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-08-02 07:00 | 2019-07-11 | 1.75 | 2 | Marcia Garay | Completed | 2019-07-16 | 3.17 | 2 | Jethro Andal | Completed | 2019-07-10 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-02 | 5.08 | 5 | Brian Le | Completed | 2019-07-18 | 1.17 | 3 | Andrew Moralez | Completed | 2019-07-29 | 6.58 | 7 | Andrew Moralez | Completed | 2019-08-02 | 0.5 | 1 | Ara Sotto | Completed | 2019-08-06 | 2.13 | 2 | Ara Sotto | Completed | 2019-07-26 | 4.83 | 2 | Brian Le | Completed | 2019-07-19 | 2.84 | 2 | Marcia Garay | Completed | 2019-07-17 | 0.96 | 1 |  | Completed | 2019-07-23 | 4.67 | 1 | Andrew Clemons | Completed | 2019-08-16 | 10.67 | 1 | Marcia Garay | Completed | 2019-08-09 | 3 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-11 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-09-18 | 4.75 | 2 | Ashley Rockwood | Completed |  | 23.33 | 2 | Marcia Garay | Current | 2019-09-19 | 1 | 1 | Jill Allen | Completed | 2019-08-06 15:24 |  | 2019-08-20 | 12 | 2 | Ara Sotto | Completed | [10 empty] | 14.83 | [11 empty] | 2019-07-29 | 2019-08-06 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26966 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26966 | https://completesolar.sugarondemand.com/#Opportunities/bb8b3878-a2a2-11e9-90c2-02ae981fbade | Oscar Hernandez |  | 2019-07-08 | Power Town Solar Electric | bb8b3878-a2a2-11e9-90c2-02ae981fbade | 18 | 4 | -15 | 0 | 5 | 5 | 5 | -5
27054 | PIP_APPROVED | PIP_APPROVED | 26571 Sun City Boulevard | Menifee | CA | 92586 | Delores Murray | 2019-07-12 12:35 | 7608355527 | havamurray@gmail.com | Michael Prawn | 9518670996 |  | 6993 | 0.152 | Michael Marlaire | 2019-07-12 | 3.965 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-11 | 2019-07-12 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | MPU | 2019-08-02 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-02 07:00 | 2019-07-12 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 1.96 | 2 | Jethro Andal | Completed | 2019-07-12 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-02 | 3.96 | 5 | Brian Le | Completed | 2019-07-29 | 7 | 3 | Ernesto Enriquez | Completed | 2019-07-30 | 0.92 | 0 | Ernesto Enriquez | Completed | 2019-08-02 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-26 | 15.79 | 2 | Ara Sotto | Completed | 2019-07-29 | 7.76 | 2 | Brian Le | Completed | 2019-07-16 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 0.91 | 1 |  | Completed | 2019-07-25 | 5.58 | 1 | Andrew Clemons | Completed | 2019-08-05 | 1.54 | 1 | Darlynn Lacap | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-28 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-08-29 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-09-05 | 0.08 | 2 | Delvin Villavicencio | Completed |  | 0 | 1 |  | Inactive | 2019-08-23 13:52 |  | 2019-08-23 | 0.08 | 2 | Ara Sotto | Completed |  | 51.75 | 1 | Ara Sotto | Current | 2019-07-18 | 1 | 2 | Darlynn Lacap | Completed | 1.83 | [11 empty] | 2019-07-29 | 2019-08-26 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=27054 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27054 | https://completesolar.sugarondemand.com/#Opportunities/1eb1cf9e-a4dc-11e9-872f-069e4f790264 | PHNX Power |  | 2019-07-11 | Green Road Solar Crew | 1eb1cf9e-a4dc-11e9-872f-069e4f790264 | 21 | 24 | -25 | -2 | 5 | 5 | 5 | -17
27265 | PIP_APPROVED | PIP_APPROVED | 12462 Rosey Road | El Cajon | CA | 92021 | Bradley Clark | 2019-07-22 11:11 | 6194438842 | califbckc@cox.net |  |  |  | 9201 | 0.169 | Ryan Malloy | 2019-07-22 | 5.49 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-07-19 | 2019-07-22 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar |  |  | Composite | NO | 2019-08-02 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-08-02 07:00 | 2019-07-22 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-25 | 2.92 | 2 | Jethro Andal | Completed | 2019-07-25 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-02 | 4 | 5 | Brian Le | Completed | 2019-07-25 | 0 | 3 | Andrew Moralez | Completed | 2019-07-25 | 0.13 | 0 | Andrew Moralez | Completed | 2019-08-02 | 0.33 | 2 | Ara Sotto | Completed | 2019-08-05 | 1.21 | 2 | Ara Sotto | Completed | 2019-07-26 | 0.08 | 2 | Brian Le | Completed | 2019-07-29 | 2 | 2 | Marcia Garay | Completed | 2019-07-25 | 0 | 1 |  | Completed | 2019-07-26 | 1.04 | 1 | Andrew Clemons | Completed |  | 55.54 | 1 | Marcia Garay | Current | 2019-08-08 | 2.5 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-12 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-09-17 | 22.92 | 2 | Marcia Garay | Completed | 2019-08-21 | 4.88 | 1 | Andrew Clemons | Completed | 2019-08-05 12:33 |  | 2019-08-06 | 2 | 2 | Ara Sotto | Completed | [10 empty] | 26.13 | [11 empty] | 2019-07-25 | 2019-08-05 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=27265 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27265 | https://completesolar.sugarondemand.com/#Opportunities/ff2c23ea-acab-11e9-82f1-069e4f790264 | Mario Washington |  | 2019-07-19 | Blalock Electric&Solar | ff2c23ea-acab-11e9-82f1-069e4f790264 | 4 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26299 | PIP_APPROVED | PIP_APPROVED | 37469 Bristol Court | Palmdale | CA | 93550 | Luis Reyes | 2019-06-17 16:32 | 6618604026 | daiseyreyes_7_2002@hotmail.com | Daisey Reyes | 8053548043 |  | 9251 | 0.119 | Shaun Labelle | 2019-06-11 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-10 | 2019-06-11 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar |  |  | Tile Concrete | NO | 2019-08-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-30 07:00 | 2019-06-17 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-06-18 | 3.34 | 2 | Daniel Speegle | Completed | 2019-07-17 | 20.42 | 1 | Ara Sotto | Completed | 2019-08-01 | 4.17 | 5 | Brian Le | Completed | 2019-07-08 | 12.29 | 3 | Andrew Moralez | Completed | 2019-07-25 | 12.96 | 0 | Andrew Moralez | Completed | 2019-08-01 | 6.59 | 2 | Ara Sotto | Completed | 2019-08-19 | 11.88 | 2 | Ara Sotto | Completed | 2019-07-26 | 26.71 | 2 | Brian Le | Completed | 2019-06-17 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 1.17 | 1 |  | Completed | 2019-06-28 | 8.59 | 1 | Andrew Clemons | Completed | 2019-07-30 | 3.8 | 1 | Darlynn Lacap | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-16 | 5.92 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 8.17 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 3.33 | 1 | Jill Allen | Completed | 2019-08-09 22:56 |  | 2019-08-09 | 4.92 | 2 | Ara Sotto | Completed | [10 empty] | 9.5 | [11 empty] | 2019-07-08 | 2019-08-19 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26299 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26299 | https://completesolar.sugarondemand.com/#Opportunities/e6855090-8c9a-11e9-b423-022c40d974e6 | CUIC Inc | Henry Garcia | 2019-06-10 | JK Solar | e6855090-8c9a-11e9-b423-022c40d974e6 | 8 | 18 | -5 | -2 | 5 | 5 | 5 | 3
26459 | PIP_APPROVED | PIP_APPROVED | 5537 Alleghany Street | San Diego | CA | 92139 | Myrna Aragon | 2019-06-20 18:42 | 7606539226 | myrnaaragon45@gmail.com |  |  |  | 8376 | 0.21 | Chad Malloy | 2019-06-20 | 5.185 | Christina Horton | UpGrid Inc | Darlynn Lacap | 2019-06-18 | 2019-06-20 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-01 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-08-01 07:00 | 2019-07-02 | 2.75 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 0.79 | 2 | Jethro Andal | Completed | 2019-07-24 | 12.67 | 1 | Christina Horton | Completed | 2019-07-31 | 0.25 | 5 | Brian Le | Completed | 2019-07-22 | 2.17 | 3 | Ernesto Enriquez | Completed | 2019-07-22 | 0 | 15 | Ernesto Enriquez | Completed | 2019-08-01 | 1.42 | 2 | Christina Horton | Completed | 2019-08-19 | 11.83 | 2 | Christina Horton | Completed | 2019-07-25 | 5.75 | 2 | Brian Le | Completed | 2019-07-17 | 2.21 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 8.63 | 1 |  | Completed | 2019-07-09 | 2.83 | 1 | Andrew Clemons | Completed | 2019-08-01 | 1.55 | 1 | Darlynn Lacap | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 12.92 | 2 | Ashley Rockwood | Completed |  | 30.17 | 2 | Darlynn Lacap | Current | 2019-09-11 | 2 | 1 | Jill Allen | Completed |  | 2019-08-16 | 2019-08-15 | 6.92 | 2 | Christina Horton | Completed | [10 empty] | 28.72 | [11 empty] | 2019-08-12 | 2019-08-19 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26459 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26459 | https://completesolar.sugarondemand.com/#Opportunities/c9d4298a-93c5-11e9-a0b9-02ae981fbade | UpGrid Inc |  | 2019-06-17 | Greenday Electric Solar | c9d4298a-93c5-11e9-a0b9-02ae981fbade | 14 | 18 | -15 | -2 | 5 | 5 | 5 | -7
26616 | SP APPROVED |  | 519 Heyer Street | Lancaster | CA | 93534 | Anthony Trama | 2019-06-24 15:00 | 6613906446 | tramabills@aol.com | Susan Trama |  |  | 12015 | 0.14 | Bill Angevine | 2019-06-24 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-22 | 2019-06-24 15:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | MPU | 2019-08-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-01 12:00 | 2019-06-25 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-06-27 | 2.04 | 2 | Daniel Speegle | Completed | 2019-07-25 | 19 | 1 | Ara Sotto | Completed | 2019-08-01 | 2 | 5 | Brian Le | Completed | 2019-06-28 | 0 | 3 | Andrew Moralez | Completed | 2019-07-30 | 20.5 | 1 | Andrew Moralez | Completed | 2019-08-01 | 9.8 | 2 | Ara Sotto | Completed |  | 56.08 | 2 | Ara Sotto | Current | 2019-07-25 | 17.96 | 2 | Brian Le | Completed | 2019-06-28 | 1 | 2 | Darlynn Lacap | Completed | 2019-06-28 | 1.33 | 1 |  | Completed | 2019-07-03 | 3.96 | 1 | Andrew Clemons | Completed | 2019-08-01 | 1.12 | 1 | Darlynn Lacap | Completed | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-30 | 2.79 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 3.17 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 7.08 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 4.04 | 1 | Andrew Clemons | Completed | 2019-08-27 14:05 |  | 2019-08-27 | 16.96 | 2 | Ara Sotto | Completed | 2019-08-02 | 10.8 | 1 | Ara Sotto | Completed | 2019-07-03 | 3.75 | 2 | Darlynn Lacap | Completed | 20.49 | [11 empty] | 2019-07-01 |  | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26616 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26616 | https://completesolar.sugarondemand.com/#Opportunities/61e9f698-96cb-11e9-9e86-02ae981fbade | SCES Division |  | 2019-06-22 | JK Solar | 61e9f698-96cb-11e9-9e86-02ae981fbade | 25 | 81 | -25 | -2 | 5 | 5 | 5 | -17
26672 | PIP_APPROVED | PIP_APPROVED | 29222 Via San Sebastian | Laguna Niguel | CA | 92677 | David Murtaugh | 2019-06-28 15:57 | 9492906109 | tazmurtaugh7@gmail.com |  | 9494953335 |  | 6537 | 0.19 | Chris Peaslee | 2019-06-28 | 4.27 | Christina Horton | PHNX Power | Darlynn Lacap | 2019-06-24 | 2019-06-27 09:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-08-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-08-01 07:00 | 2019-07-01 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 3.04 | 2 | Daniel Speegle | Completed | 2019-07-10 | 2.79 | 1 | Christina Horton | Completed | 2019-08-01 | 0.08 | 5 | Brian Le | Completed | 2019-07-09 | 1.79 | 3 | Andrew Moralez | Completed | 2019-07-24 | 11.04 | 5 | Andrew Moralez | Completed | 2019-08-01 | 0.71 | 1 | Christina Horton | Completed | 2019-08-12 | 7.08 | 2 | Christina Horton | Completed | 2019-07-26 | 14.58 | 2 | Brian Le | Completed | 2019-07-05 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 0.04 | 1 |  | Completed | 2019-07-09 | 1.83 | 1 | Jill Allen | Completed | 2019-08-01 | 0.91 | 1 | Darlynn Lacap | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-09 | 3.88 | 2 | Ashley Rockwood | Completed | 2019-08-13 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 3.96 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 1.96 | 1 | Andrew Clemons | Completed | 2019-08-05 14:08 |  | 2019-08-05 | 2.04 | 2 | Christina Horton | Completed | [10 empty] | 13.97 | [11 empty] | 2019-07-16 | 2019-08-09 | LAGUNA NIGUEL | Laguna Niguel | https://heliotrack.completesolar.com/job.php?action=review&jobID=26672 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26672 | https://completesolar.sugarondemand.com/#Opportunities/f890f860-99f7-11e9-bc4a-069e4f790264 | Peyton Bennett | Bryan Rosenvall | 2019-06-24 | T.A.K. Electric | f890f860-99f7-11e9-bc4a-069e4f790264 | 4 | 11 | 0 | -2 | 5 | 5 | 5 | 8
26868 | PIP_APPROVED | PIP_APPROVED | 14856 Galen Court | Hesperia | CA | 92345 | Maurice Baker | 2019-07-05 12:11 | 3106256756 | bmfracing565@yahoo.com | Chris Baker | 3106253642 |  | 7676 | 0.14 | Shaun Labelle | 2019-07-05 | 3.965 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-02 | 2019-07-05 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-08-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-31 07:00 | 2019-07-08 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-11 | 2.83 | 2 | Jethro Andal | Completed | 2019-07-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-08-01 | 4.08 | 5 | Brian Le | Completed | 2019-07-26 | 10.67 | 3 | Andrew Moralez | Completed | 2019-07-26 | 0 | 14 | Ernesto Enriquez | Completed | 2019-08-01 | 1.33 | 1 | Ara Sotto | Completed | 2019-08-05 | 2.33 | 2 | Ara Sotto | Completed | 2019-07-26 | 10.88 | 2 | Brian Le | Completed | 2019-07-11 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-11 | 0.21 | 1 |  | Completed | 2019-07-29 | 12 | 1 | Andrew Clemons | Completed | 2019-10-15 | 53.46 | 1 | Marcia Garay | Completed | 2019-08-02 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-08 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 0.75 | 2 | Ashley Rockwood | Completed |  | 50.33 | 2 | Marcia Garay | Current | 2019-08-15 | 4.29 | 1 | Andrew Clemons | Completed | 2019-08-02 16:15 |  | 2019-08-02 | 1.04 | 2 | Ara Sotto | Completed | [10 empty] | 34.04 | [11 empty] | 2019-08-15 | 2019-08-05 | HESPERIA | Hesperia | https://heliotrack.completesolar.com/job.php?action=review&jobID=26868 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26868 | https://completesolar.sugarondemand.com/#Opportunities/9222d3c6-9f58-11e9-8de7-0630baf9dcb8 | SCES Division |  | 2019-07-02 | HDM Electric Inc | 9222d3c6-9f58-11e9-8de7-0630baf9dcb8 | 1 | 4 | 10 | 0 | 5 | 5 | 5 | 20
27036 | PIP_APPROVED | PIP_APPROVED | 43354 Fanchon Avenue | Lancaster | CA | 93536 | Daniel Oswalt | 2019-07-11 14:52 | 8186449784 | melodyanna4@gmail.com | Melody Oswalt |  | deoswalt@live.com | 11023 | 0.137 | Bill Angevine | 2019-07-11 | 5.795 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-10 | 2019-07-11 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-08-01 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-30 | 2019-07-16 | 2.92 | 2 | Marcia Garay | Completed | 2019-07-18 | 2.25 | 2 | Jethro Andal | Completed | 2019-07-26 | 5.5 | 1 | Ara Sotto | Completed | 2019-08-01 | 4.08 | 5 | Brian Le | Completed | 2019-07-19 | 0.21 | 3 | Andrew Moralez | Completed | 2019-07-26 | 4.46 | 1 | Andrew Moralez | Completed | 2019-08-01 | 2.33 | 2 | Ara Sotto | Completed | 2019-08-16 | 11.04 | 2 | Ara Sotto | Completed | 2019-07-26 | 4.92 | 2 | Brian Le | Completed | 2019-07-19 | 0.67 | 2 | Marcia Garay | Completed | 2019-07-19 | 0.79 | 1 |  | Completed | 2019-07-25 | 4.38 | 1 | Jill Allen | Completed |  | 58.54 | 1 | Marcia Garay | Current | 2019-08-08 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-15 | 10.08 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 0.67 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 9.21 | 2 | Marcia Garay | Completed | 2019-08-21 | 3 | 1 | Andrew Clemons | Completed | 2019-08-01 16:37 | 2019-07-31 | 2019-08-01 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 3.42 | [11 empty] | 2019-07-22 | 2019-08-16 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27036 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27036 | https://completesolar.sugarondemand.com/#Opportunities/26b77984-a426-11e9-9eff-0630baf9dcb8 | SCES Division | Cody Booth | 2019-07-10 | JK Solar | 26b77984-a426-11e9-9eff-0630baf9dcb8 | 0 | 15 | 10 | -2 | 5 | 5 | 5 | 18
20564 | PIP_APPROVED | PIP_APPROVED | 12 Granger Road | Westborough | MA | 1581 | Oleksandr Sverlov | 2019-03-14 14:16 | 5089047274 | sverlov@gmail.com |  |  |  | 7866 | 0.142 |  | 2018-12-21 | 7.32 | Christina Horton | Aten Concepts | Darlynn Lacap | 2018-12-18 | 2018-12-20 09:00 | Q.PEAK-G4.1 305 | 305 | 24 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-07-31 | NEM Submitted | SunRun Monthly | 0 |  |  | 0 |  |  | 2019-07-30 07:00 | 2019-03-14 | 1 | 2 | Darlynn Lacap | Completed | 2019-03-15 | 1.71 | 2 | Daniel Speegle | Completed | 2019-03-18 | 20.26 | 1 | Ara Sotto | Completed | 2019-07-30 | 36.29 | 5 | Christina Horton | Completed | 2019-03-15 | 12.92 | 3 | Ernesto Enriquez | Completed | 2019-05-15 | 47 | 10 | Ernesto Enriquez | Completed | 2019-07-31 | 1.55 | 2 | Christina Horton | Completed | 2019-08-08 | 6.08 | 2 | Christina Horton | Completed | 2019-06-21 | 59.71 | 2 | Brian Le | Completed | 2019-03-18 | 4.09 | 2 | Darlynn Lacap | Completed | 2019-03-15 | 2.26 | 1 |  | Completed | 2019-05-30 | 59.18 | 1 | Jill Allen | Completed | 2019-07-30 | 0.76 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-14 | 1.21 | 2 | Ashley Rockwood | Completed |  | 47.17 | 2 | Ashley Rockwood | Current |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  | 2019-08-23 | 2019-08-07 | 1.08 | 2 | Christina Horton | Completed | [10 empty] | 58.42 | [11 empty] | 2019-03-23 | 2019-08-08 | Default | Westborough | https://heliotrack.completesolar.com/job.php?action=review&jobID=20564 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=20564 | https://completesolar.sugarondemand.com/#Opportunities/d0eb4ec6-0557-11e9-878a-02ae981fbade | Aten Concepts |  | 2018-11-08 | Skyline Solar | d0eb4ec6-0557-11e9-878a-02ae981fbade | 7 | 8 | -5 | -2 | 5 | 5 | 5 | 3
24369 | PIP_APPROVED | PIP_APPROVED | 1621 West Avenue K 10 | Lancaster | CA | 93534 | Michael Jensen | 2019-07-04 23:24 | 6613171174 | hailmike85@gmail.com |  |  |  | 8535 | 0.15 | Bill Angevine | 2019-04-11 | 5.185 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-04-05 | 2019-04-09 09:00 | Q.PEAK-G4.1 305 | 305 | 17 | Hanwha Q CELLS | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 |  |  | 0 | 1 |  | 2019-07-29 07:00 | 2019-07-05 | 0.55 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 3.13 | 2 | Daniel Speegle | Completed | 2019-07-25 | 22.58 | 1 | Ara Sotto | Completed | 2019-07-31 | 16.66 | 5 | Brian Le | Completed | 2019-07-05 | 0.04 | 3 | Ernesto Enriquez | Completed | 2019-07-19 | 16.8 | 1 | Ernesto Enriquez | Completed | 2019-07-31 | 20.55 | 2 | Ara Sotto | Completed | 2019-09-17 | 33.21 | 2 | Ara Sotto | Completed | 2019-07-24 | 24.21 | 2 | Brian Le | Completed | 2019-07-05 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 0.84 | 1 |  | Completed | 2019-07-10 | 26.88 | 1 | Jill Allen | Completed | 2019-07-29 | 6.8 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-17 | 4 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 6.08 | 2 | Ashley Rockwood | Completed |  | 18.13 | 2 | Darlynn Lacap | Current | 2019-09-26 | 0.83 | 1 | Andrew Clemons | Completed | 2019-07-31 12:46 |  | 2019-09-04 | 24.25 | 2 | Ara Sotto | Completed | [10 empty] | 14.61 | 2019-07-29 | 15.13 | 14 | James Fernandez | Completed | 2019-07-26 | 2019-07-29 | 1.46 | 1 | James Fernandez | Completed | 2019-07-05 | 2019-09-17 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=24369 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24369 | https://completesolar.sugarondemand.com/#Opportunities/6090f056-5c6c-11e9-990a-0630baf9dcb8 | SCES Division | Cody Booth | 2019-04-05 | JK Solar | 6090f056-5c6c-11e9-990a-0630baf9dcb8 | 35 | 48 | -25 | -2 | 5 | 5 | 5 | -17
25747 | PIP_APPROVED | PIP_APPROVED | 2101 Westhaven Avenue | Bakersfield | CA | 93304 | Andres Olivas | 2019-07-02 12:21 | 6613332124 | andresolivas044@gmail.com |  |  |  | 10897 | 0.18 | Bill Angevine | 2019-05-23 | 7.015 | Christina Horton | CUIC Inc | Darlynn Lacap | 2019-05-20 | 2019-05-21 14:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-07-31 07:00 | 2019-07-02 | 0.63 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 3.09 | 2 | Jethro Andal | Completed | 2019-07-05 | 2.75 | 1 | Ara Sotto | Completed | 2019-07-31 | 2.83 | 5 | Brian Le | Completed | 2019-07-02 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-02 | 0 | 0 | Ernesto Enriquez | Completed | 2019-07-31 | 7.01 | 2 | Christina Horton | Completed | 2019-08-02 | 1.79 | 2 | Christina Horton | Completed | 2019-07-12 | 3.79 | 2 | Brian Le | Completed | 2019-07-08 | 1.21 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 0.08 | 1 |  | Completed | 2019-07-10 | 5.71 | 1 | Andrew Clemons | Completed | 2019-08-01 | 4.25 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-03 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-09-19 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 1.96 | 1 | Jill Allen | Completed | 2019-08-29 14:18 |  | 2019-08-29 | 19.38 | 2 | Christina Horton | Completed | [10 empty] | 34.54 | [11 empty] | 2019-07-02 | 2019-08-02 | BAKERSFIELD | Bakersfield | https://heliotrack.completesolar.com/job.php?action=review&jobID=25747 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25747 | https://completesolar.sugarondemand.com/#Opportunities/d21b51a6-7dc0-11e9-87c6-02ae981fbade | SCES Division | Ryan Wilcox | 2019-05-20 | Peak Energy Electric | d21b51a6-7dc0-11e9-87c6-02ae981fbade | 29 | 2 | -25 | 4 | 5 | 5 | 5 | -11
25948 | PIP_APPROVED | PIP_APPROVED | 1854 Lilac Court | Carlsbad | CA | 92011 | Joelle Szymanski | 2019-06-18 10:19 | 7608140169 | Jodszy@yahoo.com |  | 7606020162 |  | 9138 | 0.212 | Alex Holdridge | 2019-06-06 | 9.455 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-27 | 2019-05-29 13:00 | LR6-60PB-305M | 305 | 31 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Composite | Line-side Tap | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-30 07:00 | 2019-06-18 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-06-20 | 3.08 | 2 | Jethro Andal | Completed | 2019-07-01 | 8.96 | 1 | Christina Horton | Completed | 2019-07-30 | 9 | 5 | Brian Le | Completed | 2019-06-25 | 2.3 | 3 | Ernesto Enriquez | Completed | 2019-06-25 | 0.08 | 15 | Andrew Moralez | Completed | 2019-07-31 | 2.8 | 3 | Christina Horton | Completed | 2019-08-20 | 11.62 | 2 | Christina Horton | Completed | 2019-06-26 | 4.75 | 2 | Brian Le | Completed | 2019-06-20 | 1.05 | 2 | Darlynn Lacap | Completed | 2019-06-24 | 2.38 | 1 |  | Completed | 2019-06-27 | 6.67 | 1 | Andrew Clemons | Completed | 2019-07-30 | 1.97 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 0 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 7.13 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 2.33 | 1 | Noe Gomez | Completed | 2019-08-16 12:48 |  | 2019-08-16 | 2.75 | 2 | Christina Horton | Completed | 2019-07-11 | 2.21 | 1 | Christina Horton | Completed | 2019-06-27 | 0.04 | 2 | Darlynn Lacap | Completed | 31.48 | [11 empty] | 2019-07-17 | 2019-08-20 | CARLSBAD | Carlsbad | https://heliotrack.completesolar.com/job.php?action=review&jobID=25948 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25948 | https://completesolar.sugarondemand.com/#Opportunities/0898d440-825a-11e9-8a7f-022c40d974e6 | Gavin Seeberger |  | 2019-05-27 | Infinity Energy Inc | 0898d440-825a-11e9-8a7f-022c40d974e6 | 16 | 20 | -15 | -2 | 5 | 5 | 5 | -7
26238 | PIP_APPROVED | PIP_APPROVED | 45903 York Place | Lancaster | CA | 93534 | Phillip Santiago | 2019-07-16 17:07 | 8052795238 | phil.santiago86@yahoo.com | Jennifer Santiago | 8052310215 | j.santiago99@yahoo.com | 11742 | 0.14 | Bill Angevine | 2019-06-26 | 7.015 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-07 | 2019-06-10 12:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-30 | 2019-07-16 | 1.63 | 2 | Marcia Garay | Completed | 2019-07-18 | 7 | 2 | Daniel Speegle | Completed | 2019-07-26 | 5.91 | 1 | Ara Sotto | Completed | 2019-07-31 | 4.75 | 5 | Brian Le | Completed | 2019-07-18 | 0 | 3 | Andrew Moralez | Completed | 2019-07-19 | 1 | 1 | Andrew Moralez | Completed | 2019-07-31 | 1.71 | 2 | Ara Sotto | Completed | 2019-08-22 | 16.08 | 2 | Ara Sotto | Completed | 2019-07-24 | 2.92 | 2 | Brian Le | Completed | 2019-07-19 | 1.13 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.29 | 1 |  | Completed | 2019-07-27 | 6.5 | 1 | Andrew Clemons | Completed |  | 59.08 | 1 | Marcia Garay | Current | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-10 | 5.75 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 8.13 | 2 | Marcia Garay | Completed | 2019-09-12 | 1.29 | 1 | Noe Gomez | Completed | 2019-07-31 16:08 |  | 2019-07-31 | 0.17 | 2 | Ara Sotto | Completed | [10 empty] | 33.38 | [11 empty] | 2019-07-19 | 2019-08-22 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26238 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26238 | https://completesolar.sugarondemand.com/#Opportunities/d120fc02-988b-11e9-b45e-02ae981fbade | Emily Bowden | Kevin Adams | 2019-06-06 | HDM Electric Inc | d120fc02-988b-11e9-b45e-02ae981fbade | 0 | 22 | 10 | -2 | 5 | 5 | 5 | 18
26383 | PIP_APPROVED | PIP_APPROVED | 6257 Plateau Drive | San Diego | CA | 92139 | Tomiko Denbow | 2019-06-18 15:21 | 8582470313 | denbowtomiko@gmail.com |  |  |  | 7827 | 0.207 | Ryan Malloy | 2019-06-18 | 4.575 | Christina Horton | UpGrid Inc | Darlynn Lacap | 2019-06-15 | 2019-06-18 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-31 07:00 | 2019-06-19 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-06-24 | 2.75 | 2 | Daniel Speegle | Completed | 2019-07-18 | 16.92 | 1 | Christina Horton | Completed | 2019-07-31 | 0.08 | 5 | Christina Horton | Completed | 2019-07-16 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-16 | 0.08 | 15 | Andrew Moralez | Completed | 2019-07-31 | 0.46 | 1 | Christina Horton | Completed | 2019-08-22 | 12.67 | 2 | Christina Horton | Completed | 2019-07-26 | 15.63 | 2 | Brian Le | Completed | 2019-07-02 | 2.91 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 7.87 | 1 |  | Completed | 2019-07-17 | 16.17 | 1 | Jeremiah Liend | Completed | 2019-08-01 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-23 | 1.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 3.92 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 1.88 | 2 | Ashley Rockwood | Completed |  | 41.25 | 2 | Darlynn Lacap | Current | 2019-08-23 | 1 | 1 | Jill Allen | Completed |  | 2019-08-16 | 2019-08-14 | 9.92 | 2 | Christina Horton | Completed | [10 empty] | 28.87 | [11 empty] | 2019-08-06 | 2019-08-22 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26383 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26383 | https://completesolar.sugarondemand.com/#Opportunities/5c56aea0-9217-11e9-b795-069e4f790264 | UpGrid Inc |  | 2019-06-13 | T.A.K. Electric | 5c56aea0-9217-11e9-b795-069e4f790264 | 14 | 22 | -15 | -2 | 5 | 5 | 5 | -7
26509 | PIP_APPROVED | PIP_APPROVED | 11460 Hadar Drive | San Diego | CA | 92126 | Paul Rothstein | 2019-07-02 16:29 | 8587224883 | prothstein@san.rr.com | Thembie Rothstein |  |  | 4848 | 0.16 | Michael Marlaire | 2019-07-02 | 3.05 |  | Wilder Jordan | Marcia Garay | 2019-06-19 | 2019-06-24 15:00 | LR6-60PB-305M | 305 | 10 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-07-31 07:00 | 2019-07-03 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-08 | 2.04 | 2 | Jethro Andal | Completed | 2019-07-25 | 12.75 | 1 | Christina Horton | Completed | 2019-07-31 | 3 | 5 | Brian Le | Completed | 2019-07-25 | 6.96 | 3 | Ernesto Enriquez | Completed | 2019-07-25 | 0 | 15 | Ernesto Enriquez | Completed | 2019-07-31 | 0.33 | 1 | Christina Horton | Completed | 2019-08-12 | 8.08 | 2 | Christina Horton | Completed | 2019-07-26 | 9.67 | 2 | Brian Le | Completed | 2019-07-11 | 0.08 | 2 | Marcia Garay | Completed | 2019-07-16 | 5.75 | 1 |  | Completed | 2019-07-25 | 12.75 | 1 | Andrew Clemons | Completed | 2019-08-01 | 1.29 | 1 | Marcia Garay | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-16 | 0 | 4 | Marcia Garay | Completed | 2019-07-16 | 0 | 5 | Marcia Garay | Completed | 2019-07-16 | 0 | 12 | Marcia Garay | Completed | 2019-08-08 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-08-12 | 1.96 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 4.17 | 2 | Marcia Garay | Completed | 2019-08-15 | 3 | 1 | Andrew Clemons | Completed | 2019-08-02 13:26 |  | 2019-08-02 | 1.96 | 2 | Christina Horton | Completed | [10 empty] | 4.58 | [11 empty] | 2019-08-15 | 2019-08-07 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26509 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26509 | https://completesolar.sugarondemand.com/#Opportunities/31703408-9d21-11e9-b9c7-0630baf9dcb8 | Wilder Jordan |  | 2019-06-18 | iEnergy ElectricSolar | 31703408-9d21-11e9-b9c7-0630baf9dcb8 | 2 | 12 | 7 | -2 | 5 | 5 | 5 | 15
26621 | PIP_APPROVED | PIP_APPROVED | 14573 La Habra Road | Victorville | CA | 92392 | Aaron Ramirez | 2019-07-12 11:16 | 7606286800 | jramirez714@yahoo.com |  |  |  | 9671 | 0.11 | Shaun Labelle | 2019-06-26 | 4.88 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-22 | 2019-06-26 09:00 | LR6-60PB-305M | 305 | 16 | LONGi Solar | SolarEdge | SE5000H-US RGM |  | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 0 | 2019-07-31 07:00 | 2019-07-12 | 2.17 | 2 | Marcia Garay | Completed | 2019-07-12 | 2 | 2 | Daniel Speegle | Completed | 2019-07-22 | 5.91 | 1 | Ara Sotto | Completed | 2019-07-31 | 4.96 | 5 | Brian Le | Completed | 2019-07-16 | 0.04 | 3 | Ernesto Enriquez | Completed | 2019-07-24 | 10.05 | 10 | Ernesto Enriquez | Completed | 2019-07-31 | 0.38 | 1 | Ara Sotto | Completed | 2019-08-02 | 1.83 | 2 | Ara Sotto | Completed | 2019-07-24 | 8.21 | 2 | Brian Le | Completed | 2019-07-15 | 6.55 | 2 | Marcia Garay | Completed | 2019-07-16 | 2.75 | 1 |  | Completed | 2019-07-15 | 7.79 | 1 | Andrew Clemons | Completed | 2019-07-31 | 0.5 | 1 | Marcia Garay | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-08 | 5.71 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 11.08 | 2 | Marcia Garay | Completed | 2019-08-15 | 4.29 | 1 | Jill Allen | Completed | 2019-07-31 16:35 |  | 2019-07-31 | 0 | 2 | Ara Sotto | Completed | [10 empty] | 3.87 | [11 empty] | 2019-07-24 | 2019-08-01 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=26621 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26621 | https://completesolar.sugarondemand.com/#Opportunities/c4943a04-983f-11e9-8a46-069e4f790264 | SCES Division | Shane Montana | 2019-06-22 | Power Town Solar Electric | c4943a04-983f-11e9-8a46-069e4f790264 | 0 | 2 | 10 | 4 | 5 | 5 | 5 | 24
26643 | PIP_APPROVED | PIP_APPROVED | 5815 Crown Drive | Jurupa Valley | CA | 91752 | Shannon Savala | 2019-06-27 15:22 | 9092005266 | sj.savala66@yahoo.com | Yolanda Savala | 909-969-1073 |  | 8878 | 0.152 | Chris Peaslee | 2019-06-27 | 5.49 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-26 | 2019-06-27 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-31 | 2019-06-28 | 0.92 | 2 | Darlynn Lacap | Completed | 2019-07-02 | 2.08 | 2 | Daniel Speegle | Completed | 2019-07-16 | 8.75 | 1 | Christina Horton | Completed | 2019-07-29 | 11.34 | 5 | Brian Le | Completed | 2019-07-09 | 1.96 | 3 | Andrew Moralez | Completed | 2019-07-15 | 4.25 | 0 | Ernesto Enriquez | Completed | 2019-07-31 | 1.84 | 2 | Christina Horton | Completed | 2019-09-04 | 23.38 | 2 | Christina Horton | Completed | 2019-07-09 | 3.67 | 2 | Brian Le | Completed | 2019-07-02 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 0.08 | 1 |  | Completed | 2019-07-09 | 3.92 | 1 | Andrew Clemons | Completed | 2019-08-01 | 2.96 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-14 | 3.29 | 2 | Ashley Rockwood | Completed | 2019-08-15 | 0.79 | 2 | Ashley Rockwood | Completed |  | 46.25 | 2 | Darlynn Lacap | Current |  | 43 | 1 | Andrew Clemons | Current | 2019-08-08 15:06 |  | 2019-08-09 | 6.67 | 2 | Christina Horton | Completed | 2019-07-30 | 0.71 | 1 | Christina Horton | Completed | 2019-07-03 | 0.63 | 2 | Darlynn Lacap | Completed | 19.72 | [11 empty] | 2019-07-09 | 2019-09-04 | MIRA LOMA | Mira Loma | https://heliotrack.completesolar.com/job.php?action=review&jobID=26643 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26643 | https://completesolar.sugarondemand.com/#Opportunities/03edcc0c-992a-11e9-a2f9-022c40d974e6 | Lindsey Lange |  | 2019-06-22 | Infinity Energy Inc | 03edcc0c-992a-11e9-a2f9-022c40d974e6 | 9 | 35 | -5 | -2 | 5 | 5 | 5 | 3
26886 | PIP_APPROVED | PIP_APPROVED | 3351 Mount Ariane Drive | San Diego | CA | 92111 | Douglas Spunaugle | 2019-07-09 12:49 | 6193183646 | doug.spunaugle@landcare.com |  |  |  | 5517 | 0.002 | Ryan Malloy | 2019-07-09 | 4.575 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-08 | 2019-07-09 09:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-30 12:00 | 2019-07-10 | 1.04 | 2 | Marcia Garay | Completed | 2019-07-12 | 1.79 | 2 | Jethro Andal | Completed | 2019-07-26 | 10.13 | 1 | Christina Horton | Completed | 2019-07-31 | 2.92 | 5 | Brian Le | Completed | 2019-07-24 | 6.08 | 3 | Andrew Moralez | Completed | 2019-07-24 | 0 | 15 | Andrew Moralez | Completed | 2019-07-31 | 0.79 | 1 | Christina Horton | Completed | 2019-08-07 | 2.13 | 2 | Christina Horton | Completed | 2019-07-25 | 7.92 | 2 | Brian Le | Completed | 2019-07-15 | 1.08 | 2 | Marcia Garay | Completed | 2019-07-16 | 2 | 1 |  | Completed | 2019-07-26 | 10.08 | 1 | Andrew Clemons | Completed |  | 58.17 | 1 | Marcia Garay | Current | 2019-08-21 | 9.87 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-13 | 3.79 | 2 | Ashley Rockwood | Completed | 2019-08-15 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-10-02 | 33.21 | 2 | Marcia Garay | Completed | 2019-08-21 | 4.04 | 1 | Andrew Clemons | Completed |  | 2019-08-08 | 2019-08-07 | 5.25 | 2 | Christina Horton | Completed | [10 empty] | 4.96 | [11 empty] | 2019-08-14 | 2019-08-07 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26886 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26886 | https://completesolar.sugarondemand.com/#Opportunities/9e42de94-a282-11e9-9aa3-022c40d974e6 | Blake Sanders | Dylan Glasser | 2019-07-03 | Infinity Energy Inc | 9e42de94-a282-11e9-9aa3-022c40d974e6 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26908 | PIP_APPROVED | PIP_APPROVED | 14618 Parkwood Court | Moreno Valley | CA | 92553 | Antonio Aguilar Meza | 2019-07-08 15:07 | 7146038929 | antonioaguilarmeza@gmail.com |  |  |  | 6756 | 0.155 | Chris Peaslee | 2019-07-08 | 3.965 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-05 | 2019-07-06 15:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-30 07:00 | 2019-07-09 | 0.79 | 2 | Marcia Garay | Completed | 2019-07-11 | 2.08 | 2 | Daniel Speegle | Completed | 2019-07-09 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-31 | 3.71 | 5 | Brian Le | Completed | 2019-07-18 | 1.08 | 3 | Andrew Moralez | Completed | 2019-07-26 | 5.63 | 25 | Andrew Moralez | Completed | 2019-07-31 | 1.17 | 1 | Ara Sotto | Completed | 2019-08-01 | 1.21 | 2 | Ara Sotto | Completed | 2019-07-25 | 9.13 | 2 | Brian Le | Completed | 2019-07-12 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-17 | 4.13 | 1 |  | Completed | 2019-07-18 | 4.75 | 1 | Jill Allen | Completed |  | 58.54 | 1 | Marcia Garay | Current |  | 56.13 | 2 | Andrew Clemons | Current | [15 empty] | 2019-09-11 | 16.12 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-09-23 | 7.08 | 2 | Marcia Garay | Completed |  | 27.29 | 1 | Andrew Clemons | Current | 2019-07-30 14:59 |  | 2019-08-02 | 2.08 | 2 | Ara Sotto | Completed | [10 empty] | 10.96 | [11 empty] | 2019-08-22 | 2019-08-01 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26908 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26908 | https://completesolar.sugarondemand.com/#Opportunities/a748aa98-a1cc-11e9-b0aa-0630baf9dcb8 | 300 Stars Inc | Oscar Hernandez | 2019-07-03 | HDM Electric Inc | a748aa98-a1cc-11e9-b0aa-0630baf9dcb8 | 2 | 1 | 7 | 5 | 5 | 5 | 5 | 22
26989 | PIP_APPROVED | PIP_APPROVED | 26296 Brandywine Drive | Menifee | CA | 92586 | Carolyn Caffey | 2019-07-11 12:11 | 7042453352 | ccaffey@carolina.rr.com |  |  |  | 10695 | 0.109 | Michael Marlaire | 2019-07-11 | 6.1 | Ara Sotto | PHNX Power | Darlynn Lacap | 2019-07-09 | 2019-07-11 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-29 07:00 | 2019-07-11 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-15 | 1.88 | 2 | Jethro Andal | Completed | 2019-07-16 | 0.88 | 1 | Ara Sotto | Completed | 2019-07-31 | 4.75 | 5 | Brian Le | Completed | 2019-07-16 | 0 | 3 | Andrew Moralez | Completed | 2019-07-23 | 5.21 | 0 | Andrew Moralez | Completed | 2019-07-31 | 2.17 | 2 | Ara Sotto | Completed | 2019-07-29 | 0.08 | 2 | Ara Sotto | Completed | 2019-07-24 | 3.04 | 2 | Brian Le | Completed | 2019-07-19 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 0.88 | 1 |  | Completed | 2019-07-18 | 3.09 | 1 | Jill Allen | Completed | 2019-07-29 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 1.13 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-05 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-08-06 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 14.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.79 | 1 | Andrew Clemons | Completed | 2019-07-31 13:30 |  | 2019-07-31 | 0.13 | 2 | Ara Sotto | Completed | [10 empty] | 6.13 | [11 empty] | 2019-07-16 | 2019-07-29 | SUN CITY | Sun City | https://heliotrack.completesolar.com/job.php?action=review&jobID=26989 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26989 | https://completesolar.sugarondemand.com/#Opportunities/94a5d5d8-a40f-11e9-842d-0630baf9dcb8 | PHNX Power |  | 2019-07-09 | Power Town Solar Electric | 94a5d5d8-a40f-11e9-842d-0630baf9dcb8 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
27058 | PIP_APPROVED | PIP_APPROVED | 3146 Softwood Court | Lancaster | CA | 93536 | Shawna Clark | 2019-07-12 15:07 | 6614007121 | clark.orene@gmail.com | Orine Clark | 6619929887 |  | 9699 | 0.148 | Bill Angevine | 2019-07-12 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-11 | 2019-07-12 09:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-30 07:00 | 2019-07-19 | 5 | 2 | Marcia Garay | Completed | 2019-07-17 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-26 | 4.38 | 1 | Ara Sotto | Completed | 2019-07-31 | 5 | 5 | Brian Le | Completed | 2019-07-18 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-19 | 0.17 | 1 | Ernesto Enriquez | Completed | 2019-07-31 | 1.84 | 2 | Ara Sotto | Completed | 2019-08-15 | 11.04 | 2 | Ara Sotto | Completed | 2019-07-24 | 2.92 | 2 | Brian Le | Completed | 2019-07-19 | 0 | 2 | Marcia Garay | Completed | 2019-07-18 | 0.08 | 1 |  | Completed | 2019-07-26 | 4.88 | 1 | Jeremiah Liend | Completed |  | 58.96 | 1 | Marcia Garay | Current | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-08 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 18.21 | 2 | Marcia Garay | Completed | 2019-08-15 | 4.29 | 1 | Andrew Clemons | Completed | 2019-08-06 16:36 | 2019-07-31 | 2019-08-06 | 3.92 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-22 | 2019-08-15 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=27058 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27058 | https://completesolar.sugarondemand.com/#Opportunities/5daa88de-a4f1-11e9-9bf0-0630baf9dcb8 | George Sarkis |  | 2019-07-11 | JK Solar | 5daa88de-a4f1-11e9-9bf0-0630baf9dcb8 | 6 | 15 | -5 | -2 | 5 | 5 | 5 | 3
27067 | PIP_APPROVED | PIP_APPROVED | 43191 San Mateo Way | Hemet | CA | 92544 | Shantel Lundberg | 2019-07-13 16:57 | 2092724865 | shantel1674@gmail.com | Noe Ochoa | 7609084078 |  | 14182 | 0.155 | Chad Malloy | 2019-07-13 | 8.54 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-07-11 | 2019-07-13 09:00 | LR6-60PB-305M | 305 | 28 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-07-31 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-31 07:00 | 2019-07-15 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-18 | 2.71 | 2 | Jethro Andal | Completed | 2019-07-25 | 5.54 | 1 | Ara Sotto | Completed | 2019-07-31 | 1.92 | 5 | Brian Le | Completed | 2019-07-22 | 1.04 | 3 | Ernesto Enriquez | Completed | 2019-07-25 | 3.17 | 1 | Andrew Moralez | Completed | 2019-07-31 | 0.38 | 2 | Ara Sotto | Completed | 2019-08-15 | 11.08 | 2 | Ara Sotto | Completed | 2019-07-29 | 5.04 | 2 | Brian Le | Completed | 2019-07-22 | 2.08 | 2 | Darlynn Lacap | Completed | 2019-07-19 | 0.96 | 1 |  | Completed | 2019-07-24 | 3.96 | 1 | Andrew Clemons | Completed | 2019-08-01 | 1.58 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-09-06 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-09-25 | 12.13 | 2 | Darlynn Lacap | Completed | 2019-09-11 | 2.13 | 1 | Andrew Clemons | Completed | 2019-09-04 12:31 |  | 2019-09-05 | 24.96 | 2 | Ara Sotto | Completed | [10 empty] | 2.92 | [11 empty] | 2019-07-23 | 2019-08-14 | HEMET | Hemet | https://heliotrack.completesolar.com/job.php?action=review&jobID=27067 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27067 | https://completesolar.sugarondemand.com/#Opportunities/21b5195a-a44e-11e9-b4f5-02ae981fbade | Ryan Ostronic |  | 2019-07-11 | Blalock Electric&Solar | 21b5195a-a44e-11e9-b4f5-02ae981fbade | 36 | 15 | -25 | -2 | 5 | 5 | 5 | -17
21943 | PIP_APPROVED | PIP_APPROVED | 1019 West Olive Street | Corona | CA | 92882 | Chris McCorkell | 2019-07-03 16:57 | 9514156735 | mccorkell2@hotmail.com |  |  |  | 15222 | 0.17 | Alex Holdridge | 2019-01-28 | 10.37 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-01-21 | 2019-01-23 15:00 | Q.PEAK-G4.1 305 | 305 | 34 | Hanwha Q CELLS | SolarEdge Technologies | SE10000H-US | Composite | NO | 2019-07-30 | PTO Received | SunRun Monthly | 0 |  |  | 0 | 1 |  | 2019-07-30 | 2019-07-05 | 2.29 | 2 | Darlynn Lacap | Completed | 2019-07-04 | 3.25 | 2 | Daniel Speegle | Completed | 2019-07-16 | 10.54 | 1 | Ara Sotto | Completed | 2019-07-30 | 2.17 | 5 | Brian Le | Completed | 2019-07-16 | 11.29 | 3 | Ernesto Enriquez | Completed | 2019-07-30 | 6.87 | 14 | Ernesto Enriquez | Completed | 2019-07-30 | 0 | 3 | Ara Sotto | Completed | 2019-07-31 | 0.92 | 2 | Ara Sotto | Completed | 2019-07-26 | 11 | 2 | Brian Le | Completed | 2019-07-05 | 11.92 | 2 | Darlynn Lacap | Completed | 2019-07-06 | 2.67 | 1 |  | Completed | 2019-07-31 | 18.83 | 1 | Andrew Clemons | Completed | 2019-08-01 | 2.08 | 1 | Darlynn Lacap | Completed | 2019-08-01 | 0.88 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-05 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-08-23 | 12.21 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 7.71 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 3.5 | 1 | Andrew Clemons | Completed | 2019-07-31 15:25 |  | 2019-08-01 | 1.79 | 2 | Ara Sotto | Completed | [10 empty] | 54.68 | 2019-07-17 | 0 | 14 | James Fernandez | Completed | 2019-07-17 | 2019-07-17 | 0 | 1 | James Fernandez | Completed | 2019-08-08 | 2019-07-31 | CORONA | Corona | https://heliotrack.completesolar.com/job.php?action=review&jobID=21943 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=21943 | https://completesolar.sugarondemand.com/#Opportunities/53247f1c-2352-11e9-97a0-022c40d974e6 | CUIC Inc | Marco Valdizan | 2019-01-21 | Zachary Noah Gamez | 53247f1c-2352-11e9-97a0-022c40d974e6 | 2 | 1 | 7 | 5 | 5 | 5 | 5 | 22
25698 | PIP_APPROVED | PIP_APPROVED | 17037 Montura Drive | San Diego | CA | 92128 | Anna Tran | 2019-07-23 11:25 | 8584876126 | anna9942@gmail.com |  |  |  | 3833 | 0.183 | Chad Malloy | 2019-05-20 | 2.44 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-05-17 | 2019-05-20 12:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Tile Concrete | NO | 2019-07-30 | PTO Received | SunRun Monthly | 1 | 0 |  |  |  | 1 | 2019-07-30 07:00 | 2019-07-23 | 2.83 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-26 | 2.91 | 1 | Ara Sotto | Completed | 2019-07-30 | 20.88 | 5 | Ara Sotto | Completed | 2019-07-23 | 3.96 | 3 | Ernesto Enriquez | Completed | 2019-07-23 | 7.67 | 15 | Andrew Moralez | Completed | 2019-07-30 | 0.46 | 1 | Ara Sotto | Completed | 2019-08-13 | 9.79 | 2 | Ara Sotto | Completed | 2019-07-23 | 9.05 | 2 | Brian Le | Completed | 2019-07-23 | 0.21 | 2 | Darlynn Lacap | Completed | 2019-07-23 | 0.96 | 1 |  | Completed | 2019-07-31 | 8.67 | 1 | Andrew Clemons | Completed | 2019-07-24 | 0.08 | 1 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-24 | 3.83 | 4 | Darlynn Lacap | Completed | 2019-07-23 | 0.24 | 5 | Darlynn Lacap | Completed | 2019-07-23 | 0.08 | 12 | Darlynn Lacap | Completed | 2019-08-28 | 3.33 | 2 | Ashley Rockwood | Completed | 2019-09-03 | 3.33 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 6.96 | 2 | Darlynn Lacap | Completed | 2019-09-04 | 0.71 | 1 | Jill Allen | Completed | 2019-07-31 12:28 |  | 2019-08-02 | 2.79 | 2 | Ara Sotto | Completed | [10 empty] | 29.47 | [11 empty] | 2019-08-02 | 2019-08-10 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=25698 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25698 | https://completesolar.sugarondemand.com/#Opportunities/0fcd2e20-7b4b-11e9-a786-02ae981fbade | Jordan Litrownik |  | 2019-05-17 | Blalock Electric&Solar | 0fcd2e20-7b4b-11e9-a786-02ae981fbade | 3 | 14 | 0 | -2 | 5 | 5 | 5 | 8
27029 | PIP_APPROVED | PIP_APPROVED | 1105 Sutter Lane | San Marcos | CA | 92069 | Abraham Vargas | 2019-07-11 13:54 | 7604151812 | abefranco16@gmail.com |  | 7607411548 |  | 7905 | 0.145 | Chad Malloy | 2019-07-11 | 4.575 | Christina Horton | Kyle Wilson | Darlynn Lacap | 2019-07-10 | 2019-07-11 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-07-30 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 0 | 2019-07-29 07:00 | 2019-07-11 | 0.13 | 2 | Darlynn Lacap | Completed | 2019-07-15 | 1.79 | 2 | Daniel Speegle | Completed | 2019-07-17 | 1.96 | 1 | Ara Sotto | Completed | 2019-07-29 | 3.26 | 5 | Brian Le | Completed | 2019-07-16 | 0.21 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 0 | 0 | Ernesto Enriquez | Completed | 2019-07-30 | 1.33 | 1 | Christina Horton | Completed |  | 56.08 | 2 | Christina Horton | Current | 2019-07-19 | 0.88 | 2 | Brian Le | Completed | 2019-07-18 | 2.92 | 2 | Darlynn Lacap | Completed | 2019-07-16 | 0.88 | 1 |  | Completed | 2019-07-17 | 2.08 | 1 | Andrew Clemons | Completed | 2019-07-29 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-08-22 | 0.16 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-14 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 1.71 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 9 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 4.33 | 1 | Andrew Clemons | Completed | 2019-08-08 14:21 |  | 2019-08-08 | 6.92 | 2 | Christina Horton | Completed | [10 empty] | 4.93 | [11 empty] | 2019-07-16 | 2019-08-05 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=27029 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27029 | https://completesolar.sugarondemand.com/#Opportunities/e6b17554-a41d-11e9-9035-069e4f790264 | Kyle Wilson |  | 2019-07-10 | Greenday Electric Solar | e6b17554-a41d-11e9-9035-069e4f790264 | 9 | 83 | -5 | -2 | 5 | 5 | 5 | 3
20289 | PIP_APPROVED | PIP_APPROVED | 1349 Calle Colnett | San Marcos | CA | 92069 | Christopher Maris | 2019-07-03 16:28 | 7608052836 | rubberbiscuit77@att.net | Lori Maris | 7608052835 |  | 7224.91 |  | Ryan Malloy | 2019-07-03 | 4.27 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-28 | 2019-07-02 15:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-29 | PTO Received | Sunlight Financial Loan | 1 | 0 |  | 0 | 0 | 0 | 2019-07-29 12:00 | 2019-07-08 | 1.83 | 2 | Marcia Garay | Completed | 2019-07-10 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-15 | 2.96 | 1 | Christina Horton | Completed | 2019-07-29 | 7.71 | 5 | Brian Le | Completed | 2019-07-11 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-11 | 0.08 | 0 | Andrew Moralez | Completed | 2019-07-29 | 0.46 | 1 | Christina Horton | Completed | 2019-07-30 | 0.92 | 2 | Christina Horton | Completed | 2019-07-11 | 1.04 | 2 | Brian Le | Completed | 2019-07-10 | 0 | 2 | Marcia Garay | Completed | 2019-07-10 | 0.08 | 1 |  | Completed | 2019-07-13 | 2.5 | 1 | Andrew Clemons | Completed | 2019-08-06 | 6.34 | 1 | Marcia Garay | Completed | 2019-08-07 | 5.67 | 2 | Andrew Clemons | Completed | 2019-07-14 | 0.08 | 4 | Marcia Garay | Completed | 2019-07-14 | 0.08 | 5 | Marcia Garay | Completed | 2019-07-22 | 5.54 | 12 | Marcia Garay | Completed | 2019-08-07 | 1.33 | 2 | Ashley Rockwood | Completed | 2019-08-08 | 0.67 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 15 | 2 | Marcia Garay | Completed |  | 51.17 | 1 | Andrew Clemons | Current | 2019-08-06 13:13 |  | 2019-08-06 | 5.83 | 2 | Christina Horton | Completed | [10 empty] | 11.17 | [11 empty] | 2019-07-11 | 2019-07-29 | SAN MARCOS | San Marcos | https://heliotrack.completesolar.com/job.php?action=review&jobID=20289 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=20289 | https://completesolar.sugarondemand.com/#Opportunities/2c71d76c-9dea-11e9-8a50-022c40d974e6 | Revo Home Solutions | Trey Greenhill | 2018-10-27 | Infinity Energy Inc | 2c71d76c-9dea-11e9-8a50-022c40d974e6 | 8 | 1 | -5 | 5 | 5 | 5 | 5 | 10
26106 | PIP_APPROVED | PIP_APPROVED | 10924 Martinique Way | San Diego | CA | 92126 | Jeffrey May | 2019-06-07 16:24 | 8585781270 | jrmay28@hotmail.com | Elysa May |  |  | 5615 | 0.222 | Chad Malloy | 2019-06-07 | 3.355 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-03 | 2019-06-07 14:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-07-29 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 1 | 1 | 2019-07-29 07:00 | 2019-06-11 | 1.96 | 2 | Darlynn Lacap | Completed | 2019-06-14 | 2.88 | 2 | Daniel Speegle | Completed | 2019-07-16 | 20.88 | 1 | Ara Sotto | Completed | 2019-07-29 | 8.79 | 5 | Brian Le | Completed | 2019-06-26 | 0 | 3 | Andrew Moralez | Completed | 2019-07-12 | 10.92 | 15 | Andrew Moralez | Completed | 2019-07-29 | 0.38 | 1 | Christina Horton | Completed | 2019-07-31 | 1.92 | 2 | Christina Horton | Completed | 2019-07-09 | 8.63 | 2 | Brian Le | Completed | 2019-06-25 | 3.12 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 0.21 | 1 |  | Completed | 2019-06-24 | 5.71 | 1 | Andrew Clemons | Completed | 2019-07-29 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-01 | 1 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 8.83 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 4.25 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.96 | 1 | Jill Allen | Completed | 2019-07-31 16:03 |  | 2019-07-31 | 1.92 | 2 | Christina Horton | Completed | [10 empty] | 21.04 | 2019-07-14 | 5.21 | 14 | James Fernandez | Completed | 2019-07-25 | 2019-07-16 | 0.08 | 1 | James Fernandez | Completed | 2019-07-18 | 2019-08-21 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26106 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26106 | https://completesolar.sugarondemand.com/#Opportunities/47caf8b4-897b-11e9-8806-069e4f790264 | Kellee Benjamin | Andrew Goff | 2019-06-01 | Infinity Energy Inc | 47caf8b4-897b-11e9-8806-069e4f790264 | 2 | 2 | 7 | 4 | 5 | 5 | 5 | 21
26393 | PIP_APPROVED | PIP_APPROVED | 3321 Bronco Lane | Norco | CA | 92860 | Hector Weckmann | 2019-06-15 15:27 | 9512830510 | lauralizardo29@yahoo.com | Joanne |  |  | 11274 | 0.13 | Chris Peaslee | 2019-06-15 | 7.015 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-06-13 | 2019-06-15 15:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-07-29 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-29 07:00 | 2019-06-18 | 1.42 | 2 | Darlynn Lacap | Completed | 2019-06-21 | 2.96 | 2 | Daniel Speegle | Completed | 2019-06-17 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-29 | 7.13 | 5 | Brian Le | Completed | 2019-07-03 | 3.88 | 3 | Andrew Moralez | Completed | 2019-07-22 | 5.66 | 14 | Andrew Moralez | Completed | 2019-07-29 | 0.42 | 2 | Ara Sotto | Completed | 2019-08-08 | 7.67 | 2 | Ara Sotto | Completed | 2019-07-18 | 16 | 2 | Brian Le | Completed | 2019-06-25 | 2.04 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 1.04 | 1 |  | Completed | 2019-07-03 | 8.13 | 1 | Andrew Clemons | Completed | 2019-07-29 | 0.38 | 1 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-02 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-05 | 0.83 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 29.08 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 2.92 | 1 | Andrew Clemons | Completed | 2019-07-31 12:32 |  | 2019-07-31 | 1.92 | 2 | Ara Sotto | Completed | [10 empty] | 10.3 | [11 empty] | 2019-08-02 | 2019-08-08 | NORCO | Norco | https://heliotrack.completesolar.com/job.php?action=review&jobID=26393 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26393 | https://completesolar.sugarondemand.com/#Opportunities/b3ba316a-8fbc-11e9-beaa-0630baf9dcb8 | Ryan Ostronic |  | 2019-06-13 | Blalock Electric&Solar | b3ba316a-8fbc-11e9-beaa-0630baf9dcb8 | 2 | 10 | 7 | -2 | 5 | 5 | 5 | 15
26853 | PIP_APPROVED | PIP_APPROVED | 2818 Eureka Road | San Jacinto | CA | 92582 | Ramon Sagarnaga | 2019-07-05 17:56 | 9514878105 | namdrehad69@yahoo.com | Nectar Sagarnaga | 9512599607 |  | 9552 | 0.132 | Shaun Labelle | 2019-07-05 | 5.49 | Ara Sotto | PHNX Power | Marcia Garay | 2019-07-02 | 2019-07-03 09:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-29 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-29 | 2019-07-08 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-09 | 0.96 | 2 | Jethro Andal | Completed | 2019-07-25 | 11.88 | 1 | Ara Sotto | Completed | 2019-07-29 | 2.96 | 5 | Brian Le | Completed | 2019-07-12 | 2.83 | 3 | Ernesto Enriquez | Completed | 2019-07-23 | 7.04 | 10 | Andrew Moralez | Completed | 2019-07-29 | 0 | 2 | Ara Sotto | Completed | 2019-07-30 | 0.88 | 2 | Ara Sotto | Completed | 2019-07-24 | 5.83 | 2 | Brian Le | Completed | 2019-07-16 | 5.04 | 2 | Marcia Garay | Completed | 2019-07-09 | 0.04 | 1 |  | Completed | 2019-07-16 | 4.88 | 1 | Andrew Clemons | Completed |  | 59.13 | 1 | Marcia Garay | Current | 2019-07-31 | 1 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-01 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-08-07 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-08-15 | 6.13 | 2 | Marcia Garay | Completed | 2019-08-09 | 2.08 | 1 | Andrew Clemons | Completed | 2019-07-30 13:37 |  | 2019-07-31 | 1.75 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-26 | 2019-07-30 | SAN JACINTO | San Jacinto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26853 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26853 | https://completesolar.sugarondemand.com/#Opportunities/c8eeea22-9f88-11e9-a703-022c40d974e6 | PHNX Power |  | 2019-07-02 | Zachary Noah Gamez | c8eeea22-9f88-11e9-a703-022c40d974e6 | 2 | 1 | 7 | 5 | 5 | 5 | 5 | 22
26936 | PIP_APPROVED | PIP_APPROVED | 12218 Champlain Street | Moreno Valley | CA | 92557 | Bryan Quevedo | 2019-07-08 17:16 | 9095530401 | bryanquevedo@yahoo.com | Kari Quevedo | 9093154870 |  | 5605 | 0.157 | Shaun Labelle | 2019-07-08 | 3.355 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-06 | 2019-07-08 15:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar | SolarEdge | SE3000H-US RGM |  | NO | 2019-07-29 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-29 07:00 | 2019-07-09 | 0.71 | 2 | Marcia Garay | Completed | 2019-07-11 | 2.08 | 2 | Jethro Andal | Completed | 2019-07-09 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-29 | 2.96 | 5 | Brian Le | Completed | 2019-07-16 | 0.25 | 3 | Ernesto Enriquez | Completed | 2019-07-22 | 4.17 | 25 | Ernesto Enriquez | Completed | 2019-07-29 | 0.38 | 1 | Ara Sotto | Completed | 2019-07-30 | 1.08 | 2 | Ara Sotto | Completed | 2019-07-24 | 8.17 | 2 | Brian Le | Completed | 2019-07-12 | 0.83 | 2 | Marcia Garay | Completed | 2019-07-16 | 2.83 | 1 |  | Completed | 2019-07-24 | 8.71 | 1 | Andrew Clemons | Completed | 2019-08-06 | 6.17 | 1 | Marcia Garay | Completed | 2019-07-31 | 0.79 | 2 | Jeremiah Liend | Completed | [15 empty] | 2019-08-13 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.79 | 2 | Ashley Rockwood | Completed | 2019-08-21 | 5.17 | 2 | Marcia Garay | Completed | 2019-08-15 | 1 | 1 | Andrew Clemons | Completed | 2019-08-06 13:37 |  | 2019-08-07 | 6.96 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-08-20 | 2019-07-30 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26936 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26936 | https://completesolar.sugarondemand.com/#Opportunities/b9b649ee-a1de-11e9-ba4f-02ae981fbade | 300 Stars Inc | Oscar Hernandez | 2019-07-06 | Green Road Solar Crew | b9b649ee-a1de-11e9-ba4f-02ae981fbade | 9 | 1 | -5 | 5 | 5 | 5 | 5 | 10
25706 | PIP_APPROVED | PIP_APPROVED | 42450 62nd Street West | Quartz Hill | CA | 93536 | Jordan Manns | 2019-05-23 07:23 | 6615757525 | mannsj87@gmail.com | Laura Manns | 6615757560 |  | 15083 | 0.157 | Bill Angevine | 2019-05-22 | 8.845 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-05-18 | 2019-05-22 10:00 | LR6-60PB-305M | 305 | 29 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-07-27 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-07-17 07:00 | 2019-05-30 | 4.08 | 2 | Marcia Garay | Completed | 2019-06-03 | 2.21 | 2 | Daniel Speegle | Completed | 2019-06-14 | 8.67 | 1 | Ara Sotto | Completed | 2019-07-27 | 26.58 | 5 | Brian Le | Completed | 2019-06-05 | 0.96 | 3 | Andrew Moralez | Completed | 2019-07-12 | 25.92 | 1 | Andrew Moralez | Completed | 2019-07-27 | 9 | 2 | Ara Sotto | Completed | 2019-07-30 | 1.58 | 2 | Ara Sotto | Completed | 2019-06-20 | 9.96 | 2 | Brian Le | Completed | 2019-06-05 | 1.71 | 2 | Marcia Garay | Completed | 2019-06-04 | 0.79 | 1 |  | Completed | 2019-06-06 | 2.63 | 1 | Andrew Clemons | Completed | 2019-07-30 | 10.71 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-01 | 1 | 2 | Ashley Rockwood | Completed | 2019-08-02 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 28.25 | 2 | Marcia Garay | Completed | 2019-08-08 | 3.92 | 1 | Andrew Clemons | Completed | 2019-07-29 15:24 |  | 2019-07-31 | 2.29 | 2 | Ara Sotto | Completed | [10 empty] | 1.96 | [11 empty] | 2019-06-06 | 2019-07-30 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=25706 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25706 | https://completesolar.sugarondemand.com/#Opportunities/3134c51a-7d66-11e9-82aa-069e4f790264 | Emily Bowden |  | 2019-05-18 | Power Town Solar Electric | 3134c51a-7d66-11e9-82aa-069e4f790264 | 4 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26421 | PIP_APPROVED | PIP_APPROVED | 13983 Wimbleton Drive | Victorville | CA | 92395 | Thomas Newton | 2019-06-15 18:13 | 6266099864 | newtonsdogs@gmail.com |  |  |  | 10797 | 0.14 | Shaun Labelle | 2019-06-15 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-14 | 2019-06-15 15:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | Line-side Tap | 2019-07-12 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-06-17 | 0.54 | 2 | Darlynn Lacap | Completed | 2019-06-26 | 5.25 | 2 | Jethro Andal | Completed | 2019-06-17 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-12 | 4.83 | 5 | Brian Le | Completed | 2019-06-27 | 0 | 3 | Andrew Moralez | Completed | 2019-07-02 | 2.88 | 10 | Andrew Moralez | Completed | 2019-07-27 | 3.46 | 2 | Ara Sotto | Completed | 2019-07-30 | 2.83 | 2 | Ara Sotto | Completed | 2019-07-05 | 5.71 | 2 | Brian Le | Completed | 2019-06-26 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-06-27 | 0.92 | 1 |  | Completed | 2019-06-30 | 2.38 | 1 | Jeremiah Liend | Completed | 2019-07-29 | 3.46 | 1 | Darlynn Lacap | Completed | 2019-07-31 | 0.88 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-01 | 1.13 | 2 | Ashley Rockwood | Completed | 2019-08-05 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-08 | 3.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 2.88 | 1 | Jill Allen | Completed | 2019-07-30 21:29 |  | 2019-07-31 | 0 | 2 | Ara Sotto | Completed | 2019-07-31 | 8.13 | 1 | Ara Sotto | Completed | 2019-07-02 | 3.92 | 2 | Darlynn Lacap | Completed | 27.83 | [11 empty] | 2019-07-12 | 2019-07-30 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=26421 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26421 | https://completesolar.sugarondemand.com/#Opportunities/e2618150-8fd3-11e9-a93f-0630baf9dcb8 | SCES Division |  | 2019-06-14 | Power Town Solar Electric | e2618150-8fd3-11e9-a93f-0630baf9dcb8 | 0 | 3 | 10 | 2 | 5 | 5 | 5 | 22
26491 | PIP_APPROVED | PIP_APPROVED | 13912 Smoke Tree Road | Victorville | CA | 92395 | Miles Dixon | 2019-07-05 10:26 | 9513133551 | mdixon123@icloud.com | Melissa Dixon | 9513133551 |  | 10739 | 0.142 | Bill Angevine | 2019-06-22 | 6.405 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-18 | 2019-06-22 12:00 | LR6-60PB-305M | 305 | 21 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | NO | 2019-07-27 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-27 | 2019-07-05 | 2.67 | 2 | Marcia Garay | Completed | 2019-07-09 | 4.83 | 2 | Jethro Andal | Completed | 2019-07-25 | 12.08 | 1 | Ara Sotto | Completed | 2019-07-27 | 0.08 | 5 | Brian Le | Completed | 2019-07-17 | 5.79 | 3 | Andrew Moralez | Completed | 2019-07-23 | 5.25 | 10 | Andrew Moralez | Completed | 2019-07-27 | 0.08 | 2 | Ara Sotto | Completed | 2019-08-01 | 3.58 | 2 | Ara Sotto | Completed | 2019-07-24 | 8.92 | 2 | Brian Le | Completed | 2019-07-11 | 4.96 | 2 | Marcia Garay | Completed | 2019-07-09 | 2.21 | 1 |  | Completed | 2019-07-11 | 5.05 | 1 | Andrew Clemons | Completed |  | 59.71 | 1 | Marcia Garay | Current | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-02 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-08-05 | 0.88 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 18.08 | 2 | Marcia Garay | Completed | 2019-08-08 | 2.92 | 1 | Andrew Clemons | Completed | 2019-08-01 14:53 |  | 2019-08-01 | 3.5 | 2 | Ara Sotto | Completed | [10 empty] | 4.66 | [11 empty] | 2019-07-30 | 2019-08-01 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=26491 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26491 | https://completesolar.sugarondemand.com/#Opportunities/072d70e0-954f-11e9-b632-069e4f790264 | SCES Division |  | 2019-06-18 | HDM Electric Inc | 072d70e0-954f-11e9-b632-069e4f790264 | 5 | 5 | -5 | -2 | 5 | 5 | 5 | 3
26504 | PIP_APPROVED | PIP_APPROVED | 1103 West Avenue H 8 | Lancaster | CA | 93534 | Roger Long | 2019-06-27 19:13 | 6616180694 | rogelo@hotmail.com |  |  |  | 6805 | 0.151 | Bill Angevine | 2019-06-27 | 3.66 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-18 | 2019-06-20 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-27 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-26 07:00 | 2019-06-28 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-07-04 | 3.42 | 2 | Daniel Speegle | Completed | 2019-07-11 | 4.42 | 1 | Ara Sotto | Completed | 2019-07-27 | 8.54 | 5 | Brian Le | Completed | 2019-07-05 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-10 | 2.96 | 1 | Ernesto Enriquez | Completed | 2019-07-27 | 2.54 | 1 | Ara Sotto | Completed | 2019-08-06 | 6.58 | 2 | Ara Sotto | Completed | 2019-07-18 | 6.63 | 2 | Brian Le | Completed | 2019-07-05 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 0.67 | 1 |  | Completed | 2019-07-08 | 1.63 | 1 | Andrew Clemons | Completed | 2019-07-29 | 1.42 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-05 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-08-06 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-08-08 | 2.17 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.92 | 1 | Andrew Clemons | Completed | 2019-07-31 16:30 |  | 2019-07-31 | 2.54 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-08 | 2019-08-06 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26504 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26504 | https://completesolar.sugarondemand.com/#Opportunities/3cfcaaca-994a-11e9-9c09-022c40d974e6 | Emily Bowden |  | 2019-06-18 | JK Solar | 3cfcaaca-994a-11e9-9c09-022c40d974e6 | 4 | 10 | 0 | -2 | 5 | 5 | 5 | 8
26607 | PIP_APPROVED | PIP_APPROVED | 6364 Vittoria Avenue | Palmdale | CA | 93552 | Silvia Villaneda | 2019-06-24 12:52 | 6618398661 | silvia.villaneda@yahoo.com | Raymundo Avellaneda |  |  | 8786 | 0.001 | Alex Holdridge | 2019-06-24 | 4.575 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-22 | 2019-06-24 12:00 | LR6-60PB-305M | 305 | 15 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-07-28 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 07:00 | 2019-06-24 | 0.13 | 2 | Marcia Garay | Completed | 2019-06-28 | 4 | 2 | Daniel Speegle | Completed | 2019-07-17 | 11.71 | 1 | Ara Sotto | Completed |  | 70.04 | 5 | Brian Le | Current | 2019-07-06 | 3.54 | 3 | Andrew Moralez | Completed | 2019-07-17 | 7.42 | 0 | Andrew Moralez | Completed | 2019-07-27 | 5.96 | 1 | Ara Sotto | Completed | 2019-08-01 | 3.67 | 2 | Ara Sotto | Completed | 2019-07-12 | 5.88 | 2 | Brian Le | Completed | 2019-07-03 | 3.04 | 2 | Marcia Garay | Completed | 2019-07-01 | 0.71 | 1 |  | Completed | 2019-07-02 | 1.75 | 1 | Andrew Clemons | Completed | 2019-07-24 | 3.63 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-05 | 2.83 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-08-21 | 8.29 | 2 | Marcia Garay | Completed | 2019-08-15 | 4.33 | 1 | Andrew Clemons | Completed | 2019-07-31 16:52 | 2019-07-29 | 2019-07-31 | 2.58 | 2 | Ara Sotto | Completed | [10 empty] | 0.38 | [11 empty] | 2019-07-06 | 2019-08-01 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26607 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26607 | https://completesolar.sugarondemand.com/#Opportunities/75e767be-96b9-11e9-a65b-069e4f790264 | SCES Division | Henry Garcia | 2019-06-21 | JK Solar | 75e767be-96b9-11e9-a65b-069e4f790264 | 4 | 5 | 0 | -2 | 5 | 5 | 5 | 8
26998 | PIP_APPROVED | PIP_APPROVED | 44447 Palo Verde Street | Lancaster | CA | 93536 | Gergos Alhosari | 2019-07-11 07:30 | 6617940099 | fayrouz2@msn.com | FAYROUZ ABDULHAY | 6615269726 |  | 10585 | 0.115 | Bill Angevine | 2019-07-11 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-09 | 2019-07-10 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-27 | PTO Received | SunRun Monthly | 0 |  |  |  |  | 1 | 2019-07-26 07:00 | 2019-07-12 | 1.21 | 2 | Darlynn Lacap | Completed | 2019-07-15 | 1.17 | 2 | Jethro Andal | Completed | 2019-07-16 | 0.71 | 1 | Ara Sotto | Completed |  | 63 | 5 | Brian Le | Current | 2019-07-17 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-19 | 2.17 | 1 | Andrew Moralez | Completed | 2019-07-27 | 0.79 | 2 | Ara Sotto | Completed | 2019-07-30 | 1.54 | 2 | Ara Sotto | Completed | 2019-07-23 | 5.96 | 2 | Brian Le | Completed | 2019-07-15 | 0 | 2 | Darlynn Lacap | Completed | 2019-07-17 | 1.92 | 1 |  | Completed | 2019-07-22 | 4.79 | 1 | Jill Allen | Completed | 2019-07-29 | 1.38 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 0.08 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-08 | 5.96 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 1.04 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 6 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 4.29 | 1 | Andrew Clemons | Completed | 2019-07-29 19:43 |  | 2019-07-31 | 2.29 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-18 | 2019-07-30 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26998 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26998 | https://completesolar.sugarondemand.com/#Opportunities/633bdf1e-a3e8-11e9-b6ff-0630baf9dcb8 | SCES Division |  | 2019-07-09 | Green Road Solar Crew | 633bdf1e-a3e8-11e9-b6ff-0630baf9dcb8 | 4 | 3 | 0 | 2 | 5 | 5 | 5 | 12
27195 | PIP_APPROVED | PIP_APPROVED | 3260 Grande Vista Avenue | San Bernardino | CA | 92405 | Veronica Driskill | 2019-07-19 10:39 | 9094747652 | jmdriskill@gruwup.net | James Driskill | 9098828759 |  | 8953 | 0.161 | Bill Angevine | 2019-07-19 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-17 | 2019-07-18 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-27 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-27 07:00 | 2019-07-19 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-22 | 1.08 | 2 | Daniel Speegle | Completed | 2019-07-22 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-27 | 0.54 | 5 | Brian Le | Completed | 2019-07-25 | 0 | 3 | Andrew Moralez | Completed | 2019-07-25 | 0 | 1 | Andrew Moralez | Completed | 2019-07-27 | 0.08 | 2 | Ara Sotto | Completed | 2019-07-29 | 0.42 | 2 | Ara Sotto | Completed | 2019-07-26 | 2.71 | 2 | Brian Le | Completed | 2019-07-23 | 1.08 | 2 | Darlynn Lacap | Completed | 2019-07-25 | 2.79 | 1 |  | Completed | 2019-07-26 | 3.92 | 1 | Noe Gomez | Completed | 2019-07-29 | 0.54 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 1.21 | 2 | Jill Allen | Completed | [15 empty] | 2019-08-08 | 4 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 5.96 | 2 | Ashley Rockwood | Completed | 2019-08-30 | 10.13 | 2 | Darlynn Lacap | Completed | 2019-08-21 | 2.92 | 1 | Andrew Clemons | Completed | 2019-07-30 14:54 |  | 2019-08-02 | 4.42 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-26 | 2019-07-29 | SAN BERNARDINO | San Bernardino | https://heliotrack.completesolar.com/job.php?action=review&jobID=27195 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=27195 | https://completesolar.sugarondemand.com/#Opportunities/11d44a0c-aa4c-11e9-8375-069e4f790264 | 300 Stars Inc | Oscar Hernandez | 2019-07-17 | HDM Electric Inc | 11d44a0c-aa4c-11e9-8375-069e4f790264 | 6 | 2 | -5 | 4 | 5 | 5 | 5 | 9
24409 | PIP_APPROVED | PIP_APPROVED | 6173 Spring Valley Drive | Atwater | CA | 95301 | Mark Allen | 2019-06-24 10:43 | 2093269499 | soccrscot11@gmail.com |  |  |  | 10725 | 0.179 | Ricardo Virgen | 2019-05-21 | 7.015 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-05-16 | 2019-05-21 09:00 | LR6-60PB-305M | 305 | 23 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-07-26 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 07:00 | 2019-06-24 | 1.83 | 2 | Marcia Garay | Completed | 2019-06-27 | 9.88 | 2 | Daniel Speegle | Completed | 2019-07-03 | 17.95 | 1 | Christina Horton | Completed | 2019-07-23 | 8 | 5 | Brian Le | Completed | 2019-07-09 | 19.83 | 3 | Andrew Moralez | Completed | 2019-07-10 | 0.92 | 0 | Andrew Moralez | Completed | 2019-07-26 | 3.17 | 2 | Christina Horton | Completed | 2019-08-06 | 7.17 | 2 | Christina Horton | Completed | 2019-07-09 | 6.04 | 2 | Brian Le | Completed | 2019-06-28 | 7.13 | 2 | Marcia Garay | Completed | 2019-06-28 | 1.13 | 1 |  | Completed | 2019-07-04 | 11.54 | 1 | Andrew Clemons | Completed | 2019-07-29 | 4.5 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-02 | 1.75 | 2 | Ashley Rockwood | Completed | 2019-08-13 | 7.08 | 2 | Ashley Rockwood | Completed | 2019-08-20 | 5 | 2 | Marcia Garay | Completed | 2019-08-15 | 1.88 | 1 | Jeremiah Liend | Completed | 2019-07-31 12:03 | 2019-07-31 | 2019-07-31 | 3.29 | 2 | Christina Horton | Completed | [10 empty] | 15.13 | [11 empty] | 2019-07-09 | 2019-08-06 | ATWATER | Atwater | https://heliotrack.completesolar.com/job.php?action=review&jobID=24409 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24409 | https://completesolar.sugarondemand.com/#Opportunities/a6f6ef5e-7bfd-11e9-8ff3-069e4f790264 | Roofing 101 | Graham Dessert | 2019-04-08 | Infinity Energy Inc | a6f6ef5e-7bfd-11e9-8ff3-069e4f790264 | 5 | 11 | -5 | -2 | 5 | 5 | 5 | 3
26382 | PIP_APPROVED | PIP_APPROVED | 14300 Homestead Drive | Moreno Valley | CA | 92553 | Carlos M Gonzalez | 2019-06-14 14:29 | 9514868092 | mgonzalez_308@yahoo.com | Maria | +1 (951) 455-9214 |  | 10118 | 0.13 | Alex Holdridge | 2019-06-14 | 5.795 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-13 | 2019-06-14 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-26 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-06-18 | 1.79 | 2 | Darlynn Lacap | Completed | 2019-06-20 | 2.04 | 2 | Daniel Speegle | Completed | 2019-06-17 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-26 | 6.17 | 5 | Brian Le | Completed | 2019-07-03 | 5.83 | 3 | Ernesto Enriquez | Completed | 2019-07-03 | 0.08 | 25 | Andrew Moralez | Completed | 2019-07-26 | 1.46 | 2 | Ara Sotto | Completed | 2019-07-29 | 0.67 | 2 | Ara Sotto | Completed | 2019-07-18 | 3.63 | 2 | Brian Le | Completed | 2019-07-12 | 3.12 | 2 | Darlynn Lacap | Completed | 2019-06-22 | 1.5 | 1 |  | Completed | 2019-07-12 | 8.21 | 1 | Andrew Clemons | Completed | 2019-07-25 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 1.33 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-13 | 2.71 | 2 | Ashley Rockwood | Completed | 2019-08-14 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 7.92 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 0.96 | 1 | Andrew Clemons | Completed | 2019-08-08 16:17 | 2019-08-12 | 2019-08-08 | 8.13 | 2 | Ara Sotto | Completed | [10 empty] | 13.3 | [11 empty] | 2019-08-08 | 2019-07-29 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26382 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26382 | https://completesolar.sugarondemand.com/#Opportunities/6eea8dea-8eeb-11e9-960d-069e4f790264 | 300 Stars Inc |  | 2019-06-13 | Power Town Solar Electric | 6eea8dea-8eeb-11e9-960d-069e4f790264 | 13 | 3 | -15 | 2 | 5 | 5 | 5 | -3
26786 | PIP_APPROVED | PIP_APPROVED | 57912 Hidden Gold Drive | Yucca Valley | CA | 92284 | Catherine Collins | 2019-06-29 15:10 | 7609020928 | ccollins828@msn.com | FLOYD COLLINS | 7606416390 |  | 6864 | 0.15 | Shaun Labelle | 2019-06-29 | 4.27 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-28 | 2019-06-29 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-07-26 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-25 07:00 | 2019-07-01 | 0.42 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 2.25 | 2 | Jethro Andal | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-26 | 2.96 | 5 | Brian Le | Completed | 2019-07-17 | 2 | 3 | Andrew Moralez | Completed | 2019-07-25 | 9.71 | 0 | Andrew Moralez | Completed | 2019-07-26 | 1.5 | 1 | Ara Sotto | Completed | 2019-08-14 | 12.96 | 2 | Ara Sotto | Completed | 2019-07-23 | 12.96 | 2 | Brian Le | Completed | 2019-07-03 | 0 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 0.96 | 1 |  | Completed | 2019-07-08 | 1.67 | 1 | Andrew Clemons | Completed | 2019-07-25 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-10-09 | 4.17 | 2 | Ashley Rockwood | Completed | 2019-10-10 | 0.71 | 2 | Ashley Rockwood | Completed | 2019-10-18 | 6 | 2 | Darlynn Lacap | Completed | 2019-10-11 | 1.08 | 1 | Noe Gomez | Completed | 2019-08-02 19:44 |  | 2019-08-02 | 4.71 | 2 | Ara Sotto | Completed | [10 empty] | 43.92 | [11 empty] | 2019-07-24 | 2019-08-09 | YUCCA VALLEY | Yucca Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26786 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26786 | https://completesolar.sugarondemand.com/#Opportunities/95b71486-9aba-11e9-bec1-022c40d974e6 | Ryan Wilcox |  | 2019-06-28 | HDM Electric Inc | 95b71486-9aba-11e9-bec1-022c40d974e6 | 7 | 19 | -5 | -2 | 5 | 5 | 5 | 3
26860 | PIP_APPROVED | PIP_APPROVED | 4337 Lerida Drive | San Diego | CA | 92115 | Anthony Griffiths | 2019-07-03 14:23 | 6198736446 | meurigusa@gmail.com |  |  |  | 6471 | 0.16 | Chad Malloy | 2019-07-03 | 4.27 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-07-02 | 2019-07-03 12:00 | LR6-60PB-305M | 305 | 14 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-26 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-07-05 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-04 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-05 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-26 | 6.08 | 5 | Brian Le | Completed | 2019-07-16 | 7.04 | 3 | Andrew Moralez | Completed | 2019-07-16 | 0.08 | 15 | Ernesto Enriquez | Completed | 2019-07-26 | 1.42 | 1 | Ara Sotto | Completed | 2019-08-12 | 11.04 | 2 | Ara Sotto | Completed | 2019-07-18 | 8.88 | 2 | Brian Le | Completed | 2019-07-05 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-05 | 0.08 | 1 |  | Completed | 2019-07-09 | 2.08 | 1 | Jeremiah Liend | Completed |  | 61.54 | 1 | Marcia Garay | Current | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-01 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-08-02 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 22.92 | 2 | Marcia Garay | Completed |  | 55.13 | 1 | Jill Allen | Current | 2019-07-26 15:03 |  | 2019-07-26 | 0.08 | 2 | Christina Horton | Completed | [10 empty] | 0.58 | [11 empty] | 2019-08-06 | 2019-08-07 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26860 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26860 | https://completesolar.sugarondemand.com/#Opportunities/c3367a8e-9dd8-11e9-994c-0630baf9dcb8 | Jordan Litrownik |  | 2019-07-02 | Blalock Electric&Solar | c3367a8e-9dd8-11e9-994c-0630baf9dcb8 | 0 | 17 | 10 | -2 | 5 | 5 | 5 | 18
25194 | PIP_APPROVED | PIP_APPROVED | 1148 Ashford Lane | Lincoln | CA | 95648 | Bernard S Altamirano | 2019-06-14 13:39 | 9258647365 | brandi.altamirano@gmail.com |  | 9258640358 |  | 12992 | 0.19 | Ricardo Virgen | 2019-06-07 | 9.455 | Christina Horton | Blue Bright | Darlynn Lacap | 2019-06-04 | 2019-06-07 15:00 | LR6-60PB-305M | 305 | 31 | LONGi Solar | SolarEdge | SE10000A-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-06-14 | 0.71 | 2 | Darlynn Lacap | Completed | 2019-06-17 | 1.79 | 2 | Jethro Andal | Completed | 2019-07-01 | 10.13 | 1 | Christina Horton | Completed | 2019-07-25 | 4.67 | 5 | Brian Le | Completed | 2019-07-08 | 13.83 | 3 | Andrew Moralez | Completed | 2019-07-15 | 0.08 | 0 | Andrew Moralez | Completed | 2019-07-25 | 0.63 | 2 | Christina Horton | Completed | 2019-08-07 | 8.04 | 2 | Christina Horton | Completed | 2019-07-16 | 19.96 | 2 | Brian Le | Completed | 2019-06-17 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-06-17 | 0.04 | 1 |  | Completed | 2019-06-20 | 2.63 | 1 | Jill Allen | Completed | 2019-07-25 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-07-31 | 0.08 | 2 | Noe Gomez | Completed | 2019-07-03 | 0 | 4 | Darlynn Lacap | Completed | 2019-07-03 | 0 | 5 | Darlynn Lacap | Completed | 2019-07-03 | 0 | 12 | Darlynn Lacap | Completed | 2019-07-31 | 1.83 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 12.88 | 2 | Ashley Rockwood | Completed | 2019-08-29 | 8 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 3.25 | 1 | Andrew Clemons | Completed | 2019-07-29 19:28 |  | 2019-07-29 | 1.88 | 2 | Christina Horton | Completed | [10 empty] | 18.75 | [11 empty] | 2019-07-15 | 2019-08-07 | LINCOLN | Lincoln | https://heliotrack.completesolar.com/job.php?action=review&jobID=25194 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25194 | https://completesolar.sugarondemand.com/#Opportunities/e827c7a6-899e-11e9-be2a-022c40d974e6 | Blue Bright |  | 2019-05-02 | Golden Gate Electric Service | e827c7a6-899e-11e9-be2a-022c40d974e6 | 4 | 13 | 0 | -2 | 5 | 5 | 5 | 8
25338 | PIP_APPROVED | PIP_APPROVED | 26386 Primrose Way | Moreno Valley | CA | 92555 | Chibunna Nwaobia | 2019-06-25 11:02 | 9512868537 | chnwaobia@gmail.com | Ogonna | 951-289-2731 |  | 10687 |  | Chris Peaslee | 2019-05-07 | 6.1 | Ara Sotto | Solar Power Marketing | Darlynn Lacap | 2019-05-06 | 2019-05-07 09:00 | Q.PEAK-G4.1 305 | 305 | 20 | Hanwha Q CELLS | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun PPA Prepaid | [6 empty] | 2019-07-23 07:00 | 2019-06-25 | 0.29 | 2 | Darlynn Lacap | Completed | 2019-06-25 | 1.92 | 2 | Jethro Andal | Completed | 2019-06-28 | 15.83 | 1 | Ara Sotto | Completed | 2019-07-25 | 20.21 | 5 | Brian Le | Completed | 2019-06-25 | 0.88 | 3 | Ernesto Enriquez | Completed | 2019-06-25 | 0 | 25 | Ernesto Enriquez | Completed | 2019-07-25 | 16.67 | 2 | Ara Sotto | Completed | 2019-07-29 | 1.88 | 2 | Ara Sotto | Completed | 2019-06-26 | 14.08 | 2 | Brian Le | Completed | 2019-06-26 | 3.04 | 2 | Darlynn Lacap | Completed | 2019-06-25 | 2.88 | 1 |  | Completed | 2019-07-01 | 17.79 | 1 | Noe Gomez | Completed | 2019-07-23 | 6.96 | 1 | Darlynn Lacap | Completed | 2019-08-29 | 23.04 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-21 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-08-27 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-09-11 | 9.96 | 2 | Darlynn Lacap | Completed | 2019-08-29 | 1.79 | 1 | Jeremiah Liend | Completed | 2019-08-08 15:34 | 2019-08-12 | 2019-08-07 | 9.17 | 2 | Ara Sotto | Completed | [10 empty] | 20.13 | [11 empty] | 2019-07-31 | 2019-07-26 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=25338 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25338 | https://completesolar.sugarondemand.com/#Opportunities/93e53ce4-70fa-11e9-80c1-0630baf9dcb8 | Solar Power Marketing |  | 2019-05-06 | Power Town Solar Electric | 93e53ce4-70fa-11e9-80c1-0630baf9dcb8 | 13 | 4 | -15 | 0 | 5 | 5 | 5 | -5
25488 | PIP_APPROVED | PIP_APPROVED | 12787 Cypress Avenue | Victorville | CA | 92395 | Laverna Fletcher | 2019-05-15 19:13 | 7609512622 | carolyn.hook@yahoo.com | Carolyn Hook | 7602842586 |  | 13043 | 0.127 | Bill Angevine | 2019-05-15 | 6.71 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-05-10 | 2019-05-15 09:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Ground Mount | NO | 2019-07-25 | PTO Received | SunRun Monthly | [6 empty] | 2019-07-24 07:00 | 2019-05-16 | 0.75 | 2 | Darlynn Lacap | Completed | 2019-05-30 | 3.34 | 2 | Daniel Speegle | Completed | 2019-05-28 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-25 | 24.3 | 5 | Brian Le | Completed | 2019-05-31 | 0 | 3 | Andrew Moralez | Completed | 2019-06-12 | 8 | 10 | Andrew Moralez | Completed | 2019-07-25 | 18.63 | 2 | Ara Sotto | Completed | 2019-07-29 | 1.83 | 2 | Ara Sotto | Completed | 2019-06-20 | 12.59 | 2 | Brian Le | Completed | 2019-06-03 | 1.71 | 2 | Darlynn Lacap | Completed | 2019-05-31 | 0.96 | 1 |  | Completed | 2019-06-18 | 12.96 | 1 | Andrew Clemons | Completed | 2019-07-24 | 3.96 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 1.21 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-07-31 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-08-01 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-06 | 3.04 | 2 | Darlynn Lacap | Completed | 2019-08-02 | 1.25 | 1 | Andrew Clemons | Completed | 2019-07-26 14:48 |  | 2019-07-26 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 19.3 | [11 empty] | 2019-06-14 | 2019-07-29 | VICTORVILLE | Victorville | https://heliotrack.completesolar.com/job.php?action=review&jobID=25488 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25488 | https://completesolar.sugarondemand.com/#Opportunities/12fb8318-7780-11e9-b3d6-0630baf9dcb8 | SCES Division | Cody Booth | 2019-05-10 | HDM Electric Inc | 12fb8318-7780-11e9-b3d6-0630baf9dcb8 | 1 | 4 | 10 | 0 | 5 | 5 | 5 | 20
26252 | SP APPROVED |  | 38620 2nd Street East | Palmdale | CA | 93550 | Genara Carrera | 2019-06-11 10:21 | 6619474154 |  | Johanna Marquez | 6616740590 |  | 10182 | 0.145 | Bill Angevine | 2019-06-11 | 5.795 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-08 | 2019-06-10 09:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | MPU | 2019-07-25 | Installation Complete | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-18 07:00 | 2019-06-12 | 1.17 | 2 | Marcia Garay | Completed | 2019-06-25 | 5.87 | 2 | Jethro Andal | Completed | 2019-07-18 | 14.42 | 1 | Ara Sotto | Completed | 2019-07-25 | 7.79 | 5 | Brian Le | Completed | 2019-07-05 | 4.88 | 3 | Andrew Moralez | Completed | 2019-07-17 | 7.83 | 0 | Andrew Moralez | Completed | 2019-07-25 | 8.38 | 2 | Ara Sotto | Completed |  | 61.29 | 2 | Ara Sotto | Current | 2019-07-15 | 4.96 | 2 | Brian Le | Completed | 2019-07-08 | 6.17 | 2 | Marcia Garay | Completed | 2019-06-27 | 0.25 | 1 |  | Completed | 2019-07-01 | 1.92 | 1 | Jill Allen | Completed | 2019-07-18 | 3.63 | 1 | Marcia Garay | Completed |  | 0 | 2 |  | Inactive | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0 | 2 | Ara Sotto | Inactive |  | 69.71 | 1 | Ara Sotto | Current | 2019-06-25 | 0.13 | 2 | Marcia Garay | Completed | 15.45 | [11 empty] | 2019-07-05 |  | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26252 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26252 | https://completesolar.sugarondemand.com/#Opportunities/40d0f636-8c6d-11e9-ad3d-02ae981fbade | Solar Raze | Emily Bowden | 2019-06-07 | JK Solar | 40d0f636-8c6d-11e9-ad3d-02ae981fbade |  | 88 | -25 | -2 | 5 | 5 | 5 | -17
26303 | PIP_APPROVED | PIP_APPROVED | 6267 Idyllwild Court | Rialto | CA | 92377 | Nicholas Gutierrez | 2019-06-17 13:37 | 9092636210 | srrural@yahoo.com |  |  |  | 8372 | 0.002 | Chris Peaslee | 2019-06-17 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-10 | 2019-06-17 12:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 07:00 | 2019-06-18 | 0.83 | 2 | Marcia Garay | Completed | 2019-06-21 | 3.17 | 2 | Jethro Andal | Completed | 2019-06-21 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-25 | 4.13 | 5 | Brian Le | Completed | 2019-06-28 | 2.88 | 3 | Ernesto Enriquez | Completed | 2019-07-18 | 13.13 | 7 | Ernesto Enriquez | Completed | 2019-07-25 | 4.71 | 2 | Ara Sotto | Completed | 2019-08-01 | 4.96 | 2 | Ara Sotto | Completed | 2019-07-19 | 15.88 | 2 | Brian Le | Completed | 2019-06-26 | 2.96 | 2 | Marcia Garay | Completed | 2019-06-25 | 1.96 | 1 |  | Completed | 2019-07-01 | 5.79 | 1 | Jill Allen | Completed | 2019-07-29 | 6.75 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-14 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 30.08 | 2 | Ashley Rockwood | Completed |  | 17.21 | 2 | Marcia Garay | Current | 2019-10-03 | 4.88 | 1 | Andrew Clemons | Completed | 2019-07-29 15:42 | 2019-07-29 | 2019-07-29 | 1.96 | 2 | Ara Sotto | Completed | [10 empty] | 9.75 | [11 empty] | 2019-07-10 | 2019-08-01 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=26303 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26303 | https://completesolar.sugarondemand.com/#Opportunities/9ce87526-913f-11e9-84b4-02ae981fbade | 300 Stars Inc |  | 2019-06-10 | Zachary Noah Gamez | 9ce87526-913f-11e9-84b4-02ae981fbade | 4 | 7 | 0 | -2 | 5 | 5 | 5 | 8
26311 | PIP_APPROVED | PIP_APPROVED | 28356 Agajanian Dr | Santa Clarita | CA | 91390 | Steve Orbon | 2019-07-02 12:26 | 6612447852 | corbon07@yahoo.com | Cecile Orbon | 6612447852 |  | 6361 | 0.17 | Bill Angevine | 2019-07-02 | 3.965 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-17 | 2019-06-19 09:00 | LR6-60PB-305M | 305 | 13 | LONGi Solar | SolarEdge | SE3800H-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun Monthly | 1 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-07-05 | 1.83 | 2 | Marcia Garay | Completed | 2019-07-05 | 0.13 | 2 | Jethro Andal | Completed | 2019-07-03 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-25 | 11.96 | 5 | Brian Le | Completed | 2019-07-11 | 3.71 | 3 | Andrew Moralez | Completed | 2019-07-11 | 0.04 | 0 | Andrew Moralez | Completed | 2019-07-25 | 0.42 | 1 | Christina Horton | Completed | 2019-08-08 | 0.08 | 2 | Christina Horton | Completed | 2019-07-09 | 1.83 | 2 | Brian Le | Completed | 2019-07-05 | 0.04 | 2 | Marcia Garay | Completed | 2019-07-05 | 0.13 | 1 |  | Completed | 2019-07-08 | 1.08 | 1 | Andrew Clemons | Completed | 2019-07-25 | 0.46 | 1 | Marcia Garay | Completed | 2019-08-09 | 0.08 | 2 | Andrew Clemons | Completed | 2019-07-12 | 5.04 | 4 | Marcia Garay | Completed | 2019-07-16 | 2.21 | 5 | Marcia Garay | Completed | 2019-07-19 | 2.92 | 12 | Marcia Garay | Completed | 2019-08-12 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-08-13 | 0.16 | 2 | Jeremiah Liend | Completed | 2019-09-16 | 22.96 | 2 | Marcia Garay | Completed | 2019-08-15 | 1.92 | 1 | Jill Allen | Completed | 2019-08-07 11:45 |  | 2019-08-07 | 0.08 | 2 | Christina Horton | Completed | [10 empty] | 13.87 | [11 empty] | 2019-07-11 | 2019-08-08 | SANTA CLARITA | Santa Clarita | https://heliotrack.completesolar.com/job.php?action=review&jobID=26311 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26311 | https://completesolar.sugarondemand.com/#Opportunities/30acd084-9cff-11e9-b588-02ae981fbade | Joshua Shin |  | 2019-06-10 | Infinity Energy Inc | 30acd084-9cff-11e9-b588-02ae981fbade | 13 | 14 | -15 | -2 | 5 | 5 | 5 | -7
26574 | PIP_APPROVED | PIP_APPROVED | 3673 Ray Street | San Diego | CA | 92104 | Jodie Hulden | 2019-07-01 09:22 | 6199810857 | jodiehulden47@gmail.com | Cheryl Dean | 619-888-7212 |  | 5483 | 0.19 | Chad Malloy | 2019-07-01 | 3.355 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-26 | 2019-06-28 09:00 | LR6-60PB-305M | 305 | 11 | LONGi Solar |  |  | Composite | NO | 2019-07-25 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-25 07:00 | 2019-07-02 | 1.25 | 2 | Marcia Garay | Completed | 2019-07-09 | 3.96 | 2 | Daniel Speegle | Completed | 2019-07-17 | 6 | 1 | Christina Horton | Completed | 2019-07-25 | 2.17 | 5 | Brian Le | Completed | 2019-07-17 | 3.96 | 3 | Andrew Moralez | Completed | 2019-07-17 | 0.08 | 15 | Andrew Moralez | Completed | 2019-07-25 | 0.42 | 1 | Christina Horton | Completed | 2019-08-13 | 13 | 2 | Christina Horton | Completed | 2019-07-18 | 4.96 | 2 | Brian Le | Completed | 2019-07-11 | 1.71 | 2 | Marcia Garay | Completed | 2019-07-11 | 1.83 | 1 |  | Completed | 2019-07-19 | 7.71 | 1 | Andrew Clemons | Completed | 2019-07-25 | 0.46 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-21 | 5.88 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 17.13 | 2 | Ashley Rockwood | Completed | 2019-09-26 | 7.83 | 2 | Marcia Garay | Completed | 2019-09-17 | 0.67 | 1 | Andrew Clemons | Completed |  | 2019-08-16 | 2019-08-13 | 3.75 | 2 | Christina Horton | Completed | [10 empty] | 14.71 | [11 empty] | 2019-08-07 | 2019-08-13 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26574 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26574 | https://completesolar.sugarondemand.com/#Opportunities/553b1c78-9c1c-11e9-952b-02ae981fbade | Daniel Boyce | Lisa Mcdermott | 2019-06-20 | Infinity Energy Inc | 553b1c78-9c1c-11e9-952b-02ae981fbade | 19 | 19 | -15 | -2 | 5 | 5 | 5 | -7
26625 | PIP_APPROVED | PIP_APPROVED | 37833 Tackstem Street | Palmdale | CA | 93552 | Auda Vasquez | 2019-06-28 17:22 | 6616449600 | djvip661@yahoo.com | Jose Vasquez | 6614805715 |  | 9389 | 0.132 | Alex Holdridge | 2019-06-28 | 5.49 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-22 | 2019-06-24 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun Monthly | [6 empty] | 2019-07-25 07:00 | 2019-07-03 | 2.83 | 2 | Marcia Garay | Completed | 2019-07-05 | 1 | 2 | Jethro Andal | Completed | 2019-07-22 | 10.75 | 1 | Ara Sotto | Completed | 2019-07-25 | 5.13 | 5 | Brian Le | Completed | 2019-07-11 | 3.38 | 3 | Andrew Moralez | Completed | 2019-07-18 | 5.21 | 0 | Andrew Moralez | Completed | 2019-07-25 | 0.42 | 2 | Ara Sotto | Completed | 2019-08-01 | 5.04 | 2 | Ara Sotto | Completed | 2019-07-18 | 6.08 | 2 | Brian Le | Completed | 2019-07-10 | 2.75 | 2 | Marcia Garay | Completed | 2019-07-06 | 0.38 | 1 |  | Completed | 2019-07-09 | 1.96 | 1 | Andrew Clemons | Completed |  | 61.5 | 1 | Marcia Garay | Current | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-02 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-05 | 0.75 | 2 | Ashley Rockwood | Completed | 2019-08-08 | 3.17 | 2 | Marcia Garay | Completed | 2019-08-08 | 2.92 | 1 | Andrew Clemons | Completed | 2019-07-31 16:53 | 2019-07-30 | 2019-07-31 | 3.96 | 2 | Ara Sotto | Completed | [10 empty] | 8 | [11 empty] | 2019-07-11 | 2019-08-01 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=26625 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26625 | https://completesolar.sugarondemand.com/#Opportunities/eee6c11c-9a03-11e9-b0e8-02ae981fbade | Henry Garcia |  | 2019-06-22 | JK Solar | eee6c11c-9a03-11e9-b0e8-02ae981fbade | 6 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26660 | PIP_APPROVED | PIP_APPROVED | 701 West 139th Street | Compton | CA | 90222 | Lourdes Jimenez | 2019-06-27 10:39 | 5626537637 | lourdejimenez89@gmail.com | Ruben Jimenez |  |  | 9863 | 0.156 | Alex Holdridge | 2019-06-27 | 6.1 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-24 | 2019-06-27 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Composite | Line-side Tap | 2019-07-25 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-07-25 07:00 | 2019-06-27 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 3.71 | 2 | Daniel Speegle | Completed | 2019-06-27 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-25 | 1.21 | 5 | Brian Le | Completed | 2019-07-19 | 3.46 | 3 | Ernesto Enriquez | Completed | 2019-07-19 | 0 | 1 | Andrew Moralez | Completed | 2019-07-25 | 0.46 | 2 | Ara Sotto | Completed | 2019-08-19 | 16.88 | 2 | Ara Sotto | Completed | 2019-07-24 | 7.88 | 2 | Brian Le | Completed | 2019-07-12 | 0.13 | 2 | Marcia Garay | Completed | 2019-07-15 | 1.04 | 1 |  | Completed | 2019-07-16 | 2.08 | 1 | Jill Allen | Completed | 2019-08-01 | 5.46 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-12 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-08-20 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-09-24 | 0.08 | 2 | Zedel Morgan | Completed | 2019-08-22 | 0.08 | 1 | Noe Gomez | Completed | 2019-08-06 15:13 |  | 2019-08-07 | 0.08 | 2 | Ara Sotto | Completed |  | 56.5 | 1 | Ara Sotto | Current | 2019-07-15 | 1.17 | 2 | Marcia Garay | Completed | 11.68 | [11 empty] | 2019-07-22 | 2019-08-16 | COMPTON | Compton | https://heliotrack.completesolar.com/job.php?action=review&jobID=26660 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26660 | https://completesolar.sugarondemand.com/#Opportunities/98c43d9e-9901-11e9-8de7-02ae981fbade | Solar Raze | Cesar Valdizan | 2019-06-24 | Green Road Solar Crew | 98c43d9e-9901-11e9-8de7-02ae981fbade | 13 | 25 | -15 | -2 | 5 | 5 | 5 | -7
26925 | PIP_APPROVED | PIP_APPROVED | 1723 Rhone Avenue | Highland | CA | 92346 | Charles Godsey | 2019-07-08 10:21 | 9094859002 | charlesgodsey74@gmail.com |  |  |  | 12845 | 0.16 | Shaun Labelle | 2019-07-08 | 7.625 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-07-05 | 2019-07-06 15:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Composite | NO | 2019-07-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-25 07:00 | 2019-07-10 | 2.04 | 2 | Marcia Garay | Completed | 2019-07-12 | 1.92 | 2 | Jethro Andal | Completed | 2019-07-19 | 5.21 | 1 | Ara Sotto | Completed | 2019-07-25 | 4.21 | 5 | Brian Le | Completed | 2019-07-18 | 2.21 | 3 | Ernesto Enriquez | Completed | 2019-07-18 | 0 | 14 | Ernesto Enriquez | Completed | 2019-07-25 | 0.46 | 2 | Ara Sotto | Completed | 2019-08-02 | 0.12 | 2 | Ara Sotto | Completed | 2019-07-19 | 3.67 | 2 | Brian Le | Completed | 2019-07-15 | 1.25 | 2 | Marcia Garay | Completed | 2019-07-16 | 2 | 1 |  | Completed | 2019-07-25 | 8.75 | 1 | Andrew Clemons | Completed | 2019-07-30 | 3.42 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-26 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-08-27 | 0.08 | 2 | Jeremiah Liend | Completed | 2019-09-03 | 0.08 | 2 | Delvin Villavicencio | Completed | 2019-08-29 | 0.08 | 1 | Noe Gomez | Completed | 2019-07-31 15:25 |  | 2019-08-11 | 0.12 | 2 | Ara Sotto | Completed | [10 empty] | 64.12 | [11 empty] | 2019-08-07 | 2019-08-02 | HIGHLAND | Highland | https://heliotrack.completesolar.com/job.php?action=review&jobID=26925 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26925 | https://completesolar.sugarondemand.com/#Opportunities/b8d47d5a-a1a4-11e9-bef1-022c40d974e6 | 300 Stars Inc |  | 2019-07-05 | Power Town Solar Electric | b8d47d5a-a1a4-11e9-bef1-022c40d974e6 | 17 | 8 | -15 | -2 | 5 | 5 | 5 | -7
26941 | PIP_APPROVED | PIP_APPROVED | 44009 Ruthron Avenue | Lancaster | CA | 93536 | Martha Wood | 2019-07-09 16:29 | 6618782530 | jwoodinca@aol.com |  |  |  | 11912 | 0.15 | Bill Angevine | 2019-07-09 | 6.1 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-06 | 2019-07-09 09:00 | LR6-60PB-305M | 305 | 20 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-25 07:00 | 2019-07-10 | 0.67 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 2.13 | 2 | Daniel Speegle | Completed | 2019-07-16 | 1.92 | 1 | Ara Sotto | Completed | 2019-07-25 | 5.13 | 5 | Brian Le | Completed | 2019-07-12 | 0 | 3 | Andrew Moralez | Completed | 2019-07-17 | 3.04 | 1 | Andrew Moralez | Completed | 2019-07-25 | 0.42 | 2 | Ara Sotto | Completed | 2019-08-01 | 5.04 | 2 | Ara Sotto | Completed | 2019-07-18 | 2.96 | 2 | Brian Le | Completed | 2019-07-15 | 1 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 0.13 | 1 |  | Completed | 2019-07-18 | 4.08 | 1 | Noe Gomez | Completed | 2019-07-25 | 0.29 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-05 | 2.88 | 2 | Ashley Rockwood | Completed | 2019-08-06 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 9.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 1.92 | 1 | Andrew Clemons | Completed | 2019-07-26 09:24 |  | 2019-07-31 | 3.92 | 2 | Ara Sotto | Completed | [10 empty] | 0 | [11 empty] | 2019-07-15 | 2019-08-01 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26941 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26941 | https://completesolar.sugarondemand.com/#Opportunities/526c44d2-a2a1-11e9-a02f-069e4f790264 | SCES Division |  | 2019-07-06 | HDM Electric Inc | 526c44d2-a2a1-11e9-a02f-069e4f790264 | 6 | 7 | -5 | -2 | 5 | 5 | 5 | 3
26955 | PIP_APPROVED | PIP_APPROVED | 44253 36th Street West | Lancaster | CA | 93536 | Roy Tapia | 2019-07-09 16:55 | 6619027604 | roytapia@verizon.net | Ann Tapia | 6619027461 |  | 13199 | 0.13 | Bill Angevine | 2019-07-09 | 6.71 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-07-08 | 2019-07-09 15:00 | LR6-60PB-305M | 305 | 22 | LONGi Solar | SolarEdge | SE6000H-US RGM | Tile Concrete | NO | 2019-07-25 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-24 07:00 | 2019-07-10 | 0.83 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 1.96 | 2 | Daniel Speegle | Completed | 2019-07-11 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-25 | 3.83 | 5 | Brian Le | Completed | 2019-07-12 | 0 | 3 | Andrew Moralez | Completed | 2019-07-17 | 3.04 | 1 | Andrew Moralez | Completed | 2019-07-25 | 1.21 | 2 | Ara Sotto | Completed | 2019-08-30 | 26.25 | 2 | Ara Sotto | Completed | 2019-07-18 | 0.08 | 2 | Brian Le | Completed | 2019-07-19 | 2.34 | 2 | Darlynn Lacap | Completed | 2019-07-12 | 0.08 | 1 |  | Completed | 2019-07-19 | 4.79 | 1 | Noe Gomez | Completed | 2019-07-24 | 0.54 | 1 | Darlynn Lacap | Completed |  | 35.04 | 2 | Andrew Clemons | Current | [15 empty] | 2019-07-30 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-07-31 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 18.13 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 5.96 | 1 | Andrew Clemons | Completed | 2019-07-26 14:26 |  | 2019-07-26 | 1.17 | 2 | Ara Sotto | Completed | [10 empty] | 2.58 | [11 empty] | 2019-07-15 | 2019-08-30 | LANCASTER | Lancaster | https://heliotrack.completesolar.com/job.php?action=review&jobID=26955 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26955 | https://completesolar.sugarondemand.com/#Opportunities/ff552cc4-a2a4-11e9-b9f3-069e4f790264 | SCES Division |  | 2019-07-08 | Green Road Solar Crew | ff552cc4-a2a4-11e9-b9f3-069e4f790264 | 1 | 36 | 10 | -2 | 5 | 5 | 5 | 18
25335 | PIP_APPROVED | PIP_APPROVED | 4954 Vandever Avenue | San Diego | CA | 92120 | Randall Miller | 2019-06-20 15:58 | 6192516956 | rwmiller1@cox.net | Cheryl Miller |  |  | 4613 | 0.187 | Ryan Malloy | 2019-05-09 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-06 | 2019-05-09 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-24 | PTO Received | SunRun Monthly | [6 empty] | 2019-07-24 07:00 | 2019-06-21 | 3.66 | 2 | Darlynn Lacap | Completed | 2019-06-21 | 6.88 | 2 | Daniel Speegle | Completed | 2019-07-15 | 21.09 | 1 | Christina Horton | Completed | 2019-07-24 | 8.83 | 5 | Brian Le | Completed | 2019-07-08 | 7.79 | 3 | Andrew Moralez | Completed | 2019-07-15 | 5.13 | 15 | Andrew Moralez | Completed | 2019-07-24 | 0.42 | 1 | Christina Horton | Completed | 2019-08-26 | 4.71 | 2 | Christina Horton | Completed | 2019-07-09 | 10.04 | 2 | Brian Le | Completed | 2019-06-24 | 4.91 | 2 | Darlynn Lacap | Completed | 2019-06-25 | 0.29 | 1 |  | Completed | 2019-07-14 | 18.63 | 1 | Andrew Clemons | Completed | 2019-07-24 | 0.54 | 1 | Darlynn Lacap | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-20 | 6.88 | 2 | Ashley Rockwood | Completed | 2019-08-22 | 1.79 | 2 | Ashley Rockwood | Completed | 2019-09-09 | 11.17 | 2 | Darlynn Lacap | Completed | 2019-08-23 | 1 | 1 | Jeremiah Liend | Completed | 2019-07-29 15:11 |  | 2019-07-29 | 2.83 | 2 | Christina Horton | Completed | [10 empty] | 46.16 | [11 empty] | 2019-07-29 | 2019-08-22 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=25335 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25335 | https://completesolar.sugarondemand.com/#Opportunities/49871abc-7296-11e9-8708-02ae981fbade | Valerie Jetter | Kellee Benjamin | 2019-05-06 | Infinity Energy Inc | 49871abc-7296-11e9-8708-02ae981fbade | 5 | 33 | -5 | -2 | 5 | 5 | 5 | 3
26097 | PIP_APPROVED | PIP_APPROVED | 3437 Arizona Street | San Diego | CA | 92104 | Shane Hardin | 2019-06-10 17:47 | 6198717034 | shanehodads57@gmail.com | Varvara Hardin | 6197530235 |  | 3561 | 0.17 | Michael Marlaire | 2019-06-10 | 2.44 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-01 | 2019-06-06 09:00 | LR6-60PB-305M | 305 | 8 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 | 2019-06-11 | 0.67 | 2 | Marcia Garay | Completed | 2019-06-14 | 3.33 | 2 | Jethro Andal | Completed | 2019-07-12 | 18.88 | 1 | Ara Sotto | Completed | 2019-07-23 | 5.5 | 5 | Brian Le | Completed | 2019-06-19 | 0 | 3 | Ernesto Enriquez | Completed | 2019-07-12 | 15.92 | 15 | Ernesto Enriquez | Completed | 2019-07-24 | 1.13 | 1 | Christina Horton | Completed | 2019-08-02 | 5.13 | 2 | Christina Horton | Completed | 2019-07-09 | 14.92 | 2 | Brian Le | Completed | 2019-06-17 | 0.71 | 2 | Marcia Garay | Completed | 2019-06-19 | 1.04 | 1 |  | Completed | 2019-06-24 | 5.5 | 1 | Andrew Clemons | Completed | 2019-08-01 | 7.46 | 1 | Marcia Garay | Completed | 2019-07-30 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-01 | 5.29 | 2 | Ashley Rockwood | Completed | 2019-08-06 | 2.58 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 26.13 | 2 | Marcia Garay | Completed | 2019-08-08 | 1.79 | 1 | Noe Gomez | Completed | 2019-07-25 17:07 |  | 2019-07-25 | 1.25 | 2 | Christina Horton | Completed | [10 empty] | 8.34 | [11 empty] | 2019-07-11 | 2019-08-02 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26097 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26097 | https://completesolar.sugarondemand.com/#Opportunities/65e909ee-8be2-11e9-ae82-0630baf9dcb8 | Trey Greenhill | Lisa Mcdermott | 2019-06-01 | Infinity Energy Inc | 65e909ee-8be2-11e9-ae82-0630baf9dcb8 | 1 | 9 | 10 | -2 | 5 | 5 | 5 | 18
26355 | PIP_APPROVED | PIP_APPROVED | 1426 Roxanne Drive | El Cajon | CA | 92021 | Ryan McDowell | 2019-07-02 16:28 | 8605144783 | ryancmcdowell@yahoo.com |  |  |  | 8930 | 0.188 | Ryan Malloy | 2019-06-24 | 5.49 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-18 | 2019-06-21 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-24 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-23 07:00 | 2019-07-02 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-07-08 | 6.67 | 2 | Jethro Andal | Completed | 2019-07-12 | 6.3 | 1 | Christina Horton | Completed | 2019-07-23 | 4.01 | 5 | Brian Le | Completed | 2019-07-16 | 4.71 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 0.55 | 0 | Ernesto Enriquez | Completed | 2019-07-24 | 1.21 | 2 | Christina Horton | Completed | 2019-07-31 | 3.88 | 2 | Christina Horton | Completed | 2019-07-08 | 0.08 | 2 | Brian Le | Completed | 2019-07-08 | 0.38 | 2 | Darlynn Lacap | Completed | 2019-07-09 | 1.71 | 1 |  | Completed | 2019-07-09 | 3.17 | 1 | Andrew Clemons | Completed | 2019-07-23 | 0.5 | 1 | Darlynn Lacap | Completed |  | 57.08 | 2 | Jill Allen | Current | [15 empty] | 2019-08-05 | 3.04 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 3.88 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 5.83 | 2 | Darlynn Lacap | Completed | 2019-08-15 | 4.13 | 1 | Andrew Clemons | Completed | 2019-07-31 09:29 | 2019-08-09 | 2019-07-31 | 5.21 | 2 | Christina Horton | Completed | [10 empty] | 9.92 | [11 empty] | 2019-07-16 | 2019-08-20 | EL CAJON | El Cajon | https://heliotrack.completesolar.com/job.php?action=review&jobID=26355 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26355 | https://completesolar.sugarondemand.com/#Opportunities/42c6d2c6-969f-11e9-be2c-069e4f790264 | Matthew McKay | Jonathan Weaver | 2019-06-12 | Infinity Energy Inc | 42c6d2c6-969f-11e9-be2c-069e4f790264 | 7 | 7 | -5 | -2 | 5 | 5 | 5 | 3
24044 | PIP_APPROVED | PIP_APPROVED | 1718 Boyle Place | Escondido | CA | 92027 | Joseph Clark | 2019-04-15 13:26 | 7605356628 | josephclark007@yahoo.com | Irma Clark | 7605947261 |  | 13526 | 0.164 | Ryan Malloy | 2019-04-09 | 7.93 | Ara Sotto | Tier1 Power | Marcia Garay | 2019-04-02 | 2019-04-08 15:00 | Q.PEAK-G4.1 305 | 305 | 26 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Composite | MPU | 2019-07-23 | Installation Complete | SunRun Monthly | 0 | 0 |  | 0 |  |  | 2019-07-23 07:00 | 2019-05-03 | 5.79 | 2 | Marcia Garay | Completed | 2019-05-07 | 1.96 | 2 | Daniel Speegle | Completed | 2019-05-17 | 8.12 | 1 | Ara Sotto | Completed |  | 80.62 | 5 | Christina Horton | Current | 2019-05-09 | 2 | 3 | Andrew Moralez | Completed | 2019-05-09 | 0.08 | 15 | Andrew Moralez | Completed | 2019-07-23 | 0 | 2 | Ara Sotto | Completed | 2019-09-12 | 23.25 | 2 | Ara Sotto | Completed | 2019-06-12 | 19.21 | 2 | Brittany Faconti | Completed | 2019-05-08 | 1.25 | 2 | Marcia Garay | Completed | 2019-05-07 | 0.17 | 1 |  | Completed | 2019-05-30 | 16.25 | 1 | Jill Allen | Completed | 2019-08-22 | 22.13 | 1 | Marcia Garay | Completed | 2019-07-24 | 0.08 | 2 | Noe Gomez | Completed | [16 empty] | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 2 |  | Inactive |  | 0 | 1 |  | Inactive |  |  |  | 0.08 | 2 | Ara Sotto | Inactive |  | 40.58 | 1 | Ara Sotto | Current | 2019-05-09 | 1.96 | 2 | Marcia Garay | Completed | 41.64 | [11 empty] | 2019-05-31 | 2019-09-12 | ESCONDIDO | Escondido | https://heliotrack.completesolar.com/job.php?action=review&jobID=24044 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=24044 | https://completesolar.sugarondemand.com/#Opportunities/12b59f44-5b18-11e9-a4a9-022c40d974e6 | Jordan Litrownik |  | 2019-03-25 | Blalock Electric&Solar | 12b59f44-5b18-11e9-a4a9-022c40d974e6 |  | 51 | -25 | -2 | 5 | 5 | 5 | -17
25163 | PIP_APPROVED | PIP_APPROVED | 37633 Vintage Drive | Palmdale | CA | 93550 | Guadalupe Velarde | 2019-06-11 16:31 | 5628221156 | gorda58@sbcglobal.net | (661)382-1433 | (661)382-1433 |  | 13944 | 0.002 | Alex Holdridge | 2019-05-01 | 8.54 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-04-30 | 2019-05-01 11:00 | Q.PEAK-G4.1 305 | 305 | 28 | Hanwha Q CELLS | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-07-23 | PTO Received | SunRun Monthly |  | 0 |  |  | 1 |  | 2019-07-23 | 2019-06-12 | 8.63 | 2 | Marcia Garay | Completed | 2019-06-14 | 3.38 | 2 | Jethro Andal | Completed | 2019-06-26 | 15.54 | 1 | Ara Sotto | Completed | 2019-07-23 | 3.13 | 5 | Brian Le | Completed | 2019-07-09 | 17.13 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 10.83 | 0 | Ernesto Enriquez | Completed | 2019-07-23 | 0.55 | 2 | Ara Sotto | Completed | 2019-07-31 | 5.75 | 2 | Ara Sotto | Completed | 2019-07-18 | 21.04 | 2 | Brian Le | Completed | 2019-06-18 | 8.58 | 2 | Marcia Garay | Completed | 2019-06-14 | 0.54 | 1 |  | Completed | 2019-06-17 | 3.42 | 1 | Andrew Clemons | Completed | 2019-07-24 | 1.59 | 1 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-01 | 1 | 2 | Ashley Rockwood | Completed | 2019-08-02 | 1 | 2 | Ashley Rockwood | Completed | 2019-08-12 | 6.13 | 2 | Marcia Garay | Completed |  | 55.33 | 1 | Jill Allen | Current | 2019-07-30 16:49 | 2019-07-30 | 2019-07-31 | 5.67 | 2 | Ara Sotto | Completed | [10 empty] | 36.74 | 2019-06-28 | 0 | 14 | James Fernandez | Completed | 2019-06-29 | 2019-06-29 | 3.29 | 1 | James Fernandez | Completed | 2019-07-09 | 2019-07-31 | PALMDALE | Palmdale | https://heliotrack.completesolar.com/job.php?action=review&jobID=25163 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25163 | https://completesolar.sugarondemand.com/#Opportunities/2250d9d6-6c49-11e9-9b14-069e4f790264 | SCES Division |  | 2019-04-30 | JK Solar | 2250d9d6-6c49-11e9-9b14-069e4f790264 | 8 | 8 | -5 | -2 | 5 | 5 | 5 | 3
25185 | PIP_APPROVED | PIP_APPROVED | 9276 High Rise Way | Santee | CA | 92071 | Darrel Baldridge | 2019-05-02 09:37 | 6198551609 | jddbathome@cox.net | Jeanne Mellon | 619-855-1173 |  | 8138 | 0.22 | Ryan Malloy | 2019-05-02 | 5.185 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-04-30 | 2019-05-01 15:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 1 | 1 | 2019-07-22 07:00 | 2019-05-02 | 0 | 2 | Marcia Garay | Completed | 2019-05-06 | 2.21 | 2 | Jethro Andal | Completed | 2019-05-24 | 13.96 | 1 | Christina Horton | Completed | 2019-07-17 | 40.75 | 5 | Christina Horton | Completed | 2019-05-16 | 4.13 | 3 | Andrew Moralez | Completed | 2019-06-06 | 13.75 | 10 | Andrew Moralez | Completed | 2019-07-23 | 1.97 | 2 | Christina Horton | Completed | 2019-07-26 | 3.17 | 2 | Christina Horton | Completed | 2019-05-19 | 8.46 | 2 | Brittany Faconti | Completed | 2019-05-07 | 0.88 | 2 | Marcia Garay | Completed | 2019-05-10 | 3.79 | 1 |  | Completed | 2019-05-17 | 5.67 | 1 | Jeremiah Liend | Completed | 2019-07-22 | 1.34 | 1 | Marcia Garay | Completed | 2019-07-24 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-07-31 | 2.92 | 2 | Ashley Rockwood | Completed | 2019-08-01 | 1.08 | 2 | Ashley Rockwood | Completed | 2019-08-05 | 2 | 2 | Marcia Garay | Completed | 2019-08-02 | 1.08 | 1 | Andrew Clemons | Completed | 2019-07-26 17:01 |  | 2019-07-26 | 3.17 | 2 | Christina Horton | Completed | [10 empty] | 27.34 | 2019-07-16 | 1.46 | 14 | James Fernandez | Completed | 2019-08-02 | 2019-08-02 | 0.46 | 1 | James Fernandez | Completed | 2019-05-31 | 2019-07-26 | SANTEE | Santee | https://heliotrack.completesolar.com/job.php?action=review&jobID=25185 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25185 | https://completesolar.sugarondemand.com/#Opportunities/903e80e2-6cf8-11e9-85f4-02ae981fbade | Domingo Beddingfield | Jonathan Weaver | 2019-04-30 | Infinity Energy Inc | 903e80e2-6cf8-11e9-85f4-02ae981fbade | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
25597 | PIP_APPROVED | PIP_APPROVED | 1310 North Ash Avenue | Rialto | CA | 92376 | Nicolas Garcia | 2019-06-28 16:24 | 9092588542 | nramos7769.nr@gmail.com | Rosadelia Ramos | 909-284-3778 |  | 8287 | 0.166 | Alex Holdridge | 2019-06-13 | 5.185 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-05-16 | 2019-05-18 17:00 | LR6-60PB-305M | 305 | 17 | LONGi Solar | SolarEdge | SE5000H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 07:00 | 2019-06-28 | 1.83 | 2 | Marcia Garay | Completed | 2019-07-03 | 2.92 | 2 | Jethro Andal | Completed | 2019-07-17 | 8.87 | 1 | Ara Sotto | Completed | 2019-07-23 | 3.17 | 5 | Brian Le | Completed | 2019-07-06 | 0.38 | 3 | Andrew Moralez | Completed | 2019-07-16 | 6.38 | 7 | Andrew Moralez | Completed | 2019-07-23 | 0.67 | 1 | Ara Sotto | Completed | 2019-07-29 | 3.67 | 2 | Ara Sotto | Completed | 2019-07-18 | 8.83 | 2 | Brian Le | Completed | 2019-07-05 | 0.96 | 2 | Marcia Garay | Completed | 2019-07-05 | 0.96 | 1 |  | Completed | 2019-07-08 | 2 | 1 | Andrew Clemons | Completed | 2019-07-23 | 0.88 | 1 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-07 | 2.04 | 2 | Ashley Rockwood | Completed | 2019-08-08 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-08-21 | 9.13 | 2 | Marcia Garay | Completed | 2019-08-09 | 1.21 | 1 | Andrew Clemons | Completed | 2019-07-25 15:15 |  | 2019-07-26 | 2.67 | 2 | Ara Sotto | Completed | [10 empty] | 15.92 | [11 empty] | 2019-07-17 | 2019-07-29 | RIALTO | Rialto | https://heliotrack.completesolar.com/job.php?action=review&jobID=25597 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25597 | https://completesolar.sugarondemand.com/#Opportunities/5b35a948-8e0e-11e9-aef6-069e4f790264 | Hugo Vicuna |  | 2019-05-15 | Power Town Solar Electric | 5b35a948-8e0e-11e9-aef6-069e4f790264 | 3 | 6 | 0 | -2 | 5 | 5 | 5 | 8
25854 | PIP_APPROVED | PIP_APPROVED | 3601 Arnold Avenue | San Diego | CA | 92104 | Timothy Cathey | 2019-06-06 19:54 | 6199809419 | catfood91@yahoo.com | Laura Cathey | 6199928925 |  | 5496 | 0.19 | Chad Malloy | 2019-06-06 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-05-24 | 2019-06-03 16:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | [6 empty] | 2019-07-23 07:00 | 2019-06-11 | 2.54 | 2 | Darlynn Lacap | Completed | 2019-06-14 | 3.29 | 2 | Daniel Speegle | Completed | 2019-07-12 | 18.92 | 1 | Ara Sotto | Completed | 2019-07-23 | 10 | 5 | Brian Le | Completed | 2019-08-13 | 3.96 | 3 | Ernesto Enriquez | Completed | 2019-08-28 | 8.04 | 15 | Andrew Moralez | Completed | 2019-07-23 | 0.38 | 1 | Christina Horton | Completed | 2019-09-09 | 33 | 2 | Christina Horton | Completed | 2019-07-08 | 13.04 | 2 | Brian Le | Completed | 2019-06-18 | 1.83 | 2 | Darlynn Lacap | Completed | 2019-08-12 | 0.37 | 1 |  | Completed | 2019-07-01 | 10.83 | 1 | Andrew Clemons | Completed | 2019-09-03 | 1 | 1 | Darlynn Lacap | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-09-10 | 1 | 2 | Ashley Rockwood | Completed | 2019-09-12 | 1.88 | 2 | Ashley Rockwood | Completed | 2019-09-24 | 7.96 | 2 | Darlynn Lacap | Completed |  | 27.17 | 1 | Andrew Clemons | Current |  | 2019-09-06 | 2019-09-09 | 32.04 | 2 | Christina Horton | Completed | [10 empty] | 58.67 | [11 empty] | 2019-09-09 | 2019-09-09 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=25854 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=25854 | https://completesolar.sugarondemand.com/#Opportunities/85a6e910-88cf-11e9-a565-022c40d974e6 | Trey Greenhill | Lisa Mcdermott | 2019-05-23 | Infinity Energy Inc | 85a6e910-88cf-11e9-a565-022c40d974e6 | 48 | 48 | -25 | -2 | 5 | 5 | 5 | -17
26158 | PIP_APPROVED | PIP_APPROVED | 12011 Canary Court | Grand Terrace | CA | 92313 | Terry McNeill | 2019-06-07 12:19 | 9098255872 | 4tazman@sbcglobal.net |  | 9096453233 |  | 11658 | 0.17 | Michael Marlaire | 2019-06-07 | 7.93 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-04 | 2019-06-07 09:00 | LR6-60PB-305M | 305 | 26 | LONGi Solar | SolarEdge Technologies | SE10000H-US | Tile Concrete | Line-side Tap | 2019-07-23 | PTO Received | SunRun Monthly |  | 0 |  | 0 | 0 |  | 2019-07-22 07:00 | 2019-06-11 | 0.17 | 2 | Darlynn Lacap | Completed | 2019-06-14 | 3.16 | 2 | Jethro Andal | Completed | 2019-06-07 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-23 | 8.92 | 5 | Brian Le | Completed | 2019-06-19 | 0.33 | 3 | Andrew Moralez | Completed | 2019-07-18 | 19.83 | 14 | Andrew Moralez | Completed | 2019-07-23 | 7.63 | 2 | Ara Sotto | Completed | 2019-07-23 | 0 | 2 | Ara Sotto | Completed | 2019-07-10 | 15.29 | 2 | Brian Le | Completed | 2019-06-17 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-06-19 | 1 | 1 |  | Completed | 2019-06-25 | 5.17 | 1 | Andrew Clemons | Completed | 2019-07-22 | 1.13 | 1 | Darlynn Lacap | Completed | 2019-07-25 | 1.71 | 2 | Jill Allen | Completed | [15 empty] | 2019-07-30 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-08-01 | 2.21 | 2 | Ashley Rockwood | Completed | 2019-08-26 | 1.75 | 2 | Darlynn Lacap | Completed |  | 55.79 | 1 | Andrew Clemons | Current | 2019-07-25 15:03 |  | 2019-07-25 | 0.08 | 2 | Christina Horton | Completed | 2019-07-25 | 8.09 | 1 | Ara Sotto | Completed | 2019-06-18 | 0 | 2 | Darlynn Lacap | Completed | 51.06 | [11 empty] | 2019-07-10 | 2019-07-23 | GRAND TERRACE | Grand Terrace | https://heliotrack.completesolar.com/job.php?action=review&jobID=26158 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26158 | https://completesolar.sugarondemand.com/#Opportunities/17e011ec-8959-11e9-8531-0630baf9dcb8 | 300 Stars Inc |  | 2019-06-04 | HDM Electric Inc | 17e011ec-8959-11e9-8531-0630baf9dcb8 | 0 | 0 | 10 | 5 | 5 | 5 | 5 | 25
26162 | PIP_APPROVED | PIP_APPROVED | 4348 Aragon Way | San Diego | CA | 92115 | Marilyn Phelps | 2019-06-17 14:41 | 6195821382 | marilynmadre@gmail.com |  |  |  | 4472 | 0.18 | Ryan Malloy | 2019-06-17 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-06-14 | 2019-06-17 12:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | [6 empty] | 2019-07-23 07:00 | 2019-06-18 | 0.75 | 2 | Marcia Garay | Completed | 2019-06-21 | 3.21 | 2 | Jethro Andal | Completed | 2019-07-12 | 14 | 1 | Christina Horton | Completed | 2019-07-23 | 8.83 | 5 | Brian Le | Completed | 2019-07-09 | 9 | 3 | Ernesto Enriquez | Completed | 2019-07-15 | 3.96 | 15 | Ernesto Enriquez | Completed | 2019-07-23 | 0.38 | 1 | Christina Horton | Completed | 2019-09-04 | 26.83 | 2 | Christina Horton | Completed | 2019-07-09 | 9.88 | 2 | Brian Le | Completed | 2019-06-24 | 0.88 | 2 | Marcia Garay | Completed | 2019-06-25 | 2 | 1 |  | Completed | 2019-07-03 | 8 | 1 | Andrew Clemons | Completed | 2019-07-24 | 1.54 | 1 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-07-31 | 3.83 | 2 | Ashley Rockwood | Completed | 2019-08-02 | 2.08 | 2 | Ashley Rockwood | Completed | 2019-09-05 | 23.04 | 2 | Marcia Garay | Completed |  | 55.13 | 1 | Noe Gomez | Current | 2019-07-25 17:08 |  | 2019-07-25 | 2.04 | 2 | Christina Horton | Completed | [10 empty] | 10.55 | [11 empty] | 2019-07-30 | 2019-09-04 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26162 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26162 | https://completesolar.sugarondemand.com/#Opportunities/a5e97720-9148-11e9-b33f-02ae981fbade | Blake Sanders |  | 2019-06-04 | Infinity Energy Inc | a5e97720-9148-11e9-b33f-02ae981fbade | 2 | 43 | 7 | -2 | 5 | 5 | 5 | 15
26338 | PIP_APPROVED | PIP_APPROVED | 25581 San Lupe Avenue | Moreno Valley | CA | 92551 | Robert Morales | 2019-07-01 11:42 | 9513138661 | jerrymorales7517@gmail.com |  |  |  | 9581 | 0.16 | Michael Marlaire | 2019-06-18 | 5.49 | Ara Sotto | CUIC Inc | Darlynn Lacap | 2019-06-12 | 2019-06-17 15:00 | LR6-60PB-305M | 305 | 18 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  | 0 | 0 | 1 | 2019-07-23 | 2019-07-01 | 0.04 | 2 | Darlynn Lacap | Completed | 2019-07-03 | 2.08 | 2 | Jethro Andal | Completed | 2019-07-11 | 4.83 | 1 | Ara Sotto | Completed | 2019-07-23 | 1 | 5 | Brian Le | Completed | 2019-07-10 | 0.13 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 3.54 | 25 | Ernesto Enriquez | Completed | 2019-07-23 | 0.46 | 2 | Ara Sotto | Completed | 2019-07-25 | 1.83 | 2 | Ara Sotto | Completed | 2019-07-18 | 0.08 | 2 | Brian Le | Completed | 2019-07-18 | 0.25 | 2 | Darlynn Lacap | Completed | 2019-07-10 | 4.04 | 1 |  | Completed | 2019-07-10 | 4 | 1 | Andrew Clemons | Completed | 2019-07-23 | 0.5 | 1 | Darlynn Lacap | Completed | 2019-07-24 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-15 | 3.58 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-09-10 | 16.38 | 2 | Darlynn Lacap | Completed | 2019-08-22 | 4.33 | 1 | Andrew Clemons | Completed | 2019-08-07 15:32 |  | 2019-08-08 | 12.25 | 2 | Ara Sotto | Completed | [10 empty] | 21.05 | [11 empty] | 2019-08-14 | 2019-07-24 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26338 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26338 | https://completesolar.sugarondemand.com/#Opportunities/e3384790-91ee-11e9-97b8-022c40d974e6 | 300 Stars Inc |  | 2019-06-11 | HDM Electric Inc | e3384790-91ee-11e9-97b8-022c40d974e6 | 16 | 2 | -15 | 4 | 5 | 5 | 5 | -1
26441 | PIP_APPROVED | PIP_APPROVED | 26055 Eliot Avenue | Moreno Valley | CA | 92555 | Jorge Ramirez | 2019-06-29 16:39 | 9519020616 | jluisarias1968@gmail.com |  |  |  | 11059 | 0.16 | Michael Marlaire | 2019-06-29 | 7.625 | Ara Sotto | CUIC Inc | Marcia Garay | 2019-06-25 | 2019-06-29 09:00 | LR6-60PB-305M | 305 | 25 | LONGi Solar | SolarEdge | SE7600H-US RGM | Tile Concrete | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-22 07:00 | 2019-07-01 | 0.67 | 2 | Marcia Garay | Completed | 2019-07-09 | 3.46 | 2 | Jethro Andal | Completed | 2019-07-01 | 0.08 | 1 | Ara Sotto | Completed | 2019-07-24 | 4.17 | 5 | Brian Le | Completed | 2019-07-10 | 0.13 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 3.54 | 25 | Ernesto Enriquez | Completed | 2019-07-23 | 1.25 | 2 | Ara Sotto | Completed | 2019-07-29 | 4.21 | 2 | Ara Sotto | Completed | 2019-07-18 | 4.83 | 2 | Brian Le | Completed | 2019-07-11 | 2.17 | 2 | Marcia Garay | Completed | 2019-07-10 | 1.25 | 1 |  | Completed | 2019-07-17 | 5.92 | 1 | Andrew Clemons | Completed | 2019-07-22 | 0.29 | 1 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-05 | 0.92 | 2 | Ashley Rockwood | Completed | 2019-08-09 | 4.13 | 2 | Ashley Rockwood | Completed | 2019-09-16 | 25 | 2 | Marcia Garay | Completed |  | 50.17 | 1 | Jill Allen | Current | 2019-07-23 15:06 |  | 2019-07-24 | 1 | 2 | Ara Sotto | Completed | [10 empty] | 8.04 | [11 empty] | 2019-08-14 | 2019-07-29 | MORENO VALLEY | Moreno Valley | https://heliotrack.completesolar.com/job.php?action=review&jobID=26441 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26441 | https://completesolar.sugarondemand.com/#Opportunities/1cfafb5e-9ac7-11e9-a6dd-022c40d974e6 | 300 Stars Inc |  | 2019-06-15 | Power Town Solar Electric | 1cfafb5e-9ac7-11e9-a6dd-022c40d974e6 | 1 | 6 | 10 | -2 | 5 | 5 | 5 | 18
26632 | PIP_APPROVED | PIP_APPROVED | 4776 Filipo Street | San Diego | CA | 92115 | Bruce Klowden | 2019-06-26 10:30 | 6198408218 | bklowden1@gmail.com |  |  |  | 5884 | 0.192 | Chad Malloy | 2019-06-26 | 3.66 | Christina Horton | Revo Home Solutions | Darlynn Lacap | 2019-06-25 | 2019-06-26 09:00 | LR6-60PB-305M | 305 | 12 | LONGi Solar | SolarEdge | SE3800H-US RGM | Composite | NO | 2019-07-23 | NEM Submitted | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-23 12:00 | 2019-06-26 | 0.08 | 2 | Darlynn Lacap | Completed | 2019-07-01 | 3.08 | 2 | Jethro Andal | Completed | 2019-07-17 | 10.79 | 1 | Christina Horton | Completed | 2019-07-23 | 9.63 | 5 | Brian Le | Completed | 2019-07-16 | 7.08 | 3 | Andrew Moralez | Completed | 2019-07-16 | 0 | 15 | Ernesto Enriquez | Completed | 2019-07-23 | 0.54 | 1 | Christina Horton | Completed | 2019-07-26 | 1.87 | 2 | Christina Horton | Completed | 2019-07-09 | 3.67 | 2 | Brian Le | Completed | 2019-07-02 | 1.13 | 2 | Darlynn Lacap | Completed | 2019-07-05 | 2.96 | 1 |  | Completed | 2019-07-05 | 2.67 | 1 | Andrew Clemons | Completed | 2019-07-23 | 0.5 | 1 | Darlynn Lacap | Completed | 2019-07-25 | 0.08 | 2 | Andrew Clemons | Completed | [15 empty] | 2019-08-16 | 6.05 | 2 | Ashley Rockwood | Completed |  | 7 | 2 | Ashley Rockwood | Inactive | 2019-09-26 | 0.08 | 2 | Cynthia Morales | Completed | 2019-09-11 | 0.08 | 1 | Noe Gomez | Completed | 2019-07-26 13:31 |  | 2019-07-26 | 2.75 | 2 | Christina Horton | Completed | [10 empty] | 50.13 | [11 empty] | 2019-08-06 | 2019-07-26 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26632 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26632 | https://completesolar.sugarondemand.com/#Opportunities/f45206de-9837-11e9-b77d-022c40d974e6 | Blake Sanders |  | 2019-06-22 | Infinity Energy Inc | f45206de-9837-11e9-b77d-022c40d974e6 | 3 | 3 | 0 | 2 | 5 | 5 | 5 | 12
26770 | PIP_APPROVED | PIP_APPROVED | 5124 Kesling Street | San Diego | CA | 92117 | Jacob Gagne | 2019-07-02 13:54 | 7603152659 | gagne32@gmail.com |  |  |  | 4522 | 0.179 | Ryan Malloy | 2019-07-02 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-01 | 2019-07-02 12:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  | 0 | 1 | 2019-07-23 12:00 | 2019-07-05 | 1.88 | 2 | Marcia Garay | Completed | 2019-07-04 | 0.08 | 2 | Daniel Speegle | Completed | 2019-07-17 | 7.96 | 1 | Christina Horton | Completed | 2019-07-23 | 0.42 | 5 | Brian Le | Completed | 2019-07-16 | 6 | 3 | Ernesto Enriquez | Completed | 2019-07-16 | 0 | 15 | Ernesto Enriquez | Completed | 2019-07-23 | 0.54 | 1 | Christina Horton | Completed | 2019-08-20 | 18.54 | 2 | Christina Horton | Completed | 2019-07-17 | 7.13 | 2 | Brian Le | Completed | 2019-07-08 | 0.92 | 2 | Marcia Garay | Completed | 2019-07-08 | 1.17 | 1 |  | Completed | 2019-07-09 | 2.13 | 1 | Andrew Clemons | Completed | 2019-07-24 | 1.54 | 1 | Marcia Garay | Completed | 2019-07-25 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-09 | 3.96 | 2 | Ashley Rockwood | Completed | 2019-08-13 | 1.92 | 2 | Ashley Rockwood | Completed | 2019-08-19 | 4.04 | 2 | Marcia Garay | Completed | 2019-08-15 | 1.96 | 1 | Jill Allen | Completed | 2019-08-05 13:59 |  | 2019-08-05 | 8.75 | 2 | Christina Horton | Completed | [10 empty] | 6.46 | [11 empty] | 2019-08-06 | 2019-08-20 | SAN DIEGO | San Diego | https://heliotrack.completesolar.com/job.php?action=review&jobID=26770 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26770 | https://completesolar.sugarondemand.com/#Opportunities/84560d34-9d0b-11e9-ad2f-022c40d974e6 | Daniel Boyce | Dylan Glasser | 2019-06-27 | Infinity Energy Inc | 84560d34-9d0b-11e9-ad2f-022c40d974e6 | 13 | 28 | -15 | -2 | 5 | 5 | 5 | -7
26915 | PIP_APPROVED | PIP_APPROVED | 4918 Roja Drive | Oceanside | CA | 92057 | Florencia Jones | 2019-07-08 14:44 | 7605194918 | b2tulu@cox.net | Elizabeth Oakley Austin | 760-212-4444 |  | 4434 | 0.17 | Chad Malloy | 2019-07-08 | 2.745 | Christina Horton | Revo Home Solutions | Marcia Garay | 2019-07-06 | 2019-07-08 09:00 | LR6-60PB-305M | 305 | 9 | LONGi Solar | SolarEdge | SE3000H-US RGM | Composite | NO | 2019-07-23 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-22 07:00 | 2019-07-09 | 1 | 2 | Marcia Garay | Completed | 2019-07-11 | 2 | 2 | Daniel Speegle | Completed | 2019-07-15 | 1.83 | 1 | Christina Horton | Completed | 2019-07-23 | 3.46 | 5 | Brian Le | Completed | 2019-07-11 | 0.08 | 3 | Andrew Moralez | Completed | 2019-07-15 | 1.75 | 10 | Andrew Moralez | Completed | 2019-07-23 | 0.71 | 1 | Christina Horton | Completed | 2019-09-05 | 31.29 | 2 | Christina Horton | Completed | 2019-07-15 | 1.04 | 2 | Brian Le | Completed | 2019-07-12 | 0.88 | 2 | Marcia Garay | Completed | 2019-07-11 | 0.04 | 1 |  | Completed | 2019-07-15 | 1.92 | 1 | Jill Allen | Completed | 2019-07-22 | 0.08 | 1 | Marcia Garay | Completed |  | 32.21 | 2 | Noe Gomez | Current | [15 empty] | 2019-09-19 | 2.96 | 2 | Ashley Rockwood | Completed | 2019-09-20 | 0.96 | 2 | Ashley Rockwood | Completed | 2019-10-11 | 14.79 | 2 | Marcia Garay | Completed |  | 21.08 | 1 | Jill Allen | Current | 2019-09-05 14:20 |  | 2019-09-05 | 24.54 | 2 | Christina Horton | Completed | [10 empty] | 15.96 | [11 empty] | 2019-07-25 | 2019-09-05 | OCEANSIDE | Oceanside | https://heliotrack.completesolar.com/job.php?action=review&jobID=26915 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26915 | https://completesolar.sugarondemand.com/#Opportunities/8e53168e-a1c9-11e9-b5fe-0630baf9dcb8 | Brett Martinez |  | 2019-07-05 | Infinity Energy Inc | 8e53168e-a1c9-11e9-b5fe-0630baf9dcb8 | 44 | 44 | -25 | -2 | 5 | 5 | 5 | -17
26760 | PIP_APPROVED | PIP_APPROVED | 604 5th Street | Ramona | CA | 92065 | Luis Budd | 2019-07-09 15:23 | 8439971395 | midgard0010@gmail.com |  |  |  | 9543 | 0.195 | Michael Marlaire | 2019-06-28 | 5.795 | Ara Sotto | Tier1 Power | Darlynn Lacap | 2019-06-27 | 2019-06-28 12:00 | LR6-60PB-305M | 305 | 19 | LONGi Solar | SolarEdge | SE5000H-US RGM | Tile Concrete | NO | 2019-07-22 | PTO Received | SunRun Monthly | 0 | 0 |  |  |  | 1 | 2019-07-15 07:00 | 2019-07-09 | 2.21 | 2 | Darlynn Lacap | Completed | 2019-07-10 | 1.84 | 2 | Jethro Andal | Completed | 2019-07-12 | 1.75 | 1 | Ara Sotto | Completed | 2019-07-22 | 5.04 | 5 | Brian Le | Completed | 2019-07-11 | 0.54 | 3 | Ernesto Enriquez | Completed | 2019-07-11 | 0 | 0 | Andrew Moralez | Completed | 2019-07-22 | 5.29 | 2 | Ara Sotto | Completed | 2019-07-31 | 6.75 | 2 | Ara Sotto | Completed | 2019-07-15 | 1.88 | 2 | Brian Le | Completed | 2019-07-11 | 1.04 | 2 | Darlynn Lacap | Completed | 2019-07-10 | 0.17 | 1 |  | Completed | 2019-07-12 | 1.79 | 1 | Andrew Clemons | Completed | 2019-07-15 | 0.42 | 1 | Darlynn Lacap | Completed | 2019-07-24 | 0.08 | 2 | Noe Gomez | Completed | [15 empty] | 2019-08-05 | 3.08 | 2 | Ashley Rockwood | Completed | 2019-08-07 | 1.67 | 2 | Ashley Rockwood | Completed | 2019-08-16 | 7.17 | 2 | Darlynn Lacap | Completed | 2019-08-08 | 0.96 | 1 | Andrew Clemons | Completed | 2019-07-30 22:03 |  | 2019-07-31 | 6.92 | 2 | Ara Sotto | Completed | [10 empty] | 2.95 | [11 empty] | 2019-07-11 | 2019-07-31 | RAMONA | Ramona | https://heliotrack.completesolar.com/job.php?action=review&jobID=26760 | https://heliotrack.completesolar.com/OPFHT/index.php#job_id=26760 | https://completesolar.sugarondemand.com/#Opportunities/f051568e-99ef-11e9-9f20-0630baf9dcb8 | MarioUSPS Washington | Jordan Litrownik | 2019-06-27 | Blalock Electric&Solar | f051568e-99ef-11e9-9f20-0630baf9dcb8 | 9 | 9 | -5 | -2 | 5 | 5 | 5 | 3
Formulas:
Days to Final Inspection = IF([FINAL_INSPEC_completion_date]="",IF([msp_m_target_duration]=1,IF([msp_m_completion_date]>0,TODAY()-MAX([msp_m_completion_date],[IC_completion_date]),""),TODAY()-MAX([msp_m_completion_date],[IC_completion_date])),[FINAL_INSPEC_completion_date]-MAX([msp_m_completion_date],[IC_completion_date]))
Days to PIP = MAX(0,IF([PIP_completion_date]="",TODAY()-[IC_completion_date],[PIP_completion_date]-[IC_completion_date]))